## A-62
[7 empty] | State, County(Name) | Routine, FC, bridge washing, etc | Truss, Deck girder, etc | A52, UB60, A62 | Basket operator name
Date | Day | Time | Region | Structure | Feature On | Feature Under | Owner | Work Type | Bridge Type | Truck(s) needed | Operator | Notes
April 2 | MON | 8:30-12:00pm | SW-MAD | B-28-152 | STH 26 NB | Rock River | STATE | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
|  | LUNCH | SW-MAD | [7 empty] | Brad Williams
|  | 12:00PM-12:30PM | SW-MAD | B-28-153 | STH 26 SB | Rock River | STATE | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
2018-04-03 | TUE | 8:30AM-12:00PM | SW-MAD | B-11-1 | STH 13/16/23-Broadway St WB | Wisconsin River | STATE | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
|  | LUNCH | SW-MAD | [7 empty] | Brad Williams
|  | 12:00PM-3:30PM | SW-MAD | B-11-104 | STH 13/16/23-Broadway St EB | Wisconsin River | STATE | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
2018-04-04 | WED | 900AM-2:00PM | SW-MAD | B-13-8 | USH 51 -Stoughton Rd NB | Cottage Grove Rd | STATE | Routine/FC | Steel Girder | A62 | Brad Williams | FC Steel Pier Cap
|  |  | SW-MAD | [7 empty] | Brad Williams
|  | LUNCH | SW-MAD | [7 empty] | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
2018-04-05 | THR | 8AM - 10AM | SW-MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
|  | 10:30AM - 12:00PM | SW-MAD
|  | LUNCH | SW-MAD
|  | 12:30PM - 2:00PM | SW-MAD
|  | 2PM - 4PM | SW-MAD
April 9 | Mon | 9:00am - 11:00am | NE | B-05-119 | USH 41 | Ashland over 41 (Green Bay) | State | FC | Steel Deck Girder | A62 | Jim McDowell
|  | 1:00pm - 2:30 pm | NE | B-05-269 | STH 29 EB | Walnut St. (Green Bay) | State | FC | Moveable | A62 | Jim McDowell
|  | 3:00pm - 4:30pm | NE | B-05-134 | STH 54 EB | Mason St. (Green Bay) | State | Routine | Moveable | A62 | Jim McDowell
April 10 | Tue | 9:00am - 12:00pm | NE | B-15-4 | STH 42/57 | Bayview (Sturgeon Bay) | State | Routine | Moveable | A62 | Jim McDowell
|  | 1:00pm - 4:00pm | NE | B-15-23 | Local Street | Maple/Oregon (Sturgeon Bay) | State | FC | Moveable | A62 | Jim McDowell
April 11 | Wed | 9:00am - 10:30am | NE | B-70-56 | USH 45 | Main St (Oshkosh) | State | Routine | Moveable | A62 | Jim McDowell
|  | 11:00am - 1:00pm | NE | B-70-11 | Local Road | Oregon St. (Oshkosh) | State | Routine | Moveable | A62 | Jim McDowell
|  | 2:00pm - 4:00pm | NE | B-70-247 | STH 44 | Wisconsin St. (Oshkosh) | State | Routine | Moveable | A62 | Jim McDowell
April 12 | Thur | 9:00am - 10:30am | NE | B-70-1 | Local Street | Racine St. (Menasha) | State | Routine | Moveable | A62 | Jim McDowell
|  | 11:00am - 1:00pm | NE | B-70-91 | STH 21 | Congress Ave. (Oshkosh) | State | Routine | Moveable | A62 | Jim McDowell
April 16 | Mon | 9:00am - 3:00pm | NE | B-70-913 | STH 116 | Winneconne | State | FC | Moveable | A62 | Jim McDowell
April 17 | Tue | 9:00am - 12:00pm | NE | B-38-140 | USH 141 | Menominee River (Niagra) | State | Routine | Steel Deck Girder | A62 | Jim McDowell
|  | 1:00pm - 3:00pm | NE | B-38-11 | STH 8 | Menominee River (Norway) | State | Routine | Steel Deck Girder | A62 | Jim McDowell
April 18 | Wed | 9:00am - 3:00pm | NE | B-38-16 | Local Street | Menekaunee Bridge (Marinette) | State | Routine | Moveable | A62 | Jim McDowell
April 19 | Thur | No inspection scheduled, backup day for rain/snow | NE | [6 empty] | A62 | Jim McDowell
2018-04-23 | Mon | Open-Self Rescue Training
2018-04-24 | tues | Open-Self Rescue Training
2018-04-25 | wed | Open-Self Rescue Training
2018-04-26 | thur | Open-Self Rescue Training
April 30 | Mon | 900AM-300PM | SW-MAD | B-13-8 |  |  | State | Routine |  | A62 |  | Brad Williams
May 1 | Tues | 9:00AM-3:30PM | SW-MAD | B-28-666 |  |  | State | Routine |  | A62 |  | Brad Williams
A62
May 2 | Wed | 9:00AM-3:30PM | SW-MAD | B-56-182 |  |  | State | Routine |  | A62 |  | Brad Williams
|  |  |  | B-56-217 |  |  | State | Routine |  | A62 |  | Brad Williams
May 3 | Thur |  | SW-MAD | [8 empty] | Open/Rain Day/Operator Training
May 7 | Mon | 9:00am - 3:00pm | NE | B-15-100 | Local Street | Michigan Street (Sturgeon Bay) | State | Routine | Moveable | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 8 | Tue | 9:00am - 3:00pm | NE | B-36-142 | Local Street | 8th Street (Manitowoc) | Local - City of Manitowoc | Routine | Moveable | A62 | Jim McDowell
|  |  | NE | B-36-128 | Local Street | 10th Street (Manitowoc) | Local - City of Manitowoc | Routine | Moveable | A62 | Jim McDowell
NE
May 9 | Wed | 9:00am - 3:00pm | SE | B-51-69 | State Street | Root River | Local-Racine | FC | Movable | A62 | Steve Doocy
|  |  | SE | B-51-80 | Main Street | Root River | Local-Racine | FC | Movable | A62 | Steve Doocy
NE
May 10 | Thur | 9:00am - 12:00pm | NE | B-44-184 | Local Street | Main Street (Kaukauna) | Local - City of Kaukauna | Routine | Prestressed Deck Girder | A62 | Jim McDowell
|  | 1:00pm - 4:00pm | NE | B-44-185 | Local Street | Lawe Street (Kaukauna) | Local - City of Kaukauna | Routine | Prestressed Deck Girder | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 14 | Mon | 9:00am - 3:00pm | NE | B-31-1 | Local Street | 2nd Street (Algoma) | Local - Kewaunee County | FC | Steel Through Girder | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 15 | Tue | 9:00am - 12:00pm | NE | B-44-886 | Local Street | Olde Oneida St (Appleton) | Local - City of Appleton | Routine | Moveable | A62 | Jim McDowell
|  | 1:00pm - 4:00pm | NE | P-44-717 | Local Street | Lawe St (Appleton) | Local - City of Appleton | Routine | Moveable | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 16 | Wed | 9:00am - 3:00pm | NE | B-44-98 | Local Street | Memorial Drive (Appleton) | Local - City of Appleton | Routine | Steel Deck Girder | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 17 | Thur | 9:00am - 3:00pm | NE | B-44-260 | Local Street | New College Ave (Appleton) | Local - City of Appleton | Routine | Prestressed Deck Girder | A62 | Jim McDowell
|  |  | NE | [7 empty] | Jim McDowell
May 21 | Mon | 9:00AM-300PM | SW-MAD | B-28-146 | STH 26 NB | Crawfish River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | B-28-147 | STH26 SB | Crawfish River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | B-28-89 | USA 18 Racine St. | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
May 22 | Tue |  | SW-MAD | B-53-210 | STH 11 EB | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | B-53-211 | STH 11 WB | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW-MAD | [7 empty] | Brad Williams
May 23 | Wed |  | SW-MAD | B-53-906 | USH 14 | Rock River | WisDOT | Routine/FC | Steel Girder | A62 | Brad Williams | 2 Girder System
|  |  | SW-MAD | [7 empty] | Brad Williams
May 24 | Thur |  | SW-MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
|  |  | SW-MAD | [7 empty] | Brad Williams
May 28 | Mon | Todd on Vacation
Todd on Vacation
Todd on Vacation
May 29 | Tues | Todd on Vacation
Todd on Vacation
Todd on Vacation
Todd on Vacation
May 30 | Wed | Todd on Vacation
Todd on Vacation
May 31 | Thur | Todd on Vacation
June 4 & 5 | Mon&Tue | 6 am - 12 pm | SW-LAX | B320115 | STH 16 EB | LA CROSSE RIVER/CP RR | STATE HIGHWAY DEPT | In-depth | Deck truss/plate girder | Both UB60 & A62 | Jim Kast / Mark Dent | RR flagger needed. Move grace date to June
June 4 | Tue | 12 pm - 2 pm | SW-LAX | B320111 | STH 16 WB | LA CROSSE RIVER/CP RR | STATE HIGHWAY DEPT | Interim | Steel girdr w/ P/H system | Both UB60 & A62 | Jim Kast / Mark Dent
June 5 | Tue | 12 pm - 4 pm | SW-LAX | B320077 | CTH B/CLINTON ST | CTH B/CLINTON ST | STATE-S 84.10 | Interim | Concrete Deck Girder | A62 | Mark Dent
June 6 | Wed | 7 am - 9 am | SW-LAX | B520856 | STH 130/133 | Wisconsin River | STATE HWY DEPT | FC/Routine | Pony Truss | A62 | Jim Kast | Annual FC inspections
|  | 9 am - 4 pm | SW-LAX | B520857 | STH 130/133 | Wisconsin River | STATE HWY DEPT | FC/Routine | Overhead Truss | A62 | Jim Kast | Annual FC inspections
June 7 | Thur | 7 am - 4 pm | SW-MAD | B250081 | STH 130/133 | Wisconsin River | STATE HWY DEPT | FC/Routine | Overhead Truss | A62 | Jim Kast
june 11 | Mon | 9:00 am - 9:00 pm | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 12 | Tues | 9:00 am - 9:00 pm | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 13 | Wed | 8:00 - 3:00 | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 14 | Thur | 8:00 - 3:00 | NC-WR | B-71-11 | Jackson | Wisconsin River | local | routine | steel | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | b-71-57 | Grand | Wisconsin River | local | routine | prestressed
NC-WR
June 18 | Mon | 1:00pm - 3:00pm | NE | B-20-86 | Local Street | Grand River (Fairwater) | Local - Village of Fairwater | Routine | R.C. Flat Slab | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
June 19 | Tue | 9:00am - 3:00pm | NE | B-31-28 | Local Street | CTH E | Local - Kewaunee County | Routine | R.C. Haunched Slab | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
June 20 | Wed | 9:00am - 3:00pm | NE | B-59-124 | Local Street | CTH A over Sheboygan River | Local - Sheboygan County | Routine | Steel Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
June 21 | Thur | Reserved for Bridge Maintenance | NE | [6 empty] | A62 | Roy Tilleman
June 25 | Mon | 9:00am - 2:30pm | NE | B-70-61 | STH 441 SB | LLBDM (Menasha | State | Routine - Initial | Steel Deck Girder | A62 & A52 w/Special bucket | Jim Kast / Mark Dent
NE
June 26 | Tue | 8:00am - 2:30pm | NE | B-70-61 | STH 441 SB | LLBDM (Menasha | State | Routine - Initial | Steel Deck Girder | A62 & A52 w/Special bucket | Jim Kast / Mark Dent
NE
June 27 | Web | 9:00am - 3:00pm | NE | B-70-406 | STH 441 SB | 441 SB Ramp to 41 NB | State | Routine - Initial | Steel Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
June 28 | Thur | 9:00am - 3:00pm | NE | B-70-405 | STH 441 SB | 441 SB Ramp to 41 SB | State | Routine - Initial | Prestressed Deck Girder | A62 | Roy Tilleman
July 2 | Mon |  | SW MAD | B-28-162 | STH 26 NB | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-28-163 | STH 26 SB | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | [7 empty] | Brad Williams
July 3 | Tues |  | SW MAD | B-28-164 | E Horseshoe Rd | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-28-11 | STH 26 - Main St | Rock River | WisDOT | Routine | Steel Girder | A62 | Brad Williams
July 4 | Wed | HOLIDAY
July 5 | Thur |  | SW MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
July 9 | Mon | 9:00am-3:00pm | NE | B-44-126 | STH 441 NB | Fox River (Little Chute) | State | Routine | Steel Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
July 10 | Tue | 9:00am - 2:00pm | NE | B-44-166 | STH 54 | Wolf River Bridge (Shiocton) | State | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
July 11 | Wed | 9:00am - 2:30pm | NE | B-70-403 | STH 441 NB | LLBDM (Menasha) | State | Routine | Prestressed Deck Girder | A62 & A52 w/Special bucket | Mark and Jim
|  |  | NE | [7 empty] | Mark and Jim
July 12 | Thur | 9:00am - 2:30pm | NE | B-70-403 | STH 441 NB | LLBDM (Menasha) | State | Routine | Prestressed Deck Girder | A62 & A52 w/Special bucket | Mark and Jim
July 16 | Mon |  | SW MAD | B-11-23 | IH 90/94 WB | Wisconsin River | WisDOT | Routine/FC | Steel Girder | A62 | Brad Williams | Dekorra
|  |  | SW MAD | [7 empty] | Brad Williams
July 17 | Tues |  | SW MAD | B-11-22 | IH 90/94 EB | Wisconsin River | WisDOT | Routine/FC | Steel Girder | A62 | Brad Williams | Dekorra
|  |  | SW MAD | [7 empty] | Brad Williams
July 18 | Wed |  | SW MAD | B-28-44 | IH 94 EB | Crawfish River | WisDOT | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-28-584 | IH 94 WB | Crawfish River | WisDOT | Routine | Steel Girder | A62 | Brad Williams
July 19 | Thur |  | SW MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
|  |  | SW MAD | [7 empty] | Brad Williams
July 23 | Mon |  | SW MAD | B-53-90 | STH 213 - Broad St | Rock River | City of Beloit | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-53-136 | Shirland Ave | Rock River | City of Beloit | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-53-171 | USH 51 - E Grand Ave | Turtle Creek | City of Beloit | Routine | Prestressed Girder | A62 | Brad Williams | Beloit Determined Reach All Not required
|  |  | SW MAD | B-53-173 | Grand Ave | Rock River | City of Beloit | Routine | Prestressed Girder | A62 | Brad Williams
July 24 | Tues |  | SW MAD | [7 empty] | Brad Williams
|  |  | SW MAD | [7 empty] | Brad Williams
|  |  | SW MAD | B-53-1 | Henry Ave | Rock River | City of Beloit | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-53-151 | STH 81 - Milwaukee Rd | Turtle Creek | City of Beloit | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-53-240 | CTH S - Shopirer Rd | Turtle Creek | City of Beloit | Routine | Haunched Slab | A62 | Brad Williams
|  |  | SW MAD | P-53-707 | Cranston Rd | Turtle Creek | City of Beloit | Routine | Haunched Slab | A62 | Brad Williams
|  |  | SW MAD | P-53-737 | Park Ave | Turtle Creek | City of Beloit | Routine | Prestressed Girder | A62 | Brad Williams | Beloit Determined Reach All Not required
|  |  | SW MAD | [7 empty] | Brad Williams
July 25 | Wed |  | SW MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
|  |  | SW MAD | [7 empty] | Brad Williams
July 26 | Thur |  | SW MAD | [7 empty] | Brad Williams | Open/Rain Day/Operator Training
July 30 | Mon | 7 am - 5 pm | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine | Deck Truss | Both UB60 & A62 | Jim Kast / Mark Dent
July 31 | Tues | 7 am - 5 pm | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine | Deck Truss | Both UB60 & A62 | Jim Kast / Mark Dent
August 1 | Wed |  | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine |  | A 62 | Jim Kast / Mark Dent
August 2 | Thur |  | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine |  | A 62 | Jim Kast / Mark Dent
August 6 | MON | 8AM - 10AM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 10:30AM - 12:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | LUNCH | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 12:30PM - 2:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 2PM - 4PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
August 7 | TUE | 8AM - 10AM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
August 9 |  | 10:30AM - 12:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | LUNCH | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 12:30PM - 2:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 2PM - 4PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
August 8 | WED | 8AM - 10AM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 10:30AM - 12:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | LUNCH | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 12:30PM - 2:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 2PM - 4PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
August 9 | THR | 8AM - 10AM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 10:30AM - 12:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | LUNCH | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 12:30PM - 2:00PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
|  | 2PM - 4PM | NW-SUP | B16-38 | USH 2 | IH 35 - MINNESOTA | STATE | ROUTINE | TIED ARCH | A62 | Mark | BONG
August 13 | Mon | open | [7 empty] | A62
A62
August 14 | Tue | 9:00 AM - 2:00 PM | SE | B-40-1211-1 | IH 43 SB | IH 794 | State | Routine | Steel Deck Girder | A62 | Scott Reay | Marquette Interchange
|  | 9:00 AM - 2:00 PM | SE | B-40-1211-2 | IH 43 SB | W St Paul Ave | State | Routine | Steel Deck Girder | A62 | Scott Reay | Marquette Interchange
|  |  | SE | [6 empty] | A62
August 15 | Wed | 9:00 AM - 2:00 PM | SE | B-40-457 | STH 100 NB | CMSTPP RR | State | FC/Routine | Steel Deck Girder/Cap Beams | A62 | Scott Reay | RR Coordination
|  |  | SE | [6 empty] | A62
August 16 | Thur | 9:00 AM - 2:00 PM | SE | B-40-457 | STH 100 SB | CMSTPP RR | State | FC/Routine | Steel Deck Girder/Cap Beams | A62 | Scott Reay | RR Coordination
August 20 | Mon | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
August 21 | Tue | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
August 22 | Wed | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
August 23 | Thur | Todd Open | [7 empty] | A62
A62
August 27 | Mon | Todd open | [7 empty] | A62
A62
A62
A62
A62
August 28 | Tues | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
August 29 | Wed | Todd Open | [7 empty] | A62
|  | Todd Open | [7 empty] | A62
August 30 | Thur | Todd Open | [7 empty] | A62
Sept 3 | Mon | HOLIDAY
Sept 4 | Tues |  | SW MAD | B-53-145 | USH 51 | Rock River | WisDOT | Routine | Deck Truss | A62 | Mark Dent | Needs Experienced Operator
SW MAD
Sept 5 | Wed |  | SW MAD | B-53-172 | STH 81 -Portland Ave | Rock River | WisDOT | Routine | Prestressed Girder | A62 | Mark Dent
SW MAD
|  |  | SW MAD | B-33-365 | CTH D | Pecatonica River | Lafayette County | Routine/FC | Overhead Truss | A62 | Mark Dent | Needs Experienced Operator
Sept 6 | Thur |  | SW MAD | B-33-625 | CTH G | Pecatonica River | Lafayette County | Routine/FC | Overhead Truss | A62 | Mark Dent | Needs Experienced Operator
|  |  | SW MAD | [7 empty] | Mark Dent
|  |  | SW MAD | Rock Locals | [6 empty] | Mark Dent
Sept 10 | Mon | 9:00am - 12:00pm | NE | B-59-91,309 | STH 23 | Mullet River (Plymouth) | State | Routine | Steel & Prestressed Deck Girder | A62 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-59-101 | STH 28 | Onion River (Sheboygan Falls) | State | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 11 | Tue | 9:00am - 12:00pm | NE | B-36-112,113 | STH 42 | Manitowoc River (Manitowoc) | State | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-31-23 | STH 42 | Kewaunee River (Kewaunee) | State | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 12 | Wed | 8:00am - 3:00pm | NE | B-36-189 | Local Street | 17th St Bascule (Two Rivers) | Local - City of Two Rivers | Routine | Moveable | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 13 | Thur | 9:00am - 12:00pm | NE | B-70-51 | STH 21 | Fox River (Omro) | State | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
NE
Sept 17 | Mon | 9:00am - 2:30pm | NE | B-5-158 | I 43 | Tower Drive (Green Bay) | State | FC | Tied Arch | A62 & A52 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 18 | Tue | 9:00am - 2:30pm | NE | B-5-158 | I 43 | Tower Drive (Green Bay) | State | FC | Tied Arch | A62 & A52 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 19 | Wed | 9:00am - 10:30am | NE | B-36-106 | Local Street | 21st Street (Manitowoc) | Local - City of Manitowoc | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 11:00am - 12:30pm | NE | B-36-29 | Local Street | Waldo Blvd (Manitowoc) | Local - City of Manitowoc | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-36-124 | Local Street | Broadway Street (Manitowoc) | Local - City of Manitowoc | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Sept 20 | Thur | 9:00am | NE | B-70-306 | Local Street | Oak St. (Neenah) | Local - City of Neenah | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
NE
Sept 24 | Mon |  | SW MAD | B-56-207 | USH 12 EB | Baraboo River | WisDOT | Routine | Prestressed Girder | A62 | Brad W.
|  |  | SW MAD | B-56-208 | USH 12 WB | Baraboo River | WisDOT | Routine | Prestressed Girder | A62 | Brad W.
Brad W.
Sept 25 | Tue |  | SW MAD | B-56-47 | IH 90/94 EB | Mirror Lake | WisDOT | Routine/FC | Steel Girder - Rigid Frame | A62 | Brad W.
|  |  | SW MAD | [7 empty] | Brad W.
Sept 26 | Wed |  | SW MAD | B-56-48 | IH 90/94 WB | Mirror Lake | WisDOT | Routine/FC | Steel Girder - Rigid Frame | A62 | Brad W.
|  |  | SW MAD | [7 empty] | Brad W.
|  |  | SW MAD | [7 empty] | Brad W.
|  |  | SW MAD | [7 empty] | Brad W.
Sept 27 | Thur |  | SW MAD |  |  |  | Rock Locals |  |  |  | Brad W.
SW MAD
Oct 1 | Mon |  | SW MAD | B-56-0063 | Golf Course Rd | Baraboo River | Sauk County | Routine | Turtle Creek | A62 | Brad Williams
|  |  | SW MAD | B-56-0072 | STH 23/33 - Main St | Baraboo River | Sauk County | Routine | Haunched Slab | A62 | Brad Williams
|  |  | SW MAD | B-56-0672 | CTH PF - Maple St | Baraboo River | Sauk County | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | P-56-0125 | S Dewey Ave | Baraboo River | Sauk County | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | [7 empty] | Brad Williams
Oct 2 | Tues |  | SW MAD | B-56-0020 | CTH X | Baraboo River | Sauk County | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-56-0079 | Manchester St | Baraboo River | Sauk County | Routine | Haunched Slab | A62 | Brad Williams
|  |  | SW MAD | B-56-0116 | 2nd Ave | Baraboo River | Sauk County | Routine | Prestressed Girder | A62 | Brad Williams
Oct 3 | Wed | 9:00AM-2:00PM | SE | B-4-188 | IH-41 SB | Ramp NB IH 41 SB | State | Routine | Steel Deck | A62 | Scott Reay | Hale intrerchange
Oct 4 | Thur
Oct 8 | Mon | 9:00am - 3:00pm | NE | B-5-311 | Nitscke Bridge | Green Bay | Local - City of Green Bay | Routine | Moveable | A62 | Jim McDowell
NE
Oct 9 | Tue | 9:00am - 12:00pm | NE | P-44-713 | Local Street | Kaukauna | Local - City of Kaukauna | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-44-187 | Local Street | Little Chute | Local - Outagamie County | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Oct 10 | Wed | 8:00am - 10:00am | NE | B-59-33 | Local Street | 14th Street (Sheboygan) | Local - City of Sheboygan | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 11:00am - 1:00pm | NE | B-59-64 | Local Street | Penn. Ave (Sheboygan) | Local - City of Sheboygan | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 2:00pm - 4:00pm | NE | P-59-717 | Local Street | New Jersey Ave (Sheboygan) | Local - City of Sheboygan | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Oct 11 | Thur | 9:00am - 12:00pm | NE | B-70-62 | STH 114 | Washington Steet (Menasha) | Local - City of Menasha | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-70-908 | STH 114 | Commercial Street (Neenah) | Local - City of Neenah | Routine | Prestressed Deck Girder | A62 | Roy Tilleman
|  |  | NE | [6 empty] | A62 | Roy Tilleman
Oct 15 | Mon | 9:00 AM - 2:00 PM | SE | B-40-400-01A | IH 794 WB | Milwaukee River | State | FC | Tie Girder | A 62 | Scott Reay | Hoan Bridge
|  |  | SE | [6 empty] | A 62
Oct 16 | Tue | 9:00 AM - 2:00 PM | SE | B-40-400-01B | IH 794 EB | Milwaukee River | State | FC | Tie Girder | A 62 | Scott Reay | Hoan Bridge
|  |  | SE | [6 empty] | A 62
Oct 17 | Wed | 9:00 AM - 2:00 PM | SE | B-40-400-0S2B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0S3B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0S4B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0S5B | IH 794 EB | Land | State | Routine | Steel Deck Girder | A 62 | Scott Reay | Hoan Bridge
|  |  | SE | [6 empty] | A 62
Oct 18 | Thur | 9:00 AM - 2:00 PM | SE | B-40-400-0S6B | IH 794 EB | Land | State | Routine | Steel Deck Girder | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0S7B | IH 794 EB | Land | State | Routine | Steel Deck Girder | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0N2B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0N3B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
|  | 9:00 AM - 2:00 PM | SE | B-40-400-0N4B | IH 794 EB | Land | State | Routine/In-Depth | Steel Deck Girder/Floor Beams | A 62 | Scott Reay | Hoan Bridge
LOCAL
Oct 22 | Mon | Todd Open
Oct 23 | Tue | Todd Open
Oct 24 | Wed | Todd Open
Todd Open
Todd Open
Oct 25 | Thur | Todd Open
Oct 29 | Mon | Todd Open
Todd Open
Oct 30 | Tue | Todd Open
Todd Open
Oct 31 | Wed | Todd Open
Todd Open
Todd Open
Nov 1 | Thur | Todd Open
Nov 5 | Mon |  | SW MAD | B-13-612 | CTH B - Adams St | Koshkonong Creek | Dane County | Routine | Prestressed Girder | A62 | Brad Williams | Dane county determind reach not required
|  |  | SW MAD | B-13-34 | CTH B | Yahara River | Dane County | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-13-613 | CTH N | Yahara River | Dane County | Routine | Haunched Slab | A62 | Brad Williams | Dane county determind reach not required
|  |  | SW MAD | B-13-681 | CTH N | Yahara River | Dane County | Routine | Prestressed Girder | A62 | Brad Williams | Dane county determind reach not required
|  |  | SW MAD | [7 empty] | Brad Williams
Nov 6 | Tues |  | SW MAD | B-13-371 | CTH BW - S Broadway | Baraboo River | Dane County | Routine | Prestressed Girder | A62 | Brad Williams
|  |  | SW MAD | B-13-647 | CTH M | WSOR RR | Dane County | Routine | Haunched Slab | A62 | Brad Williams
|  |  | SW MAD | B-13-952 | CTH MS - University Ave | Old Middleton Rd | Dane County | Routine/FC | Steel Girder | A62 | Brad Williams | FC Steel Pier Caps
|  |  | SW MAD | [7 empty] | Brad Williams
Nov 7 | Wed |  | SW MAD | B-13-75 | CTH AB | Yahara River | Dane County | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-13-47 | CTH PB | W Branch Sugar River | Dane County | Routine | Steel Girder | A62 | Brad Williams
|  |  | SW MAD | B-13-685 | CTH A | Sugar River | Dane County | Routine | Prestressed Girder | A62 | Brad Williams | Dane county determind reach not required
SW MAD
Nov 8 | Thur |  | SW MAD | [8 empty] | Open/Rain Day/Operator Training

## UB-60
[7 empty] | State, County(Name) | Routine, FC, bridge washing, etc | Truss, Deck girder, etc | A52, UB60, A62 | Basket operator name
Date | Day | Time | Region | Structure | Feature On | Feature Under | Owner | Work Type | Bridge Type | Truck(s) needed | Operator | Notes
April 2 | Mon | 9:00am - 2:30pm | NWEC | B-17-0005 | [5 empty] | UB60 | LEE | Practice run for Lee in Morning
|  |  | NWEC | B-17-0130 | USH 12 WB-STH 25 NB | RED CEDAR RIVER | STATE | Wash and Routine (Full Day) | Weathering Steel Girder | UB60 | LEE
|  |  | NWEC | [6 empty] | UB60 | LEE
|  |  | NWEC | [6 empty] | UB60 | LEE
April 3 | Tue | 8:00am - 2:30pm | NWEC | B-17-0638 | USH 12 EB-STH 25 SB | RED CEDAR RIVER | STATE | Routine (Full Day) | Steel Girder | UB60 | LEE
|  |  | NWEC | [6 empty] | UB60 | LEE
|  |  | NWEC | [6 empty] | UB60 | LEE
April 4 | Wed | 8:00am - 11:00am | NWEC | B-17-0002 | STH 170-WHEELER ST | RED CEDAR RIVER | STATE | Routine (1/2 Day) | Steel Girder | UB60 | LEE
|  | 12:00pm - 4:00pm | NWEC | B-17-0852 | STH 72 | EAU GALLE RIVER | STATE | Routine (1/2 Day) | Steel Girder | UB60 | LEE
|  |  | NWEC | [6 empty] | UB60 | LEE
[10 empty] | UB60 | LEE
April 5 | Thur | 8:00am - 10:00am | NWEC | B-61-0054 | STH 93 | TREMPEALEAU RIVER | STATE | Routine (1/3 Day) | Prestressed Girder | UB60 | LEE
|  | 11:00am - 2:00pm | NWEC | B-61-0019 | STH 35 | TANK CREEK | STATE | Routine (1/3 Day) | Steel Girder | UB60 | LEE
|  | 2:30pm - 4:00pm | NWEC | B-61-0130 | USH 53-MAIN ST | K | STATE | Routine (1/3 Day) | Prestressed Girder | UB60 | LEE
2018-04-09 | Mon | 8:00am - 2:30pm | NWEC | B-47-0040 | USH 10 | ST CROIX RIVER 01 | STATE | FC, MECHANICAL INSP | Steel Girder Bascule | UB60 | LEE
[10 empty] | UB60 | LEE
LEE
LEE
2018-04-10 | Tue | 8:00am - 2:30pm | NWEC | B-47-0040 | USH 10 | ST CROIX RIVER 01 | STATE | ROUTINE, FC, MECHANICAL INSP | Steel Girder Bascule | UB60 | LEE
[10 empty] | UB60 | LEE
[10 empty] | UB60 | LEE
2018-04-11 | Wed | 8:00am - 9:00am | NWEC | B-47-0982 | STH 35 | TRIMBELLE RIVER | STATE | Routine | Steel Girder | UB60 | LEE
|  | 9:30am - 11:00am | NWEC | B-47-0019 | STH 72 | PLUM CREEK | STATE | Routine | Steel Girder | UB60 | LEE
|  | 12:00pm - 3:00pm | NWEC | B-47-0023 | USH 63 | MISS R WIS CHANNEL | STATE | Routine | Steel Girder | UB60 | LEE
LEE
2018-04-12 | Thurs | 8:00am - 9:30am | NWEC | B-47-0033 | STH 29 | RUSH RIVER | STATE | Routine | Steel Girder | UB60 | LEE
|  | 11:00am - 2:30pm | NWEC | B-06-0002 | STH 88 | BUFFALO RIVER | STATE | Routine | Steel Girder | UB60 | LEE
2018-04-16 | MON | 8AM - 10AM | NW-SUP | B60-11 | LOCAL | LOCAL | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 10:30AM - 12:00PM | NW-SUP |  | LOCAL | LOCAL | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | LUNCH | NW-SUP |  | LOCAL | LOCAL | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 12:30PM - 2:00PM | NW-SUP | B60-71 | LOCAL | LOCAL | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 2PM - 4PM | NW-SUP |  | LOCAL | LOCAL | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
2018-04-17 | TUE | 8AM - 10AM | NW-SUP |  | LOCAL ROADS | TAYLOR | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 10:30AM - 12:00PM | NW-SUP |  | LOCAL ROADS | TAYLOR | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | LUNCH | NW-SUP |  | LOCAL ROADS | TAYLOR | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 12:30PM - 2:00PM | NW-SUP |  | LOCAL ROADS | TAYLOR | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 2PM - 4PM | NW-SUP |  | LOCAL ROADS | TAYLOR | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
2018-04-18 | WED | 8AM - 10AM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 10:30AM - 12:00PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | LUNCH | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 12:30PM - 2:00PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 2PM - 4PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
2018-04-19 | THR | 8AM - 10AM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 10:30AM - 12:00PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | LUNCH | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 12:30PM - 2:00PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
|  | 2PM - 4PM | NW-SUP |  | LOCAL ROADS | RUSK CO | LOCAL | ROUTINE |  | UB60 | Bill Kovaleski
2018-04-23 | Mon | Open-Self Rescue Training
2018-04-24 | tues | Open-Self Rescue Training
2018-04-25 | wed | Open-Self Rescue Training
2018-04-26 | thur | Open-Self Rescue Training
April 30 | Mon | 9:00am - 3:00pm | NC-WR | B-71-179 | STH 80 | Yellow river | Wood | ROUTINE | Prestress | UB-60 | Tom
|  |  | NC-WR | B-68-739 | STH 54 | Little WOLF RIVER | WAUPACA | ROUTINE | Steel Girder | UB-60 | Tom
May 1 | Tue | 8:00am - 3:00pm | NC-WR | B-68-90 | USH 10 | WOLF RIVER | WAUPACA | ROUTINE | Steel Girder | UB-60 | Tom
|  |  | NC-WR | B-68-31 | USH 96 | Wolf RIVER | WaUPACA | ROUTINE | Steel Girder | UB-60 | Tom
|  |  | NC-WR | B-68-89 | USH 10 | Wolf RIVER | WAUPACA | ROUTINE | Steel Girder | UB-60 | Tom
May 2 | Wed | [8 empty] | UB-60 | Tom | B49-90 cancled due to high water Will reschedule in June
[10 empty] | UB-60 | Tom
May 3 | Thur | 8:00am - 12:00pm | NC-WR | B-39-50 | STH 22 | Montello River | Marquette | Bird netting | slab | UB-60 | Tom
|  |  | NC-WR | [6 empty] | UB-60 | Tom
May 7 | Mon | 10:00 AM - 3PM | NC-RHI | B-50-22 | STH 13 | N fork Flambeau | State | Routine | Prestressed girder | UB-60 | Brock
|  |  | NC-RHI | B-50-82 | STH 182 | N fork Flambeau | State | Routine | Prestressed girder | UB-60 | Brock
|  |  | NC-RHI | B-50-4 | STH 70 | Flambeau River | State | Routine | Steel Girger | UB-60 | Brock
May 8 | Tue | 9:00am - 3:00pm | NC-RHI | B-26-7 | USH 2 | Montreal River | State | Routine | Steel Girger | UB-60 | Brock
|  |  | NC-RHI | B-26-8 | USH 2 | Montreal River | State | Routine | Steel Girger | UB-60 | Brock
May 9 | Wed | Weather delay | NC-RHI | [6 empty] | UB-60 | Brock | Weather delay
|  |  | NC-RHI | [6 empty] | UB-60 | Brock
May 10 | Thur | 8:00AM-3:00PM | NC-RHI | B-43-33 | Hatrapids | WI. River | local | Routine | Prestressed girder | UB-60 | Brock
|  |  | NC-RHI | B-43-03 | Kemp St | WI. River | local | Routine | Steel girder | UB-60 | Brock
|  |  | NC-RHI | B-35-15 | CTH Q | WI. River | Local | Routine | Steel girder | UB-60 | Brock
May 14 | MON | OPEN | NW-SUP
NW-SUP
May 15 | TUE | 8 AM-4PM | NW-SUP | B-54-18 | CTH D | Chippewa River | STATE | ROUTINE/ PIN &HANGER INSPECTION | STEEL | UB60 | Bill K.
May 16 | Wed | 8:00AM-400PM | NW-SUP | B-54-50 | STH 8 | FLAMBEAU RIVER | STATE | Routine | Steel Girder | UB60 | Bill K.
|  |  | NW-SUP | B-54-65 | STH 8 | FLAMBEAU RIVER | STATE | Routine | Presttressed Girder | UB60 | Bill K.
May 17 | Thur | 800AM-200PM | NW-SUP | B-60-71 | CTH H | Jump River | Local | Pier cap repair | Prestressed girder | UB60 | Bill K.
May 21 | Mon | 7 am - 8 am | SW-LAX | B220034 | STH 133 | BLAKES CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 8:30 am - 9:30 am | SW-LAX | B220827 | STH 81 | HACKETT BRANCH | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 10:30 am - 12 pm | SW-LAX | B220617 | STH 11 | SINSINAWA RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 1 pm - 2 pm | SW-LAX | B220144 | USH 61-STH 35 | PLATTE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | Snoop off westside/heading south.
|  | 2:30 pm - 4 pm | SW-LAX | B220108 | STH 133 | GRANTS CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
May 22 | Tue |  | SW-LAX | B220108 | STH 133 | GRANTS CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 7 am - 10 am | SW-LAX | B220046 | CTH T | WISCONSIN RIVER | STATE-S 84.10 | Interim |  | UB60 | Mike O.
|  | 10: 15 am - 1:30 pm | SW-LAX | B520025 | CTH T | WISCONSIN RIVER 03 | STATE-S 84.10 | Interim |  | UB60 | Mike O.
|  | 2 pm - 4 pm | SW-LAX | B520012 | STH 80 | PINE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
May 23 | Wed | 7 am - 9 am | SW-LAX | B120010 | USH 61-STH 131 | KICKAPOO RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 9:15 am - 10:30 am | SW-LAX | B120013 | USH 61-STH 131-4TH ST | TROUT CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 11 am - 12 pm | SW-LAX | B120019 | USH 61 | RICHLAND CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 1 pm - 2 pm | SW-LAX | B120023 | STH 60 | RICHLAND CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 2:30 pm - 5 pm | SW-LAX | B120363 | STH 179 | KICKAPOO RIVER | STATE HIGHWAY DEPT | FC |  | UB60 | Mike O.
May 24 | Thur | 7 am - 9:30 am | SW-LAX | B620009 | STH 35 | COON CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 10:15 am - 11 am | SW-LAX | B620006 | USH 14-USH 61 | SPRING VALLEY CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 12 pm - 3 pm | SW-LAX | B620034 | STH 131 | KICKAPOO RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 3:15 pm - 4:30 pm | SW-LAX | B620187 | STH 131 | UNNAMED STREAM | STATE HIGHWAY DEPT | FC |  | UB60 | Mike O.
May 28 | Mon | HOLIDAY
May 29 | Tues | 8:00am - 10:00am | NW EAU | B-61-62 | CTH D / 5th AVE | BUFFALO RIVER | Trempealeau County | Routine | Prestressed Girder | UB60 | LEE | Mark Pilgrim needs it in Strum for 1 day, preferrably in May.
|  | 10:30am - 12:00pm | NW EAU | B-61-751 | USH 53 | BEAVER CREEK | STATE | Routine | Steel Girder | UB60 | LEE
|  | 1:00pm - 2:30pm | NW EAU | B-27-233 | STH 54 | WILSON CREEK | STATE | Routine | Steel Girder | UB60 | LEE
May 30 | Wed | OPEN
May 31 | Thur | OPEN
June 4 & 5 | Mon | 6 am - 12 pm | SW-LAX | B320115 | STH 16 EB | LA CROSSE RIVER/CP RR | STATE HIGHWAY DEPT | In-depth | Deck truss/plate girder | Both UB60 & A62 | Jim Kast / Mark Dent | RR flagger needed. Move grace date to June
June 4 | Tues | 12 pm - 2 pm | SW-LAX | B320111 | STH 16 WB | LA CROSSE RIVER/CP RR | STATE HIGHWAY DEPT | Interim | Steel girdr w/ P/H system | Both UB60 & A62 | Jim Kast / Mark Dent
June 5 | Tues | 12 pm - 2 pm | SW-LAX | B320288 | STH 162 | LA CROSSE RIVER | STATE HIGHWAY DEPT | Interim | Steel Girder | UB60 | Mark Dent | Go to Cameron Ave bridge if done with others.
|  | 2 pm - 4 pm | SW-LAX | B320555 | STH 16 | BIG CREEK | STATE HIGHWAY DEPT | Interim | Steel Girder | UB60 | Mark Dent
June 6 & 7 | Wed | 7 am - 5 pm | SW-LAX | B320202 | USH 14 EB | Mississippi River | STATE HIGHWAY DEPT | FC | Tub girder/tied arch | UB60 | Mark Dent | Notify Coast Guard
| Thur | 7 am - 5 pm | SW-LAX | B320202 | USH 14 EB | Mississippi River | STATE HIGHWAY DEPT | FC | Tub girder/tied arch | UB 60 | Mark Dent | Notify Coast Guard
|  |  | SW-LAX | B320202 | USH 14 EB | Mississippi River | STATE HIGHWAY DEPT | FC | Tub girder/tied arch | UB60 | Mark Dent | Notify Coast Guard
june 11 | Mon | 9:00 am - 9:00 pm | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 12 | Tues | 9:00 am - 9:00 pm | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 13 | Wed | 8:00 - 3:00 | NC-WR | B-37-360 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | B-37-362 | STH 29 | USH 51 | STATE HWY DEPT | FC/Routine | Tub Girder | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
NC-WR
june 14 | Thur | 8:00 - 3:00 | NC-WR | B-71-11 | Jackson | Wisconsin River | local | routine | steel | Both UB60 & A62 | Jim Kast / Mark Dent | tub inspections
|  |  | NC-WR | b-71-57 | Grand | Wisconsin River | local | routine | prestressed
NC-WR
June 19 | Tues | 9:00AM-2:00PM | SE | B-40-40-1 | STH 175 SB | Ramp STH 175 NB 94 W | State | Routine | Steel Deck Girder | UB 60 | Scott Reay
|  | 900AM-2:00PM | SE | B-40-40-2 | STH 175 SB | Land | State | Routine | Steel Deck Girder | UB 60 | Scott Reay
|  |  | SE | [6 empty] | UB 60
June 20 | Wed | 9:00 AM - 2:00 PM | SE | B-40-40-3 | STH 175 SB | IH 94 | State | Routine | Steel Deck Girder | UB 60 | Scott Reay
|  | 9:00AM-2:00PM | SE | B-40-40-4 | Ramp IH 94 WB-STH 175 SB | Land | State | Routine | Steel Deck Girder | UB 60
June 21 | Thur | 9:00 AM - 2:00 PM | SE | B40-40-5 | Ramp IH 94 WB-STH 175 SB | IH 94 EB | State | Routine | Steel Deck Girder | UB 60 | Scott Reay
June 25 | Mon | 9:00am - 3:00pm | NW EAU | B-55-0061 | IH 94 WB-USH 12 WB | ST CROIX RIVER 03 | STATE | Routine | Steel Girder | UB 60 | Lee B. | talk to greg
|  |  | NW EAU | [6 empty] | UB 60 | Lee B.
June 26 | Tues | 9:00am - 3:00pm | NW EAU | B-55-0061 | IH 94 WB-USH 12 WB | ST CROIX RIVER 03 | STATE | Routine | Steel Girder | UB 60 | Lee B.
|  |  | NW EAU | [6 empty] | UB 60 | Lee B.
June 27 | Wed | 9:00am - 3:00pm | NW EAU | B-55-0126 | IH 94 EB-USH 12 EB | ST CROIX RIVER 02 | STATE | Routine | Weathering Steel Girder | UB 60 | Lee B.
|  |  | NW EAU | [6 empty] | UB 60 | Lee B.
June 28 | Thur | 9:00am - 3:00pm | NW EAU | B-55-0126 | IH 94 EB-USH 12 EB | ST CROIX RIVER 02 | STATE | Routine | Weathering Steel Girder | UB 60 | Lee B.
July 2 | Mon | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
July 3 | Tues | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
July 4 | Wed | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
|  | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
July 5 | Thur | Craig OFF, Mark OFF and JIM OFF | [7 empty] | UB60
UB60
UB60
July 9 | Mon | Craig Open | [7 empty] | UB60
|  | Craig Open | [7 empty] | UB60
July 10 | Tue | 8:00:00 AM-4:00PM | NC WR | B-49-90 | CTH HH | WI RIVER | STATE | Routine |  | UB60 | Tom Hardinger
|  |  | NC WR | B-68-37 | Ostrander Rd | Little Wolf RIVER | LOCAL | Routine |  | UB60 | Tom Hardinger
July 11 | Wed | Craig Open | [7 empty] | UB60
|  | Craig Open | [7 empty] | UB60
July 12 | Thur | Craig Open | [7 empty] | UB60
July 16 | Mon | 7 am - 10 am | SW-LAX | B320016 | STH 35 | E BLACK RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 10 am - 12 pm | SW-LAX | B320018 | STH 35 | W BLACK RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 12:30 pm - 1:30 p, | SW-LAX | B320079 | USH 53 | BLACK RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 2 pm - 4 pm | SW-LAX | B320069 | CTH C | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger/TC flagger for CTH B - remove loose concrete
[10 empty] | UB60 | Mike O.
July 17 | Tues | 7 am - 8 am | SW-LAX | B320023 | IH 90 EB | LA CROSSE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 8:30 am - 10 am | SW-LAX | B320025 | IH 90 EB | CP RR/Bike Trail | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 10:30 am - 12pm | SW-LAX | B320029 | IH 90 EB | STH 162 | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | Flagger needed for STH 162
|  | 1 pm - 2:30 pm | SW-LAX | B320030 | IH 90 WB | STH 162 | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | Flagger needed for STH 162
|  | 3 pm -4 pm | SW-LAX | B320026 | IH 90 WB | CP RR/Bike Trail | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 4:30 pm - 5:30 pm | SW-LAX | B320024 | IH 90 WB | LA CROSSE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
July 18 | Wed | 7 am - 8 am | SW-LAX | B290007 | USH 12-STH 16 | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 8:30 am - 9:30 am | SW-LAX | B290018 | IH 90 EB - IH 94 EB | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 10 am - 12 pm | SW-LAX | B290019 | IH 90 WB - IH 94 WB | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 1 pm - 2pm | SW-LAX | B410026 | IH 90 EB | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 2:30 pm - 3:30 pm | SW-LAX | B410027 | IH 90 WB | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 4 pm - 5pm | SW-LAX | B410147 | USH 12-STH 16 | CP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
July 19 | Thur | 7 am - 8:30 am | SW-LAX | B410028 | IH 94 EB | Foley Avenue/UP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 9 am - 10:30 am | SW-LAX | B410029 | IH 94 WB | Foley Avenue/UP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 11 am - 12:30 pm | SW-LAX | B410063 | IH 94 WB | UP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
|  | 1 pm - 3 pm | SW-LAX | B410062 | IH 94 EB | UP RR | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O. | RR flagger needed.
July 23 | Mon |  | NWSUP | B160014 | STH 13 | MIDDLE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | PIER, BEARING, AND PLATE INSPECTION
|  |  | NWSUP | B160015 | STH 13 | POPLAR RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | PIER, BEARING, AND PLATE INSPECTION
|  |  | NWSUP | B160016 | STH 13 | LAKE CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | PIER, BEARING, AND PLATE INSPECTION
|  |  | NWSUP |  |  |  | STATE HIGHWAY DEPT |  |  | UB60 | Bill K.
July 24 | Tues |  | NWSUP | B160053 | STH 13 | MILLER CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | NEW DECK SOON / TOP PLATE INSPECT PRE
|  |  | NWSUP | B040011 | STH 13 | SAND RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | PIER, BEARING & PLATES
|  |  | NWSUP |  |  |  | STATE HIGHWAY DEPT |  |  | UB60 | Bill K.
July 25 | Wed |  | NWSUP | B040014 | STH 27 | EAU CLAIRE RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | INSPECT COVER PLATES
|  |  | NWSUP | B160003 | STH 105 | POKEGAMA CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Bill K. | 12 MO SCHEDULE / PIER & BEARING INSPECT
NWSUP
July 26 | Thur
July 30 | Mon | 7 am - 5 pm | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine | Deck Truss | Both UB60 & A62 | Jim Kast / Mark Dent
July 31 | Tues | 7 am - 5 pm | SW-LAX | B290011 | STH 82 | WISCONSIN RIVER 17 | STATE HIGHWAY DEPT | FC/Routine | Deck Truss | Both UB60 & A62 | Jim Kast / Mark Dent
Aug 1 | Wed | 7 am - 5 pm | SW-LAX | B290070 | WASHINGTON ST | BARABOO RIVER | TOWN | Interim |  | UB60 | Mike O.
|  | 7 am - 5 pm | SW-LAX | B290071 | CTH G | CASTLE ROCK FLOWAGE | COUNTY | Interim |  | UB60 | Mike O.
|  | 7 am - 5 pm | SW-LAX | B290098 | CTH H | LEMONWEIR RIVER | COUNTY | Interim |  | UB60 | Mike O.
|  | 7 am - 5 pm | SW-LAX | B290127 | CTH H | CTH C/CPRS RR | COUNTY | Interim |  | UB60 | Mike O.
Aug 2 | Thurs | 7 am - 8 am | SW-LAX | B410015 | STH 71-STH 131-WALKER ST | KICKAPOO RIVER | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 8:30 am - 9:30 am | SW-LAX | B410005 | STH 27 | SOPER CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
|  | 10:30 am - 12 pm | SW-LAX | B410397 | STH 27 | DUSTIN CREEK | STATE HIGHWAY DEPT | Interim |  | UB60 | Mike O.
August 6 | Mon | 9:00 -2:00 | NC-WR | B-71-33 | STH 54 | Wisconsin River | state | Routine | Prestressed | UB60 | TOM
NC-WR
August 7 | Tues | 8:00 - 3:00 | NC-WR | B-37-75 | I39 NB | Wisconsin River | STATE HIGHWAY DEPT | Routine | Steel | UB60 | TOM
|  |  | NC-WR | B-37-108 | I39 SB | Wisconsin River | STATE HIGHWAY DEPT | routine | steel | UB60 | TOM
August 8 | Wed | 8:00 - 3:00 | NC-WR |  | City of Wausau Bridges |  | No request yet -Contract not negoiated | Placeholder |  | UB60 | TOM
|  |  | NC-WR | [6 empty] | UB60 | TOM
August 9 | Thur | 8:00 - 3:00 | NC-WR |  | City of Wausau Bridges |  |  | placeholder |  | UB60 | TOM
|  |  | NC-WR | [6 empty] | UB60 | TOM
August 13 | MON | MEETINGS | [7 empty] | UB 60
UB 60
UB 60
UB 60
UB 60
August 14 | TUE | 8;00AM-4;00PM | NW-SUP | B-16-38 | US-2 | IH 35 Minnesota | STATE | Routine | Steel | UB 60 | Bill. K
UB 60
UB 60
UB 60
UB 60
August 15 | WED | 8:00AM-4:00PM | NW-SUP | B-16-38 | US-2 | IH-35-Minnesota | STATE | Routine | Steel | UB 60 | Bill. K
UB 60
UB 60
UB 60
UB 60
August 16 | Thur | 8:00AM-4:00PM | NW-SUP | B-16-38 | US-2 | IH-35-Minnesota | STATE | Routine | Steel | UB 60 | Bill. K
UB 60
UB 60
August 20 | MON | 8:00AM-400PM | NW-SUP | B-16-38 | US-2 | IH-35-Minnesota | STATE | Routine | Steel | UB 60 | Bill. K
UB 60
UB 60
UB 60
UB 60
August 21 | TUE | 8:00AM-4:00PM | NW-SUP | B-16-38 | US-2 | IH-35-Minnesota | STATE | Routine | Steel | UB 60 | Bill. K
UB 60
UB 60
UB 60
UB 60
August 22 | WED | 8;00AM-4:00PM | NW-SUP | B-16-38 | US-2 | IH-35-Minnesota | State | Routtine | Steel | UB 60 | Bill. K
UB 60
UB 60
UB 60
UB 60
August 23 | Thur | [8 empty] | UB 60
UB 60
August 27 | Mon | Working with the repwir crew | [7 empty] | UB 60
UB 60
UB 60
UB 60
UB 60
August 28 | Tues | Working with the repair crew | [7 empty] | UB 60
UB 60
UB 60
UB 60
[10 empty] | UB 60 | TOM
August 29 | Wed | 8:00AM-400PM | NC-WR |  |  |  | LOCAL |  |  | UB 60
UB 60
August 30 | Thur | 8:00AM-400PM | NC-WR |  |  |  | LOCAL |  |  | UB 60 | TOM
Sept 3 | Mon | HOLIDAY
Sept 4 | Tue | 11:00:00 AM - 4 PM | NC-RHI | B-19-1 | STH 101 | Popple River | State | Routine | Steel beams | UB-60 | Brock
|  |  | NC-RHI | B-19-509 | STH 101 | Pine River | State | Routine, FC | Steel Truss | UB-60 | Brock
|  |  | NC-RHI | B-19-6 | USH 2 | Menominee River | State | Routine | Concrete Girder | UB-60 | Brock
Sept 5 | Wed | 9:00 - 230 PM | NC-RHI | B-19-3 | CTH N | Menominee River | County | Routine | Concrete Girder | UB-60
|  |  | NC-RHI | B-19-12 | CTH N | River | County | Routine | Concrete Girder | UB-60
|  |  | NC-RHI | [6 empty] | UB-60
Sept 6 | Thur | 9:00 - 2:00 PM | NC-RHI | B-58-55 | Stoney Hill | Embarrass River | Town | Routine | Steel girder | UB-60
|  |  | NC-RHI | B-58-718 | CTH A | Red River | County | Routine | steel thru girder | UB-60
|  |  | NC-RHI | [6 empty] | UB-60
Sept 10 | Mon | 9:00am - 11:00am | NW EAU | B-17-951 | CTH BB | TAINTER LAKE | Dunn County | ROUTINE | Deck Truss | UB-60 | LEE
|  | 11:30am - 12:30pm | NW EAU | B-17-853 | CTH G | TAINTER LAKE | Dunn County | ROUTINE | Prestressed Girder | UB-60 | LEE
|  | 1:00pm - 3:00pm | NW EAU | B-17-68 | CTH D | HAY RIVER | Dunn County | ROUTINE | Steel Girder | UB-60 | LEE
Sept 11 | Tue | 9:00am - 11:00am | NW EAU | B-17-62 | CTH MW | RED CEDAR RIVER | Dunn County | ROUTINE | Steel Girder | UB-60 | LEE
|  | 11:30am - 2:00pm | NW EAU | B-17-192 | CTH V | RED CEDAR RIVER | Dunn County | ROUTINE | Prestressed Girder | UB-60 | LEE
Sept 12 | Wed | 9:00am - 11:00am | NW EAU | B-17-78 | CTH D | RED CEDAR RIVER | Dunn County | ROUTINE | Prestressed Girder | UB-60 | LEE
|  | 11:30am - 2:00pm | NW EAU | B-17-154 | CTH Y | RED CEDAR RIVER | Dunn County | ROUTINE | Prestressed Girder | UB-60 | LEE
Sept 13 | Thur | 8:00am - 11:00am | NW EAU | B-10-378 | CTH G | BLACK RIVER | CLARK County | ROUTINE | Overhead Truss | UB-60 | LEE
|  | 11:30am - 12:30pm | NW EAU | B-10-100 | OPETT AVE | BLACK RIVER | CLARK County | ROUTINE | Prestressed Girder | UB-60 | LEE
|  | 1:00pm - 3:00pm | NW EAU | B-10-36 | CTH D | POPPLE RIVER | CLARK County | ROUTINE | Prestressed Girder | UB-60 | LEE
Sept 17 | MON | 8AM - 10AM | NW SUP | B48-3 | USH 8 | ST CROIX RIVER | STATE | ROUTINE | STEEL TRUSS MOD | UB60 | Bill K.
|  | 10:30AM - 12:00PM | NW SUP | B48-3 | USH 8 | ST CROIX RIVER | STATE | ROUTINE | STEEL TRUSS MOD | UB60 | Bill K.
|  | LUNCH | NW SUP | B48-3 | USH 8 | ST CROIX RIVER | STATE | ROUTINE | STEEL TRUSS MOD | UB60 | Bill K.
|  | 12:30PM - 2:00PM | NW SUP | B48-3 | USH 8 | ST CROIX RIVER | STATE | ROUTINE | STEEL TRUSS MOD | UB60 | Bill K.
|  | 2PM - 4PM | NW SUP | B48-3 | USH 8 | ST CROIX RIVER | STATE | ROUTINE | STEEL TRUSS MOD | UB60 | Bill K.
Sept 18 | TUE | 8AM - 10AM | NW SUP | B48-10 | STH 65 | SOO LINE | STATE | ROUTINE / REPAIR | STEEL | UB60 | Bill K.
|  | 10:30AM - 12:00PM | NW SUP | B48-10 | STH 65 | SOO LINE | STATE | ROUTINE / REPAIR | STEEL | UB60 | Bill K.
|  | LUNCH | NW SUP | B48-10 | STH 65 | SOO LINE | STATE | ROUTINE / REPAIR | STEEL | UB60 | Bill K.
|  | 12:30PM - 2:00PM | NW SUP | B48-10 | STH 65 | SOO LINE | STATE | ROUTINE / REPAIR | STEEL | UB60 | Bill K.
|  | 2PM - 4PM | NW SUP | B48-10 | STH 65 | SOO LINE | STATE | ROUTINE / REPAIR | STEEL | UB60 | Bill K.
2018-09-19 | Wed | Polk county | NW SUP |  |  |  | State |  |  | UB60 | Bill K
2018-09-20 | Thur | Polk county | NWSUP |  |  |  | State |  |  | UB60 | Bill K
Sept 24 | Mon | 9:00am - 11:00am | NW EAU | B-27-73 | USH 12 - STH 27/54 - MAIN ST | BLACK RIVER | Jackson County | ROUTINE | Steel Girder | UB60 | LEE
|  | 12:00pm - 2:30pm | NW EAU | B-27-98 | HOGG STREET | DOUGLAS CREEK | Jackson County | ROUTINE | Prestressed Girder | UB60 | LEE
Sept 25 | Tue | 9:00am - 11:00am | NW EAU | P-27-129 | SUNNY VALE ROAD | ROARING CREEK | Jackson County | ROUTINE | Prestressed Girder | UB60 | LEE
|  | 11:30am - 12:30pm | NW EAU | B-27-96 | WEST KNUTES ROAD | E FK BLACK RIVER | Jackson County | ROUTINE | Haunched Slab | UB60 | LEE
|  | 1:00pm - 2:30pm | NW EAU | B-27-78 | PRAY ROAD | E FK BLACK RIVER | Jackson County | ROUTINE | Haunched Slab | UB60 | LEE
NW EAU
Sept 26 | Wed | 9:00AM-2:00PM | SE | B-40-1132 | Ramp,IH43 NB-W Michigan St | IH 94 | STATE | ROUTINE | Steel Girder | UB60 | Scot Reay
|  |  | SE | B-40-1111-1 | IH 43 NB | W St Paul Ave | STATE | ROUTINE | Steel Girder | UB60 | Scot Reay
Sept 27 | Thur | 9:00AM-2:00PM | SE | B-40-1111-2 | IH 43 NB | IH 794 | STATE | ROUTINE | Steel Girder | UB60 | Scot Reay
Oct 1 | Mon | 8AM - 10AM | NW-SUP | B7-20 | STH 70 | ST CROIX RIVER | STATE | ROUTINE | STEEL | UB60 | Bill K. | BORDER BRIDGE
|  | 10:30AM - 12:00PM | NW-SUP | B7-20 | STH 70 | ST CROIX RIVER | STATE | ROUTINE | STEEL | UB60 | Bill K. | BORDER BRIDGE
|  | LUNCH | NW-SUP | B7-20 | STH 70 | ST CROIX RIVER | STATE | ROUTINE | STEEL | UB60 | Bill K. | BORDER BRIDGE
|  | 12:30PM - 2:00PM | NW-SUP | B7-20 | STH 70 | ST CROIX RIVER | STATE | ROUTINE | STEEL | UB60 | Bill K. | BORDER BRIDGE
|  | 2PM - 4PM | NW-SUP | B7-20 | STH 70 | ST CROIX RIVER | STATE | ROUTINE | STEEL | UB60 | Bill K. | BORDER BRIDGE
Oct 2 | TUE | 8AM - 10AM | NW-SUP | B7-6 | STH 77 | ST CROIX RIVER | STATE | ROUTINE | CONC | UB60 | Bill K. | BORDER BRIDGE
|  | 10:30AM - 12:00PM | NW-SUP | B7-6 | STH 77 | ST CROIX RIVER | STATE | ROUTINE | CONC | UB60 | Bill K. | BORDER BRIDGE
|  | LUNCH | NW-SUP | B7-6 | STH 77 | ST CROIX RIVER | STATE | ROUTINE | CONC | UB60 | Bill K. | BORDER BRIDGE
|  | 12:30PM - 2:00PM | NW-SUP
Oct 3 | WED
Oct 4 | Thur
Oct 8 | Mon | 9:00am - 11:00am | NW EAU | B-09-3 | CTH M | Chippewa River | Chippewa County | FC, Routine | Low Truss | UB60 | Mark Dent
|  | 11:30am - 12:30pm | NW EAU | B-09-9 | CTH S | Yellow River | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
|  | 1:00pm - 1:30pm | NW EAU | B-09-98 | CTH XX | Yellow River | Chippewa County | Routine | Prestressed Girders | UB60 | Mark Dent
|  | 2:00pm - 3:30pm | NW EAU | B-09-116 | CTH S | Lake Wissota | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
Oct 9 | Tue | 7:00am - 9:00am | NW EAU | B-09-123 | CTH Y | Chippewa River | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
|  | 9:30am - 11:30am | NW EAU | B-09-379 | CTH G | Yellow River | Chippewa County | FC, Routine | Overhead Truss | UB60 | Mark Dent
|  | 12:00pm - 1:00pm | NW EAU | B-09-382 | CTH O | Yellow River | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
|  | 1:30pm - 3:00pm | NW EAU | B-09-497 | CTH K | Yellow River | Chippewa County | FC, Routine | Overhead Truss | UB60 | Mark Dent
|  | 3:30pm - 4:30pm | NW EAU | P-09-85 | CTH S | Yellow River | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
Oct 10 | Wed | 7:00am - 8:30am | NW EAU | B-09-120 | 130th AVE | Yellow River | Chippewa County | Routine | Prestressed Girder | UB60 | Mark Dent
|  | 9:00am - 10:00am | NW EAU | P-09-948 | 170th AVE/Otter Lake Rd | Otter Creek | Chippewa County | Routine | Prestressed Girder | UB60 | Mark Dent
|  | 10:30am - 11:30am | NW EAU | B-09-001 | STH 124 | Duncan Creek | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
|  | 12:00pm - 1:00pm | NW EAU | B-09-97 | Bridgewater Ave | Duncan Creek | Chippewa County | Routine | Steel Girder | UB60 | Mark Dent
|  | 1:30pm - 3:00pm | NW EAU | B-09-100 | Columbia Street | Duncan Creek | Chippewa County | Routine | Prestressed Girder | UB60 | Mark Dent
Oct 11 | Thur | 7:00am - 8:00am | NW EAU | B-09-264 | Grand AVE | Duncan Creek | Chippewa County | Routine | Prestressed Box Girder | UB60 | Mark Dent
|  | 8:30am - 9:30am | NW EAU | B-09-711 | Spring Street | Duncan Creek | Chippewa County | Routine | Concrete Arch | UB60 | Mark Dent
|  | 10:00am - 12:00pm | NW EAU | P-09-715 | Central Street | Duncan Creek | Chippewa County | FC, Routine | Overhead Truss | UB60 | Mark Dent
|  | 12:30pm - 2:00pm | NW EAU | B-09-101 | Main Street | Yellow River | Chippewa County | Routine | Prestressed Girder | UB60 | Mark Dent
Oct 15 | Mon | 9:00am - 12:00pm | NW | B-18-167 | USH 53 NB | Eau Claire River | State | Routine | Steel Deck Girder | UB60 | Lee Balsiger
|  | 12:00pm - 3:00pm | NW | B-18-168 | USH 53 SB | Eau Claire River | State | Routine | Steel Deck Girder | UB60 | Lee Balsiger
Oct 16 | Tue | 8:00am - 10:00am | NW | B-09-146 | STH 124 NB | Chippewa River | State | Routine | Steel Deck Girder | UB60 | Lee Balsiger
|  | 10:00am - 2:00pm | NW | B-09-147 | STH 124 SB | Chippewa River | State | Routine/Repairs | Steel Deck Girder | UB60 | Lee Balsiger
Oct 17 | Wed | 8:00am - 12:00pm | NW | B-09-49 | USH 53 NB | Chippewa River | State | Routine/Repairs | Steel Deck Girder | UB60 | Lee Balsiger
|  | 12:00pm - 2:00pm | NW | B-09-48 | USH 53 SB | Chippewa River | State | Routine | Steel Deck Girder | UB60 | Lee Balsiger
Oct 18 | Thur | 9:00am - 2:00pm | NW | B-09-87 | STH 64- Bridge Street | Chippewa River | State | FC, Routine | Steel Tied Arch | UB60 | Mark and Craig | Need Experienced Operator
Oct 22 | Mon |  | NW | B-18-2,5,13,47,80, P18-99 |  |  | Local - Eau Claire County |  |  |  | Craig and ???
|  |  |  | B-18-60, 88, 172, P-18-57 |  |  | Local - Eau Claire County |  |  |  | Craig and ???
Oct 23 | Tue |  | NW |  |  |  | Local - Eau Claire County |  |  |  | Craig and ???
[7 empty] | Local - Eau Claire County |  |  |  | Craig and ???
Oct 24 | Wed |  | NW |  |  |  | Local - Eau Claire County |  |  |  | Craig and ???
[7 empty] | Local - Eau Claire County |  |  |  | Craig and ???
[7 empty] | Local - Eau Claire County |  |  |  | Craig and ???
Oct 25 | Thur |  | NW |  |  |  | Local - Eau Claire County |  |  |  | Craig and ???
Oct 29 | Mon | Truck Unavailable
Oct 30 | Tue | Truck Unavailable
Oct 31 | Wed | Truck Unavailable
Nov 1 | Thur | Truck Unavailable
Nov 5 | Mon | 9:00am - 12:00pm | NE | B-36-6 | Local Road | CTH R (Rapids) | Local - Manitowoc County | Routine | Steel Deck Girder | UB60 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-36-1 | Local Road | Old CTH Y (Larabee) | Local - Town of Gibson | Routine | Steel Deck Girder | UB60 | Roy Tilleman
|  |  | NE | [6 empty] | UB60 | Roy Tilleman
Nov 6 | Tue | 9:00am - 12:00pm | NE | B-5-18 | Local Street | Ashland over R/R (Green Bay) | Local - City of Green Bay | Routine | Steel Deck Girder | UB60 | Roy Tilleman
|  | 1:00pm - 3:00pm | NE | B-5-225 | Local Street | Atkinson over R/R (Green Bay) | Local - City of Green Bay | Routine | Steel Deck Girder | UB60 | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Nov 7 | Wed | Reserved for Bridge Maintenance | NE | [7 empty] | Roy Tilleman
|  |  | NE | [7 empty] | Roy Tilleman
Nov 8 | Thur | Reserved for Bridge Maintenance | NE | [7 empty] | Roy Tilleman
NE

## A-52
Date | Region | Structure(s) | Feature On | Feature Under | Owner | Work Type | Bridge Type | Truck(s) needed | Crew Needed | Notes
2018-04-02 | NWEC | B-47-0040 | USH 10 | St. Croix River | State | Wash |  | A52 | Jim/Mark
2018-04-03 | NWEC | B-47-0040 | USH 10 | St. Croix River | State | Wash |  | A52 | Jim/Mark
2018-04-04 | NCWR | B-39-50 |  |  |  | Birdnetting |  | A52 | Jim/Mark
2018-04-05 | NCWR | B-39-970, B-39-49 |  |  |  | Birdnetting |  | A52 | Jim/Mark
2018-04-09 | NE | TBD |  |  |  | Maintenance work |  | A52 | Jim/Mark
2018-04-10 | NE | B-15-4-3 | STH 42 (Bayview Bridge) | Sturgeon Bay | State | Conduit Install |  | A52 | Jim/Mark
2018-04-11 | NE | TBD |  |  |  | Maintenance work |  | A52 | Jim/Mark
2018-04-12 | NE | TBD |  |  |  | Maintenance work |  | A52 | Jim/Mark
2018-04-16 | SWL | B120027 | USH 18 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 2 Days
2018-04-17 | SWL | B120027 | USH 18 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 2 Days
2018-04-18 | SWL | B120009 | STH 82 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 1.5 Days
2018-04-19 | SWL | B120009 | STH 82 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 1.5 Days
2018-04-23 | --- | --- | --- | --- | --- | --- | --- | --- | --- | Mark with UB-60 Crew; Jim down at Self Rescue Training.
2018-04-24 | --- | --- | --- | --- | --- | --- | --- | --- | --- | Mark with UB-60 Crew; Jim down at Self Rescue Training.
2018-04-25 | --- | --- | --- | --- | --- | --- | --- | --- | --- | Mark with UB-60 Crew; Jim down at Self Rescue Training.
2018-04-26 | --- | --- | --- | --- | --- | --- | --- | --- | --- | Mark with UB-60 Crew; Jim down at Self Rescue Training.
2018-04-30 | SWL | B220060 | USH 61/151 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 1.5 Days
2018-05-01 | SWL | B220060 | USH 61/151 | Mississippi River | State | Washing |  | A52 | Jim/Mark | 1.5 Days
2018-05-02 | SWL | B220020 | STH 133 | Green River | State | Washing/Repair |  | A52 | Jim/Mark
2018-05-03 | SWL | B220020 | STH 133 | Green River | State | FC Insp |  | A52 | Jim/Mark
2018-05-07 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-08 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-09 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-10 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-14 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-15 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-16 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-17 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-21 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-22 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-23 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-24 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark | May take 2-weeks
2018-05-28
2018-05-29
2018-05-30
2018-05-31
2018-06-04 | SW-LAX | B320115 | STH 16 EB | LA CROSSE RIVER | State | In-depth |  | Both UB60 & A62 | Jim/Mark
2018-06-05 | SW-LAX |  |  |  | State |  |  |  | Jim/Mark
2018-06-06 | SW-LAX | Various (split crew) | USH 14 EB | Mississippi River | State | FC |  | UB60 | Jim/Mark
2018-06-07 | SW-LAX | Various (split crew) | USH 14 EB | Mississippi River | State | FC |  | 80" lift & UB 60 | Jim/Mark
2018-06-11 | NC-WR |  |  |  | State |  |  | Both UB60 & A62 | Jim/Mark | tub inspections
2018-06-12 | NC-WR |  |  |  | State |  |  | Both UB60 & A62 | Jim/Mark | tub inspections
2018-06-13 | NC-WR |  |  |  | State |  |  | Both UB60 & A62 | Jim/Mark | tub inspections
2018-06-14 | NC-WR |  |  |  | State |  |  | Both UB60 & A62 | Jim/Mark | tub inspections
2018-06-18 | SE | B-40-854 | Ramp, IH 94 WB - IH 41 SB | IH 41/IH 94 | State | Initial FC/Routine | Steel Tub Girder | A52 w/Platform | Jim/Mark | Zoo Interchange
2018-06-19 | --- | --- | --- | --- | --- | --- | --- | CHANGE OUT TO BUCKET | Jim/Mark | CHANGE OUT PLATFORM
2018-06-20 | --- | --- | --- | --- | --- | --- | --- | CHANGE OUT TO BUCKET | Jim/Mark | CHANGE OUT PLATFORM
2018-06-21 | --- | --- | --- | --- | --- | --- | --- | CHANGE OUT TO BUCKET | Jim/Mark | CHANGE OUT PLATFORM
2018-06-25 | NE | B-70-61 | STH 441 SB | LLBDM (Menasha) | State | Routine - Initial | Steel Deck Girder | A62 & A52 w/Special bucket | Jim/Mark
2018-06-26 | NE | B-70-61 | STH 441 SB | LLBDM (Menasha) | State | Routine - Initial | Steel Deck Girder | A62 & A52 w/Special bucket | Jim/Mark
2018-06-27
2018-06-28
2018-07-02 | --- | --- | --- | --- | --- | --- | --- | VACATION (Mark/Jim) | --- | VACATION
2018-07-03 | --- | --- | --- | --- | --- | --- | --- | VACATION (Mark/Jim) | --- | VACATION
2018-07-04 | --- | --- | --- | --- | --- | --- | --- | VACATION (Mark/Jim) | --- | VACATION
2018-07-05 | --- | --- | --- | --- | --- | --- | --- | VACATION (Mark/Jim) | --- | VACATION
2018-07-09 | --- | --- | --- | --- | --- | --- | --- | CHANGE BACK TO PLATFORM | Jim/Mark | CHANGE OUT PLATFORM
2018-07-10 | --- | --- | --- | --- | --- | --- | --- | CHANGE BACK TO PLATFORM | Jim/Mark | CHANGE OUT PLATFORM
2018-07-11 | NWEC | EAU CLAIRE | --- | --- | --- | --- | --- | --- | --- | CHANGE OUT PLATFORM
2018-07-12 | NWEC | EAU CLAIRE
2018-07-16 | SWM | B-25-92 | STH 78 | BLUE MOUNDS ROAD | STATE | FLASHING |  | A52 | Jim/Matt | Open rail flashing installation
2018-07-17 | SWM | B-25-165 | STH 39 | BLUE MOUNDS ROAD | STATE | FLASHING |  | A52 | Jim/Matt | Open rail flashing installation
2018-07-18 | NWEC | EAU CLAIRE | [7 empty] | Filler Work
2018-07-19 | NWEC | EAU CLAIRE | [7 empty] | Filler Work
2018-07-23 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark
2018-07-24 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark
2018-07-25 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark
2018-07-26 | SWM | B560041 | Trout Road | IH90/94 | State | Heat Straightening |  | MANLIFTS | Jim/Mark
2018-07-30 | SW-LAX | B290011 | STH 82 | Wisconsin River | State | FC/Routine |  | Both UB60 & A62 | Jim/Matt | Mark with UB60
2018-07-31 | SW-LAX | B290011 | STH 82 | Wisconsin River | State | FC/Routine |  | Both UB60 & A62 | Jim/Matt | Mark with UB60
2018-08-01 | SW-LAX | [8 empty] | Mark with UB60
2018-08-02 | SW-LAX | [8 empty] | Mark with UB60
2018-08-06 | SW Mad | b13-649/650 | USH 151-Verona Road | roundabout | State | Routine/FC | Steel Pier Cap | Portable Man Lift | Nate | Provide Man Lift.
Monday, August 06 | NW |  | STH 124 | Chippewa Falls | State | Research Install |  | A52 | Jim/Matt | Install Ice Protection
2018-08-07 | NW |  | STH 124 | Chippewa Falls | State | Research Install |  | A52 | Jim/Matt | Install Ice Protection
2018-08-08 | NE | B44-184 | Lawe St (STH 55) | Fox River | State |  |  | A52 | Jim/Matt/Nate
2018-08-09
2018-08-13 | BOS | ANNUAL MEETING |  |  |  |  | ANNUAL MEETING
2018-08-14 | NW |  | STH 124 | Chippewa Falls | State | Research Install |  | A52 | Jim/Matt/Nate
2018-08-15 | NW |  | STH 124 | Chippewa Falls | State | Research Install |  | A52 | Jim/Matt/Nate
2018-08-16 | NW |  | STH 124 | Chippewa Falls | State | Research Install |  | A52 | Jim/Matt/Nate
2018-08-20 | SWL | B-22-46 | CTH T | Wisconsin River | State | Bearing Replacement |  | A52 | Jim/Matt/Nate
2018-08-21 | SWL | B-22-46 | CTH T | Wisconsin River | State | Bearing Replacement |  | A52 | Jim/Matt/Nate
2018-08-22 | SWL | B-22-46 | CTH T | Wisconsin River | State | Bearing Replacement |  | A52 | Jim/Matt/Nate
2018-08-23 | SWL | B-22-46 | CTH T | Wisconsin River | State | Bearing Replacement |  | A52 | Jim/Matt/Nate
2018-08-27 | NW | TBD | [5 empty] | A52 | JIM/MATT
2018-08-28 | NW | TBD | [5 empty] | A52 | JIM/MATT
2018-08-29 | NW | TBD | [5 empty] | A52 | JIM/MATT
2018-08-30 | NW | TBD | [5 empty] | A52 | JIM/MATT
2018-09-03 | NE | S-70-132, S-70-151 | [5 empty] | A52 | JIM/MATT | Try out new Torque Gun from Representative on a couple of signs
2018-09-04 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-05 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-06 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-10 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-11 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-12 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-13 | NE | TBD | [5 empty] | A52 | JIM/MATT
2018-09-17 | NE | B-5-158 | I 43 | Fox River | State | FC | Tied Arch | A62 & A52 | Jim/Mark
2018-09-18 | NE | B-5-158 | I 43 | Fox River | State | FC | Tied Arch | A62 & A52 | Jim/Mark
2018-09-19 | NE | B-5-158 | I 43 | Fox River | State | FC | Tied Arch | A62 & A52 | Jim/Mark
2018-09-20 | NE | B-5-158 | I 43 | Fox River | State | FC | Tied Arch | A62 & A52 | Jim/Mark
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-08 | NW EAU |  |  |  | Chippewa County |  |  | UB60 | CO Expert | Just Mark, or whole Repair Crew?
2018-10-09 | NW EAU |  |  |  | Chippewa County |  |  | UB60 | CO Expert | Just Mark, or whole Repair Crew?
2018-10-10 | NW EAU |  |  |  | Chippewa County |  |  | UB60 | CO Expert | Just Mark, or whole Repair Crew?
2018-10-11 | NW EAU |  |  |  | Chippewa County |  |  | UB60 | CO Expert | Just Mark, or whole Repair Crew?
2018-10-15 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-16 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-17 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-18 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-22 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-23 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-24 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-25 | NC | B-37-337 |  |  |  | BEARING ANCHORAGE |  | A52 | JIM/MATT
2018-10-29 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-10-30 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-10-31 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-01 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-05 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-06 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-07 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-08 | NE | B-70-247 |  |  | Oshkosh | Maintenance Painting |  | A52 | Jim/Nate/Matt
2018-11-12 | NC | B26-6 |  |  |  | Heat Straightening |  | A52 | Jim/Nate/Matt
2018-11-13 | NC | B26-6 |  |  |  | Heat Straightening |  | A52 | Jim/Nate/Matt
2018-11-14 | NC | B26-6 |  |  |  | Heat Straightening |  | A52 | Jim/Nate/Matt
2018-11-15 | NC | B26-6 |  |  |  | Heat Straightening |  | A52 | Jim/Nate/Matt
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-12-03
2018-12-04
2018-12-05
2018-12-06
2018-12-10
2018-12-11
2018-12-12
2018-12-13
2018-12-17
2018-12-18
2018-12-19
2018-12-20
2018-12-24
2018-12-25
2018-12-26
2018-12-27