## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20160614 | 20160614010 | 10 | Questions | Can we get a copy of the engineers schedule? and soil borings? | Engineer's schedule and soil borings information can be found at: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | WisDOT Q&A | 1 | 2016-05-27 09:42 | 2016-05-31 14:49
20160614 | 20160614010 | 10 | Earthwork | It appears the plan for the subject project doesn't include excavation of the existing organics/topsoil on to top of the section of the graded roadway that was been previously constructed. Is WisDOT planning on building the new base and pavement on-top of the existing topsoil in this area? Will the excavation of the existing organics be added into the project plans? | Existing topsoil/organics under the proposed roadway section will be removed as part of the project. In areas where the subgrade elevation is below the topsoil, the existing topsoil removal is quantified as Common Excavation. Additional topsoil on the project is being removed as part of the Salvaged Topsoil item. A review of the soil borings shows the expansion project will result in excess topsoil that is not fully covered as part of the Salvaged Topsoil item. In order to account for the removal of the excess topsoil on the project, an undistributed quantity of 2,500 CY of EBS will be added to the project to cover the removal of the existing surface topsoil/organics. An addendum will be issued to resolve this. | Mike Coleman | 2 | 2016-05-31 15:33 | 2016-06-06 14:40
20160614 | 20160614016 | 16 | Contract Start Date | Why is the job being bid in June with January 1 start date? Material suppliers can not predict the costs that far ahead. | It is anticipated a full construction year is needed to complete the project, and with the construction staging requirements and commitments to the local municipality, we could not allow construction to start until 2017. | Mike Coleman | 1 | 2016-06-01 17:09 | 2016-06-02 14:15
20160614 | 20160614014 | 14 | Start Date | The project has a June 5, 2017 start date. Can any work occur prior? | The region will allow work prior to the June 5, 2017 start date, but only in the eastbound lanes of STH 29 east of the CTH X interchange. | Mike Coleman | 1 | 2016-06-06 11:11 | 2016-06-06 11:12
20160614 | 20160614005 | 5 | Dowel Bars | DOT received the following question: There are no dowel bars in the plan, are there supposed to be? | There are no dowel bars in the plan because the existing pavement is not doweled and we want all the concrete panels to behave the same. | Mike Coleman | 1 | 2016-06-06 12:38 | 2016-06-06 13:20
20160614 | 20160614010 | 10 | Storm Sewer | Please check the bid quantities for the manhole 4 ft diameter and catch basin 4 ft diameter items on projects 3738-02-73 and 3738-06-60. I find the following differences: Manholes 4 ft diameter bid as 5 each. I only find 2 each. Catch basins 4 ft diameter bid as 3 each. I find 5 each. | An addendum will be issued to resolve the associated quantity revisions. | Mike Coleman | 3 | 2016-06-06 15:49 | 2016-06-06 15:54
20160614 | 20160614010 | 10 | Earthwork Tables | The cut areas seem high for the work shown in the earthwork data tables for Eastbound STH 165 on ID 3738-02-73. | An addendum will be issued to resolve the associated quantity revisions. | Mike Coleman | 4 | 2016-06-06 15:50 | 2016-06-06 15:55
20160614 | 20160614016 | 16 | Miscellaneous Water/Sewer | 1) Who is the project leader/engineer going to be? 2) New water distribution piping is taking place throughout the project. Based on new water main being in the same proximity of existing water mains, temporary water service will need to be provided to each property along this project. Does the village have certain requirements for this. Is hooking up temp water services to hose bibs at each property acceptable? 3) Stage I construction identifies the work limits from street side edge of sidewalk to opposite side edge of sidewalk. The new sanitary, water and storm laterals need to be installed to the right of way during this stage. What will be required if this work impedes phase II limits? | 1) Wonâ€™t likely know until late this fall. 2) The City doesnâ€™t have a problem with the temporary hook-ups providing the contractor is responsible for installing and removing the hook-up as well as any resulting problems with backflow devices encountered, and that all WisDNR regulations are adhered to. 3) Please refer to Article #4, Prosecution and Progress, page 6, paragraph 3 under Stage 1 in the special provisions. | Scott lawry | 2 | 2016-06-07 12:40 | 2016-06-07 12:42
20160614 | 20160614016 | 16 | Staging | Stage 2 Question: Are flaggers needed in areas designated for local traffic? Question: If the west side sidewalk is constructed first, could they move pedestrians to the newly constructed sidewalk and then construct the east side. | Question: Are flaggers needed in areas designated for local traffic? Answer: No. This area is intended to be shared between construction and local traffic. The intent is to provide enough available width for a single lane of local traffic to safely pass. Question: If the west side sidewalk is constructed first, could they move pedestrians to the newly constructed sidewalk and then construct the east side. Answer: Will be considered providing pedestrians have the same ability to cross to the opposite side of the street as indicated in the plans and special provisions. | Scott lawry | 3 | 2016-06-07 12:44 | 2016-06-07 12:45
20160614 | 20160614016 | 16 | DBE Requirement | Why is the DBE goal so high for this project? . From past experiences with similar jobs we have difficulties obtaining goals of 6 to 8 percent. Is there a reason the goal is so high and/or is a possible to change it to a lower level? | The assigned goal of 14% was arrived after reviewing the project work activities and of those activities which are traditionally completed by a DBE contractor. The goal will not be revised. The process that should be followed if unable to achieve the assigned goal is outlined in ASP 3 of the proposal. | Scott lawry | 4 | 2016-06-07 13:26 | 2016-06-07 15:07
20160614 | 20160614016 | 16 | Soil Borings | Are there soil borings available for any/all of this project? | The soil borings information can be found at the following location: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nc.aspx | Mike Coleman | 5 | 2016-06-07 15:06 | 2016-06-08 14:41
20160614 | 20160614014 | 14 | Staging | The staging shown in the plans does not show a separate stating for the Diamond Grinding. Will the Grinding operation need to mobilize after each repair stage or can all grinding be completed after all repairs are completed? | It could be done either way. The diamond grinding should include precautions to avoid impacting the permanent asphaltic shoulders. | Mike Coleman | 2 | 2016-06-08 07:13 | 2016-06-08 10:27
20160614 | 20160614005 | 5 | Sawing | Is the sawing quantity correct? | Yes, all remaining concrete joints will get sawed on both sides of it and get a concrete base patch. Concrete Joint and Crack Cleaning item is for Crack Cleaning. | Mike Coleman | 2 | 2016-06-08 10:28 | 2016-06-08 10:29
20160614 | 20160614011 | 11 | Quantities | What is the purpose of having an undistributed quantity of item 465.0110 - Asphaltic Surface Patching in the contract? Does the region have more background on what their intent is for the use of this item? Was it put in the plan in case it's needed during construction, or is there a specific application for this item? | The item of 465.0110 â€“ Asphaltic Surface Patching was included in the contract to allow for patching of asphalt that is carrying traffic during the construction project if deemed necessary by the project engineer. Traffic staging is expected to require traffic to be pushed onto shoulders for a period of time. If shoulder conditions are found to need to be patched at the time of construction, the item allows for that. Also, per article number 3 of the special provisions, traffic will be allowed to run on certain milled surfaces for a period of time. If the contractors operations require traffic to run on the milled surface, and the milled surface has potholes/pop-outs after milling, this item will allow for repairs to those areas and provide sufficient surface for traffic. The item was included in the contract per the guidance provided in FDM 19-7-1. The item usage will be determined by the project engineer in the field and will be based on existing field conditions and contractor operations. The item should be bid accordingly. | Mike Coleman | 1 | 2016-06-09 12:42 | 2016-06-09 14:04
20160614 | 20160614015 | 15 | Shaping Shoulders & Base patching asphaltic: | 1) Shaping Shoulders: Is this item intended to be paid along with the 3/4â€ base aggregate item for the shouldering process? 2a) Base patching asphaltic: What is the intent for this item? This item specs a 25 mm mix. 2b) Can the item be switched to a 465 item or a note added to allow 19mm mix? | 1) Yes, the shaping shoulders item is noted in the typical sections and was included to pay for the work required to shape the existing shoulder aggregate away from the edge of existing pavement and then shape the existing aggregate back to the edge of new HMA pavement. The base aggregate 3/4-inch along the mill and overlay sections is typically for low shoulder areas as noted in the typical sections. Since shaping is required and low shoulders are spotty, the shaping item will be paid for as well. 2a) The intent of this items it to fill the existing cracks and joints in the concrete pavement after removing concrete surface partial depth and preparing the foundation. 2b) We would not propose to make this a 465 item. This item could be adjusted from the typical 25mm mix requirement for base patching. Use of a 19mm or 12.5mm mix would be allowed. | Mike Coleman | 1 | 2016-06-09 15:10 | 2016-06-09 15:14
20160614 | 20160614015 | 15 | Ramps | 1) It looks like you only plan on closing the USH 45 interchange ramps? 2) Based on the typical on sheet 96 I see no way of constructing the 3â€™ and 5â€™ shoulder while the ramp is open. I believe there is a constructability issue with the STH 47 Ramps trying to do this while the ramp is open. The machinery will have to be up on the concrete to construct the 3â€™ shoulder so I think the ramps are going to have to be closed. 3) Also looking at the 16 ramps that have to be completed in this time period I believe closing one ramp at a time is going to cause issues getting this done in the time period. | 1) Correct, the closures are for the partial depth concrete removal and HMA overlay of the USH 45 ramp travel lanes. Per the note in the special provisions, the ramp shoulder work could also be done during these closures at the USH 45 interchanges. 2) Width restrictions or ramp closures are not allowed at the STH 47 ramps. Other means and methods may be required to complete the ramp shoulder work. Any suggested changes in working restrictions would have to be negotiated with the Department during construction but we anticipate it can be constructed as proposed in the plans. 3) Each of the USH 45 ramps (8) are allowed to be closed for 2 nights. That is a total of 16 nights of ramp closures at the USH 45 interchanges. Again, not all work has to be done in those nights, just the concrete mill and overlay at the top of the ramps. | Mike Coleman | 2 | 2016-06-09 15:17 | 2016-06-09 15:18
20160614 | 20160614010 | 10 | Bid Item 611.8115 Adjusting Inlet Covers as it Relates to STH165 Rehab Project 3738-06-60 | Question: 1. See Detail on Plan Sheet 15. Please clarify which of the following work activities related to the subject bid item are incidental to the bid item or will be paid for under a separate item: Saw Cut, Removal of Existing C&G, Removal of Existing Pavement, Replacement of C&G, Replacement of Pavement, Pavement Ties. 2. Can the activities that are specified to be incidental be changed to payment under separate bid items? 3. Most of the adjustments for the rehab project occur at the bridge over Canadian RR, see Sheet 28. The detail on Sheet 15 doesnâ€™t look like it applies to these inlets. Is that the case? If so, please clarify the detail. | 1. Per the detail Concrete HES and Pavement Ties are incidental to the subject bid items. 2. No 3. All adjustments shall be in accordance with the standard spec. The detail in question applies to the adjustment at the County H intersection. | Mike Coleman | 7 | 2016-06-09 15:22 | 2016-06-10 06:34
20160614 | 20160614007 | 7 | Existing Storm & Culvert Pipe along I94 under Elm Grove Rd Bridge | There is existing storm sewer and culvert pipe along I94 under the Elm Grove Rd Bridge in the vicinity of the proposed piping. There isn't any indication on the plans nor bid items for the removal of the existing pipe. Does the existing pipe get removed or does it stay in place? If it's to be removed can bid items be added? If it stays in place it will be in conflict with the proposed pipe. | An addendum will be issued to correct this on 6/13/2016. | Mike Coleman | 1 | 2016-06-09 18:16 | 2016-06-10 11:10
20160614 | 20160614016 | 16 | Abandon utility removal | Item #25 of the SP's. Can you elaborate what this paragraph is identifying or attempting to tell us? Is there something else other than what the scheduled removals items are addressing? | The provision is stating that any abandoned utilities encountered during trenching that interfere with any work associated with new storm sewer installation, that would otherwise be allowed to remain in place, is the contractors responsibility to remove and dispose of. For example, all expense associated with removing and disposing of an abandoned water service, electrical wire, etcâ€¦ that is located where a new storm sewer lateral is located would be removed and disposed of as part of the pipe bid item. Any items scheduled for removal under other bid items would be paid for as part of the appropriate bid item. | Mike Coleman | 6 | 2016-06-10 13:11 | 2016-06-13 09:26
20160614 | 20160614011 | 11 | Quantities | Why is there a line item for Excavation Common in the schedule of items for 126.00 CY? It seems as though the common excavation quantities are covered under other items. The 126.00 CY isn't listed in the MQ sheets. Does the department expect other common excavation quantities on the project? | An addendum is being issued to remove the bid item 205.0100 Excavation Common | Mike Coleman | 2 | 2016-06-13 06:35 | 2016-06-13 06:45
20160614 | 20160614008 | 8 | Schedule | Can you please provide a design schedule for Proposal #08? | Engineer's design schedule can be found at: http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Mike Coleman | 1 | 2016-06-13 08:37 | 2016-06-13 13:56