## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20180814 | 20180814001 | 1 | Earthwork Summary | Is there an earthwork summary table available for this project? | Yes, an addendum will be issued that will provide the earthwork summary table. | Jill Fehrman | 1 | 2018-07-13 08:49 | 2018-07-17 16:27
20180814 | 20180814001 | 1 | Abandoning Culvert Pipes | Can a explanation of exactly what pipes are to be abandoned be provided? Are these the pipes associated with the inlet removals? If so why wouldn't DOT just want these pipes removed as new inlets / pipes are basically getting installed in the same area. | The pipes at stations 113+03â€SBâ€, 113+53â€NBâ€, 159+06â€SBâ€, and 158+58â€NBâ€ are being abandoned, as called out in the Miscellaneous Quantities table. They are associated with the inlet removals at the same stations. The inlets and pipes at station 190+52â€EBâ€ and 193+02â€EBâ€ are to be removed and replaced. A bid item for removing the storm sewer pipes at stations 190+52â€EBâ€ and 193+02â€EBâ€ was missed and an addendum will be issued to add a bid item for the removal of storm sewer pipes at these locations. | Mike Coleman | 2 | 2018-07-30 09:05 | 2018-07-30 13:58
20180814 | 20180814001 | 1 | B-25-23 Joint Repair Concrete | Bridge B-25-23 has the bid item of joint repair but no concrete bid item. How will the joint repair concrete be paid? | The joint repair concrete will be paid for per Standard Specification 509.5.4 (2) Joint Repair. Indicating the department will pay for the volume of concrete used under the Concrete Masonry Overlay bid items which is included in the contract. | Jill Fehrman | 3 | 2018-08-06 15:43 | 2018-08-13 11:29
20180814 | 20180814002 | 2 | Arch Fascia Options | Would the DOT consider utilizing a Precast Arch Fascia option? | A cast-in-place arch fascia is required. A precast arch fascia was considered during design; however, it was not selected due to the structure type required at this site and the anticipated pressure flow on the bottoms of the arches during the 100 year flood event. | Mike Coleman | 1 | 2018-07-24 14:56 | 2018-07-25 10:48
20180814 | 20180814002 | 2 | Cofferdams and dewatering | Article 23 note 2 indicates concrete must be placed in a dry condition. Typically with solid shaft piers, these are poured under water with the purpose of the cofferdam to be mainly to control sedimentation and water disturbance. Since the cofferdams here are also serving a dual purpose of containment for the structure removal, dewatering may be an issue when attempting to pour the pier shaft in the dry. One - To what extent does the contractor have to remove the existing pier (2' below existing grade?)? Two - Would the DOT reconsider and allow the pier shafts to be poured underwater similar to other solid shaft piers? | The existing substructures shall be removed down to an elevation no higher than the natural stream bed elevation, per subsection 203.3.2.2(1) of the Standard Specifications. Dewatering and placing concrete in dry conditions is required for this structure. The schedule dictates that the substructure work will take place during the late fall and winter months. To meet the minimum temperature requirements in subsection 502.3.9 of the Standard Specifications, dewatering will be necessary. | Mike Coleman | 2 | 2018-07-31 13:45 | 2018-08-02 09:50
20180814 | 20180814002 | 2 | Temporary Storm Sewer Outlet | Proposal article 26 discusses that a temporary storm sewer outlet will be required at both abutments. What was the designers thought on the location of these temporary outlets since the abutments are contained in cofferdams that must be in a dry condition? The project site has very limited capabilities to handle the storm sewer drainage during construction. | Outletting of the storm water during construction was anticipated to be handled by some method of diversion and/or pumping system. The contractor is to determine the exact means and methods. | Mike Coleman | 3 | 2018-07-31 15:09 | 2018-08-02 13:42
20180814 | 20180814002 | 2 | Seal Concrete at Abutments and Piers | If the concrete for the piers and abutments is to be poured in the dry, then a concrete masonry seal item should be added for this construction so that the cofferdams can be dewatered. Can a concrete masonry seal item be added? | A concrete masonry seal will be added to the plans for construction of the piers. Concrete poured underwater will be allowed at the abutments. An addendum will be posted with these revisions. | Mike Coleman | 4 | 2018-08-03 13:37 | 2018-08-07 13:12
20180814 | 20180814002 | 2 | 404 Permit | Could you please make the 404 permit available for review as soon as possible? | The 404 permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180814002/ | Mike Coleman | 5 | 2018-08-06 08:32 | 2018-08-07 13:11
20180814 | 20180814002 | 2 | Schedule | Can the designers assumed construction schedule be provided. Considering the highly variable steam depths and cofferdams required, It does not appear the designer considered the physical, general notes and other access limitations for the project. These limitations do not allow for efficient nor an adequate number of operations to proceed simultaneously to realistically meet schedule. | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180814002/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2018-08-07 13:15 | 2018-08-09 13:09
20180814 | 20180814002 | 2 | Schedule and Water flows | The response to question one, as it relates to utilizing precast arches expressed a desire for cast-in-place arches due to potential problems with high water flows. Did the designer take into account any temporary falsework that will be required during the typical high water flow season when the arch work would take place. It would appear the falsework would be within the Q2 elevation which is problematic for both schedule and construction. Will additional time be allowed if high water flows prevent the arch work to proceed? | Clearance for temporary falsework was reviewed in the design process and approved by the department. Allowance for additional time would be determined by construction staff on a case-by-case basis. | Mike Coleman | 7 | 2018-08-07 13:16 | 2018-08-09 13:10
20180814 | 20180814002 | 2 | Causeway Clarification | Does rock installed, contained and removed within sheet pile limits constitute as a causeway? | It was our interpretation that rock installed, contained and removed within sheet pile for construction access to the river does not constitute a causeway. | Mike Coleman | 8 | 2018-08-07 13:17 | 2018-08-08 14:22
20180814 | 20180814002 | 2 | Follow up to 404 Question | As a follow up to the 404 permit, would it be possible to also supply the information used and provided to the Corp in order to obtain the permit? | Supporting documentation for the 404 permit have been uploaded and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180814002/ | Mike Coleman | 9 | 2018-08-07 13:25 | 2018-08-08 09:10
20180814 | 20180814002 | 2 | Concrete Steps Structural Design | Per the special provisions for the concrete steps and supports (item SPV.0105.03) structural design is required as part of this item. It appears the design is already complete per the plan. What design is needed? If nothing additional is required can this be removed from the special provision? | Details in the plans, if utilized, should be included as part of the contractor provided shop drawings that are approved by a licensed engineer. The provision will remain. | Mike Coleman | 10 | 2018-08-07 16:57 | 2018-08-08 11:21
20180814 | 20180814004 | 4 | Diversion Channel | Both box culverts require that existing waterways get diverted prior to the start of the new culvert construction. Does a diversion channel have to be constructed or can pipes be used to bypass the flow? | For C-51-85 (ID 2704-00-78), the Special Provision article for Item SPV.0105.004 indicates the contractor can select from three methods to convey the required flow. For B-30-142 (ID 3763-00-75), the Special Provision article for Item SPV.0105.005 indicates the contractor must provide a temporary diversion channel of sufficient size to convey the required flow. | Mike Coleman | 1 | 2018-07-26 13:41 | 2018-07-26 13:42
20180814 | 20180814004 | 4 | Article 15 Haul Restrictions | Please delete Article 15 Haul Restrictions as it was deleted for other projects in the area, N-S IH 94 Projects bid May 22, 2018. | Due to the coordination required between multiple entities for hauling, this article will not be deleted. | Mike Coleman | 2 | 2018-08-08 08:26 | 2018-08-08 13:51
20180814 | 20180814004 | 4 | Article 3 Wisconsin Inclusion Plan | "All Bidders should submit a Wisconsin Utilization Plan at the time of bid demonstrating how s/he will achieve the inclusion objectives for targeted businesses and workforce participants. The submission should comply with the Wisconsin Utilization Plan." - If this in not submitted at the time of Bid, will your bid be rejected? - What if you don't make the goals, will your bid be rejected? | WisDOT strongly encourages bidders to submit an Inclusion Plan at the time of bid. Submittal of an Inclusion plan is not a condition of award, but will provide desired documentation of the bidders outreach to targeted businesses and work force participants. | Jill Fehrman | 3 | 2018-08-08 08:34 | 2018-08-13 08:02
20180814 | 20180814001 | 1 | Lump sum x over removals | Can the Salvage topsoil and the restoration items be separated out of the lump sum removal of the x overs and be paid as contract items that are already in the contract? |  |  | 4 | 2018-08-10 15:06
20180814 | 20180814001 | 1 | paint clarification structure b25-24 | What are the paint parameters for coating the beam ends? Is there work required over traffic lanes with full containment with recycled abrasive? |  |  | 5 | 2018-08-13 08:27