## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20181211 | 20181211001 | 1 | Design Files, Soils Reports, Asbestos Reports, Schedules, Permits | Can we get a copy of the design files, Soils Reports, Asbestos Reports, Design Schedules, and permits for these projects? | The files can be located at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211001/ | Deanna Goebel | 1 | 2018-11-26 17:07 | 2018-11-26 17:08
20181211 | 20181211001 | 1 | Cold Weather Pavement Markings | On page 1851 of the plans, the 4" cold weather markings in the misc. quantities have the wrong total. The column ads up to 74,550, and not 49,668 that is shown. Can you please verify the quantities, and which color marking the 4" cold weather markings are to be? All white? All Yellow? Mix? Total Bid item is for 59,510'. |  |  | 2 | 2018-11-26 17:13
20181211 | 20181211001 | 1 | Pre-Bid Meeting | Can we get a copy of the sign in sheet for the Pre-Bid Meeting? | The file can be located at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211001/10051077_PreBid_Meeting_Sign_In_181114.pdf | Deanna Goebel | 3 | 2018-11-26 17:14 | 2018-11-26 17:14
20181211 | 20181211001 | 1 | More CAD Files | Please provide the existing surface CAD file, alignments in dwg and all surfaces for the previous southbound widening project within the project limits. | The existing surface CAD file for this project includes the previous widening project. The metadata for the previous widening project (1005-10-73) and current project can be picked up at the DOT Edgerton Office, 111 Interstate Blvd, Edgerton, WI 53534. | Mike Coleman | 4 | 2018-11-27 11:15 | 2018-11-28 07:50
20181211 | 20181211011 | 11 | Soils Report | Could you post the soils report? | The soils report has been posted and can be found: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211011/ | Deanna Goebel | 1 | 2018-11-26 17:17 | 2018-11-26 17:17
20181211 | 20181211011 | 11 | Colored Crosswalk | It is my understanding that the City of Madison would prefer to use Transpo MMA for the material in the colored crosswalks. The spec that is in the proposal is not for an MMA, but rather a High Friction Overlay like a bridge deck, and the colored aggregate will not be a true green, or red. If the DOT would like to use the current spec, can you please let us know what material manufacturer or product you would like us to use? |  |  | 2 | 2018-11-26 17:23
20181211 | 20181211014 | 14 | Pavement Marking Arrows? | The misc. Quantities cal for 29 Type 1 Arrows. The drawings do not show any Type 1 arrows, but it does show Type 5 arrows, and bike arrows. Can you check the quantity of Type 1 arrows, and where they are to be installed on the plans? Also add the type 5 arrows, and bike arrows if needed. | You are correct, there are no Type 1 arrows but there are Type 5 and bike lane arrows. The quantities and plans will be adjusted accordingly and will be included in an addendum. We anticipate a minor change in the overall quantity of marking arrows. | Deanna Goebel | 1 | 2018-11-26 17:24 | 2018-11-26 17:24
20181211 | 20181211016 | 16 | Pavement Markings | Looking over the bid items and misc. quantities for this project, and we seem to be missing items or duplicating items in the misc. quantities or bid item quantities. Bid items 0612 and 0824 are both for the 18" Yield lines in the round a bouts. One is by the each (4- 0612) and one is by LF (90' - 0824). This item seems to be duplicated, which one will you use in the round a bout? Bid item 0514 is for 50' of 12" Diagonals. The misc. quantities on page 431 has two columns for the 12" diagonals totaling 370'. This seems to be the correct quantity, and not 50' as the bid item is missing the 12" diagonals in the round a bout. Can you please check these quantities/items and let us know which ones are correct? | Bid item 646.6220 Marking Yield Line Epoxy 18-Inch â€“ 4 Each will be deleted in a future addendum. Bid item SPV.0090.15 Marking Line Yield Line Epoxy 18-Inch â€“ 90 LF will be uses as the yield line at the roundabout. On page 431, the heading for one of the 646.7120 12-Inch Diagonal should be SPV.0090.14 6-Inch Diagonal as shown on page 430. The 50 LF quantity for 12-Inch Diagonal as shown on page 431 and in the proposal line number0514 is correct. In addition the quantity for SPV.0090.14 6-Inch Diagonal is incorrect on page 431, but in the proposal on line 0822 the quantity is correct as 140 LF. Page 431 of the miscellaneous quantities will be updated in a future addendum. | Deanna Goebel | 1 | 2018-11-26 17:25 | 2018-11-27 11:19
20181211 | 20181211016 | 16 | Storm Sewer Rermovals | Is there depths available for the existing storm sewer system so that we can calculate the amount of backfill required? | As-built plans are being provided and can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211016/ These plans are being provided for information only. It is the contractor's responsibility for verifying as-built depths. | Mike Coleman | 2 | 2018-11-27 11:18 | 2018-11-28 10:10
20181211 | 20181211016 | 16 | Water Main work | Plans show a 20" Casing pipe. Do not see a bid item. | A 20â€ casing pipe will be added via an addendum for the watermain work. | Deanna Goebel | 3 | 2018-11-27 11:58 | 2018-11-27 11:59
20181211 | 20181211016 | 16 | SPV 0060.11Concrete Cap over sanitary sewer | Will the concrete used be classified as Class II or Class III? | Class II concrete. An addendum will be issued to clarify. | Deanna Goebel | 4 | 2018-11-27 12:11 | 2018-11-27 12:12
20181211 | 20181211016 | 16 | Removing Sanitary sewer | Special provisions for Removing Sanitary Sewer Pipe call for native backfill to be used to backfill the trench. Yet when we got to the removing sanitary manhole special provisions it tells us to backfill with materials that conform to 209.2. Should the backfill for removing sanitary manholes be native also? | Backfilling of removed MHs should conform to section 209.2 Granular Backfill as shown in the special provisions. | Mike Coleman | 5 | 2018-11-27 12:14 | 2018-11-28 10:30
20181211 | 20181211016 | 16 | Mini Sewers | Under A. Description it says to install according to the standard spec 608 and 612. Not sure if we are to follow 608 or 612 when it comes to bedding or backfill. | The special provision article will be clarified in an addendum to define bedding and backfill requirements. | Mike Coleman | 6 | 2018-11-27 12:17 | 2018-11-28 10:48
20181211 | 20181211016 | 16 | Water Main | B. Materials Provide all gaskets in conformance with the latest AWWA C-111. It further requires the use of nitrile or fluorocarbon gaskets depending on ground conditions. None appear to be called out on the plans anywhere so if they end up being required would these be considered extra work and paid for accordingly? | This Materials section will be updated in a future addendum. | Mike Coleman | 7 | 2018-11-27 12:18 | 2018-11-29 06:59
20181211 | 20181211016 | 16 | Water Main | B.2 Granular bedding and Backfill. This section first tells us select soils coming from the different soil classification groups GW, GP, SW and SP. The next sentence then says. "Aggregate shall pass a 3/4" Sieve and not more than 35% shall be retrained on a No 10 sieve. Maximum 5% by weight shall pass a No. 200 sieve. Does this apply to the bedding? Does this apply to the Backfill? What god does an SP or any of those soil groups do us if it can meet the gradation? Is the water main work not supposed to be backfilled with native soils. | An addendum will be issued changing the type of backfill required. | Mike Coleman | 8 | 2018-11-27 12:18 | 2018-11-29 07:02
20181211 | 20181211016 | 16 | Project Schedule | Can we get the designers schedule for this project | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211016/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions, and any addendum that is developed. | Mike Coleman | 9 | 2018-11-27 12:19 | 2018-11-28 10:28
20181211 | 20181211016 | 16 | Water Main Work | Is the water main work not supposed to be backfilled with native soils |  |  | 10 | 2018-11-27 12:20
20181211 | 20181211017 | 17 | Miscellaneous Quantities-LandscapIng Summary | This section first tells us select soils coming from the different soil classification groups GW, GP, SW and SP. The next sentence then says. "Aggregate shall pass a 3/4" Sieve and not more than 35% shall be retrained on a No 10 sieve. Maximum 5% by weight shall pass a No. 200 sieve. | The landscaping work in the referenced area on plan sheet no. 10 has been completed as part of the 41/10 interchange project. This work will not be completed as part of this project. | Deanna Goebel | 1 | 2018-11-27 12:21 | 2018-11-27 12:22
20181211 | 20181211017 | 17 | Pulverize and Relay | There are a number of existing concrete curb and gutter areas within this project. Should a bid item for the excavation and hauling of excess pulverzed material be added in order to match the necessary grades in these areas. Please advise. Thank you. | The quantity for excavation and hauling excess pulverized material to match existing curb and gutter is part of the excavation common item noted as EBS. | Deanna Goebel | 2 | 2018-11-27 12:31 | 2018-11-27 12:32
20181211 | 20181211017 | 17 | Street Sweeping | Does this apply to the bedding? | The bid item of Street Sweeping was included in the project in the event that material would be tracked out of the project limits after pulverization had occurred. | Deanna Goebel | 3 | 2018-11-27 12:33 | 2018-11-27 12:34
20181211 | 20181211017 | 17 | Labor Compliance Reporting-Payroll Requirements | Article 1.4 of the special provisions discusses submitting weekly certified payrolls verifying prevailing wage rates for all work performed under the contract. There is no federal project listed on the front cover of the proposal and no prevailing wage rates provided within the proposal. Could you please verify that prevailing wages are not required for this project and if they are not are certified payrolls still required to be submitted. Thank you. | There is no federal funding on this project, therefore, no Davis Bacon prevailing wage rates are required. ASP 9-S, shown on page 40 of this proposal, explains what is required for Electronic Labor Data Submittals for State Funded Only Projects. | Deanna Goebel | 4 | 2018-11-27 12:35 | 2018-11-27 12:35
20181211 | 20181211027 | 27 | Rock Exc. Special | Per the specials for Excavation Rock Special, the rock is not separated out in earthwork summary but is included in the excavation quantity. | No. If rock is encountered, the necessary Excavation Rock Special will be measured and paid for separately from the Excavation Common. All excavated material will be classified, measured, and paid for separately under either the Excavation Common item or the Excavation Rock Special item. | Deanna Goebel | 1 | 2018-11-27 12:37 | 2018-11-27 12:37
20181211 | 20181211028 | 28 | Structure Plans | Can you review and re-lease the Structure Plan? The numbers are unreadable. | An addendum is being issued to replace the planset. | Deanna Goebel | 1 | 2018-11-27 12:40 | 2018-11-27 12:40
20181211 | 20181211032 | 32 | Chain Link Fence Location | Will you be paying for both Rock Exc. Special and Common Exc. if rock is encountered? As if the Rock Exc. Special is a premium price on top of the common excavation unit price. | The fence is shown in the SW quadrant of B-57-0058 on the plan and profile sheet (sheet 132 of the plans). | Deanna Goebel | 1 | 2018-11-27 12:41 | 2018-11-27 12:41
20181211 | 20181211034 | 34 | Round Culvert Bid Items | Per Updated FDM guidance on projects under 7000 ADT, competitive bid items should be used for storm sewer and culvert bid items. (Class IIIA and/or Class IIIB) Will contractors be permitted to utilize these competitive specifications for their pricing? |  |  | 1 | 2018-11-27 12:42
20181211 | 20181211016 | 16 | SPV 0090.211 Sanitary Lateral 6 inch | Under materials the specifications say that we are to provide Schedule 40 PVC pipe which conforms to ASTM D 3034. The ASTM spec if for SDR 35 Pipe, so it can not be both. Which is it? | Schedule 40 PVC pipe should be used. This will be clarified in an upcoming addendum. | Mike Coleman | 11 | 2018-11-27 13:08 | 2018-11-28 07:48
20181211 | 20181211016 | 16 | Sanitary sewer NEW or Relay | Under the payment section it says that TESTING is included in the work required for payment. Under construction it talks about compaction and the requirement for 95% of a Standard Proctor per ASTM D 698. Is compaction testing required as incidental to this work? | A bid item for soil testing will be issued in an upcoming addendum. | Mike Coleman | 12 | 2018-11-27 13:09 | 2018-11-28 10:17
20181211 | 20181211017 | 17 | Miscellaneous Quantities-Landscaping Summary | Will an addendum be issued revising the quantities for topsoil, erosion mat, fertilizer, seed and water for seeded areas based on tht answer for question no. 1? Thank you. | Yes, we will be issuing an addendum to revise/remove quantities related to the answer for question no. 1. | Mike Coleman | 5 | 2018-11-27 15:04 | 2018-11-28 12:34
20181211 | 20181211001 | 1 | Noise walls plans? | Noise wall plans contained in the plan set appear to be incorrect - Wrong Project ID. Please send corrected set | The correct Noise Wall Plans will be included in an upcoming addendum. | Mike Coleman | 5 | 2018-11-27 15:47 | 2018-11-28 12:16
20181211 | 20181211016 | 16 | Soil Boring | Can the soil borings be posted for this proposal? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211016/ | Mike Coleman | 13 | 2018-11-28 10:11 | 2018-11-28 10:14
20181211 | 20181211001 | 1 | Updated 404 Permit | Is there an updated 404 permit? | An updated 404 permit is now available for bidders. The requirements have not changed, only the dates. The old permit had expired and the updated 404 has now been authorized under the new transportation regional general permit. The permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211001/ | Mike Coleman | 6 | 2018-11-28 10:53 | 2018-11-28 10:56
20181211 | 20181211019 | 19 | Traffic | The special provisions state, "Provide an even cross-sectional profile at the end of each days milling and/or paving". This is becoming common practice for milling, but we have not seen this for paving as it will create a safety issues with traffic control setting back in the middle of the day. Paving with the tapered joint would be a much safer option. Could the second paragraph of Traffic section be change to reflect only the milling operations and remove the "and/or paving"? | The language in the Traffic Article will be updated via addendum. | Mike Coleman | 1 | 2018-11-28 14:11 | 2018-11-29 07:00
20181211 | 20181211011 | 11 | Flexible Tubular Markers | Page 53 of the proposal under Flexible Tubular Markers it states that "attach the base with an engineer-approved adhesive" With how competitive the market is we need to know what the approved method is going to be before we bid the item as this could be very expensive and or very labor intensive to maintain. Can we get some approved methods please? | In accordance with the general notes on standard detail drawing â€œChannelizing Devices Flexible Tubular Marker Postâ€ (sheet 417 of plan) acceptable methods would include an asphaltic adhesive or butyl pad in accordance with manufacturerâ€™s recommendations. | Jill Fehrman | 3 | 2018-11-28 14:19 | 2018-11-30 13:14
20181211 | 20181211027 | 27 | DOT ROW Use | For Stages 7 thru 9, can any part of the DOT ROW within the median (basically from stations 585+00 to 630+00) be utilized for either borrow or waste or both? | Contractors should refer to Standard Specification 104.8 for pertinent information to be considered when preparing bids. Any specific proposal for use of material within the right-of-way and outside the excavation limits shown on the plans will be reviewed and evaluated at the appropriate time. | Mike Coleman | 2 | 2018-11-28 15:04 | 2018-12-04 13:16
20181211 | 20181211015 | 15 | Removing Old Structure, STA 158+18.68 | Will a complete closure of 60th Street, NB & SB, be allowed/considered, for the removal of the existing SS/Structure and replacement with 60" SSRCP? | Per the Traffic article in the special provisions, a minimum of one 12-foot lane of traffic in each direction is required on S 60th Street, therefore a full closure would not be allowed. | Mike Coleman | 1 | 2018-11-29 16:31 | 2018-12-04 13:19
20181211 | 20181211015 | 15 | Cleveland Ave Curb and Gutter project limits | Is there a plan sheet showing the limits and curb & gutter grades for the new curb and gutter in the plan set? I can find the traffic control limits for this work, but no plan sheet show grade or limits of what is to be constructed on the east and west side of Cleveland Avenue. | Beyond the reconstruct limits on the east and west legs of Cleveland Ave, the curb & gutter is initially removed for temp widening/temp asphalt for staged construction purposes. This curb & gutter would be replaced in Stage 3 to the original offsets and grades. The limits for curb & gutter removal and replacement on Cleveland Avenue are stated in the miscellaneous quantities | Mike Coleman | 2 | 2018-11-29 17:28 | 2018-12-05 07:17
20181211 | 20181211002 | 2 | Maple Street Work Restrictions | Can you clarify if the 14 calendar day work period restriction for Maple Street requiring the contractor to maintain two way access is for all of Maple Street or just the intersection of Maple Street and Madison Street? | The language in the Prosecution and Progress Article will be revised via addendum. The special provisions are revised to note: Revise paragraph 6, sentence 4, of the article to Allow local traffic two-way access at the Madison Street/Maple Street intersection excepting for a 14 calendar day period within the April 1 to June 29, 2019 time frame. | Mike Coleman | 1 | 2018-11-30 08:13 | 2018-12-05 14:43
20181211 | 20181211001 | 1 | Polymer Coated Fence on Retaining Walls | Is there a detail for mounting/installing the 3' and 6' polymer coated fence to the retaining walls? Bid items 1626 and 1628? Can these be plate mounted? | The details for mounting/installing the fence are located within each retaining wall plan. | Jill Fehrman | 7 | 2018-11-30 13:19 | 2018-12-03 15:28
20181211 | 20181211031 | 31 | Temporary pavement markings | Project 7510-02-60 has temporary paint included for the lower layer (lower layer has to be placed the same day as milling) and the upper layer. If you place paint on the upper layer, it will need to be removed prior to the permanent markings being placed after the rumble strips. Will an addendum be issued changing this to temporary or same day epoxy as is typical? Project 7510-02-62 has temporary paint included for the lower layer(lower layer placed within 48 hours of milling) and the upper layer while there is no temporary paint for the milled surface. Will an addendum be issued to account for the temporary paint on the milled surface? Also,if you place paint on the upper layer, it will need to be removed prior to the permanent markings being placed after the rumble strips. Will an addendum be issued changing this to temporary or same day epoxy as is typical? Thank you. | In reference to bid item 649.0105 â€“ Temporary Marking Line Paint 4-inch, specification section 649.5(2) states, â€œPayment for the Temporary Marking bid items is full compensation for providing the marking or marker; for maintaining, and for removing the marking or marker.â€ In lieu of installing an upper temporary marking in paint and removing it prior to the final same-day application of epoxy, the Contractor may elect to install an upper temporary marking in epoxy or use temporary raised pavement markers. Payment for these options shall be made under item 649.0105. No addendum will be issued. | Mike Coleman | 1 | 2018-12-01 08:34 | 2018-12-04 13:04
20181211 | 20181211031 | 31 | Pavement markings | With the departments increased use of wet reflective markings, including a portion of this project, wouldn't it be prudent to place wet reflective edge lines and center lines on this entire project? | No. There is a significant difference in the historic bid pricing of wet reflective markings compared to standard epoxy. Wet reflective markings will continue to be used in areas of concern while being mindful of taxpayer dollars. | Mike Coleman | 2 | 2018-12-01 08:53 | 2018-12-04 13:06
20181211 | 20181211016 | 16 | Storm Sewer removals | Removal plans show the abandonment of the existing 60" Storm Sewer from Lincoln Ave to approximately station 169+75. From that point going east to station 177+90 it tells us to remove the existing storm pipe. Yet in this same section the removal plan tells us to abandon the manholes. In addition to this this section of storm sewer is in close proximity to the existing water main that is supposed to remain in service. One would assume the existing storm sewer is also deeper that the water main. Is this section supposed to be removed or abandoned in place? | Addendum #1 answered this question. The addendum changed the plan from removal of the existing 60â€ storm sewer to abandoning this section of storm sewer. | Mike Coleman | 14 | 2018-12-01 09:56 | 2018-12-05 10:01
20181211 | 20181211027 | 27 | Grading, Shaping and Finishing Temporary Outside Widening, Sta. 200+00 to Sta. 216+80 Westbound IH94 | There are no cross sections available to determine quantities required to perform this work. Why isn't this work being paid for under standard contract items (Common Excavation, Borrow Excavation, Salvaged Topsoil, etc.) as all the other temporary widened areas are? What if high ground water is encountered and alternate subgrade treatments will be needed? Is this temporary widening staying in after contract completion, as it seems there are no quantities identified to remove this temporary widening? | This lump sum item was used to supplement a deficiency in the existing ground surface model. Estimated quantities are shown in the miscellaneous quantity table. Alternative subgrade treatment, if determined to be necessary, will be handled in a similar manner as other problem areas encountered within the project limits. At this time, the Department does not anticipate a need to remove the fill placed as part of this lump sum item. | Mike Coleman | 3 | 2018-12-02 22:17 | 2018-12-04 13:14
20181211 | 20181211027 | 27 | Barrier Pinning | With the significant amount of temporary barrier on this project would the state consider adding the item of barrier pinning? | Concrete barrier temporary precast shall be installed per standard detail drawings. The costs for any necessary pinning shall be considered incidental to items 603.8000 and 603.8125. | Mike Coleman | 4 | 2018-12-03 10:50 | 2018-12-04 13:11
20181211 | 20181211016 | 16 | SPV 0090.05 & 06 | The specifications for the flexible couplings list multiple ASTM C443, C425, C564, D1869 and C1173. These appear to cover a broad range of products non of which satisfy all of these ASTM requirements at the same time. What are we supposed to supply something that meets the majority of these requirements? | An addendum will be issued to address this question. | Mike Coleman | 15 | 2018-12-03 12:41 | 2018-12-06 07:20
20181211 | 20181211015 | 15 | Stockpiling and Crushing on Roadway ROW | Will Stockpiling and Crushing/Recycling of the pavements be allowed on the project limits? | Crushing/Recycling and Stockpiling of the pavements will be allowed. Contractor shall not crush/recycle pavements from 9:00 PM until the following 7:00 AM, and not place stockpiled material in such locations that create visual obstructions for vehicles and pedestrians. | Mike Coleman | 3 | 2018-12-03 12:52 | 2018-12-04 13:30
20181211 | 20181211016 | 16 | SPV 0060.0107 & 112 curb stops | One place the specifications tell us to provide AY Mc Donald 76100Q which is a ball style valve. The sentence prior to that tells us to provide a inverted key style stop. Suppliers are telling me it can not be both, it has to be one or the other. What are we to supply? | A future addendum will be issued to include that a ball style curb stop shall be used. | Mike Coleman | 16 | 2018-12-03 13:03 | 2018-12-05 13:31
20181211 | 20181211016 | 16 | water main pipe | the special provisions tells us to use water main pipe that has a Zinc coating. Are the fittings also required to have this same coating. From what I am being told the ASTM specs do not reference providing fittings with this same zinc coating. Are the fittings to be compatible with the pipe in terms of coatings? | Fittings are not required to have the zinc coating. | Mike Coleman | 17 | 2018-12-03 13:09 | 2018-12-06 07:16
20181211 | 20181211002 | 2 | HMA Pavement | Given the staging, lengths and # of lifts would the use of an Asphaltic Surface Special (4MT) be more appropriate? | No, please follow the Standard Specifications for the HMA items shown in the construction plans. | Mike Coleman | 2 | 2018-12-03 13:22 | 2018-12-06 06:15
20181211 | 20181211027 | 27 | HTCB Post Spacing | I could not find a working width listed in the plans. Given the 15' offset from profile line, can a 15' post spacing be assumed? | The cable barrier offset of 15â€™ from the reference line is intended to provide a working width of 12â€™. | Mike Coleman | 5 | 2018-12-04 07:20 | 2018-12-05 07:15
20181211 | 20181211031 | 31 | Pipe Lengths | On the 7510-02-62 project, in some locations, it calls for replacing end section with 8' of pipe and other locations it calls to replace end sections with 16' of pipe. The existing pipe on the project is in 4' sections. If the intent is to remove 4 existing sections, 16 feet, the excavation will be undermining the roadway and will require part of the road section to be built back. The plans do not have any quantities for BAD 1 1/4" or Asphaltic Surface. If the intent was to just replace the end section or sections, 4' or 8', I think the pipe quantities may be doubled and am unsure if 4' sections of pipe will be available by a manufacturer. Would it make sense to remove the end 4' pipe and install an AEW? The existing RC pipes do not have AEW's. | The lineal dimensions detailed in the plans reflect the actual length of pipe the designer intended on being replaced. Contract items 305.0120 and 465.0105 will be used to restore the roadway if required by the work. | Mike Coleman | 3 | 2018-12-04 07:32 | 2018-12-04 13:48
20181211 | 20181211034 | 34 | Removing Structures | There is a bid item for Removing Old Structure STA 303+17 and another bid item for Removing Old Structure Over Waterway STA 303+17. Why both items? Is one supposed to be STA 216+15? |  |  | 2 | 2018-12-04 08:30
20181211 | 20181211001 | 1 | Question about Addendum #1 - erosion mat urban class 1 type B quantity | In addendum #1 Bid item 628.2008 Erosion Mat "Urban" Class 1 Type B is listed to change "original" quantity 137000 SY to 177417 SY (add 40417 SY). The orignal quantity for 628.2008 is 168417 SY? The 137000 SY is the quantity for the Bid item above 628.2008. It is for 628.2004 Erosion Mat Class 1 type B. Expidite file has the quantity for item 628.2008 changed to 177417 (137000 + 40417). Please confirm the quantities for both bid items. |  |  | 9 | 2018-12-04 09:50
20181211 | 20181211032 | 32 | Soil Borings | Are there soil borings available for this project? If so, where can they be found? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211032/ | Mike Coleman | 2 | 2018-12-04 10:28 | 2018-12-04 13:28
20181211 | 20181211035 | 35 | Soil Reports and Surface Drains | Just wondering if you have some soil boring for this project to confirm the topsoil depth of 3â€ Also, for the surface drains, I do not see anywhere that is specifies if it should be a drain with pipe or without pipe. | No soil borings were done for this project. Install as surface drain without pipe (no item â€œ521.1012-Apron Endwalls for Culvert Pipe Steel 12-Inchâ€ or item â€œ612.0212-Pipe Underdrain Unperforated 12-Inchâ€ were included in this project). | Mike Coleman | 1 | 2018-12-04 11:59 | 2018-12-05 07:22
20181211 | 20181211032 | 32 | Hazardous Materials Report | Can you post a copy of the Hazardous Materials Report? | The Hazardous Materials Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211032/ | Mike Coleman | 3 | 2018-12-04 12:28 | 2018-12-04 13:29
20181211 | 20181211027 | 27 | B.A.D 3/4 inch under Asphalt Shoulders | The plans shows using B.A.D 3/4 inch under the asphalt shoulders adjoining the PCC mainline pavement. B.A.D 1 1/4 inch is generally specified under pavements. Should the typical section show 1 1/4 base or is 3/4 base required in this instance? | Special Provision Article 21 and the plan typical sections call for ¾-inch base course for shoulder construction. For constructability and to be consistent with recent projects in the NW Region, the Department will allow 1 ¼-inch base course that is trimmed prior to concrete pavement placement to be used in the shoulders up to the elevation of the bottom of the paved asphalt shoulder, provided the material contains 50% or less reclaimed asphalt. | Mike Coleman | 6 | 2018-12-04 13:08 | 2018-12-05 07:13
20181211 | 20181211016 | 16 | Concrete Cap over Sanitary Sewer | Addendum 1 came out and changed the Portland Cement to type II, the earlier question was what CLASS was this going to be considered in terms of submittals and testing. I thought the answer was this was going to be considered Class II? | The City of Manitowoc wants this to be class II, and the requirement for class II will be included in an upcoming addendum. | Mike Coleman | 18 | 2018-12-04 13:19 | 2018-12-06 07:22
20181211 | 20181211001 | 1 | Addendum 1 - Deck Repair items | We are having difficulty locating where the new items of deck repair are to be used. could you please point us in the right direction? | The quantities are an undistributed amount only. | Mike Coleman | 10 | 2018-12-04 13:26 | 2018-12-05 07:20
20181211 | 20181211027 | 27 | Design Files | Can we get a copy of the design files, soils reports, existing surface CAD files and alignments in dwg format for the project? | The files requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211027/ | Mike Coleman | 7 | 2018-12-04 16:09 | 2018-12-06 11:48
20181211 | 20181211016 | 16 | 204 removing storm sewer | Standard Specifications require storm removals to be backfilled with 209.2 material. My question is can any material that is allowed in the new storm sewer trench acceptable for backfilling the removal trenches such as 3/4 or 1.25" dense which can be substituted for 209 when doing storm sewer work? | In forthcoming addendum, we will address backfill material for Removing Storm Sewer. Basically, we are going to change Removing Storm Sewer backfill requirements to follow Section 608 Storm Sewer, which allows for several options of virgin material which is incidental to Removing Storm Sewer items. | Mike Coleman | 19 | 2018-12-04 17:46 | 2018-12-06 07:24
20181211 | 20181211016 | 16 | Storm sewer/ removal trenches | If a storm sewer trench or storm removal trench falls within the proposed turf areas for the median islands is granular backfill going to be required? | Currently all contractors should bid the project anticipating that granular backfill should be used for all storm sewer removal and new storm sewer trenches, regardless whether they are in the roadway or median. | Mike Coleman | 20 | 2018-12-04 17:50 | 2018-12-05 10:04
20181211 | 20181211001 | 1 | Temporary Barrier | Will the temporary barrier wall installed under Project 1005-10-78 from Station 1034â€™TSBâ€™ to 1096â€™TSBâ€™ be removed as a part of Project 1005-10-77 during Stage 3 and Stage 4 Phase 1? Will this temporary barrier then become property of the contractor? | The temporary barrier will be removed by the 1005-10-78 contract and will become property of the 1005-10-78 contractor. | Mike Coleman | 11 | 2018-12-05 08:17 | 2018-12-05 10:26
20181211 | 20181211001 | 1 | Crash Cushion Temporary Low Maintenance | The special provisions for Crash Cushion Temporary Low Maintenance, Item SPV.0060.203 states that you must â€œUse model SCI 100GM Crash Attenuator from Smart Cushion Innovations (SCI)â€. As we have proposed in previous contracts, can the Universal TAU-II-R Crash Cushion manufactured by Lindsay Transportation Solutions be included as an optional manufacturer? This model and manufacturer meet all the same specifications as the SCI Crash Cushion low maintenance and has been approved by WISDOT. We currently have these same units approved on I94 1030-20-84 1030-20-87 1035-01-72 1035-01-74 1035-01-79 1035-01-82 and i39/90 1003-10-79 / 1003-11-71. | Yes, the Universal TAU-II-R Crash Cushion manufactured by Lindsay Transportation Solutions can be used. | Fred Schunke | 12 | 2018-12-05 09:13 | 2018-12-10 14:15
20181211 | 20181211001 | 1 | Removal of temporary markings | Will you be using the pavement marking removal item for the removal of the temporary pavement markings that is required? | The removal of the temporary pavement marking is included in the temporary pavement marking item per the standard specification. | Mike Coleman | 13 | 2018-12-05 09:38 | 2018-12-05 11:48
20181211 | 20181211019 | 19 | Line number 74 Shaping Shoulders | The existing shoulder between Sta. 306+00 to 384+00 (primarily on the east side) is currently lawns or has vegetation that needs to be removed prior to placing the finished shoulder. Wouldn't this work be covered under this item as the miscellaneous quantities only show 3 stations at CTH F? | No additional quantities of shaping shoulders will be added in these areas. Additional quantities of topsoil, seed, fertilizer, and mulch will be included to restore the void areas adjacent to the milled/paved section. The typical cross section in this area will be updated to reflect the changes. These changes will be covered in an addendum. | Mike Coleman | 2 | 2018-12-05 12:15 | 2018-12-05 14:35
20181211 | 20181211019 | 19 | Line item 0074 shaping shoulders | The existing shoulder between Sta. 159+00 to 255+00 and 384+00 to 459+00 (primarily on the east side) is currently lawns or has vegetation that needs to be removed prior to placing the finished shoulder. Wouldn't this work be covered under this item as the miscellaneous quantities only show 3 stations at CTH F? | Additional quantities for shaping shoulders will be included to address areas where there is heavy vegetation on the shoulder and where regrading of those shoulders is not covered by other bid items. The miscellaneous quantities will be updated accordingly. These changes will be covered in an addendum. | Mike Coleman | 3 | 2018-12-05 12:21 | 2018-12-05 14:35
20181211 | 20181211016 | 16 | Water Main SPV 0090.100 thru 104 | Are the restrained joint gaskets required on all pipe joints not restrained by mechanical means? Or are only those joints that fall within the joint restraint table? If so is it either locking gaskets or bell restrainers, or BOTH being required. (This entire question came from a supplier) | Joint restraint is only required on pipe joints that fall within the joint restraint table, which are not otherwise restrained. Locking gaskets only, not both. | Mike Coleman | 21 | 2018-12-05 12:31 | 2018-12-06 07:19
20181211 | 20181211019 | 19 | Common Excavation | Sta 97+30-133+71 has limited information; On sheet 502 there are no sf areas shown, yet the table shows 420 cy of cut; On the cross section pages; there are only x-sections at 108+82; 109+00; 109+14 & 109+50. Can you tell me how the quantities were determined? | Most of these areas are the remote locations for curb ramp, sidewalk, and curb & gutter replacements. The earthwork for each of these areas is computed to an elevation at 3 inches below the bottom of the proposed sidewalk elevation to account for the removal of existing base and earthwork to allow for the placement of 3 inches of base aggregate under the proposed sidewalk. The cross sections shown at 108+82, 109+00, 109+14, and 109+50 were cut to account for the more extensive grading at the entrance to the Fish Creek Beach. Some errors were found in the earthwork tables during this review. This was corrected with Addendum No. 03 | Mike Coleman | 4 | 2018-12-05 15:50 | 2018-12-07 07:50
20181211 | 20181211001 | 1 | Article 223, Wall Concrete mechanically stabilized earth | page 256 of 268 (last sentence of section B.3.1 wall facing of SPV 0165) states "the ashlar stone pattern is based on minnesota ashlar #1214"? what is the intent of this statement? is minnesota ashlar #1214", the only approved liner? will department approve equivalent liners by other suppliers? | The intent is to give bidders a better understanding of what the formliner must look like. Other formliners can be approved by WisDOT if they are indeed equivalent and meet the contract requirements laid out in the bidding documents. | Mike Coleman | 14 | 2018-12-05 15:59 | 2018-12-06 10:31
20181211 | 20181211004 | 4 | Access to Property in SW Quadrant | In the Special Provisions in Item #4 Traffic it states "Maintain access to properties within the project limits at all times." With the diversion channel being on the north side of the culvert, all of the contractors equipment and materials will have to be staged on the south side of the culvert near the homeowners driveway. The top of the box culvert excavation will be approx. 15-20 LF behind the wall of the box culvert. Would the department be willing to add items for a temporary driveway further to the south for the home owner on the SW side of the culvert. This would be a much safer scenario. |  |  | 1 | 2018-12-05 16:37
20181211 | 20181211016 | 16 | Pedestrian Access | SPV Article 5 states that pedestrian traffic must be maintained on one side off the roadway at times throughout the project. The B-36-29, B-36-232, & B-36-900 structure plans do not show staged construction in order to accommodate pedestrian access. Please clarify if pedestrian access will need to be maintained during structure work. | Pedestrian traffic will not have to be maintained on one side from STA 70+00 to STA 90+00 during the construction of structures B-36-0029 and B-36-232 and pedestrian traffic will not need to be maintained on one side across B-36-900 during structure work on this structure. | Mike Coleman | 22 | 2018-12-05 17:46 | 2018-12-07 07:54
20181211 | 20181211027 | 27 | Pavement Marking Removals | WIll the pavement marking removal item(s) be used to pay for removal of the temporary paint and/or epoxy? | Consistent with Section 649 of the Standard Specifications, removal of temporary pavement markings will not be paid for separately. | Mike Coleman | 8 | 2018-12-06 06:42 | 2018-12-07 07:47
20181211 | 20181211001 | 1 | Gateway sign staining | Where can we obtain an aesthetic detail for the concrete staining required on the NB and SB gateway signs? | Per the plans and specials, artwork available upon request, contact Mike Payne 608-755-3160. | Mike Coleman | 15 | 2018-12-06 07:35 | 2018-12-06 10:33
20181211 | 20181211026 | 26 | Remove Old Structure with Debris Capture System | What is the intent of this item? There is no obvious removal on this project. Full depth repair is not specifically delineated in the plan and is at the direction of the engineer. There is no other concrete removal listed on the project other than surface repair? That item as well is undistributed. Clarification is greatly needed for this item. | The bridge is a deck replacement. The debris capture item is required. Based on the question, was this question intended for a different project? | Mike Coleman | 1 | 2018-12-06 08:16 | 2018-12-07 09:29
20181211 | 20181211016 | 16 | Steel Casing Pipe | Been told by suppliers that the ASTM 106 Grade B Spec calls for a seamless pipe, they tell me that a 42" is not available in ASTM 106. Should this be ASTM 139 Class B instead? | The intent of the spec was to have either a seamless or welded pipe. Pipe meeting ASTM 106 Grade B or ASTM A252 Grade 2 or equivalent will be ok for use for steel casing pipe. | Mike Coleman | 23 | 2018-12-06 09:23 | 2018-12-07 07:56
20181211 | 20181211001 | 1 | MSE Wall Janesville Logo | SPV.0060.850 states "The City of Janesville will supply the decorative medallion form liner". Given the aggressive schedule & the typically long lead times for urethane formliners, how does The Department/The City plan to procure the logo formliner in time to meet the supplier's casting schedule? | The City of Janesville has already procured the medallion formliner for this project. Coordination with the City will be required for the use of the formliner. | Mike Coleman | 16 | 2018-12-06 12:33 | 2018-12-07 09:49
20181211 | 20181211024 | 24 | Soil Borings | It mentions that soil borings have taken place. Would they be available for us to review? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211024/ | Mike Coleman | 1 | 2018-12-06 16:10 | 2018-12-07 09:46
20181211 | 20181211031 | 31 | alternative to 48 hour mill and pave | The bid documents show milling 3" off and paving an 1 1/4" binder lift with both operations matching up every day to eliminate drop-offs. Would it be acceptable to same day mill and pave this section and stay in one lane? We would mill a taper joint at the centerline of 1 3/4" to zero in conjunction with the milling operation (incidental). During that same day, the 1 1/4" binder lift would be placed eliminating the drop off. | Assuming the milled taper joint is an appropriate width, this would be an acceptable method to avoid a drop off between lanes at the end of the day as required by the contract. | Fred Schunke | 4 | 2018-12-06 16:46 | 2018-12-07 12:40
20181211 | 20181211024 | 24 | Sanitary Sewer and Watermain | What estimated date will the sanitary sewer and watermain project for this location be bid by the City? | The sanitary sewer and water main is not being bid out. The City of Wisconsin Rapids will be performing this work with their own City construction crews. | Fred Schunke | 2 | 2018-12-06 18:50 | 2018-12-10 12:00
20181211 | 20181211027 | 27 | Temporary Asphalt Paving Plans | It seems there are plan sheets missing, particularly between the following pages: 157/158, 1590/160, 192/193, 194/195, 196/197, 240/241. Please provide these plan sheets. | The plan sheets in question were included to show more detail and variations in the temporary asphalt required to accommodate crossovers and other alignment shifts for the various traffic control stages. Gaps in the plan sheet coverage are intentional, as the temporary asphalt for those station ranges is more consistent with the typical sections shown elsewhere in the traffic control plan. | Fred Schunke | 9 | 2018-12-07 00:54 | 2018-12-10 12:02
20181211 | 20181211027 | 27 | Interim Completion Dates | There are interim completion dates (Stage 2 and Stage 5) with associated liquidated damage that don't seem appropriate, as there are successive completion dates (Stage 3 and Final Completion) in each calendar year of the project for major traffic switches. These interim dates do not seem to provide a benefit to the traveling public and may increase the project cost by causing the contractor to accelerate a stage (or stages) that are not warranted in order to meet the Stage 3 and Final Completion dates, which seem like the critical dates of the project with respect to traffic movements. Please consider removing the liquidated damages associated with Stage 2 and Stage 5 and allow the contractor to determine what schedule is required to meet the Stage 3 and Final Completion dates in the contract. |  |  | 10 | 2018-12-07 01:07
20181211 | 20181211024 | 24 | Traffic Control, Pedestrian Access, Street Sweeping and Road Maintenance | Who is responsible to maintain these items while the sewer and water work in being completed and the primes contractors crews are offsite? | City of Wisconsin Rapidsâ€™ crews will be performing the sanitary sewer and water main work discussed in the Utility article. The City will be responsible for pedestrian and traffic control, street sweeping, and road maintenance directly related to their operations. During the water and sanitary work, the roadway contractor will still be responsible for the overall traffic control shown in the plans and any items related to the roadway contractorâ€™s operations. Coordinate the roadway work with the City and their sanitary and water work. | Fred Schunke | 3 | 2018-12-07 07:17 | 2018-12-10 12:00
20181211 | 20181211001 | 1 | Longitudinal Construction Joints | In an effort to eliminate potential future maintenance issues and extend the life of the new bridge decks can the longitudinal construction joints be removed if the contractor elects to do so? Currently it appears there are joints shown on all the bridges except B-53-346 & B-53-347. | The plans should be bid as advertised. If the contractor would like to propose possible changes regarding the longitudinal joints, they can follow the RFI process once the contract has been awarded. | Fred Schunke | 17 | 2018-12-07 07:34 | 2018-12-10 12:14
20181211 | 20181211011 | 11 | Phase 2.5 Investigation | Can you post the lab reports and summary tables from the Phase 2.5 Investigation for this project? | The file can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211011/ | Mike Coleman | 4 | 2018-12-07 08:06 | 2018-12-07 08:09
20181211 | 20181211035 | 35 | Guardrail - Contractor Designed Transition | On page 7 of the plan, there are 2 areas, "contractor designed transition length" and "contractor designed transition section." What information will be required for these 2 areas? Will these be anticipated to include shop drawings and PE stamps or something else? | Design details for each installation that are signed and sealed by a professional engineer registered in the State of Wisconsin are required. See Standard Specifications â€œ614.2.7 Crash Cushionsâ€ for more information. | Fred Schunke | 2 | 2018-12-07 09:08 | 2018-12-10 12:04
20181211 | 20181211012 | 12 | Bent Guardrail at Sta. 162+95 to Sta. 163+20 | Does the Department have any details showing the single-point bends in guardrail shown on pages 10, 15, and 71? We aren't sure that the product can do what is being requested and meet specifications. | Bid the project as shown. If plan changes are required, they will be addressed during construction. | Fred Schunke | 1 | 2018-12-07 09:16 | 2018-12-10 14:11
20181211 | 20181211014 | 14 | Soils Report and Design Schedule. | Can a copy of the soils report be made avaiable? Can the Design schedule be made available? |  |  | 2 | 2018-12-07 09:46
20181211 | 20181211001 | 1 | Follow up to Question 16 | In response to the answer for question 16...it is impossible for The City to have already procured the medallion formliner unless an MSE wall supplier has already been selected (or sole sourced) and the panels have been pre-produced for the project. In order for the medallion to properly fit within the wall panels at the specified locations per the contract plans the formliner needs to be custom-tooled to fit within the MSE wall supplier's proprietary form dimensions. Typical lead times for these items are 8-10 weeks. Please respond. | The City of Janesville has already procured the formliner and has it in their possession. For specific questions about the formliner itself, please contact the City of Janesville per the special provisions. | Fred Schunke | 18 | 2018-12-07 09:59 | 2018-12-10 13:07
20181211 | 20181211002 | 2 | Soil Borings | Are there any soil borings available for this project? | The Soil Boring Report is at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181211002/ush61-soilsreport.pdf | Fred Schunke | 3 | 2018-12-07 10:04 | 2018-12-10 14:50
20181211 | 20181211022 | 22 | Removing pavement item | Looking through the quantities for item 204.0100 Removing Pavement, it is my understanding that this item is being paid in the areas of the Base Patching Asphaltic item 390.0201. Is this correct? | Item 204.0100 Removing Pavement is being used to pay for the removal of the existing median as shown in the typical sections. Any pavement areas being removed for Item 390.0201 Base Patching Asphaltic are paid under that item per Standard Specifications 390.5(2). | Fred Schunke | 1 | 2018-12-07 10:49 | 2018-12-10 12:01
20181211 | 20181211015 | 15 | Internal Sanitary Manhole Seals | Both item #320 Internal Sanitary Manhole Seals & Item #322 Adjusting Sanitary Manholes call for the Furnishing and Installation of 53 each internal rubber or frame/chimney seals. The misc. qtys. do not call out specific locations for the Seals/Adjusting Sanitary MH's. It seems that Item #320 may not be needed as the seals are called for in Item #322 as well. | Internal Sanitary Manhole Seals will be paid separately from the item Adjusting Sanitary Manholes. Payment for the Adjusting Sanitary Manhole shall be revised to read â€œPayment is full compensation for furnishing and installing all materials including adjusting rings, masonry; for excavating, backfilling, and compacting; for disposing of surplus materials; and for cleaning out and restoring the structure.â€ | Fred Schunke | 4 | 2018-12-07 11:00 | 2018-12-10 12:03
20181211 | 20181211002 | 2 | Crack and Damage Survey | Is it the intent of the Department for this item to complete both interior and exterior surveys of businesses and residences with existing concrete sidewalk or other concrete slabs or steps, and steps made of other materials, abutting the work area on this project? |  |  | 4 | 2018-12-07 15:29
20181211 | 20181211011 | 11 | Steel Casing Pipe | The casing pipe detail (sheet 54) says the casing pipe shall be a minimum 24" larger than the largest OD of the carrier pipe. The bid item is a 24" diameter steel casing for a 12" watermain carrier pipe. Are we to bid a 24" diameter casing per the spec and plan sheet, or a minimum 40" diameter casing per the detail (Approx. 15" Bell OD + 24")? Thanks. |  |  | 5 | 2018-12-07 15:53
20181211 | 20181211027 | 27 | Temporary Shoring | To construct Structures B-17-214/215, while keeping CTH Q open to traffic under a stop condition, it seems that temporary shoring will be required to excavate the piers for these structures while allowing for the safe passage of traffic on the roadway. Please provide an item for temporary shoring for these structures. |  |  | 11 | 2018-12-07 16:22
20181211 | 20181211031 | 31 | Addendum No. 1 - Clarification | Is the stationing shown in Addendum No.01 for project 7510-02-60 or 7510-02-62? | That is for 7510-02-60. The stationing corresponds to an area from the Levis Creek crossing to Ho Chunk Gaming. | Fred Schunke | 5 | 2018-12-07 16:44 | 2018-12-10 14:22
20181211 | 20181211019 | 19 | Wall R-15-11 | On Page 491 - The square footage of Geometry Chart does not match what is being bid. Could these numbers be verified? |  |  | 5 | 2018-12-10 10:35
20181211 | 20181211032 | 32 | HDPE Watermain | 1) Will the inside diameter of the directionally drilled HDPE watermain need to match the interior of the C900 PVC watermain. I do not see a specification noting HDPE will need to be upsized to accommodate the inside diameter. 2) Will the inside diameter of the pipe bursting HDPE sanitary sewer need to match the interior of the SDR 35 PVC sewer main? | 1) No. The size shown in the plans is controlling. The specifications inadvertently did not specify that the pipe needs to be DIPS and not IPS. 2) No. The size shown in the plans is controlling. | Fred Schunke | 4 | 2018-12-10 12:09 | 2018-12-10 12:10
20181211 | 20181211002 | 2 | Temp Aggregate Driving Surface | There is a temp Aggregate driving surface spelled out in the spec. There is no bid item for Temp Aggregate Materials. How is this to be paid? |  |  | 5 | 2018-12-10 14:08
20181211 | 20181211001 | 1 | Follow up to Question 16 & 18 | We have viewed the formliner on hand at the City of Janesville. Considering the size of the liner, the proprietary dimensions of the different MSE wall manufacturers, and the ashlar/stone/smooth band integration at the desired locations, the desired aesthetic canNOT be achieved as shown in the contract documents. The formliner at the City of Janesville was manufactured by Karlson Forming Specialties. Similar style & size formliners from Karlson have a typical 6-10 week lead time (excluding shop drawings). How does The Department plan to provide the formliner needed to achieve the desired aesthetic and meet the demanding schedule? We recommend eliminating the logo aesthetic from the MSE walls. |  |  | 19 | 2018-12-10 14:47