|  |  |
| --- | --- |
| Date and Time of Meeting:  | September 20, 2022, 10:00 a.m. - 11:30 a.m. |
| Location:  | Teams |
| Subject:  | 1229-04-71/72/73/77 – I-43 South End |

**Attendees:**

|  |  |  |  |
| --- | --- | --- | --- |
| Aaron Bowe | Holveck, James T  | Kiepczynski, Kenneth T - DOT | Peter Duffek |
| Andrew Kowske | Jackie Spoor | Kody Weber (Guest) | Phil Bielefeld |
| Andrew Weaver | James Buggs | Kutka, Justin - DOT  | Prasad S. Narayan, PE |
| Ann Neshek | James Carter | Lange, Michael | Roberson, Rosalind - DOT |
| Ben Mehring | Jeff Batchelor | Lucas Doxtater | Ryan Janke |
| Dan Baumann | Jeremy Napiwocki | Matt Grove | Sellers, Daniel P - DOT |
| Dan Zignego | Joe Lodde | Nag, Manojoy - DOT | Shawn Hoffman |
| David Burt | John Krinke | Ndon, Paul J - DOT | Steve Koski |
| Gary D. Richards | John Streu | Nguyen, David Q - DOT | Tim Peterson |
| Haney, Helen | Jon | Nicholas Van Deraa | Tim Poehnelt |
| Heather Anders | Jon (Lunda) | Obenberger, Jay - DOT | Toni Keegan |
| Hoff, Steve - DOT | Juliette Okel | Pachniak, Josh (FHWA) | Trevor Wallner |

**Questions & Responses**

1. Trevor Wallner
* Question – During the Stage 1A temporary widening, after constructing the first 20’ from the existing outside traveled lane can the remaining width be constructed without closing a lane?
* Response – Yes, as long as the 20’ temporary clear zone specified in the special provisions is met.
1. Tim Peterson
* Question - At the private berms potential fill site location (Article 42) will the wetland permitting be cleared by the property owner or is this the responsibility of the contractor?
* Response **–** This work is incidental and is to be coordinated outside of the project. Securing all necessary approvals (including permits, if necessary) related to placing fill and construction activities on private property is the responsibility of the residents and/or contractor.
1. Tim Peterson
* Question - Can common excavation be used to construct the UPRR embankment or does grade 1 material need to be used for fill?
* Response – The embankment needs to be grade 1 material. Common excavation cannot be spoiled on the UPRR property. Also, please consider the contaminated soil quantities specified in the plans.
1. John Krinke
* Question – Has the UPRR right of way been acquired?
	+ Response – The acquisition is still pending. The stipulation has been ordered by the judge.
1. John Krinke
* Question - When does WisDOT anticipate awarding the contract?
	+ Response – WisDOT intends to award the contract within 30 days.
1. Shawn Hoffman
* Question – The design schedule shows work beginning in February but the specifications say March. Please clarify.
	+ Response - This will be updated in Addendum 1. The March start date is intended for construction activities related to paving operations. Other construction activities, such as clearing, are anticipated to begin earlier with approval from the engineer.
1. Shawn Hoffman
	* *Comment* – The award date will control when steel is able to be procured for the UPRR bridge and could impact the completion of the structure.