## Slide 1: Mega Projects Guidelines Training
Course Objectives
Van Walling, PE
Walling Consulting Services
Gary Whited, PE
Construction and Materials Support Center
UW-Madison

## Slide 2: Welcome and Introductions
Please provide…
  Name
  Title
  Office
  Mega project role
  Meaningful takeaway from today’s training

## Slide 3: Importance of Mega Projects
Comments from Secretary Gottlieb
Click on photo for video clip:

## Slide 4: Mega Project Guidelines Objectives
Mega Project Team convened in 2011
Team’s Charge was to communicate:
  Existing processes
  Organizational structure
  Best Practices
  Appropriate level of effort
  And promote consistency in management and
  oversight of Mega Projects
Team developed guidance and that is found in the
Mega Projects Guidelines
Notes: Section 7: Project Matrix
Section 9: Management Systems
Section 10: Budget Estimation & Management
Section 11: Change Management
Section 12: Management Expectations
Section 13: Best Practices

## Slide 5: Training Topic Areas
http://roadwaystandards.dot.wi.gov/standards/mega/index.htm
Notes: Section 7: Project Matrix
Section 9: Management Systems
Section 10: Budget Estimation & Management
Section 11: Change Management
Section 12: Management Expectations
Section 13: Best Practices

## Slide 6: Training Objectives
Exposure to the Guidelines
Explain content of selected sections
Identify Best Practices
Share experiences from past Mega Projects
Notes: Section 7: Project Matrix
Section 9: Management Systems
Section 10: Budget Estimation & Management
Section 11: Change Management
Section 12: Management Expectations
Section 13: Best Practices

## Slide 7: Characteristics of Mega Projects
What makes a project mega?
Notes: Large group exercise where participants are asked to identify characteristics of mega/major project. Facilitators will record answers on a flip chart.

## Slide 8: Mega projects are not business as usual !
Mega projects are large.
Avg. 3R/BB Project is $2 M
Avg. Major is $145 M
N-S Freeway Plan Set: 10,109 Sheets
Marquette Int. Specials: 883 Sheets
Zoo FEIS Document: 600 Pages

## Slide 9: Mega projects are not business as usual !
Mega projects are fast-paced.
USH 41: 351 RFI’s (2012); 1-day turnaround
4,485 Documents sent/received (2012)
N-S : 418 Contract Mods processed
4,116 Issues dealt with
USH 41: 65 Progress Estimates ≥ $1,000,000
Largest: $4,069,632
N-S: Largest Progress Estimate: $9,200,000

## Slide 10
Mega projects are not business as usual !
Ryan’s Rule of Times 10 for Mega’s

## Slide 11
Mega projects are complex to manage.
Cost
Technical
Schedule
SCOPE
Mega projects are not business as usual !
Technical
Cost
Schedule
Context
Financing
SCOPE

## Slide 12: Mega projects are not business as usual!
Mega projects require managing relationships.
Project Team
Region & Division
Management
Region support staff
Statewide Bureaus
FHWA
Regulatory Agencies

## Slide 13: Mega projects are not business as usual!
Mega projects require managing relationships.

## Slide 14: Mega projects are not business as usual!
Mega projects require managing resources.
Staff
Facilities
IT
Equipment

## Slide 15: Mega projects are not business as usual !
Mega projects are high risk.
Notes: Picture from Marquette, show monitoring tools for cost and design, OCIP?

## Slide 16: Mega projects are not business as usual!

## Slide 17
Delivering a Mega Project
Identify the biggest challenges within the following categories (each group is assigned one category)
Identify potential solutions to address the challenge.
  a) Budget b) Schedule
  c) Experience/Expertise d) Technical
  e) Staffing/Resources f) Teamwork
  g) Communication

## Slide 18
Key takeaways:
Each project is unique
Need for increased level of team work and trust
Emphasis on problem solving
Ownership of the project by team
Importance of attitude
Delivering a Mega Project

## Slide 19: Delivering a Mega Project
Comments from George Poirier, FHWA
Click on photo for video clip:

## Slide 20: Break
Please return at:
Notes: Box lunch to be provided so participants remain on sight and have chance interact with each other.

## Slide 21: Resources for Mega Projects
Wisconsin DOT
Mega Projects Guidelines on the Web
Mega Project Matrix (Section 7)
Scoping tools
Cost Estimating Tool (Section 10)
Statewide Bureau Resources
Outlook calendar
Quarterly snapshot
FHWA
Project Delivery Webpage

## Slide 22: Mega Projects Guidelines
http://roadwaystandards.dot.wi.gov/standards/mega/index.htm
Notes: Section 7: Project Matrix
Section 9: Management Systems
Section 10: Budget Estimation & Management
Section 11: Change Management
Section 12: Management Expectations
Section 13: Best Practices

## Slide 23: Mega Projects Guidelines on the Web
http://roadwaystandards.dot.wi.gov/standards/mega/index.htm

## Slide 24: Mega Project Matrix (Section 7)

## Slide 25: FDM Project Scoping Checklist

## Slide 26: I-39/90 Scoping Spreadsheet
Construction ID |  | 1005-10-71 | 1005-10-72 | 1005-10-73 | 1005-10-74 | 1005-10-75 |  | 1005-10-76 | 1005-10-77 | 1005-10-78
Project Description |  | Rock River Bridges | 2.3 miles ML paving, including STH 59 Interchange |  | Overpasses @ Goede Rd | Overpass @ Manogue Rd | Alt Route | 3 Miles ML paving & noise walls | 2 miles ML paving, include USH 14 & STH 26 intrchngs & noise walls | 6.1 miles ML paving
PS&E Date |  | May-15 |  | Aug-13 | Aug-14 |  | Nov-14 | Aug-16 |  | May-17
Design Engineering Services Contract |  | #2 |  |  |  |  |  | #3 |  | 
A. | DESIGN REPORTS |  |  |  |  |  |  |  |  | 
N | Concept Definition Report |  |  |  |  |  |  |  |  | 
Y | Design Study Report (4 updates and 3 new) | Update |  | Update | New | New | New | Update |  | Update
Y | Pavement Type Selection Report (7 new) | New |  | New | New | New | New | New |  | New
Y | Exception to Design Standards Report (1 update in B) |  |  |  |  |  |  | Update |  | 
Y | Encroachment Report (1 update in B) |  |  |  |  |  |  | Update |  | 
Y | Interchange Access Justification Reports (3 updates and 1 new) |  | Update |  |  |  |  |  | 2 updates | New (rest area ramps)
N | Design Criteria Report |  |  |  |  |  |  |  |  | 
N | Design Recommendation Reports |  |  |  |  |  |  |  |  | 
N | Hydraulic Analysis Report |  |  |  |  |  |  |  |  | 
N | Existing Conditions Report |  |  |  |  |  |  |  |  | 
N | Other reports |  |  |  |  |  |  |  |  | 
B. | ENVIRONMENTAL DOCUMENTATION |  |  |  |  |  |  |  |  | 
N | Environmental Assessments |  |  |  |  |  |  |  |  | 
N | Environmental Impact Statements |  |  |  |  |  |  |  |  | 
Y | ER |  |  |  |  |  | New |  |  | 
Y | Design Refinement Memo (1 update for A and new for B) | Update |  |  |  |  |  | New |  | 

## Slide 27: Cost Estimating Tool (Section 10)

## Slide 28: Statewide Bureau Resources

## Slide 29: Outlook Calendar for Mega Projects
Mega Project Meetings scheduled on Outlook
Agendas with desired decisions identified
Meetings scheduled by Project Teams

## Slide 30: Mega Projects Quarterly Snapshot

## Slide 31: FHWA Website
http://www.fhwa.dot.gov/ipd/project_delivery/tools_programs/project_management_plans/guidance.htm

## Slide 32: Management Systems for Mega Projects
Management and Reporting (Section 9)
Change Management (Section 11)
Management Expectations (Section 12)

## Slide 33: Management and Reporting (Section 9)
Federal level
Department level
Region and bureau level
DBE and Small Business Responsibilities
Title VI Responsibilities

## Slide 34: Federal Level
Projects receiving federal financial assistance with estimated total cost >$500M require:
  Project Management Plan - documents the procedures and processes that manage the scope, costs, schedules, quality and applicable federal requirements
  Annual Financial Plan - based on detailed estimates and assumptions of future increases in the cost to complete the project
Simplified federal financial plan required for projects with estimated total cost between $100M and $500M

## Slide 35: Department Level
Oversight Team meetings - Mega Projects report on a monthly basis to the Department’s Oversight Team to share information on:
  budget
  schedule
  work completed and planned
  significant issues and risks
  public involvement and legislative communication and coordination
  disadvantaged business enterprise and labor initiatives

## Slide 36: Department Level
Division Mega and Major Projects Team meetings - Region Directors, Bureau Directors, Administrator’s Office, Mega and Major Project Development Chiefs, DTIM BSHP and BTLR Directors, and FHWA meet monthly to address:
  project issues and risks
  schedule issues and priorities
  resource issues and priorities
  high level policy decisions
  best practices and successful project components
  areas for collaboration
  consistent messaging on division Mega / Major project schedules, budgets, quality, and safe product use
  technology transfer

## Slide 37: Region, Bureau and Team Management Level
A team working on a Mega Project will typically have multiple daily or weekly meetings focused on immediate project needs along with issues and risks.
The project team should hold a Change Management and Progress Meeting on a bi-weekly to monthly basis. Topics covered at the meeting should cover components required in the Project Management Plan.

## Slide 38: Region, Bureau and Team Management Level
Reports that Project Team should utilize:
  Executive summary development for Oversight Committee
  Activities and deliverables
  Issues/action items
  Schedule
  Cost
  Quality
  Other status reports, such as DBE/minority participation and contractor safety

## Slide 39: Region, Bureau and Team Management Level
Project and Program Management Controls that Project Team should utilize:
  Risk management plan
  Scope management plan
  Scheduling software
  Cost tracking software
  Project metrics
  Contracting strategies (new and innovative)
  Value engineering, value analysis, constructability reviews
  Contractor outreach meetings
  Partnering
  Change order/extra work order procedures
  Claims management procedure
  Other programs, such as Owner Controlled Insurance Programs (OCIP)

## Slide 40: DBE and Small Business Responsibilities, Management, and Reporting
The Department has federal and state responsibilities on all of its improvement program projects to fulfill DBE and SBE responsibilities
The Office of Business Opportunity & Equity Compliance (OBOEC) in DTSD oversees and manages these responsibilities

## Slide 41: DBE and Small Business Responsibilities, Management, and Reporting
OBOEC carries out a number of ongoing responsibilities for the Department that cover all programs. These include:
  Inclusive DBE goal setting
  DBE firm pre-assessment
  Encouraging formalized partnering relationships
  Bullseye marketing strategy
  Strategies for supplemental DBE contracting opportunities
  Outreach to lateral certifying agencies
  Structured networking for primes and subs
  DBE contracting update
  DBE certification workshops
  Expedited DBE certification
  Civil Rights and Compliance Tracking System (CRCS)
  Development and inclusion of contract specifications
  Training Workshops

## Slide 42: Title VI Responsibilities Management and Reporting
Title VI assures that no person in the United States shall on the grounds of race, color, disability or national origin be excluded from participation in, be denied the benefits of, or be subjected to discrimination under any program or activity receiving federal financial assistance.
The Department has federal Title VI obligations on mega projects, major projects, and high-profile projects. The Department’s Title VI Program assures compliance throughout the various stages of each individual federally-funded and state-funded project:
  Planning
  Special, Economic and Environmental Effects (SEE)
  Project Development
  Right-of-Way
  Construction

## Slide 43: Lunch
Please return at 12:30
Notes: Box lunch to be provided so participants remain on sight and have chance interact with each other.

## Slide 44: Management Systems for Mega Projects
Management and Reporting (Section 9)
Change Management (Section 11)
Management Expectations (Section 12)

## Slide 45: Mega Project Change Management (Section 11)
Change management is required and is to utilize the process outlined in this section.
Describes the change management process
for the different phases of project delivery
Identifies the level of decision making authority, frequency of reporting, review committee make up, and gives examples

## Slide 46: Mega Project Change Management

## Slide 47: Mega Project Change Management
Change Management is a proactive process of tracking and administering changes during delivery of a project.
It is done to minimize the consequences of changes and enable approved changes with minimal disruption.

## Slide 48: Mega Project Change Management
Change Management protects you and your project from changes that can damage it.
  Big changes that can be major and have serious impact.
  Small step-by-step changes that gradually add up.

## Slide 49: Mega Project Change Management
Things change on every project!
    Changes that regard the final product
    Changes that regard the time required
    Changes that regard the resources needed
The key is to manage and control it.

## Slide 50: Mega Project Change Management
You need to analyze the identified changes.
  Who needs the change
  What is to be changed and why
  How important is the change to the project
  What will happen to the project if you make the change

## Slide 51: Mega Project Change Management Tools/BP’s
  Change Management Reports
  Tracking overruns/underruns
  Cost to complete estimates
  Project level trend reports
  Top 10 issue lists
  Top 10 risk lists

## Slide 52: Mega Project Change Management Tools/BP’s
Construction Change Management starts in the
design phase.

## Slide 53: Mega Project Change Management Tools/BP’s

## Slide 54: Mega Project Change Management Tools/BP’s

## Slide 55: Mega Project Change Management Tools/BP’s

## Slide 56: Mega Project Change Management Tools/BP’s

## Slide 57: Mega Project Change Management Tools/BP’s

## Slide 58: Mega Project Change Management Tools/BP’s

## Slide 59: Mega Project Change Management Tools/BP’s

## Slide 60
The project is expected to be a success.
Mega Project Management Expectations (Section 12)

## Slide 61: Mega Project Management Expectations
That there is shared success within WisDOT.

## Slide 62: Mega Project Management Expectations
Project, Region and SWB managers are
responsible for setting the tone and
implementing these expectations.

## Slide 63: Mega Project Management Expectations
Project leaders and managers are responsible
and accountable for making sure decisions are
made.

## Slide 64: Mega Project Management Expectations
Project leaders and managers are responsible
and accountable for making sure decisions are
made.
Project
Statutes
Standards
Regulations
Political

## Slide 65: Mega Project Management Expectations
Project leaders and managers are responsible
and accountable for making sure decisions are
made.

## Slide 66: Mega Project Management Expectations
*Timelines need to be agreed upon

## Slide 67: Tools and Best Practices to help meet these expectations
Partnering is a way of conducting business that
promotes open communication, trust,
understanding, and teamwork in day-to-day
operations.

## Slide 68: Tools and Best Practices to help meet these expectations
Innovation is encouraged.
New Processes
Innovative designs
New Technology

## Slide 69: Tools and Best Practices to help meet these expectations
Innovation is encouraged.
BUT ….

## Slide 70: Tools and Best Practices to help meet these expectations
A dispute resolution plan helps prevent
opposing parties from arriving at an impasse.

## Slide 71: Staffing and organization of Mega projects (Sections 4 & 6)
Regions have flexibility on how they organize
the delivery team
Guidelines provide a functional org chart
Guidelines provide generic roles &
responsibility descriptions by position
Key is not how the team is organized but
rather how decisions are made and how timely they are made.

## Slide 72: Staffing and organization of Mega projects

## Slide 73: Generic Roles and Responsibilities for Mega Project Management

## Slide 74: Staffing and organization of Mega projects
Mega projects can have different staffing models.
DOT
Consultant
DOT
Consultant
DOT
Consultant

## Slide 75: Best practices from WisDOT’s Mega projects (Section 13)
Best practices are processes or methods that
lead to enhanced project performance when
effectively executed.
- Construction Industry Institute

## Slide 76: Best practices from WisDOT’s Mega projects
Mega Project Best Practices Guidelines detail
global best practices.
  Efficient and effective use of resources
  Management, communication and
  dissemination of key information
  Leveraging knowledge and expertise
  Facilitation of continuous organizational
  improvement

## Slide 77
The Mega Project Guidelines provide
Public Involvement best practices.
Best practices from WisDOT’s Mega projects

## Slide 78: Best practices from WisDOT’s Mega projects
Provided for each BP:
● Title
● Brief description
● details to aid in implementation
● Objective
● When to apply
● Cost implications
● Conditions for successful
application
● Cautions

## Slide 79
Best practices from WisDOT’s Mega projects

## Slide 80: Panel Discussion on Mega Projects
Participants:
Brian Roper – NER
Tracey Blankenship – FHWA
Steve Krebs – SWB
Robert Fieldbinder – URS
Notes: Participants: include:
  WisDOT experienced mega project person
  Statewide Bureau Person
  Consultant experienced mega project person
  FHWA
Answer Questions from the Audience
Take away points:
  Fast paced timeline means decisions get made
  Challenge to balance need to keep team members informed and the need to meet timelines
  You need to do your part so others can do theirs

## Slide 81: Break
Please return at:
Notes: Box lunch to be provided so participants remain on sight and have chance interact with each other.

## Slide 82: Training Evaluation
Thank you for your participation.
Please take the time to give us your candid feedback so that we know what to modify to provide the most effective training we can.
Notes: Participants: include:
  WisDOT experienced mega project person
  Statewide Bureau Person
  Consultant experienced mega project person
  FHWA
Answer Questions from the Audience
Take away points:
  Fast paced timeline means decisions get made
  Challenge to balance need to keep team members informed and the need to meet timelines
  You need to do your part so others can do theirs