## Risk List
Function | Stage Impacted |  | Probility of Occurrence (%) |  | Cost Risk Information (Millions $) |  |  | Schedule Risk Information (Months)
|  |  |  | Low Cost | Most Likely Cost | High Cost | Low Schedule | Most Likely Schedule | High Schedule
Environmental |  | Delay in environmental assessment
Determination of significance requiring EIS
Environmental regulations change
Expected controversy on environmental grounds
Wetlands impacts
Wildlife impacts, need for wildlife crossing
4(f) resources affected
Wildlife/plant sites
Impact on historic properties
Unanticipated cultural or archaeological findings
Hazardous materials present
Buried man-made objects/unidentified hazardous materials found in construction
Issues in air quality for construction materials
Project does not conform to the state implementation plan for air quality
Noise mitigation
Noise mitigation for truck deceleration at weigh station/rest area
Additional sound walls required due to new development
Growth inducement/sprawl issues
Negative community impacts cause delays
New permits or new information required
Permits or agency actions delayed or take longer than expected
Preparation of environmental permit package
New storm water rule - water quantity and quality issues
Right of Way |  | Delay in ROW document internal approval process
Delay in acquisition due to design change
Delay in eminent domain authority
Condemnation takes longer than expected
Additional cost for administrative revisions
Real estate litigation
Higher real estate cost due to development annexation, rezoning or other changes
ROW acquisition is more costly than expected due to landowner objections
Need for temporary or permanent easements
Maintaining local access
Risk of acquiring additional access
Property donation
More/less ROW needed
Utilities |  | Not having a workplan/agreement prior to construction
Delay in agreements
Design changes impact utility relocation
Betterment issues
Additional cost for utility location
Differing conditions at utility sites
Utility distribution lines
Design changes in roadway design impact utility relocations
Utility relocation may not happen on time
Discovery of unknown utilities during construction
Railroad |  | Railroad involvement
Cost of railroad flaggers
Design |  | Changes in design
Changes in alignment
Changes in profile
Changing assumptions on technical issues in design stage
Need to update traffic volumes
Schedule constraints
Late issue in design discovered, requiring more time to finalize design
Design external review delays project schedule
Obtaining design approvals from local agency takes longer than expected
Need for design exceptions or variations
Discharge from stormwater management system drainage/flowage easements
Culvert replacement
Design changes for storm drain collection system
Design changes for cross pipes
Design changes for ponds
Design constraints require additional ROW related to drainage
Drainage measures location changes
Drainage measures size changes
Poor erosion control measures - excessive turbidity levels
Full depth shoulder
Current rumble strip patch/cut out
Structures/Geotechnical |  | Changing geotechnical conditions-due to new information
Geotechnical surveys late
Subgrade issues
Changes in structures or embankments
Design changes on bridge or overpass
Cost savings opportunity for redecking bridges
Opportunity to recycle existing roadway as base
Pavement specification changes or legal load issues
Sign replacement
Caves in area with possible impact
Polymer overlay
Construction |  | Material staging area availability
Additional maintenance items included in construction
Work windows
Weather related interruptions
Excavation impacts during construction due to weather
Impacts on final paving due to winter work windows
Inaccurate contract time estimates
Nonconforming work results in schedule delay or additional costs
Safety issues delay project opening
Different site conditions
Encountering unexpected subsurface conditions
Borrow material source, reuse, disposal issues
Haul routes for borrow material
Coordianation with local agencies
Interference from other projects
Baseline traffic management solutions does not work
Traffic |  | Maintenance of traffic during construction
Maintenance of traffic at local road overpasses
Maintenance of traffic during construction at weigh station
Maintenance of separated traffic over winter months
Continuous access for emergency vehicles as well as emergency routes
Continuous access for school buses/transit
Delay in receiving ATMS items
Snow removal impacts of MOT or staging area
Adequate staging area for construction work and MOT
Alternate route issues
Access points
Incident management
Special events
Public/Local Involvement |  | Awareness campaign
Political controversy
Threat of lawsuits
Consistency with local plans
Enhancement requests
Stakeholders request late changes
Local bike trails/snow mobile trails
New stakeholders emerge which potentially changes design
Contracting and Procurement |  | Lack of qualified bidders for special construction
Change in project delivery method
Changes in contract packaging
Other construction projects in areal limit supply of labor
Other construction project in region limit supply of materials
Other issues related to contract (warranties, liquidated damages, DBE, insurance, bonding, etc.)
Delays in Ad/Bid/Award process due to addenda or bid protests
Availability of specialty labor
Labor issues interrupt construction
Delays in procurement of specialty materials or equipment and associated cost premiums
Incentives for meeting project schedule
Contractor non-performance/De-barrment
Management and Funding |  | Change in critical staffing during the project
Delay in critical decision making
Functional units not available, overloaded
Unanticipated project manager workload
Priorities change on existing program
Pressure to deliver project on an accelerated schedule
Changing political landscape
Coordination issues
Delay in funding
Advancement in funding
Funding changes due to political factors
Funding tied to project milestones