# I – START CONSTRUCTION FLOWCHART

Typically, about 4 weeks after Letting

Contract Executed

= Project Engineer action items

MS - Materials Specialist

CAS - Construction Admin. System		PEP - Plant Establishment Period

CFA – Conditional Final Acceptance		PE - Project Engineer

CS – Contract Specialist			PM – Project Manager

CWC – Contract Work Complete		PT - Project Tracking

FIT - Field Information Tracking System	QMP – Quality Management Plan

FM - Field Manager				RR - Records Reviewer

LCS – Labor Compliance Specialist		SF - Semi Final Estimate

LCS – Lane Closure System			SOM – Source of Materials

MR - Materials Reviewer			SS - Standard Specifications

SWIG_Ref_Files\constr-admin-flwchrt.docx

Contact: Sharayah Sikkema

Rev Jan 2022

# II – DURING CONSTRUCTION FLOWCHART

- FINAL AS YOU GO

- Discuss CRCS & DBE Goal status at weekly meetings

- Bi-weekly Pay Estimates

- Timely Submittal of Material Certs & Test results

- Verify QMP is contractually accurate and being followed

- Verify SOM is current

- Verify ECIP is current

- Erosion control inspections and orders

- “To Do” lists for the contractor as the project progresses

- Verify project schedule is current

- Discuss contract time at weekly meetings

- Weekly meeting minutes and weekly updates distributed

Contract Mod Process

Partial Acceptance may be requested by Contractor as defined in SS 105.11.1. PM approves request and CS sends Partial Acceptance letter

All contract bid items and change order work are complete including:

- All lanes of traffic are open on a finished surface.

- All signage and traffic control devices are in place and operating

- All drainage, erosion control, excavation, and embankments are completed.

- All safety appurtenances are completed

- PM/Project Engineer develops punch list

Project is Substantially Complete as defined in SS 105.11.2.1.3

= Project Engineer action items

MS - Materials Specialist

CAS - Construction Admin System		PEP - Plant Establishment Period

CFA – Conditional Final Acceptance		PE - Project Engineer

CS – Contract Specialist			PM – Project Manager

CWC – Contract Work Complete		PT - Project Tracking

FIT - Field Information Tracking System	QMP – Quality Management Plan

FM - Field Manager				RR - Records Reviewer

LCS – Labor Compliance Specialist		SF - Semi Final Estimate

LCS – Lane Closure System			SOM – Source of Materials

MR - Materials Reviewer			SS - Standard Specifications

*  Electronic Signatures are allowed, see SWIG 8-10-5

**  See SWIG 8-10-1 for required signatures

SWIG_Ref_Files\ constr-admin-flwchrt.docx

Contact: Sharayah Sikkema

Rev January 2022

Time Charges Stopped is entered and the project moves to the Finals process

# III-IV    FINALS   DATES & RECORDS   FLOWCHART

SWIG_Ref_Files\ constr-admin-flwchrt.docx

Contact: Sharayah Sikkema

Rev January 2022

* Contact contractor first – Supervisor approval is required to send FE without a returned semi-final est. FE can NOT be sent w/o signed Sub Retainer Cert!

After concurrence with PM, the Project Engineer enters the Time Charges Stopped date in FM.

This automatically populates Substantially Complete Date in PT & sends e-mail to PM, Project Engineer, contractor, CS, MR, RR & LCS

Project Engineer sends Punch List to CS to be included on Substantially Complete letter. Punch List includes 5 business days to complete work and 15 business days/21 calendar days to submit ALL required documentation (including Materials).

Final Acceptance Letter issued (as defined in SS 105.11.2.3), CS sends out. Completion Cert (DT1582) printed and given to Supervisor to sign

Project Engineer works with contractor to resolve issues with disputed quantities, and makes adjusting postings. Project Engineer sends an adjusted SF, PM approves adjusted SF, CS sends adjusted SF to contractor, allowing 10 working days to respond, with copies to Project Engineer & PM.

3

Contractor responds in writing with items of disagreement

30 Days after SF is sent to contractor – If signed SF has not been returned, the PM grants approval to send Final Estimate * (proceed to step 4)

Project Engineer & PM agree with resolution of items of disagreement, Project Engineer makes appropriate adjusting postings to correspond with adjusted and signed SF (proceed to step 4)

Contract Specialist forwards a copy of signed SF to Project Engineer and PM

Within 0-2 days of SF sent, the SF is approved by PM in FieldNet. PM notifies CS by email. CS sends SF to contractor with copies sent to Project Engineer and PM

After concurrence with PM, the Project Engineer sends Semi-Final Estimate in FM

- No later than 15 days after project records are returned from reviewer, Project Engineer resolves issues identified during Records Review and notifies PM.

- No later than 15 days after materials records are returned from reviewer, Project Engineer resolves issues identified during Materials Review and notifies PM.

- Material Certification (DT1310) is           completed and signed by PM and turned in to CS.

- Contract Items Review (DT 2076) completed and signed by PM.

- Section IV Part C in CAG to CS

- Retainer reduced if requested and PM concurs-  notify CS

- * Finals boxes to be turned in to CS

- * Payroll Clear date entered by LCS.

(Ok to send SF w/o PCD, just check on issues)

PM emails CS when Contract Items Review begins. No later than 30 days after the records are submitted for review, the project records and materials records are reviewed and returned to PM

Project Engineer submits project records to PM for Contract Items Review AND materials records for Materials Records Review no later than 60 days after CFA.

PM emails CS that Finals Boxes turned in. CS enters date in PT for Contact Records Submitted

* * * All items are to be

complete and correct. * * *

Project Engineer & PM verify the Punch List is acceptably completed, including submission of ALL noted missing documentation.  Project Engineer enters All Contract Work Complete date in FM & Punch List Complete date in FIT.  Do not enter CWC date for Contracts with Plant Establishment Period until the end of the PEP. The CS may send out a Conditional Final Acceptance – Planting letter to the contractor.

(4)

179-180

Calendar

days

Proceed to step 4

(1)

0-21

Calendar

days

(2)

22-126

Calendar

days

(3)

127-178

Calendar

days

3

3

2

1

2

1

2

3

44

1

= Project Engineer action items

MS - Materials Specialist

CAS - Construction Admin System		PEP - Plant Establishment Period

CFA – Conditional Final Acceptance		PE - Project Engineer

CS – Contract Specialist			PM – Project Manager

CWC – Contract Work Complete		PT - Project Tracking

FIT - Field Information Tracking System	QMP – Quality Management Plan

FM - Field Manager				RR - Records Reviewer

LCS – Labor Compliance Specialist		SF - Semi Final Estimate

LCS – Lane Closure System			SOM – Source of Materials

MR - Materials Reviewer			SS - Standard Specifications

PM must check with CS prior to sending Final Estimate, to be sure there are no outstanding issues. PM sends Final Estimate in FM, PM approves Final Estimate in FieldNet

(If there are minor changes to estimate from track #2 in Semi-Final above, they are paid on the Final Estimate)

Within 30 days of SF sent to contractor – one of 4 things will happen:

Contractor returns adjusted and signed SF

Proceed to step 4

Contractor responds with minor items of disagreement, adjusts the SF and returns signed, adjusted SF Estimate

Contractor agrees with SF and returns signed SF Estimate with items of disagreement

Project Engineer, with PM Concurrence, verifies Conditional Final Acceptance (as defined in 105.11.2.2).  This relieves the contractor of maintenance responsibility, is issued on all contracts, and does not require the contractor to request it.             CS sends letter to contractor.