## Main Form
UTILITY WORKSHEET
DT2236 02/2026 §84.063 Wis. Stats. |  |  |  | https:\\www.google.com
Locals 02/2026 v2.0
UTILITY FACILITY OWNER (OWNER):
UTILITY FACILITY TYPE:
PROJECT DESCRIPTION: |  |  | PROJECT ID(S):
Title: |  |  | Design:
Limits: |  |  | Construction:
Highway: |  |  | Right of Way:
County: |  |  | U and/or UA No:
DATES AND SUBMISSION TRACKING: |  |  | RETURN WORK PLAN TO:
Project Plan Transmittal:
Work Plan Due:
Work Plan Returned:
UC Meeting for Shared Utility Space Complete By:
(if applicable)
1. | Does the OWNER listed above have utility facilities within the limits of the project plan? Select one of the following options.
2. | Are the OWNER's existing utility facilities shown correctly and completely in the project plan? It is not necessary to address any existing utility facilities that are not depicted in areas where the project plan will not affect the existing utility facilities. Select one of the following options.
3. | Does the OWNER listed above have any existing known discontinued utility facilities within the limits of the project plan? Do not include utility facilities that will be discontinued as part of the OWNER's work plan. Select one of the following options.
4. | Will any utility work associated with the project plan involve grant funding? Select one of the following options.
Select all that apply
Review the project plan for conflicts between the highway plan(s) and the OWNER's utility facilties. Complete the Anticipated Conflicts table. After the utility conflicts are reviewed in entirety, select only the options that were included in the Anticipated Conflicts table. Select all that apply.
5. | Review the project plan for conflicts between the highway plan(s) and the OWNER's utility facilties. Complete the Anticipated Conflicts table. After the utility conflicts are reviewed in entirety, select only the options that were included in the Anticipated Conflicts table. Select all that apply.
6. | Is service work required, including removals, discontinuances, modifications, and/or relocations of existing services, and/or coordination of new service installations? Select all that apply.
7. | Is the OWNER's utility work dependent on or affected by shared utility spaces (e.g. shared poles, trenches, conduit packages, etc.)? Select one of the following options.
8. | Does the OWNER need to obtain approvals and/or permits from other entities to perform the utility work? Select one of the following options.
9. | Does the project sponsor need to complete the acquisition of any real estate parcels to enable the OWNER to perform the utility work? Select one of the following options.
10. | Does the OWNER need to obtain any easements, fee title, and/or long-term leases to enable the OWNER to perform the utility work? Select one of the following options.
11. | Will any of the following affect the OWNER's anticipated start date, schedule, and/or required utility work? Provide relevant information that may or will help prevent utility-related construction delays that will affect highway construction. Select and provide detail for all that apply.
Subsurface Utility Exploration
Inventory, condiiton reports, measurements, or survey of existing features
Survey staking by utility
Law enforcement activities, such as need for rolling stops
Rock blasting and removal
Maximum allowable cover over the existing facilities has been exceeded
Diversion of staff or contractors due to natural disaster
Restricted site access
Seasonal constraints
Required outage of adjacent powerlines
Compliance with provisions of environmental permits
Other
12. | Will the OWNER be seeking reimbursement for any of the utility work? Select one of the following options.
13. | Provide the name, address, phone number and e-mail address of the field contact person for the project ID(s) so that this information may be included in the highway plan(s).
Name:
Address:
Phone Number:
E-mail:
14. | Verify that all of the required attachments have been filled out and that any required inclusion will be submitted with this worksheet. Also provide the name, phone number (including extension), and e-mail address of the person who prepared this worksheet and the date the worksheet was prepared.
Name:
Address:
Phone Number:
E-mail:
Date:
END OF MAIN FORM
Yes - The OWNER's existing utility facilities are shown correctly and completely.
No - The OWNER's existing utility facilities are not shown correctly and/or information is missing. The following items are attached to this worksheet to provide information for the correction of the existing utility locations. Select all that apply.
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
A narrative or description of the utility facilities, using project stationing - Provide detail.
Other - Provide detail.
No - The OWNER does not have existing known discontinued utility facilities within the limits of the project plan.
Unknown - Provide Detail.
Adjustment to Finished Grade Required - The OWNER will need to have utility facilities adjusted to match the finished grade of the project plan. Details are provided on Attachment 5A.
Relocation, Reconstruction, Rearrangement, and/or New Installation Required - Conflict(s) are anticipated between the project plan and the OWNER's existing utility facilities. Installation of new utility facilities may also be required. Details are provided on Attachment 5R.
Discontinuing in Place and/or Removal of Existing Utility Facilities Required - The OWNER will need to have existing utility facilities discontinued in place and/or removed. Details are provided on Attachment 5D.
Protection of Existing Utility Facilities Required - The OWNER's existing utility facilities are not in direct conflict with the project plan, but the utility facilities may or will require protection during highway construction or during the utility work of another utility owner(s). Details are provided on Attachment 5P.
Temporary Utility Facilities Required - The installation of temporary utility facilities will be required by the OWNER. Details are provided on Attachment 5T.
Not Applicable - No utility work is required by the OWNER due to the project plan.
Yes - The OWNER's utility work is dependent on or affected by shared utility space.
Yes - The OWNER is the provider where shared utility space exists. Details of the coordination with the participant utility owner(s) are provided on Attachment 7PR.
Yes - The OWNER are participants where shared utility space exists. Details of the coordination with the providing utility owner(s) are provided on Attachment 7PT.
Yes - The OWNER are a combination of provider and participant where shared utility space exists. Details of the coordination with the other utility owner(s) are provided on Attachments 7PR and 7PT.
No - The OWNER's utility work is not dependent on or affected by shared utility space.
Not Applicable - No utility work is required by the OWNER due to the project plan.
Yes - Real estate parcels are required for the OWNER to perform the utility work. Details about these real estate parcels are provided on Attachment 9.
No - Real estate parcels are not required for the OWNER to perform the utility work.
Not Applicable - There is no right of way project ID(s) associated with the construction project ID(s).
Not Applicable - No utility work is required by the OWNER due to the project plan.
Yes - Approvals and/or permits will need to be obtained from other entities in order for the OWNER to perform the utility work. Required approvals, included the anticipated schedule to obtain them, are provided on Attachment 8.
No - Approvals and/or permits are not required from other entities in order for the OWNER to perform the utility work.
Not Applicable - No utility work is required by the OWNER due to the project plan.
Yes - The OWNER will need new easements, fee title, and/or long-term leases to perform the utility work. Details are provided on Attachment 10.
No - All of the OWNER's utility work will be performed within the existing or proposed highway right of way, existing easements and/or existing land rights.
Not Applicable - No utility work is required by the OWNER due to the project plan.
Subsurface utility exploration (aka. Potholing) - Provide detail.
Inventory, condition reports, measurements, or survey of existing facilities - Provide detail.
Survey staking by the OWNER - Provide detail.
Law enforcement activities, such as need for rolling stops - Provide detail.
Rock blasting and removal - Provide detail.
Maximum allowable cover over the existing utility facilities has been exceeded - Provide detail.
Diversion of the OWNER's staff or the OWNER's utility contractors due to natural disaster (check only if incident is already known) - Provide detail.
Restricted site access - Provide detail.
Seasonal constraints - Provide detail.
Required outage of adjacent powerlines - Provide detail.
Compliance with provisions of environmental permits - Provide detail.
Other - Provide detail.
Not Applicable.
Yes - It is anticipated that the OWNER will be seeking reimbursement for all or some portion of the utility work and an estimate of cost is included with this worksheet.
No - The OWNER is waiving reimbursement for all or any portion of the utility work and therefore an estimate is not included with this worksheet.
Not Applicable - The OWNER's utility work is not eligible for reimbursement.
Not Applicable - No utility work is required by the OWNER due to the project plan.
Transportation Economic Assistance (TEA) Funding.
Bipartisan Infrastructure Law (BIL) - Local Programs.
Road and Bridge Assistance Funding.
Local Transportation Enhancement Program Funding.
Other - Provide Detail.
Yes - The OWNER has existing known discontinued utility facilities within the limits of the project plan. Details are provided on Attachment 3.
Q2
Q3
Q7
Q7pt2
Q8
Q9
Q10
Q11
Yes - OWNER has utility facilities within the limits of the project plan.
No - OWNER does not have utility facilities within the limits of the project plan.
Other - Provide detail.
Q1
Existing Service Work - The OWNER will remove, discontinue, modify, and/or relocate existing services. Details are provided on Attachment 6E.
New Service Work - Coordination of new service installations is required by the OWNER. Details provided on Attachment 6N.
Not Applicable - No service work is required due to the project plan.
All required attachments have been filled out to the best of the preparer's ability.
All required inclusions will be submitted with this worksheet.
Other - Provide Detail.
.dwg
.dgn
.kmz
.shp
.fgdb
Not Applicable - None of the OWNER's existing utility facilities are, or need to be, depicted in the project plan.
Yes - Grant funding is involved with the utility work.
No - Grant funding is not involved with the utility work.
Unknown - Provide detail.
Q3

## Dropdowns (hidden)
ALG |  |  | PRS | UTE |  |  |  | UTT |  |  | CRW | FCO | FMA | HCW | LIR | ITM | PMT | PRO | UWP | RFA | EPA | RBY
ALIGNMENT | MIN STA | MAX STA | PROJECT STAGE | UTILITY NAME | UTILITY FACILITY TYPE | UTILITY ENTITIES | UTILITY ABBR | UTILITY FACILITY TYPE | TUMS ABBR | PLAN ABBR | CONFLICT / REASON FOR WORK | FACILITY COMPONENT | FACILITY MATERIAL | HIGHWAY CONTRACT WORK COMPLETED | LAND INTEREST REQUIRED | ITEM | PERMIT | PROTECTION TYPE | UTILITY WORK PERFORMED | REASON FOR ACQUISITION | TEMPORARY EASEMENTS, PERMISSIONS, ACCESS | REMOVAL BY

## Anticipated Conflicts
ANTICIPATED CONFLICTS
Evaluate each potential utility conflict. This list is not exhaustive and is provided as a benefit to the Utility Facility Owner (OWNER) on behalf of the utility coordinator and project team. Data contained within this table must be imported into the required attachments. Select the appropriate response for the CONFLICT ANTICIPATED OR NEW INSTALL column: • YES → It has been determined that the utility facility is in conflict, select which attachment(s) is appropriate to resolve the utility conflict. • YES-COMBINED → It has been determined that the utility facility is in conflict, but the resolution is included in another row. This utility conflict will not be imported into any attachments for question 5. • NO → It has been determined that the utility facility is not in conflict. • NO-DISCONTINUE → It has been determined that the utility facility is not in conflict, but will be discontinued. The utility conflict will be imported into Attachment 5D. • NEW INSTALL → For a new installation. Only select this for a new row that has been added to the table. 5R is automatically checked. Fill in all blank columns as proposed information. If there are additional utility conflicts that were not identified in the table, use the Add Blank Row In Table button and fill in the required information. When complete, check the box that is below the table. NOTE: The following is provided to aid in completing the table below:
| 5A | Adjustment to Finished Grade Required - Utility facilities will require adjustment to match the finished grade of the project plan. Details are provided on Attachment 5A.
| 5D | Discontinuing in Place and/or Removal of Existing Utility Facilities Required - Existing utility facilities will be discontinued in place and/or removed as a part of the work plan. Details are provided on Attachment 5D.
| 5P | Protection of Existing Utility Facilities Required - Existing utility facilities do not conflict with the highway construction, but the utility facilities may or will require protection during highway construction or during the utility work of another utility owner(s). Details are provided on Attachment 5P.
| 5R | Relocation, Reconstruction, Rearrangement, and/or New Installation Required - Conflict(s) are anticipated between the project plan and the existing utility facilities. Installation of new utility facilities may also be required. Details are provided on Attachment 5R.
| 5T | Temporary Utility Facilities Required - Installation of temporary utility facilities is required. Details are provided on Attachment 5T
| ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | IN POTENTIAL CONFLICT WITH | CONFLICT ANTICIPATED OR NEW INSTALL | ATTACHMENTS
|  | STATION | OFFSET |  | STATION | OFFSET | [7 empty] | 5A | 5D | 5P | 5R | 5T
|  |  | DIST | LOC |  | DIST | LOC
Y | ALG | START STA | START DIST | START LOC | END STA | END DIST | END LOC | CATEGORY | SIZE | COMPONENT | MATERIAL | IN ANTICIPATED CONFLICT WITH | IN CONFLICT | A | R | D | P | T
X
END OF ANTICIPATED CONFLICTS
Check this box to confirm all anticipated conflicts have been reviewed and addressed. Once checked, question #5 will be displayed on the Utility Worksheet tab.
RETURN TO MAIN FORM

## A-3
EXISTING KNOWN DISCONTINUED UTILITY FACILITIES
Attachment 3
Any portion(s) of the Utility Facility Owner's (OWNER) existing known discontinued utility facilities that may or will conflict with the project plan must be removed. Portion(s) of existing known discontinued utility facilities to remain must be properly discontinued by plugging and/or bulkheading pipe or conduit ends, and/or filling the utility facility with flowable fill or sand.
Note that conflicting portions of existing known discontinued utility facilities must be removed to the following depths:
• | Within the roadbed, to a depth at least 2 feet below the subgrade or excavation below subgrade (EBS).
• | Outside the roadbed, to a depth at least 2 feet below the finished grade line.
• | At any location, to the extent required to avoid interfering with highway construction.
1. | Does the OWNER have existing known discontinued utility facilites that directly conflict with the highway construction and how will the conflicts be addressed? Select all that apply
Attach at least one of the following items to this worksheet to clearly provide known information about the type(s), location(s), material(s), and size(s) of the existing known discontinued utility facilities. Select all that apply.
2. | Does the OWNER's existing known discontinued utility facilities that are to be removed have any asbestos coatings and/or any other hazardous materials (including contaminated soil) associated with them? Note that any required removal or mitigation of such utility facilities is the responsibility of the OWNER. Select one of the following options.
3. | When the existing known utility facility was discontinued, did the OWNER perform any of the following? Select all that apply.
4. | Does the OWNER's existing known discontinued utility facilities have any remaining product? Note that removal or mitigation of remaining product is the responsibility of the OWNER. Select one of the following options.
END OF ATTACHMENT 3
Yes - Existing known discontinued utility facilities may or will conflict with the highway construction. The OWNER will remove the conflicting portions of the existing known discontinued utility facilities prior to highway construction.
Yes - Existing known discontinued utility facilities may or will conflict with the highway construction. The OWNER will remove the conflicting portions of the existing known discontinued utility facilities during highway construction. The following highway construction work is required to be performed by the highway contractor prior to the removal by the OWNER. Information is provided for EACH location where removal is required. Select all that apply.
Yes - Existing known discontinued utility facilities may or will conflict with the highway construction. It is requested that the conflicting portion(s) of the existing known discontinued utility facilities be removed by the highway contractor during highway construction. The OWNER understands that the cost for removal of non-compensable utility facilities is the responsibility of the OWNER.
No - Existing known discontinued utility facilities are within the limits of the project plan, however they do not conflict with the highway construction. Non-conflicting portions of the existing known discontinued utility facilities will remain in place.
Rough grading complete. Location(s):
Any excavation above the existing discontinued utility facilites, that are to be removed, has been completed. Location(s):
Other - Provide detail here:
Not Applicable - No highway construction is required to be performed by the highway contractor.
A marked up copy of the project plan
A narrative or description of the existing known discontinued utility facilities, using project stationing - Provide detail.
Other - Provide detail
Existing pipe or conduit ends were plugged or bulkheaded and the utility facility was filled with flowable fill or sand.
Existing pipe connections were bulkheaded, the top of manholes or vaults were removed to below grade and the manhole or vaults were filled with flowable fill or sand.
Unknown - No information is available on how the utility facility was discontinued.
Other - Provide detail.
Yes - Any remaining product will need to be removed from the existing known discontinued utility facilities. Provide detail of the plan for removal and/or mitigation of remaining product here.
No - The existing known discontinued utility facilities have no remaining product.
Unknown - No information is available on whether or not the existing known discontinued utility facility has remaining product. Details on the plan for identifying and mitigating any remaining product associated with the existing known discontinued utility facilities is provided here.
Yes - All or a portion of the existing known discontinued utility facilities that conflict with the project plan have asbestos coatings and/or hazardous materials associated with them. Detail of the plan for removal and/or mitigation of those existing known discontinued utility facilities is provided here.
No - There are no asbestos coatings and/or any other hazardous materials associated with the existing known discontinued utility facilities to be removed.
Unknown at this time. Details on the plan for identifying and mitigating any asbestos coatings and/or any other hazardous materials associated with the existing known discontinued utility facilities is provided here.
Q2
Q4
Sketches and XYZ data, exhibits or work requests
An electronic design file
RETURN TO MAIN FORM
Not Applicable - The existing known discontinued utility facilities did not transport or contain product.
.dwg
.dgn
.kmz
.shp
.fgdb

## A-5A
ADJUSTMENT TO FINISHED GRADE REQUIRED
Attachment 5A
Adjustment of utility facilities are required to match the finished grade of the project plan.
• Fill in the following table for utility facilities to be adjusted.
• All utility facilities requiring adjustment must be identified in the Anticipated Conflicts table, and must be copied over.
• Show adjustments on the marked up copy of the project plan or other approved format.
• Answer all questions displayed after the table.
NOTE: If portions of the utility work is independent of utility work by another utility owner(s), list the anticipated start date(s) and location for those portions of the OWNER's utility work. If the OWNER's utility work consists of multiple utility facilities or locations, make sure to list the anticipated start date(s) and location(s) associated with each utility facility or location. Make sure to distinguish between total duration and 'per location' duration.
ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | CONFLICT / REASON FOR WORK | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | NARRATIVE
| STATION | OFFSET |  | STATION | OFFSET | [6 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
|  | DIST | LOC |  | DIST | LOC | [5 empty] | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
1. Who will be completing the OWNER's utility work?
2. Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
3. Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
4. What format will adjustments be shown in addition to the above table?
END OF ATTACHMENT 5A
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
RETURN TO MAIN FORM
All utility work completed by the OWNER.
All utility work included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Utility work completed by both the OWNER and included in the highway plan. Funding of the utility work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the utility work.
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
Roadway, lane, and/or shoulder closure(s) will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Yes - Pedestrian and/or bicycle facilities will be impacted.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Asphalt.
Concrete.
Temporary board.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Group Box 45
.dwg
.dgn
.kmz
.shp
.fgdb

## A-5D
DISCONTINUING IN PLACE AND/OR REMOVING OF EXISTING UTILITY FACILITIES REQUIRED
Attachment 5D
The Utility Facility Owner's (OWNER) has existing utility facilities to be discontinued in place and/or removed due to conflicts with the project plan. Properly discontinue any existing utility facilities, including services, that will remain by plugging and/or bulkheading pipe or conduit ends, and/or filling the facility with flowable fill or sand.
• Fill in the following table for existing utility facilities to be discontinued and/or removed, including the COORDINATION OF A SHARED UTILITY SPACE column.
• All utility facilities discontinued in place and/or removed must be identified in the Anticipated Conflicts table, and must be copied over.
• Show discontinuances and/or removals on the marked up copy of the project plan or other approved format.
• Answer all questions displayed after the table.
Note that conflicting portions of utility facilities to be discontinued must be removed to the following depths:
• Within the roadbed, to a depth at least 2 feet below the subgrade or excavation below subgrade (EBS) as shown on the project plans.
• Outside the roadbed, to a depth at least 2 feet below the finished grade.
• At any location, to the extent required to avoid interfering with the highway construction.
NOTE: If portions of the OWNER's utility work is independent of utility work by another utility owner(s), list the anticipated start date(s) and location for those portions of the OWNER's utility work. If the OWNER's utility work consists of multiple utility facilities or locations, make sure to list the anticipated start date(s) and location(s) associated with each utility facility or location. Make sure to distinguish between total duration and 'per location' duration.
ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | CONFLICT / REASON FOR WORK | UTILITY WORK PERFORMED | CONFLICTING PORTION(S) REMOVED BY | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | COORDINATION OF A SHARED UTILITY SPACE | PROVIDER OR PARTICIPANT | NARRATIVE
| STATION | OFFSET |  | STATION | OFFSET | [8 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
|  | DIST | LOC |  | DIST | LOC | [7 empty] | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
1. Does the OWNER's existing appurtenances, underground utility facilities, and/or utility facilities attached to structures to be discontinued in place and/or removed have any asbestos coatings and/or any other hazardous materials (including contaminated soil) associated with them?
Note that any required removal or mitigation of such facilities is the responsibility of the facility OWNER. Select one of the following options.
2. Does the OWNER's existing appurtenances, underground utility facilities, and/or utility facilities attached to structures to be discontinued in place have any remaining product?
Note that removal or mitigation of remaining product is the responsibility of the facility OWNER. Select one of the following options.
3. Who will be completing the OWNER's utility work?
4. Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
5. Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
6. What format will discontinuances and/or removals be shown in addition to the above table?
END OF ATTACHMENT 5D
Yes - All or a portion of the existing utility facilities that conflict with the project plan have asbestos coatings and/or hazardous materials associated with them. Detail of the plan for removal and/or mitigation of those existing utility facilities is provided here:
No - There are no asbestos coatings and/or any other hazardous materials associated with the existing utility facilities to be discontinued and/or removed.
Unknown at this time. Details on the plan for identifying and mitigating any asbestos coatings and/or any other hazardous materials associated with the existing utility facilities is provided here:
Yes - Any remaining product will need to be removed from the existing utility facilities to be discontinued in place. Provide detail of the plan for removal and/or mitigation of remaining product here:
No - The existing utility facilities to be discontinued in place have no remaining product.
Not Applicable - The existing utility facilities to be discontinued in place did not transport or contain product.
Group Box 8
RETURN TO MAIN FORM
Unknown at this time. Detail on the plan for identifying and mitigating any remaining product associated with the existing utility facilities is provided here:
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
All utility work completed by the OWNER.
All utility work included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Utility work completed by both the OWNER and included in the highway plan. Funding of the utility work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the utility work.
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder closure(s) will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Yes - Pedestrian and/or bicycle facilities will be impacted.
Detour pedestrian access to other side of road.
Re-route pedestrian access, same side of road.
Close pedestrian access without detour.
Provide a temporary sidewalk for pedestrian access.
Other - Provide detail here:
Not Applicable - Our work is included in the project plans.
Asphalt
Concrete
Temporary board
Other - Provide detail here:
Not Applicable - Our work is included in the project plans.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Asphalt.
Concrete.
Temporary board.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Group Box 45
.dwg
.dgn
.kmz
.shp
.fgdb
Group Box 61

## A-5P
PROTECTION OF EXISTING UTILITY FACILITIES REQUIRED
Attachment 5P
The Utility Facility Owner's (OWNER) has utility facilities that require protection as conflicts exist with the project plan.
• Fill in the following table for the protection of utility facilities, including the COORDINATION OF A SHARED UTILITY SPACE column.
• All utility facilities to be protected must be identified in the Anticipated Conflicts table, and must be copied over.
• Show protection of the utility facilities on a marked up copy of the project plan or other approved format.
• Answer all questions displayed after the table.
NOTE: If portions of the OWNER's utility work is independent of utility work by another utility owner(s), list the anticipated start date(s) and location for those portions of the OWNER's utility work. If the OWNER's utility work consists of multiple utility facilities or locations, make sure to list the anticipated start date(s) and location(s) associated with each utility facility or location. Make sure to distinguish between total duration and 'per location' duration.
ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | CONFLICT / REASON FOR WORK | UTILITY WORK PERFORMED (PROTECTION TYPE) | ANTICIPATED START DATE |  | WORKING DAYS TO PERFORM | SPECS FOR CONTRACT DOCS | COORDINATION OF A SHARED UTILITY SPACE | PROVIDER OR PARTICIPANT | NARRATIVE
| STATION | OFFSET |  | STATION | OFFSET | [7 empty] | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
|  | DIST | LOC |  | DIST | LOC
1. Who will be completing the OWNER's utility work?
2. Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
3. Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
4. What format will protections be shown in addition to the above table?
END OF ATTACHMENT 5P
RETURN TO MAIN FORM
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
All utility work completed by the OWNER.
All utility work included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Utility work completed by both the OWNER and included in the highway plan. Funding of the utility work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the utility work.
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Yes - Pedestrian and/or bicycle facilities will be impacted.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Asphalt.
Concrete.
Temporary board.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Group Box 45
.dwg
.dgn
.kmz
.shp
.fgdb

## A-5R
RELOCATION, RECONSTRUCTION, REARRANGEMENT AND/OR NEW UTILITY FACILITY INSTALLATION REQUIRED
Attachment 5R
The Utility Facility Owner's (OWNER) has utility facilities to be relocated, reconstructed, rearranged, and/or the installation of new utility facilities.
• Fill in the following table for the relocation, reconstruction, rearrangement, and/or the installation of new utility facilities, including the COORDINATION OF A SHARED UTILITY SPACE column. • All utility facilities to be relocated, reconstructed, rearranged, and/or the installation of new utility facilities must be identified in the Anticipated Conflicts table, and must be copied over. • Show the relocation, reconstruction, rearrangement, and/or the installation of new utility facilities on the marked up copy of the project plan or other approved format.
• Answer all questions displayed after the table.
NOTE: If portions of the OWNER's utility work is independent of utility work by another utility owner(s), list the anticipated start date(s) and location for those portions of the OWNER's utility work. If the OWNER's utility work consists of multiple utility facilities or locations, make sure to list the anticipated start date(s) and location(s) associated with each utility facility or location. Make sure to distinguish between total duration and 'per location' duration.
ALIGNMENT | EXISTING | [5 empty] | PROPOSED | [5 empty] | OH/UG |  | FACILITY SIZE |  | FACILITY COMPONENT |  | FACILITY MATERIAL |  | CONFLICT / REASON FOR WORK | UTILITY WORK PERFORMED | DISCONTINUED OR REMOVED AT TIME OF RELOCATION OR RECONSTRUCTION | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | COORDINATION OF A SHARED UTILITY SPACE | PROVIDER OR PARTICIPANT | NARRATIVE
| START |  |  | END |  |  | START |  |  | END | [13 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
| STATION | OFFSET |  | STATION | OFFSET |  | STATION | OFFSET |  | STATION | OFFSET |  | EX | PR | EX | PR | EX | PR | EX | PR |  |  |  | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
|  | DIST | LOC |  | DIST | LOC |  | DIST | LOC |  | DIST | LOC
1. Who will be completing the utility work?
2. Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
3. Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
4. What format will relocations, reconstructions, rearrangements, and/or new installations be shown in addition to the above table?
END OF ATTACHMENT 5R
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Yes - Pedestrian and/or bicycle facilities will be impacted.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Asphalt.
Concrete.
Temporary board.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
RETURN TO MAIN FORM
All utility work completed by the OWNER.
All utility work included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Utility work completed by both the OWNER and included in the highway plan. Funding of the utility work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the utility work.
Group Box 45
.dwg
.dgn
.kmz
.shp
.fgdb

## A-5T
TEMPORARY UTILITY FACILITIES REQUIRED
Attachment 5T
The Utility Facility Owner (OWNER) has installation and/or removal of temporary facilities, including temporary services.
• Fill in the following table for the installation and/or removal of temporary utility facilities, including the COORDINATION OF A SHARED UTILITY SPACE column. • All temporary utility facilities to be installed and/or removed must be identified in the Anticipated Conflicts table, and must be copied over.
• Show temporary utility facilities on the marked up copy of the project plan or other approved format.
• Answer all questions displayed after the table.
NOTE: If portions of the OWNER's utility work is independent of utility work by another utility owner(s), list the anticipated start date(s) and location for those portions of the OWNER's utility work. If the OWNER's utility work consists of multiple utility facilities or locations, make sure to list the anticipated start date(s) and location(s) associated with each utility facility or location. Make sure to distinguish between total duration and 'per location' duration.
ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | CONFLICT / REASON FOR WORK | INSTALL / REMOVE | UTILITY WORK PERFORMED | TEMPORARY EASEMENTS, PERMISSIONS, ACCESS | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | COORDINATION OF A SHARED UTILITY SPACE | PROVIDER OR PARTICIPANT | NARRATIVE
| STATION | OFFSET |  | STATION | OFFSET | [9 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
|  | DIST | LOC |  | DIST | LOC | [8 empty] | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
1. Could any of the following affect the OWNER's utility work or the utility work of another utility owner(s)? Select all that apply.
2. Who will be completing the OWNER's utility work?
3. Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
4. Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
5. What format will temporary utility facilities be shown in addition to the above table?
END OF ATTACHMENT 5T
RETURN TO MAIN FORM
Installation or removal of temporary lighting on behalf of a municipality.
Installation or removal of a temporary service to a lighting or signal cabinet (do not include existing services to be removed).
Other - Provide detail.
Not Applicable - The above does not apply or impact the utility work.
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder closure(s) will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Yes - Pedestrian and/or bicycle facilities will be impacted.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Asphalt.
Concrete.
Temporary board.
Other - Provide detail below.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
A marked up copy of the project plan.
Sketches and XYZ data, exhibits or work requests.
An electronic design file.
All utility work completed by the OWNER.
All utility work included in the highway plan. Funding of the utility work will require coordination with the project sponsor.
Utility work completed by both the OWNER and included in the highway plan. Funding of the utility work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the utility work.
Group Box 45
.dwg
.dgn
.kmz
.shp
.fgdb

## A-6E
EXISTING SERVICE WORK REQUIRED
Attachment 6E
The Utility Facility Owner (OWNER) has removals, discontinuances, modifications, and/or relocations of existing services. • Answer the displayed questions below for the existing service work required.
1. | Who will be completing the service work?
2. | What type of service work is required by the OWNER? Select all that apply.
3. | Has the OWNER included the service work in Attachment 5R?
Fill in the following information. Select all that apply.
4. | Will the OWNER require a property owner, associated with the service(s) work, to incur any costs related to the service work?
Identify the property, by address or parcel number, and describe the anticipated arrangements that will be made with the property owner(s) for costs associated with the service work.
5. | Does the OWNER have any service-related facilities that have not been previously addressed and are impacted by the proposed revisions to pedestrian (including curb ramps) and/or bicycle facilities? Select all that apply.
6. | When will the OWNER perform removals, discontinuances, modifications, and/or relocations? Select all that apply.
7. | What is the method of construction for the OWNER's service work? Select all that apply.
8. | Will the OWNER change any existing overhead service(s) to underground service(s) or vice-versa?
9. | Is it anticipated that the OWNER's utility work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
10. | Is it anticipated that the OWNER's utility work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet. Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the utility work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the utility work? Select all that apply.
END OF ATTACHMENT 6E
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Other - Provide detail here.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the utility work.
Asphalt.
Concrete.
Temporary board.
Not Applicable - The utility work is included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Other - Provide detail here.
Manholes or vaults.
Valves.
Cleanouts.
Curb stops.
Other - Provide detail here.
Not Applicable.
Removal of existing services.
Discontinuance of existing services.
Modification of existing services.
Relocation of existing services.
Other - Provide detail here.
Prior to Construction.
During Construction.
Anticipated start date(s) and duration(s) below.
Project stage(s) and duration(s) below.
Project milestone(s) and duration(s) (examples - upon completion of grading, once road is closed, etc) below.
Open trench.
Bore.
Other - Provide detail here.
Yes.
No.
Q3
Yes - Provide detail here.
No - Services will not be changed from overhead to underground or vice-versa.
Q8
Yes - The property owner will incur costs related to the service work.
No - The property owner will not incur costs related to the service work.
RETURN TO MAIN FORM
All service work completed by the OWNER.
All service work included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Service work completed by both the OWNER and included in the highway plan. Funding of this utility work will require coordination with the project sponsor. Provide additional information below:
Q1
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder closure(s) will not be required.
Not Applicable - There are no roadways in the vicinity of the utility work.
Q10
Yes - Pedestrian and/or bicycle facilities will be impacted.
Prior to and during Construction - Provide detail here.
Q3

## A-6N
NEW SERVICE WORK REQUIRED
Attachment 6N
The Utility Facility Owner (OWNER) needs to coordinate the installation of a new service(s). Include any service-related utility facilities that have not been previously addressed and are impacted by the project plan.
• Fill in the following table and answer the questions below for the new service work required.
• Billing is not considered coordinating with other utility owners.
• Answer all questions displayed after the table.
ALIGNMENT | PROPOSED | [5 empty] | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | COORDINATION OF SHARED UTILITY SPACE | PROVIDER OR PARTICIPANT | IMPORTED? | NARRATIVE
| START |  |  | END | [6 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
| STATION | OFFSET |  | STATION | OFFSET | [5 empty] | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
|  | DIST | LOC |  | DIST | LOC
1. Will the OWNER's service work include any of the following items or substantially similar items? Do not include utility work previously identified in Attachment 5R or Attachment 7PR or 7PT. Select all that apply.
2. Will any of the OWNER's service work identified in the above question require coordination with any of the following? Select all that apply.
3. Who will be completing the OWNER's service work?
4. Is it anticipated that the OWNER's service work will require any roadway, lane, and/or shoulder closure(s)? Preference for closures will be given to those OWNERs that indicate a need in this worksheet. Select all that apply.
5. Is it anticipated that the OWNER's service work will impact pedestrian (including curb ramps) and/or bicycle facilities? Preference for closures will be given to those OWNERs that indicate a need for a closure in this worksheet.
Select one of the following options.
How will the OWNER accommodate pedestrian (including curb ramps) and/or bicycle facilities impacted by the service work? Select all that apply.
How will the OWNER restore pedestrian and/or bicycle facilities impacted by the service work? Select all that apply.
END OF ATTACHMENT 6N
Detour pedestrian access to other side of road.
Re-route pedestrian access, same side of road.
Close pedestrian access without detour.
Provide a temporary sidewalk for pedestrian access.
Not Applicable - Our work is included in the project plans.
Other - Provide detail here:
Asphalt
Concrete
Temporary board
Not Applicable - Our work is included in the project plans.
Other - Provide detail here:
Service to a new lighting or traffic signal cabinet that requires installation of a new overhead electric line and multiple poles or that requires a different phase power.
Disconnection of an existing service to a lighting or traffic signal cabinet that results in the removal of an overhead electric line and multiple poles.
The extension of a sewer or water line to provide a new service.
New services, including connections for sewer, water, communications, or electrical, to a new or relocated utility vault or structure.
Other - Provide detail here.
Not Applicable.
The project sponsor(s).
Other utility owner(s)
Adjacent property owner(s).
Other - Provide detail here.
Not Applicable.
Yes - Pedestrian and/or bicycle facilities will be impacted.
Detour pedestrian and/or bicycle facilities to other side of roadway.
Re-route pedestrian and/or bicycle facilities on the same side of roadway.
Close pedestrian and/or bicycle facilities without a detour.
Provide temporary pedestrian and/or bicycle facilities.
Not Applicable - The service work is included in the highway plan. Funding of this service work will require coordination with the project sponsor.
Other - Provide detail here.
No - Pedestrian and/or bicycle facilities will not be impacted.
Not Applicable - There are no pedestrian and/or bicycle facilities in the vicinity of the service work.
Asphalt.
Concrete.
Temporary board.
Not Applicable - The service work is included in the highway plan. Funding of this service work will require coordination with the project sponsor.
Other - Provide detail here.
RETURN TO MAIN FORM
Yes - Roadway closure(s) will be required.
Yes - Lane closure(s) will be required.
Yes - Shoulder closure(s) will be required.
No - Roadway, lane, and/or shoulder closure(s) will not be required.
Not Applicable - There are no roadways in the vicinity of the service work.
All service work completed by the OWNER.
All service work included in the highway plan. Funding of this utility work will require coordination with the project sponsor.
Service work completed by both the OWNER and included in the highway plan. Funding of this service work will require coordination with the project sponsor. In the NARRATIVE column, include "OWNER" or "In Highway Plan" for each identified utility conflict above to indicate who is performing the service work.
Group Box 55

## A-7PR
PROVIDER COORDINATION IN SHARED UTILITY SPACE
Attachment 7PR
The Utility Facility Owner's (OWNER) proposed utility work is dependent on or affected by the utility work of another utility owner(s) in a shared utility space. Dependent means that the shared utility space is occupied by, or the location is shared with utility facilities of another utility owner(s). Provide details of coordination with other utility owner(s) below and/or on attached sheets. In the CONTACT INFO column, include the contact information of the person/people that were coordinated with at the other utility owner(s). In the NARRATIVE column, include a brief description of the utility work by the other utility owner(s) and how it impacts the OWNER and the OWNER's schedule.
• Copy utility facilities from the attachment(s) for Question 5. • Fill in the rest of the table as the provider in the shared utility space.
(CALENDAR DAYS)
| COORDINATING ENTITY | UTILITY TYPE | COORDINATION BETWEEN PROVIDER AND PARTICIPANT COMPLETED | UTILITY WORK PERFORMED | UTILITY WORK PERFORMED BY | CONCURRENT WORK POSSIBLE | ORDER OF CONSTRUCTION | ALIGNMENT | EXISTING | [5 empty] | PROPOSED | [5 empty] | OH/UG |  | FACILITY SIZE |  | FACILITY COMPONENT |  | FACILITY MATERIAL |  | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | STARTING WORKING DAY | UPPER BOUND WD | LOWER BOUND WD | NOTES FOR UCM | CONTACT INFO | NARRATIVE | time axis 0 to 1900-07-17
[9 empty] | START |  |  | END |  |  | START |  |  | END | [10 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
[9 empty] | STATION | OFFSET |  | STATION | OFFSET |  | STATION | OFFSET |  | STATION | OFFSET |  | EX | PR | EX | PR | EX | PR | EX | PR | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
[10 empty] | DIST | LOC |  | DIST | LOC |  | DIST | LOC |  | DIST | LOC
[34 empty] | 0 | 0
X
END OF ATTACHMENT 7PR
RETURN TO MAIN FORM

## A-7PT
PARTICIPANT JOINT USE COORDINATION
Attachment 7PT
The Utility Facility Owner's (OWNER) proposed utility work is dependent on or affected by the utility work of another utility owner(s) in a shared utility space. Dependent means that the shared utility space is occupied by, or the location is shared with utility facilities of another utility owner(s). Provide details of coordination with other utility owner(s) below and/or on attached sheets. In the CONTACT INFO column, include the contact information of the person/people that were coordinated with at the other utility owner(s). In the NARRATIVE column, include a brief description of the utility work by the other utility owner(s) and how it impacts the OWNER and the OWNER's schedule.
• Copy the utility facilities from the attachment(s) for Question 5. • Fill in the rest of the table as the participant in the shared utility space.
COORDINATING ENTITY | COORDINATION BETWEEN PROVIDER AND PARTICIPANT COMPLETED | ALIGNMENT | START |  |  | END |  |  | OH/UG | FACILITY SIZE | FACILITY COMPONENT | FACILITY MATERIAL | UTILITY WORK PERFORMED | ANTICIPATED START DATE |  |  | WORKING DAYS TO PERFORM | UTILITY WORK PERFORMED BY | NOTES FOR UCM | CONTACT INFO | NARRATIVE
|  |  | STATION | OFFSET |  | STATION | OFFSET | [6 empty] | PRIOR TO CONST. | DURING CONSTRUCTION
|  |  |  | DIST | LOC |  | DIST | LOC | [5 empty] | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
END OF ATTACHMENT 7PT
RETURN TO MAIN FORM

## A-8
APPROVALS REQUIRED AND SCHEDULE TO OBTAIN APPROVALS
Attachment 8
Work plan approval and/or start work notice will be issued at least 30 calendar days prior to the Utility Facility Owner's (OWNER) anticipated start date. Identify and select all other approvals required for the OWNER's utility work and provide information about the schedule to obtain those approvals.
• Fill in the following table of permits.
• The dates below were drawn from the CALENDAR DATE, within the ANTICIPATED START DATE, on an attachment(s) from Question 5. These dates may be useful in completing the table below.
5A - NA
5D - NA
5R - NA
5T - NA
• The APPROVAL PRECEDES, within the ANTICIPATED SCHEDULE, is used when the APPROVAL DATE is unknown, however it is anticipated that the approval will precede the OWNER's start date shown above.
• Any requests to change the OWNER's "Anticipated Start Date" on the attachment(s) for Question 5, due to a delay in an approval for any permit listed below, must be coordinated with the project sponsor.
PERMIT | NAME OF APPROVING AUTHORITY | ANTICIPATED SCHEDULE |  |  | NARRATIVE
|  | APPROVAL PRECEDES | SUBMITTAL DATE | APPROVAL DATE
END OF ATTACHMENT 8
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
RETURN TO MAIN FORM

## A-9
REAL ESTATE PARCELS REQUIRED
Attachment 9
Real estate parcels need to be acquired to enable the performance of the Utility Facility Owner's (OWNER) utility work. Provide details about the parcels listed below and/or on attached sheets. The following items are required, whether performed by the OWNER or by others, to enable the utility work prior to or during highway construction:
• Within the ITEM drop-down list, include description in the NARRATIVE column if "Other" is selected.
• Enter either CALENDAR DATE or HIGHWAY CONTRACT WORK COMPLETED, not both.
NOTE: The following is provided to aid in completing the table below as the dropdown list under ITEM requires scrolling in order to view all options.
ITEMS: | DESCRIPTIONS:
Real Estate Related Items
Removal of structures | Existing buildings, foundations, sheds or other structures
Removal of concrete/stone | Existing concrete or stone items, such as walls, columns, fencing, or retaining walls
Removal of crops | Existing food crops, such as grains, fruits, or vegetables
Removal of landscape features | Significant landscape features, such as decorative boulders, large berms, gardens, flower beds, and fountains
Removal of private utilities | Private utilities, such as septic tanks and fields, removal of well heads, and/or abandonment of wells
Removal/adjustment of drainage facilities | Field tile or other drainage facilities
Removal of poles/posts | Signs, flagpoles, lighting
Removal of trees | Tree removal and/or grubbing of stumps
Highway Construction Related Items
Grading | Grading, including removal, filling, and excavation
Removal of pavements | Existing private roadways, driveways, or parking improvements
Installation of structures | New structures, such as bridges, box culverts, sign bridges, or retaining walls
Installation of drainage facilities | New drainage facilities, such as the extension of a box culvert, a creek realignment, a temporary bypass channel, and installation of storm sewer
Installation of pavement | New roadway improvements, such as pavement, curb and gutter, and sidewalks
Installation of electrical and ancillary items | New roadway improvements, such as lighting, signals, ITS, and guardrail
Other Related Items
Other | Include real estate and highway construction related items that are not in the dropdown list. Provide description in NARRATIVE column.
RIGHT OF WAY PLAT OR EXHIBIT ID | PLAT / EXHIBIT APPROVAL OR LATEST REVISION DATE | PARCEL NUMBER | REMOVAL OR INSTALLATION |  |  |  | NARRATIVE
|  |  | ITEM | ANTICIPATED START DATE
|  |  |  | PRIOR TO CONST. | DURING CONSTRUCTION
|  |  |  | CALENDAR DATE | PROJECT STAGE | HIGHWAY CONTRACT WORK COMPLETED
END OF ATTACHMENT 9
RETURN TO MAIN FORM

## A-10
EASEMENTS, FEE TITLE, AND/OR LONG-TERM LEASES
Attachment 10
Identify the easements, fee title, and/or long-term leases the Utility Facility Owner (OWNER) needs to obtain to complete the utility work. Describe the location where the land interests and/or rights are needed, using reference to plat parcel numbers, project stationing, or addresses.
• Fill in the following table of easements, fee title, and/or long-term leases to the extent known at time of worksheet submittal.
LAND INTEREST REQUIRED | LOCATION | [6 empty] | APPROXIMATE WIDTH | ANTICIPATED ACQUISITION DATE | REASON FOR ACQUISITION | NARRATIVE
| BY PARCEL NUMBER | BY STATIONING |  |  |  |  | BY ADDRESS
|  | ACQUISITION ALIGNMENT | APPROXIMATE START |  | APPROXIMATE END
|  |  | STATION | LOC | STATION | LOC
END OF ATTACHMENT 10
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
The anticipated schedule is as follows:
The approval date is anticipated to precede the start date for our work stated in this worksheet. Our anticipated start date is not affected unless we coordinate with the project sponsor to revise our anticipated start date.
Group Box 5
RETURN TO MAIN FORM