## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170808 | 20170808001 | 1 | Earthwork Sheets | Can you please post the Excel Earthwork Sheets for the project? | The worksheets can be found at files to ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808001 | Scott Lawry | 1 | 2017-07-11 07:28 | 2017-07-13 11:48
20170808 | 20170808001 | 1 | Storm Sewer | The storm sewer structures listed in the miscellaneous quantity sheets for the project contain limited information on rim, invert or depth data. Will this information be provided and added to the existing tables? | For project 1003-10-76 the rim/invert/depth information is contained in the Storm Sewer section under STORM SEWER STRUCTURE DATA TABLE. For project 1003-10-81 elevation information is contained on the storm sewer profile sheets. However, we agree the rim/invert/depth information should be shown in a table format. The miscellaneous quantity sheets will be updated with the rim/invert/depth information. This will be corrected via addendum. | Scott Lawry | 2 | 2017-07-12 10:46 | 2017-07-13 11:12
20170808 | 20170808001 | 1 | Design Model Data | Could the Department provide the information for the Design Model Data on the HCCI site,as shown in the special provisions? | Several files are made available at the link below for IDs 1003-10-76 and 1003-10-81. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808001 | Scott Lawry | 3 | 2017-07-14 15:26 | 2017-07-17 18:20
20170808 | 20170808001 | 1 | Weigh-In-Motion System - SB ATR lanes | Section B.4.1 paragraph 4 of the proposal reads that piezo quartz sensors for the Southbound lanes are not a part of the WIM system. Please confirm this and if this is the case under what line should the sensors be provided? | The intention of bid item â€œSPV.0105.480 Weigh-In-Motion Systemâ€ is to include the installation of WIM quartz sensors in all six lanes. The function of the sensors installed in the southbound IH 39/90 lanes are intended to be utilized for Automatic Traffic Recorder (ATR) data collection and not for Division of State Patrol weight enforcement. | Scott Lawry | 4 | 2017-07-24 07:50 | 2017-07-24 16:52
20170808 | 20170808001 | 1 | Weigh-In-Motion System - ATR lanes layout | Sheet 251 of the plans labeled Installation of Weigh-In-Motion ATR shows a layout of left WIM sensor, loop, right WIM sensor. Is it acceptable to install these as loop, right sensor, left sensor if this is a providers standard layout and to be consistent with the rest of the SWEF WIM system? | Yes, this alternative layout is acceptable. | Scott Lawry | 5 | 2017-07-24 07:57 | 2017-07-24 16:52
20170808 | 20170808001 | 1 | Static Scale Scoreboards | Please confirm that the existing static scale scoreboards should be removed to ensure compatibility with the new static scale electronics. Sheet 250 of the plans (Weigh-In-Motion System Sheet 5) appears to read these are to remain, while the proposal reads they are to be removed. | The plan intent is the two existing overhead mounted Variable Message Signs (VMS) over the scale lane and bypass lane to remain and be compatible with the proposed system, but the four existing pole mounted weight scoreboards to be replaced with the â€œSPV.0105.480 Weigh-In-Motion Systemâ€ item. A plan addendum is being prepared to address this inconsistency. | Scott Lawry | 6 | 2017-07-24 08:46 | 2017-07-24 16:53
20170808 | 20170808001 | 1 | Weigh-In-Motion System SWEF ramp WIM | Can the lane weigh station entrance ramp be tapered to 14' from station 465+75 to 467+75 to prevent the need of additional sensors to ensure complete lane coverage? | Tapering the entrance ramp lane width (465+75 to 467+75) from 15â€™ to 14â€™ is not acceptable. | Scott Lawry | 7 | 2017-07-24 08:54 | 2017-07-24 16:54
20170808 | 20170808001 | 1 | Weigh-In-Motion System - Bypass VMS control | Would Patrol every like the potential capability for the system to automatically set the SWEF bypass lane VMS message? An example would be to sort a violator to the parking lot. If so should all vendors provide a loop at the bypass VMS near the static scale? | The department does not see a big need for it, Please submit your bid based on what is shown in the proposal and plans. | Scott Lawry | 8 | 2017-07-24 09:06 | 2017-07-27 11:06
20170808 | 20170808001 | 1 | Weigh-In-Motion - Mainline LPR Camera Pole | Please confirm that locating a camera pole 14' off of the driving lane striping, behind the guardrail at station 419+25 is acceptable. | The camera pole will need to be located a minimum of 17â€™ off of the driving lane striping, behind the guardrail at station 419+25. The proposed shoulder width is to be 10â€™ to the face of guardrail while the proposed working width of MGS Guardrail Type 3 for a typical installation is 5â€™ (measured from the front of rail according to FDM 11-45 Attachment 2.22). | Scott Lawry | 9 | 2017-07-24 09:15 | 2017-07-24 17:06
20170808 | 20170808001 | 1 | Weigh-In-Motion Continous Operating Test | Based on the initial schedule of operations could the ramp and static WIM systems be complete earlier in the project and then do the continuous operating test with the warranty starting for these systems if successfully completed? Could a second continuous operating test be done for the mainline system when the final traffic pattern is established at the end of the project? The purpose of this would be to allow officers to start using and receive the benefits of the new ramp WIM and static system earlier in the project instead of having to wait until the end. | No, a second Continuous Operating Test (COT) would not be allowed. It is preferred to have one COT performed on the WIM system as a whole, not partially. It is preferred to have one warranty start date rather than multiple dates and potential confusion. Nothing would preclude the contractor from performing their own unofficial COT on the ramp and static WIM systems. | Scott Lawry | 10 | 2017-07-24 19:50 | 2017-07-26 12:55
20170808 | 20170808001 | 1 | Concrete Plant Site on the ROW | 1. Please confirm that a batch plant can be located within the Northwest gore and the Southeast gore of the CTH S Interchange Ramps? 2. Please confirm that a batch plant can be located within the Southwest gore and the Southeast gore of the Avalon Interchange Ramps? | All areas outside the excavation limits must be approved by the engineer as noted in the specifications below. Please see Standard Specifications 104.8 and 107.9. http://wisconsindot.gov/rdwy/stndspec/ss-01-04.pdf#ss104 http://wisconsindot.gov/rdwy/stndspec/ss-01-07.pdf#ss107 | Scott Lawry | 11 | 2017-07-26 16:33 | 2017-07-27 14:35
20170808 | 20170808001 | 1 | Mining for Concrete Aggregates on the ROW | 1. Please confirm that a contractor can mine/excavate below the new roadway within the ROW from STA 310+00 to STA 330+00 as long as Embankment material replaces it conforming to the specifications? 2. Please confirm that the contractor can then crush and wash that mined material on the ROW within that same area? | All areas outside the excavation limits must be approved by the engineer as noted in the specifications below. Please see Standard Specifications 104.8 and 107.9. http://wisconsindot.gov/rdwy/stndspec/ss-01-04.pdf#ss104 http://wisconsindot.gov/rdwy/stndspec/ss-01-07.pdf#ss107 | Scott Lawry | 12 | 2017-07-26 16:35 | 2017-07-27 14:36
20170808 | 20170808001 | 1 | Pipe Boring & Jacking | 1) Please confirm if an oversized steel casing pipe is required for all of the storm sewer and culverts installed by boring and jacking, or if direct-jack installation of the RCP will be allowed. The special provision is confusing and make references to both types of installation methods. 2) If steel casing pipe is required, will you provide an E-80 loading chart specifying the minimum wall thickness requirements for applicable sizes of steel casing pipe? Primarily 48" diameter to 72" diameter? 3) If steel casing pipe is required, will an interlocking joint type be allowed in lieu of complete penetration field welded joints? 4) If steel casing pipe is required, will dry blown sand be acceptable for filling of the annular space, in lieu of grout? Your prompt response is appreciated. | Yes a casing pipe is required. The second paragraph under section B Materialâ€¦â€Furnish a casing pipe conforming to ASTM A-53-Bâ€¦â€ The manufacturer of the pipe should have wall thickness information for E-80 loading. Field welds shall be required as per bidding documents. Grout shall be used for the annular space between the casing pipe and the carrier pipe as per bidding documents. | Scott Lawry | 13 | 2017-07-27 11:14 | 2017-07-28 10:11
20170808 | 20170808001 | 1 | Pavement Removal | It appears in the miscellaneous quantity schedule for pavement removal that the concrete pavement is removed in cut and fill sections. The Standard Specifications allows the pavement to remain in place. Can the existing pavement (asphalt overlay and concrete) remain in place? If so, what needs to happen to the asphalt overlay and the concrete pavement to remain in place? | Standard Specification 205.3.2 (5) allows existing pavement to remain if there is a 2 foot or greater distance from existing pavement to top of proposed subgrade. There are some fill stretches along mainline where the 2 foot clearance could be achieved. Contained within some of these stretches are pipe installations which would require pavement removal. Instead of introducing another pavement operation (crack and seat?) the design team felt removing all the pavement created operational consistency. If the contractor chooses to leave the pavement in place as per 205.3.2 (5) then that quantity will not be measured for Removing Pavement. The standard specification does not call out for any action to the pavement left in place. | Mike Coleman | 14 | 2017-07-31 07:41 | 2017-08-02 09:57
20170808 | 20170808001 | 1 | WIM system - communication conduit | Will the WIM communication conduit containing fiber from the SWEF building to the mainline WIM cabinet be impacted by grading operations? If so, in what sections? | There are notes along the bottom of pages 247 thru 250 on the 1003-10-81 plan set that provides information into this question. Also slope intercept lines along with cross sections can be used to review possible conflict. Over excavation or inadequate conduit depth can also play into the impact question. Please review the plans and provisions per standard specification 102.5 Examining Contract Documents and Work Site http://wisconsindot.gov/rdwy/stndspec/ss-01-02.pdf#ss102 | Scott Lawry | 15 | 2017-08-02 06:48 | 2017-08-03 09:35
20170808 | 20170808001 | 1 | Pavement under s42 barrier wall | How is the pavement be for? Look at SDD #16. according to this it should be paid as 13" pavement | The median 42â€ barrier wall footing is incidental to the wall and should be included in the bid price. | Scott Lawry | 16 | 2017-08-07 11:36 | 2017-08-07 13:16
20170808 | 20170808004 | 4 | Cad Files | Can you please release the cad files for this project? Thank you. | The CAD files and the Pre-Bid sign in sheet can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808004/ | Scott Lawry | 1 | 2017-07-17 10:58 | 2017-07-19 10:36
20170808 | 20170808004 | 4 | City of Madison Prequalification | Does the contractor performing the sewer and water work for the City of Madison items have to be prequalified with the City of Madison in accordance with the City of Madison Standard Specification 102.1? | Subcontractors do not need to be prequalified with the City of Madison to perform the sewer and water work on this project. | Scott Lawry | 2 | 2017-07-26 16:32 | 2017-07-27 10:29
20170808 | 20170808004 | 4 | Geotechnical Information | Is there any geotechnical information, that is not already provided in the plan set, that is available for download? | The geotechnical reports can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808004 | Scott Lawry | 3 | 2017-07-27 14:30 | 2017-07-27 14:51
20170808 | 20170808004 | 4 | Section 19 General Provisions for Storm Sewer | This section states â€œConstruct catch basins, manholes and inlets using only precast or cast in place concrete masonry options. All structures shall be reinforced concrete. Concrete brick and block options are prohibited.â€ This section further states â€œBid all structures (manholes and inlets) as field poured, and construct all structures as fieldpoured unless the contractor receives approval of the engineer to precast the structures.â€ These statements seem to be in conflict, as one section states that the contractor can use precast or cast in place options, then the other section states specifically that only the cast in place option is available unless approved by the engineer. There are 228 storm sewer structures bid as round (diameter) in which no standard detail drawings exist, would not be feasible to construct round as cast in place and are in conflict with Section 19 if it is the intent of the department to have these structures cast in place. Additionally, it seems as if the was designed for precast round structures according to the storm sewer plans provided on the project. If the intent is to have all structures bid as cast in place, please change the diameter structure to the correct sized square or rectangular structures to bid the appropriate dimensions for each structure(s), or bid by the CY as most cast in place structures are bid. If it is the intent to allow some precast and some cast in place structures, again please identify and update the quantities in the bid schedule that are currently bid as precast structures and supplement with additional bid items for the intended cast in place structures. | This special has been used in multiple WisDOT projects in the City of Madison. The intent of the special is for the contractor to bid it as such that the structures will be poured in place, but the City of Madison wants to see all the shop drawings and may approve some of the structures as pre-cast if it can be verified that all the pipes fit. Theses drawing need to be provided by the contractor. | Scott Lawry | 4 | 2017-07-31 08:36 | 2017-08-03 09:40
20170808 | 20170808004 | 4 | Standard Detail Drawings for Cast in Place Structures | Note 2 for these structures on Sheets 1021, 1024, 1024 states â€œContractor to provide drawing(s) stamped by a professional engineer for steel reinforcing design for cast-in-place structuresâ€. Since the department is directing all structures to be bid as cast in place per Section 19 of the Special Provisions, shouldnâ€™t the details and designs stamped by a professional engineer be provided by the owner? Please provide this information for each structure size if it is the intent of the department to have all structures built as cast in place. | Per the SDD drawing and contract, the contractor is to provide stamped drawings. | Scott Lawry | 5 | 2017-07-31 08:42 | 2017-08-03 10:46
20170808 | 20170808004 | 4 | Earthwork Quantities - Borrow | On Page 806 of the plans, Division 1 Overall Project Subtotal, the quantities seem off... in particular the Mass Ordinate which would make the borrow quantity off. Can you look into this, I believe the borrow quantity should be higher?? | The Division 1 earthwork table has been checked for math errors and none were found. The negative expanded fill value accounts for the use of excavated rock in the embankment which would reduce the mass ordinate value and resulting borrow quantity within the division. | Scott Lawry | 6 | 2017-08-02 09:32 | 2017-08-07 09:06
20170808 | 20170808004 | 4 | Storm Sewer | Addendum No. 1 addressed changes to some storm sewer items. According to the American Concrete Pipe Association Fill Height Tables for Elliptical pipe with Type 2 Bedding, Class 4 pipe allows cover over the top of pipe not to exceed 22 feet. The 68x106 RCPHE storm sewer from Structure 45.1 to Structure 47.1 has fill heights near 30 feet. Per the ACPA tables a "Special Design" pipe item is required. Please advise on how this will be handled prior to the bid. | Addendum No. 2 will address this issue with the addition of a bid item for Storm Sewer Pipe Reinforced Concrete Horizontal Elliptical Class Special 68â€x106â€. | Scott Lawry | 7 | 2017-08-04 09:24 | 2017-08-04 17:09
20170808 | 20170808004 | 4 | Response to Question 4 | Please provide Standard Detail Drawings or Construction Detail Drawings for the cast in place option for the following bid items, as there is no information in the plan provided to construct these as cast in place manholes and inlets: Manholes 4-FT Diameter Manholes 5-FT Diameter Manholes 6-FT Diameter Manholes 7-FT Diameter Manholes 8-FT Diameter Manholes Variable Special 4-FT Diameter Inlets 4-FT Diameter Special 15. Pond Outlet Structure Special 16. Manholes Special 10-FT Diameter Special 17. Manholes Special 12x12-FT | The requirement to bid and construct storm sewer structures as field poured will be removed with the revision to Article 19 General Provisions For Storm Sewer in Addendum #2. | Scott Lawry | 8 | 2017-08-04 10:19 | 2017-08-05 08:21
20170808 | 20170808004 | 4 | Prosecution and Progress | D Roadway Embankment Surcharging Bullet point 2 (Sta. 142 â€˜SBâ€™ +50 to Station 147 â€˜SBâ€™ + 50 Left) states â€œThe surcharge load duration shall be 2 monthsâ€. It later states â€œâ€¦ complete final subgrade grading before the 4-month time has elapsedâ€¦â€ Which duration is correct for the surcharge? Bullet point 4 (Sta. 303 â€˜WBâ€™ +00 to Station 316 â€˜WBâ€™ +00 Left) states â€œThe surcharge loading duration shall be 1 monthâ€. It later states â€œâ€¦ before the 2-month time has elapsed unless approved by the engineerâ€. Which duration is correct for the surcharge? | Bullet point 2 (Sta. 142â€™SBâ€™+50 to Sta. 147â€™SBâ€™+50 Left): The correct duration is 2 months. Bullet point 4 (Sta.303â€™WBâ€™+00 to Station 316â€™WBâ€™+00 Left): The correct duration is 1 month. An addendum will be provided with these corrections. | Scott Lawry | 9 | 2017-08-04 14:19 | 2017-08-04 17:04
20170808 | 20170808004 | 4 | Addendum 1 | Utilities Many of the utilities had original completion dates to relocate a portion of their facilities â€œprior to constructionâ€ or â€œOctober 1, 2017, prior to constructionâ€. Per Addendum 1, many of these utility relocates have now been extended to December 1, 2017. Many of the utility relocates were required to complete the work for Stage 1 found in Section 4 Prosecution and Progress, B. Interim Completion Dates and have interim liquidated damages for work to be performed by December 1, 2017 and December 15, 2017. These areas are particularly Wellness Way, Meriter Way and Raymond Road Shouldnâ€™t the Stage 1 interim completion dates and liquidated damages be adjusted or eliminated as the utilities will not be relocated in order to perform the work required as specified? | The utility companies have requested a coordination meeting with the contractor to expedite relocations for Stage 1 conflict points based on the contractorâ€™s specific schedule for Stage 1. Underground utilities are not in conflict with the proposed grading/fill work required to meet the Stage 1 interim completion dates for ATC relocation. The utilities will be relocating to a joint trench along the east side of Meriter Way and the north side of Wellness Way. The joint trench work is planned for completion by October 24 with completion of connections expected November 7. | Scott Lawry | 10 | 2017-08-04 14:24 | 2017-08-05 08:23
20170808 | 20170808004 | 4 | Prosecution and Progress | Stage 1 (2017) states â€œIf the contractor fails to complete sanitary sewer, water main, storm sewer, select crushed material and base aggregate dense construction on Wellness Way and Meriter Way â€¦ prior to 12:01 AM December 1, 2017, the department will assess the contractor $2065 in interim liquidated damages for each calendar day that the work remains incomplete beyond 12:01 AM December 1, 2017. Please identify which portion of Wellness Way needs to be completed by this date. Will the utilities be relocated in order to achieve this interim date, as there are multiple fiber optic lines and a gas line currently in conflict to construct Wellness Way. It is confusing as to why this roadway has an interim completion date of December 1, 2017, to get gravel placed, as there is an additional interim completion date of June 15, 2018 to open Wellness Way and Meriter Way to local traffic? The December 1, 2017 date seems to have no affect on local traffic? | The interim completion date for completing Wellness Way to base aggregate surface is to provide access to Raymond Road residents during an anticipated winter work suspension. | Scott Lawry | 11 | 2017-08-06 22:35 | 2017-08-07 11:26
20170808 | 20170808004 | 4 | Rock Excavation for Storm Sewer | The contract currently has bid items for Excavation Rock and Rock Excavation, Sanitary Sewer and Watermain, but there currently is not a bid item for Rock Excavation, Storm Sewer. It appears the storm sewer from approximately Sta. 195+00 to 200+00 will be installed in a Rock Excavation area. Under which bid item will the Rock Excavation for storm sewer be paid? | Please refer to standard specification 608.5.3 | Scott Lawry | 12 | 2017-08-06 22:37 | 2017-08-07 16:07
20170808 | 20170808004 | 4 | Storm Sewer Backfill | Per Standard Specifications 608.3.5, the contractor is to place the storm sewer trench backfill from 1 foot above the pipe to subgrade with material meeting the requirements of 209.2 (Granular Backfill) or 520.2.5.2 (Foundation Backfill). Will this backfill material (granular) be required on Raymond Road for the entire trench depth in the deep storm sewer that is 20 to 30 feet deep? | Backfill material for trenches should be bid per the standard specifications as noted above. The excavation limits for the trench and resulting backfill material quantity required depends on contractor means and methods for constructing the trench. | Scott Lawry | 13 | 2017-08-06 22:39 | 2017-08-07 16:00
20170808 | 20170808009 | 9 | Pavement Markings | I am wondering if there should be a same day item and/or a temporary item for this project seeing as it is open to through traffic during the project? I am also wondering if the pavement marking paint should be epoxy or even same day epoxy seeing as you are putting wet reflective epoxy edge lines on this project? Thank you for your time and efforts in answering my questions. | We are not proposing to remove any pavement markings so there will always be some form of existing markings throughout the duration of the project. We included an undistributed quantity of removing markings for potential no passing zone corrections beyond the project limits per the FDM, but do not see a need for same day or temporary markings. Centerline PAINT was requested by Brown County. | Scott Lawry | 1 | 2017-07-27 14:40 | 2017-07-28 10:41
20170808 | 20170808009 | 9 | Business Meetings | Why is there a need to have business meetings as part of the project, especially being only 15 working days? I just want to confirm that you intended to have that in the contract, as it would add some cost and effort to the contractor to include this work. | We certainly understand the question. Our intent was to have it in the contract. We felt it was good practice to coordinate with local "businesses" plus the article includes the department and first responders such as the police/sheriff. We thought it was prudent to communicate/coordinate with them. We could see one business meeting before the project starts full speed just to let people know what's going on and the schedule. A long explanation to say, yes we intended to have at least one business meeting. | Mike Coleman | 2 | 2017-08-02 09:44 | 2017-08-02 09:45
20170808 | 20170808010 | 10 | B-70-321/322 - Pier Haunch Lengths | What are the lengths of the haunches at the piers for the slabspan bridges? | The haunch length is 8â€™-6â€ from C/L of pier. An addendum is being developed to address this issue and will be published next week. | Scott Lawry | 1 | 2017-07-17 15:38 | 2017-07-19 13:38
20170808 | 20170808010 | 10 | Document request | Can the department make the following available? 1. Copy of the 404 permit (SPV #10) 2. Copy of the USCG Permit (SPV #11) 3. Copies of the As-built drawings for the existing retaining walls (SPV #33) | The files can be found at ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808010/ | Scott Lawry | 2 | 2017-07-18 15:03 | 2017-07-19 09:59
20170808 | 20170808010 | 10 | Schedule | Can the departments proposed schedule be provided for this project? | the departments proposed schedule can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808010/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Scott Lawry | 3 | 2017-07-19 10:39 | 2017-07-19 13:36
20170808 | 20170808010 | 10 | Cofferdams at B-70-321 & B-70-322 | The Special provisions article 45. allows for concrete to be poured under water for solid shaft pier construction. However the plans states that cofferdams are required on both B-70-321 & B-70-322. Will cofferdams be required for all solid shaft pier construction? | All piers require cofferdams, but not all cofferdams need to be dewatered. See general notes in plans for B-70-321 & B-70-322. | Scott Lawry | 4 | 2017-07-19 15:47 | 2017-07-21 09:27
20170808 | 20170808010 | 10 | Geotechnical Report & Additional Existing Wall Details | Please provide geotechnical report for the project. Also, provide any details for existing seawalls that will be partially removed as required in SPV 35 & 36. | The geotechnical reports can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170808010/ The Department has no information available about the sea walls. The wall information that was posted in response to a previous question covered as-builts of existing retaining walls. | Scott Lawry | 5 | 2017-07-27 14:43 | 2017-07-28 10:19
20170808 | 20170808010 | 10 | Painted Sheet Piling | Is the permanent sheet piling intended to be painted on both the front and back face of the sheeting? General note on page 377 seems to indicate both faces of the full sheet where traditionally WisDOT has designed only the exposed front face as painted. | The sheet piling in this instance is to be painted 4â€™ below the streambed on the front face and 4â€™ below the finished grade at the back face. Below is the applicable spec. 550.3.11.3 Painting (1) Use a paint system from the departmentâ€™s approved product list. Paint steel piles that are exposed in the completed work from the top of the pile to 4 feet or more below the streambed or ground line. Ensure that painted areas are fully cured before driving. (2) Prepare the surface and apply the paint as specified in 517, except blast clean the pile conforming to SSPC-SP10. (3) Handle painted piling with padded slings, nonmetallic slings, or softeners to minimize paint damage. Repair damaged paint exposed above either the water or ground line. | Scott Lawry | 6 | 2017-07-31 16:01 | 2017-08-01 10:20
20170808 | 20170808010 | 10 | Work within the Wolf River | The provided schedule indicates that cofferdam and piling installation is planned to occur during the fall fish migration period (10-15 thru 11-30). Per the Special Provisions this is not allowed (see 9 of 162). Please clarify whether or not work will be allowed on the piers during the fall migration period. The same question is raised for bridge removal operations in the fall of 2018 and cofferdam removals in spring of 2019. | The schedule that was provided corresponds with revised language in addendum #1 that relaxes some of the work restrictions within the fall fish migration period. Contractor should refer to addendum #1 that describes what work is allowable within the fall fish migration period and the requirements that apply to this work | Scott Lawry | 7 | 2017-08-02 14:13 | 2017-08-03 10:00
20170808 | 20170808010 | 10 | Joint Heater | The joint heater on the Winneconne Bridge Approaches job poses a constructability concern. The short runs donâ€™t allow for a joint heater as the contractor would pull the short run, set back and hot lap that small area. Can be removed from the project? Is there a reason why the mix changes at the end of the radius? The parking area and the cul-de-sac make sense to change mixes, but the smaller tie ins cause concern for constructability. | For the question on the joint heater, we envision some paving in stages 3-5 may not have a â€œhot lapâ€ of the joint. There is also potential that a contractor could propose different staging such that there is more significant time between passes. We believe it is best to leave the joint heating item in the plan and all bids should be submitted accordingly. For the asphalt mix type on the intersection tie-ins, we do agree there is benefit to keeping the same mainline mix for the intersection tie-in areas. We are going to prepare an addendum to use the same mainline mix for these areas. | Scott Lawry | 8 | 2017-08-03 14:54 | 2017-08-03 14:55
20170808 | 20170808010 | 10 | Disposal of Contaminated Water | Special provisions for Contaminated soil states that coordination of holding tank mobilizations, transportation and disposal of contaminated water will be provided by environmental consultant. What are the size of the tanks and frequency of disposal would be? | One or more frac tanks (about 21,000 gallons capacity each) can be staged near dewatering activities. Or vac truck can be used to pump out excavations. The frequency of disposal will be as necessary to keep up with dewatering. | Scott Lawry | 9 | 2017-08-03 17:11 | 2017-08-04 17:05
20170808 | 20170808010 | 10 | Contaminated Soils | Is there an area inside the project limits designated for temporary stockpiling Contaminated Soils? | There is no specific area designated. Soil stockpiles are not preferred but allowed. It is preferred to direct haul contaminated soil designated for the landfill. | Scott Lawry | 10 | 2017-08-04 13:38 | 2017-08-07 08:10
20170808 | 20170808010 | 10 | Riverbed Sediment Disposal Site | Are there areas on the site that can not be disturbed? If so, can they be identified? | Plan sheet #26 gives the location of the river excavation disposal site. As explained in article #101 â€“ Preparation, Shaping and Finishing Sediment Disposal Site, the contractor needs to contact Kathie VanPrice at WisDOT NE Region to set up a review meeting at the disposal site to identify upland areas where sediment disposal is allowed, and to review site ingress/egress. | Scott Lawry | 11 | 2017-08-04 17:05 | 2017-08-07 07:59