## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20180911 | 20180911001 | 1 | Fiber Wrap Reinforcing Non-Structural, Item SPV.0165.01. | In previous versions of the Fiber Wrap Non-Structural Special Provision, the fabric's minimum tensile strength and the wrap's minimum thicknesses had been listed. The Fiber Wrap Special Provision for this project addresses neither of these aspects. Please provide the requirements, if any, for both of these items. | As this is a non-structural application, it is intended for the contractor to follow the manufacturerâ€™s instructions for application as it states throughout the SPV. | Mike Coleman | 1 | 2018-08-09 16:03 | 2018-08-14 13:31
20180911 | 20180911001 | 1 | Concrete Surface Cleaning B-41-93 - Location | The concrete surface cleaning is located on the underside of the deck. It is shown in the SW corner near south end of pier 1 and the west abutment. While at the site visit that area appears to be free of defect and there are 2 similar "defective" areas on the north underside of the deck near pier 2 & the east abutment - Please confirm the approximate location of the repair area. On sheet 226 of the plan set the "concrete surface cleaning" is called out by a note. The "hatching" on the cleaning area is different than "concrete masonry deck repair" and is only labeled as "concrete surface cleaning". How are the repairs (aside from cleaning) paid for? | The underdeck spall locations were incorrectly placed on the plans. The correct locations are mirrored and located in the NE corner of the bridge and reflect what was found during the site visit. The repair work called out to get concrete surface cleaning is paid for under the special provision â€œConcrete Surface Cleaningâ€, which details removing deteriorated concrete and cleaning and epoxy coating exposed reinforcement. There is no concrete patching for the areas called out for concrete surface cleaning. | Mike Coleman | 2 | 2018-08-20 15:34 | 2018-08-22 08:34
20180911 | 20180911001 | 1 | Pavement Markings | Since the surface layer of this project is SMA, should there be temporary marking paint quantities to delineate the final configuration on the upper layer prior to scarification? Thank you. | No temporary markings have been included to delineate the markings. It is the bidding contractorâ€™s responsibility to produce the markings per the SDD(s). Per standard specifications 646.5(2) â€œPayment for the Marking bid items under this section is full compensation for providing the markingâ€. No additional compensation should be expected by the bidding contractor electing to use temporary paint to aid in the completion of the marking bid items. | Mike Coleman | 3 | 2018-09-05 13:18 | 2018-09-06 14:42
20180911 | 20180911001 | 1 | Permanent markings and an SMA Upper Layer | In addition to my previous question, please confirm the departments position on scarifying the SMA surface prior to placing permanent pavement markings. It has always been included in the proposal and, in this case, it is not unless it was missed on this end. Thank you. | The proposal does not include language regarding scarifying. The bidding contractor should follow Standard Specification 646.3.1.1(1) â€œPrepare the surface and apply marking as the manufacturer specifies. Provide manufacturer specifications as the engineer requests. Do not mark over a marking product with less adherence or over chipped or peeled marking.â€ | Mike Coleman | 4 | 2018-09-05 13:43 | 2018-09-06 14:42
20180911 | 20180911001 | 1 | Temp barrier | I see the stationing for the temporary barrier and crash cushions in the miscellaneous quantities, but I don't see anything on the plans for traffic control details, staging etc. Is there a traffic control section missing? | The Miscellaneous Quantities calls out the location and quantities. For layout details, see Standard Detail Drawings "Traffic Control, Single Lane Crossover Entrance With Barrier" and â€œTraffic Control, Single Lane Crossover Exit with Barriersâ€ located on sheets 199 and 201 of the plans. | Mike Coleman | 5 | 2018-09-05 15:52 | 2018-09-06 14:41
20180911 | 20180911001 | 1 | Traffic Control on STH 16 | During stage 2, work is required on structure B-41-112 that will be accessed from STH 16 for pier and abutment repairs as well as the painting activities. We are unable to locate the traffic control plans and requirements for STH 16 in the plan or proposal. Would you be able to confirm what the traffic control plans are for this location? | An emergency addendum will be completed to address the traffic control on STH 16. | Mike Coleman | 6 | 2018-09-07 08:45 | 2018-09-07 09:18
20180911 | 20180911003 | 3 | Traffic Control | Will we be permitted to have a temporary 24 hour lane closure of all lanes of traffic? | No temporary 24 hour closure of all lanes of traffic will be permitted on roadways other than on Hickory Street. Hickory Street will be closed during painting operations. All lanes (including shoulders) of STH 16, CTH KC and CTH JJ shall be entirely clear for traffic during Peak Hours. A minimum of one lane (including shoulder) shall be entirely clear for traffic during Off-Peak Hours. Traffic shall run on existing asphalt or concrete pavement. Additional information about peak times and other traffic information is available on pages 3 and 4 of the special provisions, under article #3 and #4, prosecution and progress and traffic. | Mike Coleman | 1 | 2018-09-04 12:38 | 2018-09-05 06:50
20180911 | 20180911003 | 3 | 8/31/2019 Completion Date | The Completion Date of 8/31/2019 is very aggressive considering the times allowed to access the steel. A more accurate completion date would be one in 2020 or at least the Entire 2019 construction Season. If possible, please extend the completion date. Thank You. | The design team feels the time is adequate and the completion date will remain August 31, 2019. Depending on the resources available to the contractor and how they choose to allocate those resources there is a potential for multiple crews to be necessary at various stages of construction. | Mike Coleman | 2 | 2018-09-04 16:35 | 2018-09-05 13:11
20180911 | 20180911003 | 3 | Hickory St Detour | On plan SHT 23, Note 1 states CONTRACTOR SHALL OPEN ROAD WHEN WORK IS NOT BEING PERFORMED. But in the previous ? it states Hickory ST may be closed long term 24 hrs. Please clarify that we do not need to reopen Hickory St daily at the end of the work day. |  |  | 3 | 2018-09-07 11:13
20180911 | 20180911003 | 3 | Staging Area | On SHT 18 of the plans shows the ROW for staging area. We believe the area is not flat or solid enough for our heavy equipment. Our blasting recycling trailers are 70,000 plus lbs. Is there another option for staging our equipment to clean and paint this bridge? Thank you |  |  | 4 | 2018-09-07 11:22
20180911 | 20180911005 | 5 | In- Stream Disturbance as it relates to the schedule | It appears the NTP will be issued after 1/2/19 and that stage 1 traffic control cannot be placed until 3/1/19. The proposal also states that there shall be no in-stream disturbance from 3/15/19 to 6/15/19. How has the designer anticipated the stage 1 removal of the structure and accessing the pier construction in the 14 days from 3/1/19 to 3/15/19? Does this mean that if the pier access (causeway) is in prior to 3/15/19 that work can proceed? Can the bulk of the causeway be placed prior to 3/1/19 with minimal traffic interference? | The special provision states â€œDo not proceed with roadwork under this contract or close STH 20 to through traffic until March 1, 2019â€¦â€ â€œRoadworkâ€ is not intended to include construction on the bridge. Bridge construction may begin prior to March 1st with appropriate traffic control in the immediate vicinity of the bridge to maintain 1 lane of traffic in each direction across the existing structure. Traffic control and detours for the remainder of the project would not be allowed prior to 3/1/19. With a January 2, 2019 notice to proceed, this allows nearly 2 ½ months to complete the Stage 1 structure removals and new pier construction. Stage 1 structure work above water could proceed between 3/15/19 and 6/15/19. The no-instream disturbance period from 3/15/19 to 6/15/19 is mandatory and will be enforced by the DNR. | Mike Coleman | 1 | 2018-08-15 12:59 | 2018-08-17 07:34
20180911 | 20180911005 | 5 | Railing painting | The plans state that the railing on R-51-0070 is specified to be painted black. However, the Railings for the remaining structures on the project are not indicated to be painted or not painted. Could you please clarify if this correct? | All railing shall be painted (black) in accordance with section 513 of the standard specifications. An addendum will be issued to clarify that all railing will be painted black, federal color no. 17038. | Mike Coleman | 2 | 2018-08-16 13:06 | 2018-08-27 06:31
20180911 | 20180911005 | 5 | Information. | Can the Design Schedule and Soils Report be made available? | The soils reports and schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180911005/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2018-08-24 16:05 | 2018-08-27 14:39
20180911 | 20180911005 | 5 | River Access - Bridge Construction | Does the 404 Permit allow for a causeway or cofferdams for bridge demolition and pier construction? There is no pay item for cofferdam so we are assuming that a causeway will be allowed. If a causeway or cofferdams are allowed is there a timeframe in which they need to be installed and/or removed? Are they able to remain in place as long as they are installed prior to 3/15/19? | The current 404 permit does not account for a cofferdam or causeway (due to anticipated access limitations) to be utilized for bridge construction. The plans account for the fact that the DNR has stated to be out of the waterway during the prohibited time; however, an addendum will be issued to revise the in-water restriction time period to be from March 1 through June 1 (instead of 3/15-6/15). Work that does not disturb the streambed or banks may be allowed within the restriction period at the discretion of the DNR if proper BMPâ€™s are in place. A copy of the 404 and 401 permit and permit application can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20180911005/ An addendum will be issued to clarify DNR requirements for in-water construction restrictions. The DNR just cleared up conflicting dates from their previous correspondence. | Mike Coleman | 4 | 2018-09-05 10:57 | 2018-09-07 06:41
20180911 | 20180911006 | 6 | B-40-378 Sidewalk slider plates | Please provide details for the slider plates that will be required at the sidewalks and median so that they can be included in bid prices. |  |  | 1 | 2018-09-06 12:25
20180911 | 20180911006 | 6 | Traffic Control | Will work be allowed at both location (Silver Spring Drive & 76th Street) at the same? | Yes. The two locations can be worked on at the same time. | Mike Coleman | 2 | 2018-09-06 14:08 | 2018-09-07 08:41
20180911 | 20180911006 | 6 | Traffic Control - Douglas Ave | Would you be able to confirm of explain what the traffic control plans will be for W. Douglas avenue? We cannot seem to locate anything about traffic control in this area. | Douglas Avenue may be closed to through traffic during bridge painting operations immediately over or adjacent to the roadway. Traffic control barricades should be placed on either side of the work zone in accordance with SDD 15C2-6, Barricades and Signs for Mainline Closures with advance warning signs placed according to Detail C of SDD 15C2-6a. A very minor increase in TC quantities in the field would result. | Jill Fehrman | 3 | 2018-09-07 08:28 | 2018-09-07 12:13
20180911 | 20180911007 | 7 | Soil Borings | Please provide soil boring information for this project. | Soil boring information is on Pages 132-138 and 452-453 of the plan set, and the Soil Boring Reports are located on the SE Preliminary plans page https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Fred Schunke | 1 | 2018-08-15 08:16 | 2018-08-20 15:40
20180911 | 20180911007 | 7 | Sanitary manhole quantity | Quantity question for bid item SPV.0060. Bid quantity of 13 each sanitary manholes 4 ft diameter. I find 12 each sanitary manholes. They are # 1, 2, 3, 3.1, 3.2, 4, 5, 6, 7, 8, 9 and 10. Please confirm the correct quantity. | MH San-0 is listed on the Misc. Qtyâ€™s sheet (incorrectly) as having 1 SPV.0060.25 Sanitary Sewer Manhole, (4-foot diameter), however, on the plan sheet MH San-0 is an existing manhole that isnâ€™t being replaced. MH 0 was new in 2012, so it can be connected to and does not need to be replaced, therefore 12 (twelve) should be the total number of sanitary MHâ€™s. | Mike Coleman | 2 | 2018-09-05 10:25 | 2018-09-06 10:10
20180911 | 20180911007 | 7 | Crack & Damage Survey Item | How many buildings are you anticipating? There are like 10,000 buildings in the City of Whitewater, do you need them all done? What are the designerâ€™s expectations? | As per the special provisions, the design team provided 3 station ranges where we are proposing to install sanitary sewer, water and storm sewer where there is rock close to the roadway profile. Our expectations are the contractor would do a survey of the buildings immediately adjacent to the roadway, on both sides, at those 3 station ranges due to the proposed underground work. | Mike Coleman | 3 | 2018-09-07 09:15 | 2018-09-07 09:16
20180911 | 20180911007 | 7 | Granular Backfill | When is Granular Backfill paid separately for pipe removals? | Items where granular backfill paid separately under Item 209.2500: 1. Removing Storm Sewer in Stage 2 and 3 Items where granular backfill not paid separately under item 209.2500: 1. Removing Small Pipe Culverts 2. Removing Old Structure STA 134+32 3. Removing Storm Sewer in Stage 1 | Mike Coleman | 4 | 2018-09-07 09:24 | 2018-09-07 09:28
20180911 | 20180911008 | 8 | Pavement markings | There is a detour for this project and it also appears it will be open to local traffic on portions of it throughout. Should there be a temporary pavement marking item for the milled surface, the lower layer, and the upper lower layer in order to safely guide traffic through the project? Also, should there be a same day or temporary epoxy item for the center line to safely guide traffic the project as well as providing initial layout for the center line rumble strips that are on this project? Thank you for your timely response to this question. | No changes are required to the pavement markings for this project. | Mike Coleman | 1 | 2018-08-29 09:27 | 2018-08-29 14:48
20180911 | 20180911008 | 8 | Typical Pavement Cross Section of Longitudinal Joints | The detail for pavement passes on sheet 13 in the construction details states that pavement passes 1 and 2 or 3 and 4 need to be completed in the same day when the road is closed. If the road is closed, couldn't pass 1 be from one end to other followed by pass two rather than backing up to square in each given day and cutting the transverse joints in half? If the road is closed to traffic, wouldn't uneven lane signs suffice? | The roadway is closed to through traffic but local traffic will still be using portions of the roadway being constructed. Itâ€™s undesirable to have vertical pavement edges down the centerline of the roadway with local traffic present. The contractor has the option of not paving passes 1 & 2 and 3 & 4 on the same day per note #3 of the detail mentioned. If this option is chosen, per the note, itâ€™s the contractorâ€™s responsibility to place a notch and wedge during passes 1 and 3. The contractor is then responsible for the work and cost to remove the notch and wedge prior to placing passes 2 and 4. | Mike Coleman | 2 | 2018-09-04 16:06 | 2018-09-05 08:32
20180911 | 20180911008 | 8 | Heavy Duty Silt Fence | Page 52 of the specials state that the woven wire fabric shall be a minimum of 4 feet high. The Construction detail in the plan on p. 19 states a 2-foot minimum height. Please clarify which height is needed. Also, even with a 4-foot height and 1.5-foot depth of post, the Specials state that posts must be 7'-6" minimum. Shouldn't a 6-foot post be adequate? Please clarify if this is needed. | An addendum will be issued to address the discrepancies between the spec article and construction detail. | Mike Coleman | 3 | 2018-09-04 16:29 | 2018-09-05 13:29