## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20181113 | 20181113001 | 1 | Design File Data- Alignments | Could the Department make available the alignment information (xml files) for both project IDs on the pre-lim page? | The design file information for project 1007-11-79 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1007-11-79/ The design file information for project 1007-11-80 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1007-11-80/ | Mike Coleman | 1 | 2018-10-15 16:14 | 2018-10-16 07:03
20181113 | 20181113001 | 1 | Design Data for Previous Projects 1007-10-84 & 1007-10-88 | Can you provide the design data that was used for the previous widening projects 1007-10-84 & 1007-10-88? | The design files for previous project 1007-10-84 & 88 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1007-10-84-88/ | Mike Coleman | 2 | 2018-10-16 06:57 | 2018-10-16 07:01
20181113 | 20181113001 | 1 | Undistributed Signs Type II Reflective H | Where is the undistributed quantity (77 SF) that is listed on page 382 of the 1007-11-79 plan? What is it referring to? | The sign square footage in the table on page 382 of the 1007-11-79 plan is for signs that will be 1.5 SQ FT each that will have a â€˜WisDOT prairie stewardship, no mowâ€™ type message on them for specific areas of vegetation throughout the project. The sign plate detail was left out of the plan in error. There is a note on page 127 of the plan that covers the sign (12â€x18â€) installation and the fact that the sign locations will be marked in the field. All of the signs in that table on page 382 are the same type, each 12â€x18â€. The sign plate detail will be added to an addendum that will be posted around November 1st. | Fred Schunke | 3 | 2018-10-19 08:10 | 2018-10-19 08:11
20181113 | 20181113004 | 4 | Can the design schedule be provided? |  | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113004/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2018-10-16 17:45 | 2018-10-17 10:14
20181113 | 20181113005 | 5 | Stage 10D PH 4 HMA Surface Paving | What staging requirements are needed for CTH PD HMA surface paving? Temp lane closures? Off peak? If temp and off peak, will tapered joint, longitudinal joint milling and temp striping be added to the project? Are there narratives or staging plans for this work? Consider off-peak full closures to pave all lanes hot without joints. | 1. The staging plans for CTH PD STG 10D PH 4 are on sheet 492 of the plans. 2. The special provisions articles Prosecution and Progress and Traffic provide allowable lane closure times for the work on CTH PD. Page 31 of the special provisions provides a narrative of CTH PD STG 10D PH 4 work. 3. Full closures of CTH PD are not allowed in accordance with the special provisions articles mentioned in number 2 above. 4. Temporary pavement marking and longitudinal joint milling will be added, via addenda, to the CTH PD area for work related to paving the surface layer of HMA. | Mike Coleman | 1 | 2018-10-18 13:30 | 2018-10-24 06:30
20181113 | 20181113006 | 6 | Soil Borings and Construction Schedule | Could you provide the soil boring information for these projects? Could you also provide the estimated construction schedule? | The soil borings and estimated construction schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2018-10-17 08:56 | 2018-10-17 09:09
20181113 | 20181113018 | 18 | Can the design schedule be provided? |  | Yes, this has been posted at the following location ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113018/ | Fred Schunke | 1 | 2018-10-16 17:46 | 2018-10-19 12:22
20181113 | 20181113018 | 18 | Topsoil Special Item SPV.0180.001 | Is the volume of Topsoil Special SPV.0180.001 109,488 SY (@ 6" thick = 18,248 cy) included or excluded in the volumes of Topsoil Removal as listed on the Earthwork Summary Tables (plan shts. 204 & 244). Please clarify since this has a significant impact on the earthflows. Thank you | The Topsoil Removal quantity shown in the plans is the estimated volume of topsoil that needs to be removed to construct the roadway. The estimated volume of Topsoil Special was not deducted from this quantity. | Fred Schunke | 2 | 2018-10-17 11:40 | 2018-10-19 09:49
20181113 | 20181113019 | 19 | Temporary Marking Line Paint 4" | Can you please verify where all of the temporary marking line paint will be used on this project? There is enough for 3 separate applications but, at first glance, it appears we will only need 2 layers, one for the mill/CIR, and one for the leveling layer. Thank you. | The project included quantity for â€œTemporary Marking Line Paint 4-Inchâ€ for up to three possible applications. Depending on the methods and schedule used, the following applications were anticipated: (1) on the existing roadway surface after 2-inches have been milled, (2) on the new CIR Pavement, and (3) on the Leveling layer | Mike Coleman | 1 | 2018-10-22 10:47 | 2018-10-23 07:33
20181113 | 20181113027 | 27 | CIP Piling Item | Please confirm size of C-I-P Piling to be used. Foundation data and Estimate of Quantities in Plan show 10.75 x .25 wall. Bid Express and Contract items in Work Proposal state 12.75 x .25 wall. | The item 550.2104 CIP Concrete 10 3/4 x 0.25-Inch as shown on the structure sheet is correct. An addendum will be issued to add the appropriate bid item and remove the incorrect bid item. | Mike Coleman | 1 | 2018-10-11 10:37 | 2018-10-15 07:49
20181113 | 20181113028 | 28 | Causeway to pier permitted? | Does the 404 permit allow for and will the contractor be permitted to build a temporary causeway to clean out cofferdam and set girders? | The 404 Permit did NOT include a temporary causeway for this project. A temporary causeway was not anticipated for this project. It was felt that the contractor would be able to access the pier from the stream banks, especially on the east side. | Mike Coleman | 1 | 2018-10-16 11:08 | 2018-10-17 14:26
20181113 | 20181113031 | 31 | Construction Timeline | Could a copy of the construction timeline developed during design be made available for our use? | The construction timeline can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113031/ | Deanna Goebel | 1 | 2018-10-11 15:20 | 2018-10-12 16:21
20181113 | 20181113031 | 31 | Asphaltic Surface Bid Item | Construction Detail page 6 for cross drain installation calls out 5.5" Asphaltic Surface. There is no bid item for Asphaltic Surface | The construction detail in the plan is incorrect. No asphaltic surface will be used. An addendum is being issued to revise the detail. | Mike Coleman | 2 | 2018-10-16 15:13 | 2018-10-17 14:22
20181113 | 20181113031 | 31 | 1 1/4" Base Aggregate Dense | Typical section on sheet 4 shows 1" of 1 1/4" BAD (Recycled Concrete Aggregate) to be placed on the shoulder prior to paving surface course. Is it the intention to salvage this material from the mainline pavement crushing process or to import this material. If this is an import why is the material listed as Recycled Concrete Aggregate? If the existing pavement is crushed on the grade, I see difficulties in salvaging this material to make sure you have enough in the windrow to pull in after the lower layer of hot mix asphalt is paved. | The intention of the typical provided on sheet 4 was to be materially neutral when looking at the Base Aggregate Dense 1 ¼â€ item. Meaning the end area of existing concrete pavement and HMA shoulder is equal to the finished end areas shown for BAD 1 ¼ (no expansion factor was included). Therefore, should the contractor choose to provide the BAD 1 ¼ â€œ by crushing the existing pavement no additional virgin material will be required. Any excess material can be used out on the gravel foreslopes to flatten slopes. If the material is crushed on the grade (Track crush), there is plenty of room on the shoulder (10 feet per side, plus flat 6:1 foreslopes) to store a windrow of material for pulling-in after the lower layer of HMA is placed. | Mike Coleman | 3 | 2018-10-20 11:34 | 2018-10-22 10:49
20181113 | 20181113033 | 33 | Pier access for preboring | Will the contractor be permitted to build a temporary causeway to facilitate pier preboring activities? | No work shall be performed in waters of the state without prior concurrence of DNR and the U.S. Army Corps of Engineers. Accordingly, a proposed causeway not shown in the plans must be included in the ECIP, and may or may not be permitted. | Fred Schunke | 1 | 2018-10-16 11:11 | 2018-10-19 09:50
20181113 | 20181113037 | 37 | Milling Asphalt Pavement | Typical section on sheet 4 of the plan shows the 12' mainline to be milled 4.75" while the 3' shoulder is to be milled 3.5". Milling in this manner will require two milling operations and two paving operations which will add, to what appears to be, unnecessary cost to the bid items. What is the reason for this? With that said. Due to the difference in milling depths, the mainline will be 1.5" lower that the shoulder after the lower layer of asphalt is paved. What is the thought to handle storm water drain off from the 12' drive lane as it cannot flow into the ditch? | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 1 | 2018-10-22 13:59 | 2018-10-29 09:42
20181113 | 20181113005 | 5 | Structures R-13-266 and R-13-267 | General Notes on Sheet 983 and 1002 for Structures R-13-266 and R-13-267 state that Pilasters shall be cast as a one piece channel section. Please provide more information on the one piece channel section. Is this made of 5-ft. high channel sections stacked on the top of the other as MSE panels? Soil Parameters on Sheet 984 and 1003 - Unit Weight, Friction Angle and Cohesion of Retained Soil is missing. Provide the same. | 1. The MSE pilaster panels shall be one piece channel sections of the same height as the adjacent MSE panels. 2. The retained soil for the Granular Backfill (Reinforcing Zone); Unit Weight: 120pcf, Angle of Internal Friction: 30deg, Cohesion: 0psf 3. The retained soil for the Roadway Embankment Retained Soil; Unit Weight: 135pcf, Angle of Internal Friction: 30deg, Cohesion: 0psf | Mike Coleman | 2 | 2018-10-22 17:33 | 2018-10-24 11:52
20181113 | 20181113001 | 1 | Structures R-13-260 STG 2 and R-13-261 STG2 | Do the size, shape and form liner for the STG2 MSE panels need to match the size, shape and form liner of the panels that were installed in the previous contract? What is the size, shape and form liner for the MSE precast panels that were placed in the previous contract? Provide the as-built (or as shown on the shop drawings( top of level pad elevations for the precast MSE wall panels that were placed in the previous contract so that the level pad for STG2 walls can be designed without undermining the stability of the previously built walls? R-13-261 STG2 forms an acute angle with the temporary MSE wall that was built to retain Segment C. It is not feasible to place the strips in STG2 without severe skew within the limits of the acute angle. Provide the minimum design requirements for the R-13-261 STG2 within the limits of the acute angle. | 1. Preference is to match the size and shape of the panels used in Stage 1 and produced by Sine Wall. Form liner not used on panels. 2. Stage 1 panels are 10â€™ (horizontal) x 5â€™ (vertical) with square corners. Since some panel fabricators use metric units the nominal size should match Stage 1 as close as possible. 3. As-Built top of leveling pad elevation for R-13-260 (Stage 1) is 866.12 and for R-13-261 (Stage 1) is 864.23 at the stage construction line. Leveling pad elevation is slightly different than shop drawing plans. 4. The MSE wall panel supplier is responsible for design to account for the acute angle. The department believes there are options available to account for the wall layout and acute angles. | Mike Coleman | 4 | 2018-10-23 10:57 | 2018-10-24 09:50
20181113 | 20181113005 | 5 | SPV.0090.005 Concrete Barrier Special Transition S42C-S56C | Where is item SPV.0090.005 Concrete Barrier Special Transition S42C-S56C used within the plans? I cannot find the location or a special detail for this item. | Item SPV.0090.005 Concrete Barrier Special Transition S42C-S56C should not be included in the plans. The item will be revised to standard bid item 603.1142 Concrete Barrier Type S42. The item location is on plan sheet 88 in the upper right where a concrete barrier transition Type S42 to S56 is noted near station 29+25 to 29+50 C. The pay item will be revised as noted in accordance with Standard Detail Drawing (SDD) 14B32-5d, page 740 of the plans. The SDD indicates to use a cold joint to connect multiple height transitions and the length of the double cold joint in included in the total length of the CBSS. Thus, in accordance with the SDD, the transition from 56 inch to 42 inch barrier will be paid as 603.1142 Concrete Barrier Type S42. The changes will be reflected in an addenda. | Mike Coleman | 3 | 2018-10-23 11:28 | 2018-10-23 11:30
20181113 | 20181113037 | 37 | Hot Mix Asphalt | Project 8100-01-71. The HMA quantities appear to have been transposed. The quantity listed in the schedule of items for the 5MT 58-34H seems to reflect the quantity for the 3MT 58-28S and vice versa. | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 2 | 2018-10-23 12:41 | 2018-10-29 09:42
20181113 | 20181113037 | 37 | Hot Mix Asphalt | Why does the plan call out a 5MT when there is a 4MT bid item in the schedule of items? 4MT would work with a change in lift thickness (2.25" 3MT, 2.0" 4MT & 1.75" 4MT) | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 3 | 2018-10-23 12:50 | 2018-10-29 09:42
20181113 | 20181113037 | 37 | Prosecution & Progress | From discussion with project staff, it appears the verbiage in the special provisions under the prosecution and progress is changing. From our interpretation of what is being proposed, the department does not want traffic to drive on the surface after milling. From existing typical section it appears the milling depth will go beyond the existing hot mix asphalt surface into what is probably a reclaimed asphalt base course. We have the following concerns. Will the wheel path milling and paving be done prior to or after the mainline milling and paving? With the mainline milling being done separately from the shoulder milling, there will be a 4.75" trough in the roadway. What happens if a thunderstorm rolls through making the roadway to wet to pave? | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 4 | 2018-10-23 17:36 | 2018-10-29 09:42
20181113 | 20181113037 | 37 | Prosecution & Progress | Special provisions call for the lower lift of hot mix to be paved over the entire roadway width by the end of the day. This creates a staging issue. Having a paving operation in one lane and a milling operation in another lane. What was the departments plan for handling traffic? | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 5 | 2018-10-23 17:40 | 2018-10-29 09:43
20181113 | 20181113037 | 37 | Milling | Typical sections show different thickness of milling for mainline and shoulders. With only 1/2" of hot mix remaining on the shoulder after milling, it appears the shoulders would have to be milled at a separate operation. Would the department consider milling the entire roadway the same depth? Then the entire roadway is paved the same thickness. or The mainline is paved per plan. In a separate operation the lower layer of the 5' shoulder is paved. The surface course would be paved per plan. | An addenda will be issued which will address Questions 1 - 6. This addenda will revise the typical sections and quantities to mill the shoulders to the same depth as mainline and to use the same lower layer mix in the shoulders as mainline. | Mike Coleman | 6 | 2018-10-23 17:45 | 2018-10-29 09:43
20181113 | 20181113018 | 18 | Pavement Markings | You have bid items for wet reflective epoxy and the plans show contrast wet reflective epoxy. Which item do you want and, if you want contrast, will you be issuing an addendum? Thank you. | The pavement marking should be contrast wet reflective epoxy. An upcoming addendum will address this item. | Mike Coleman | 3 | 2018-10-24 06:57 | 2018-10-24 13:14
20181113 | 20181113023 | 23 | soil borings | Are there any soil boring's available for this project? Geo-technical report? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113023/ | Mike Coleman | 1 | 2018-10-24 13:46 | 2018-10-25 06:34
20181113 | 20181113002 | 2 | Soil Boring Logs | Can you please provide a copy of the soil boring logs for this project? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113002/ | Mike Coleman | 1 | 2018-10-25 06:38 | 2018-10-25 06:43
20181113 | 20181113005 | 5 | Cad Files | Can you please make the cad files for the project available? Thank you. | The digital data for USH 18 CTH PD to Raymond Rd (Stage 2) (Phase 3) is not currently available. The digital data will be provided, post award, to the bidder awarded the contract. Information currently available includes an Excel file for the earthwork summaries. The spreadsheet contains multiple worksheets for each alignment. This file can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/1206-08-77/12060877_Earthwork.xlsx | Mike Coleman | 4 | 2018-10-25 07:50 | 2018-10-29 12:54
20181113 | 20181113018 | 18 | Design Files | Can you please provide the design files? | The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113018/designfiles/ | Mike Coleman | 4 | 2018-10-25 08:47 | 2018-10-25 08:56
20181113 | 20181113023 | 23 | Soil Boring report | We are looking for soil boring report for this project 4992-00-57 2018445 Not for a salt shed in WAUKESHA County! | My apologies! I sent the wrong link. The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113023/ | Mike Coleman | 2 | 2018-10-25 11:40 | 2018-10-25 12:21
20181113 | 20181113004 | 4 | Mill & Relay | Will pulverize and relay be an acceptable method for processing the existing asphalt shoulders? Material will generally be 97% passing the 2â€ sieve. Mill and Relay Item 330.0100 requires that material be 100% passing the 1 ½â€ sieve, this typically requires crushing and screening to achieve which is not practical in this application. | No. There is underdrain under the asphalt shoulder for the entire length of the project that is to remain in place, and we think the pulverize process will damage it. That is why we chose to use the Mill and Relay item. | Mike Coleman | 2 | 2018-10-25 13:28 | 2018-10-25 13:53
20181113 | 20181113004 | 4 | Mill & Relay | Will the sizing requirement of 100% passing the 1.5" sieve be relaxed on the mill & relay item to avoid the need for using a crusher or for processing beyond what a mill can provide for sizing? | No, please follow the Standard Specifications for the Mill & Relay item. | Mike Coleman | 3 | 2018-10-25 13:57 | 2018-10-25 14:17
20181113 | 20181113006 | 6 | Staking | Will there be a bid item for construction staking of the water main and sanitary items | Per Article 8 of the Special provisions, the staking of water and sewer will be completed by Lake Mills Light & Water Utility personnel or designated representative. | Mike Coleman | 2 | 2018-10-26 08:02 | 2018-10-29 10:19
20181113 | 20181113037 | 37 | Hot Mix | Would the department consider excluding the hot mix within station 1+50 - 28+50 from the PWL specifications and run this mix as standard 460 specification. As is currently is setup, 8+00 - 23+50 is the bridge project leaving 1+50-8+00 as a stand alone. It doesn't make sense to pave 1+50 - 8+00, leave a cold joint and when the bridge is completed pave 8+00 - 23+50. | The bridge approach typical section and miscellaneous quantities have been updated for HMA upper layer type and depth which allows a single paving operation for the surface without a joint at the bridge project limits. This was part of Addendum #01 that was posted on 11/05/18. | Mike Coleman | 7 | 2018-10-26 09:35 | 2018-11-06 06:41
20181113 | 20181113023 | 23 | Project Schedule | Does the DOT have available a project schedule | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113023/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans,. special provisions and any addendum that is developed. | Mike Coleman | 3 | 2018-10-26 13:19 | 2018-10-29 10:28
20181113 | 20181113001 | 1 | Line # 710 | Where is the item Subsoiling located within the project? Cannot find in miscellaneous qtys. | The subsoiling is part of the Vegetation Mitigation plans. The item is located in the miscellaneous quantities on page 382 within the seeding schedule. The quantities are included at the CTH N (B12) and USH 51/STH 73 (B2) interchanges and are shown within the infield areas on the layout sheets. | Mike Coleman | 5 | 2018-10-26 14:22 | 2018-10-30 08:09
20181113 | 20181113004 | 4 | Pavement Markings | Can you provide more detail on the temporary pavement markings please. It appears there are enough quantities to do the edge lines, ramps, and 8" 2 times, presumably on the lower and upper lifts, but it does not appear there are quantities included for the skips. In addition, what is the expectation for how often these will need to be placed? Daily, weekly, when a five mile stretch of HMA is completed? Please advise and thank you in advance for your feedback. | The quantities for the temporary pavement marking are missing the quantity for the skips. The frequency for placing pavement marking is dependent on the staging of the project. The intent is to place temporary pavement marking so lane closures can be removed and the lanes open to traffic when work is not being done. An addendum with revised pavement marking quantities is forthcoming. | Mike Coleman | 4 | 2018-10-26 15:34 | 2018-10-29 13:36
20181113 | 20181113025 | 25 | Cold-in-place Recycling (CIR) | If the milled material meets the gradation requirements will crushing and screening be required? | The material should be crushed and screened to ensure the gradation requirements are met. | Jill Fehrman | 1 | 2018-10-27 13:32 | 2018-11-02 13:14
20181113 | 20181113031 | 31 | Temporary Marking Line, Paint | Good morning. With the detour being in place until after the lower layer of pavement is placed, is it accurate to plan on placing the temporary markings on the lower surface all at one time prior to opening the road to traffic while the upper layer is placed? Thank you. | The item used, â€œTemporary Marking Line, 4â€ Paintâ€ does require the marking to be done the same day the pavement is placed. While we will have a detour in place, there will still be local traffic needing to use USH 63 within the closed work zone to travel to and from residences only accessible via USH 63. The actual painting recurrence interval on the lower surface will be dependent on paving sequence and engineer discretion based on field conditions. It is not correct to assume this paint will be placed all at one time. | Mike Coleman | 4 | 2018-10-29 08:31 | 2018-10-29 11:52
20181113 | 20181113001 | 1 | Department Owned Field Office | How long will this contract need to provide services for the field office? | January 31, 2020. | Mike Coleman | 6 | 2018-10-29 08:33 | 2018-11-01 11:03
20181113 | 20181113005 | 5 | B-13-831 & B-13-832 Preboring Quantity & Slurry Use | How were the preboring Quantities determined for B-13-831 & B-13-832? Typically preboring is calculated from bottom of abutment grade, since drilling usually starts from there. This would increase the quantity on B-13-831 to +/- 400 LF on the west abutment and +/- 440 LF on the east abutment This would increase the quantity on B-13-832 to +/- 400 LF on the west abutment and +/- 440 LF on the east abutment If pre-boring is calculated from B/MSE Wall there is still an error on B-13-832. West abutment should be +/- 270 LF. East Abutment should be +/- 285 LF. There is also a plan note that indicates "DURING DRILLING OPERATIONS, CASING SHALL BE USED FOR THE ENTIRE HOLE DEPTH REGARDLESS WHETHER OR NOT THE HOLE IS CAPABLE OF STAYING OPEN OR IS DRY." Would the use of a shorter casing and slurry be allowed rather than full length casing? | The pre-boring is taken from the bottom of the MSE wall to a depth of El. 980. The pre-boring cannot be taken from the bottom of abutment due to the MSE backfill. Pre-boring through the MSE backfill is not permitted. The quantity of pre-boring is an estimate based on the bottom of MSE wall. The bottom of the MSE wall is variable depending on footing size, wall geometry, and construction methods. The quantity shown on the plans is an average. The final quantity will be dependent on the MSE wall geometry and construction. Shorter casing and slurry will not be allowed. Casing shall be used for the entire hole depth in accordance with the plan note. | Mike Coleman | 5 | 2018-10-29 08:55 | 2018-10-29 14:26
20181113 | 20181113005 | 5 | MSE Select Backfill Extents | The bridge details show the mechanically stabilized backfill extending +1' beyond the end of the MSE wall soil reinforcements. The retaining wall details show the mechanically stabilized backfill extending only to the end of the soil reinforcements. What are the true extents of the mechanically stabilized backfill? Thanks. | The detail of the backfill limit on the retaining wall plans is for visual purposes only. Backfill shall be placed in accordance with special provision â€œWall Concrete Panel Mechanically Stabilized Earth R-13-XXXâ€, section B.3.3 Backfill. The backfill shall be placed in a zone extending horizontally from the back face of the wall facing to 1-foot minimum beyond the end of the reinforcement. The retaining wall typical sections will be updated accordingly via addenda. | Mike Coleman | 6 | 2018-10-29 11:58 | 2018-10-30 08:11
20181113 | 20181113020 | 20 | Design Files | Are the design files available? | The design files are not available for this project. | Mike Coleman | 1 | 2018-10-29 14:09 | 2018-10-30 08:07
20181113 | 20181113005 | 5 | HPC central-mixed concrete requirement. | HPC special provision under 501.3.5.1 requires central-mixed concrete. Previous HPC bridge decks have recently been poured in the same area as this project without the central-mixed requirement. Can this central-mixed requirement be removed? | This request has been reviewed by WisDOTâ€™s Project team. The HPC specification has been used for several years now requiring central-mix on IH 39 projects. Itâ€™s WisDOTâ€™s understanding that central-mix concrete is available in the area from either permanent or temporary plants. The central-mixed requirement will not be removed. | Mike Coleman | 7 | 2018-10-30 09:45 | 2018-10-30 10:43
20181113 | 20181113005 | 5 | HPC Superstructure Concrete - central-mixed concrete | High Performance Concrete (HPC) Masonry Superstructures, Item SPV.0035.300., Section 501.3.5.1 General, states that central-mixed concrete for all work under this special provision is required. This requirement potentially creates a sole source situation for the purchase of ready-mix concrete and has the potential to increase the purchase price of the ready-mix concrete for the project. There is a ready-mix supplier in closer proximity to the project than any other, who would like to quote the supply of this concrete, but is not capable of meeting this requirement. It is assumed that the closest supplier will provide the most economical advantage to the project and WisDOT for the supply of this concrete. Please consider the waiving of this special provision language. | This question was addressed in Question #7. Here was the response: This request has been reviewed by WisDOTâ€™s Project team. The HPC specification has been used for several years now requiring central-mix on IH 39 projects. Itâ€™s WisDOTâ€™s understanding that central-mix concrete is available in the area from either permanent or temporary plants. The central-mixed requirement will not be removed. | Mike Coleman | 8 | 2018-10-30 11:19 | 2018-10-30 14:38
20181113 | 20181113020 | 20 | Can the design schedule be provided? |  | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113020/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2018-10-30 12:08 | 2018-10-31 06:34
20181113 | 20181113019 | 19 | Prep Foundation for Asphalt Shoulders/ Shaping Shoulders Quantity | Item #34 Prep Foundation for Asphalt Shoulders and item #42 Shaping Shoulders appear to only have the STA figured down centerline. I think these quantities need to be doubled to represent both sides of the road? | The quantity for those two items will be doubled from the current plan quantity. An addendum will be created. | Fred Schunke | 2 | 2018-10-31 13:01 | 2018-11-05 14:59
20181113 | 20181113019 | 19 | Item #42 Shaping Shoulders | Item #42 Shaping Shoulders â€“ This item appears to cover cutting out the 2â€™ of gravel after milling, placing the recycled millings, and shaping the shoulder again prior to shouldering. Is all this incidental to the shaping shoulders? Will placing of the millings be paid separately under a different item? | Item #42 Shaping Shoulders is intended to include the cutting out the 2â€™ of gravel after milling and shaping the shoulder again prior to shouldering. Placing the Millings for the CIR Paving process was intended to be included under Item #306 Cold-In-Place Recycling (CIR) Pavement Partial Depth (SY). | Fred Schunke | 3 | 2018-10-31 13:03 | 2018-11-05 15:02
20181113 | 20181113021 | 21 | Sawing Quantity for Curb Repairs | Will a quantity of Sawing Asphalt be added for the miscellaneous curb & gutter repair and inlet reconditioning? | The current plans include both a sawing asphalt and a sawing concrete item. The miscellaneous curb & gutter repair and inlet reconditioning generally occurs in areas where the pavement will be pulverized and overlayed. Saw cuts will not typically be required in these areas. Payment of any additional sawcuts would be address per standard specification. | Mike Coleman | 1 | 2018-10-31 14:59 | 2018-11-05 07:43
20181113 | 20181113030 | 30 | CAD Files | Can the department please provide the CAD files for all stages of work. | The CAD files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20181113030/ | Mike Coleman | 1 | 2018-11-01 09:36 | 2018-11-05 07:34
20181113 | 20181113037 | 37 | Pavement Markings | It appears that the plan includes same day epoxy markings for the surface layer prior to the rumble strip operation, but it does not include the epoxy application for after the rumbles. Will an addendum be issued to cover this item or are you planning on using the same day item for both applications? Thank you. | The miscellaneous quantities for temporary marking line have been updated and notes added clarifying that temporary marking line is for lower and upper pavement layer centerlines, and same day marking is for marking centerline after rumble strips are placed. This was part of Addendum #01 that was posted on 11/05/18. | Mike Coleman | 8 | 2018-11-01 13:06 | 2018-11-06 06:42
20181113 | 20181113025 | 25 | Culvert Pipe Transition Cut | Is material from the Pipe transition cut intended to be reused as backfill of the transition cut? If not, what to be used as backfill of transition and how is it paid | See plan detail on sheet 22 â€¢Detail identifies trench backfill locations â€“ second symbol in list of symbols â€¢Trench backfill and foundation backfill are identified on the detail by symbol across the transition â€¢See third note listed on detail: â€œTrench Backfill and Foundation backfill used in the Transition cut area is incidental to pipe installation (per STD Spec 520) â€¢Payment incidental to pipe installation â€¢520.2.5.3 identifies what is acceptable for trench back fill | Jill Fehrman | 2 | 2018-11-01 17:18 | 2018-11-02 15:27
20181113 | 20181113023 | 23 | Catch Basin Sump Depth | Is there a specific depth sump for the catch basins? Should we estimate the sump depths from the storm sewer profile sheets? | Catch basin sump depth is based on the following Standard Detail Drawings: â€¢ 08A08-02 CATCH BASINS 3-FT, 4-FT, 5-FT AND 6-FT DIAMETER â€¢ 08A09-02 CATCH BASINS 2X3-FT AND 2.5X3-FT Based on the details, sump depth is 2-feet. | Mike Coleman | 4 | 2018-11-02 13:03 | 2018-11-05 07:37
20181113 | 20181113020 | 20 | Waterway Buoys | The plan sheet, Misc quantities shows the waterway buoys but the proposal bid item schedule does not show an item there and why are waterway buoys considered traffic control? | To aid in navigation of boat traffic through the project site, waterway buoys are required per the Wisconsin Department of Natural Resources. A separate bid item is not in the plans for buoys due to the following in the WisDOT Standard Specifications, Section 107.19 Construction Over or Adjacent to Navigable Waters: Per standard specification 107.19 (8) During construction, provide temporary lights, waterway markers, other devices, or combination thereof as the governmental authority specifies and requires. Per standard specification 107.19 (9) All expenses the contractor incurs to maintain navigation are incidental to the contract cost. | Fred Schunke | 3 | 2018-11-02 15:33 | 2018-11-05 11:19
20181113 | 20181113020 | 20 | Utilities | SPV Article 6 states that the Manitowoc Public Utilities communications line will be relocated from the current location to the west right-of-way across the Manitowoc River. Is this from the pole at approx. STA 54+85, 28 feet LT, to the pole at STA 60+35, 88 feet LT? This alignment would conflict with cranes on the south and north causeways. The current alignment will conflict as well. | The Manitowoc Public Utilities communication line will be completely moved to the west right of way line. The west right of way line is approximately 85 to 90 feet west of the centerline of the new structure. Due to the location of the communication line it was anticipated that cranes would not be able to spin 360 degrees while on the anticipated causeway location. Spinning to the west then north would be restricted on the anticipated causeway, but unrestricted access would still remain to spin from east to north on the anticipated causeway. Exact causeway location and crane placement will be based on contactor operations within the communication line restriction. | Fred Schunke | 4 | 2018-11-02 15:49 | 2018-11-05 12:45
20181113 | 20181113005 | 5 | Pre-bore Hole Diameter question | Article 45 page 97 550.2.5 states the pre-bore hole size as 30 inch diameter. Plan sheet 889 & 936 show 30 inch diameter holes in the west abutment note in the elevation view. Plan sheets 898, 904, 945 and 951 all show pre-bore pile detail with a 34" diameter shaft. Please confirm the shaft diameter. If 34 inch is correct, would a 36 inch shaft be an acceptable alternate. | The pre-bore hole size shall be 34-inch diameter. Pages 889 and 932 of the plans and Article 45 will be updated accordingly. Only a 34-inch diameter hole will be allowed. | Fred Schunke | 9 | 2018-11-05 10:03 | 2018-11-05 12:31
20181113 | 20181113005 | 5 | Project Coordination | Section # 3 , Part D of the special provisions refers to coordination with project 1206-07-75. With the completion date for that project being July 31, 2019, is it to be assumed that any overlapping work zones will not be available until after that date? | Overlapping work zones with project 1206-07-75 will be available with proper coordination with the 1206-07-75 contractor and approved the project engineer as stated in the special provisions. Article 3, Section D of the special provisions references section 105.5.2 of the standard specifications which requires coordination with other contractors. In addition the special provision describes work areas that shall be expected adjacent to, overlapping, and coinciding with project 1206-07-75 in 2019. The special provision also requires attending the weekly progress meetings for project 1206-07-75 to coordinate construction schedules with project 1206-08-77. | Mike Coleman | 10 | 2018-11-05 11:54 | 2018-11-06 06:36
20181113 | 20181113025 | 25 | Earthwork Summary | Are Computer Earthwork Data sheets available? Sheet 198 of misc quantities do not provide enough detailed information. | An addenda for the project was submitted for processing to BPD on Tuesday afternoon that provides the earthwork sheets that were missing. | Fred Schunke | 3 | 2018-11-05 12:36 | 2018-11-07 10:21
20181113 | 20181113022 | 22 | Line 60 Reheating HMA Longitudinal Joints | With the castings located on the centerline and in the middle of the paver pass, the paver must pickup the screed. Doing this will also pickup the joint heater and not heat the joints as designed or specified. The joint heater also cannot be picked up high enough to go over any centerline castings so the paver must drive around the structure again not heating the joint as specified. Can this line item be eliminated? | Addendum #1 was just submitted to remove item Reheating HMA Longitudinal Joints. | Fred Schunke | 1 | 2018-11-05 13:40 | 2018-11-07 15:15
20181113 | 20181113037 | 37 | Pavement Markings | Thank you for your response to the question regarding markings after the rumbles. However, doubling the temporary paint quantity poses an issue of placing epoxy on top of paint seeing as some of the temporary paint, if placed prior to rumbles, would still remain and have epoxy placed over it. This would pose a warranty issue. As with other projects, their should be temporary or same day epoxy placed on the surface prior to rumbles and epoxy or same day epoxy placed after the rumbles. Will another addendum be issued to correct this? Thank you. | In reference to bid item 649.0105 â€“ Temporary Marking Line Paint 4-inch, specification section 649.5(2) states, â€œPayment for the Temporary Marking bid items is full compensation for providing the marking or marker; for maintaining, and for removing the marking or marker.â€ In lieu of installing an upper temporary marking in paint and removing it prior to the final same-day application of epoxy the Contractor may elect to install an upper temporary marking in epoxy or use temporary raised pavement markers. Payment for these options shall be made under item 649.0105. No addendum will be issued. | Mike Coleman | 9 | 2018-11-05 16:29 | 2018-11-06 12:11
20181113 | 20181113026 | 26 | Repointing stone masonry | See Sheet 69, 2 of 3 on the structure plans for B-35-2. In the general notes regarding the repointing it reads...."Repointing stone masonry required north and south vertical faces and underside of arches." There is a SIGNIFICANT cost difference between repointing the vertical faces and repointing the underside of the arches. A separate pay item and approximate quantity for repointing the underside of the arches would be in the departments best interest. Will that item be added? | An additional item will not be added. The Repointing Stone Masonry quantities were based on a field review that was not separated by specific locations. The project item was based on similar stone arch bridges where repointing was required at varying surface locations under a single bid item. Note: This item was used on P-40-0573 and P-40-700 and was completed under a single item. | Fred Schunke | 1 | 2018-11-05 17:05 | 2018-11-07 10:39
20181113 | 20181113021 | 21 | Contract Time | Due to the amount of water at the pipes located at sta 166+75 and sta 171+62, could the contract time be changed to 25 days and the full closure of CTH X changed from 7 days to 12 days? | Both Calumet County and the NE Region had no concerns providing an additional 5 days. An addendum will be issued to add the additional time. | Mike Coleman | 2 | 2018-11-05 17:24 | 2018-11-06 12:06
20181113 | 20181113022 | 22 | Request for Misc Quantities tables | Can miscellaneous quantity tables be provided in EXCEL format for this project? | Miscellaneous quantity tables cannot be provided in EXCEL format. | Mike Coleman | 2 | 2018-11-06 08:49 | 2018-11-06 14:30
20181113 | 20181113014 | 14 | Pier Access | Can a causeway (road) built of rock be constructed in the Yahara River? This road would be used to access the pier location for pier removal, pile driving & pier construction. Road would be removed after pier is complete. | No work shall be performed in waters of the state without prior concurrence of DNR and the U.S. Army Corps of Engineers. Accordingly, a proposed causeway not shown in the plans must be included in the ECIP, and may or may not be permitted. | Mike Coleman | 1 | 2018-11-06 08:51 | 2018-11-06 12:04
20181113 | 20181113023 | 23 | Request for Misc Quantities Tables | Can miscellaneous quantity tables be provided in EXCEL format for this project? | Miscellaneous quantity tables in excel format are not available for this project. | Mike Coleman | 5 | 2018-11-06 08:51 | 2018-11-06 09:53
20181113 | 20181113016 | 16 | soil borings | Are there soil borings available for this project? | No soil borings were completed as part of this project (due to the limited excavation work). | Mike Coleman | 1 | 2018-11-06 08:52 | 2018-11-06 09:13
20181113 | 20181113037 | 37 | Missing Signs | For the Sign summaries on page 35-36, the summary isn't showing over 100 sf of Item 637.2210 and 40 sf for Item 637.2230. Where is there a missing page? | The sign quantity tables on pages 34 and 35 contain a summation error that affects all the columns, as well as discrepancies between signing plan and tabulated values in the miscellaneous quantities. The correct quantities are as follows: 637.2210 452.75 SF 637.2230 111.00 SF 634.0614 37 EA 634.0616 44 EA 638.2602 63 EA 638.3000 57 EA An addenda will be issued with revised plan sheets. | Mike Coleman | 10 | 2018-11-06 10:08 | 2018-11-07 06:30
20181113 | 20181113024 | 24 | Concrete Pavement Rumble Strips | Are we removing the existing concrete rumble strips before the milling & HMA or just prior to pouring the new concrete pavement rumble strips (after HMA)? If we remove them prior to milling & HMA I assume we would have to patch them in with temporary asphalt. There is no temp AS item. If we remove them just prior to pouring new concrete pavement they will be sticking up 2" higher than milled surface after milling until HMA is paved. Are we going to temporarily ramp them with asphalt after milling or just put up bump signs? What is the plan for traffic while the concrete pavement is curing or can we put traffic on the new concrete by end of day? | There are no existing concrete intersection rumble strips, they are a new addition per the request of the NWR maintenance staff. The existing rumble strips are asphalt and therefore can be milled with the rest of the mainline. | Fred Schunke | 1 | 2018-11-06 11:39 | 2018-11-08 08:29
20181113 | 20181113037 | 37 | Causeway | Will the contractor be allowed to build a causeway to provide access to construct the piers in the river and set girders? | Please refer to SPV Article #15 and standard specification section 107.19. If the proper permits and approval from the governmental authority are obtained a causeway may be allowed. The Contractor is responsible to obtain all approvals and permits prior to construction. No additional compensation or contract time will be provided. | Mike Coleman | 11 | 2018-11-06 12:04 | 2018-11-06 12:59
20181113 | 20181113016 | 16 | storm sewer | Will full night freeway closures be permitted for the installation of the 3 each 24" culvert crossing installations/removals? | Per the plans and special provisions, only single lane closures will be permitted for installation of the culvert crossings. Those crossings would be constructed in halves. | Mike Coleman | 2 | 2018-11-06 12:41 | 2018-11-06 13:31
20181113 | 20181113018 | 18 | Article 3 Wisconsin Inclusion Plan | "All Bidders should submit a Wisconsin Utilization Plan at the time of bid demonstrating how s/he will achieve the inclusion objectives for targeted businesses and workforce participants. The submission should comply with the Wisconsin Utilization Plan." - If this in not submitted at the time of Bid, will your bid be rejected? - What if you don't make the goals, will your bid be rejected? | WisDOT strongly encourages bidders to submit an Inclusion Plan at the time of bid. Submittal of an Inclusion plan is not a condition of award, but will provide desired documentation of the bidderâ€™s outreach to targeted businesses and work force participants. | Mike Coleman | 5 | 2018-11-06 13:49 | 2018-11-06 14:29
20181113 | 20181113020 | 20 | Archer St./CTH R Connection | Addendum #1 has removed the June 3rd start restriction but did not address the next paragraph in the Prosecution & Progress provision which states; 'Work on the removal of Archer St. connection to CTH R and the connection of Archer St. to North Rapids Road must be completed before the reconstruction of CTH R'. Will this provision be revised to allow winter or early spring work on the bridge prior the reconstruction of this intersection? | The provision about removing the connection of Archer Street to CTH R only pertains to the roadway approach reconstruction, not the bridge replacement. Due to the removal of the connection of Archer Street to CTH R, the roadway for Archer Street needs to be reconstructed before reconstruction can take place on CTH R. This is to allow access to the houses along N. Rapids Roads using the a temporary connection from CTH R. | Fred Schunke | 5 | 2018-11-06 14:40 | 2018-11-07 09:30
20181113 | 20181113020 | 20 | WPS Gas Line - Pier #1 conflict | Based on Plan Detail sheets (pg. 8 of the plan), the existing gas line appears to lie directly under the Pier 1 footing. Per the Utilities special provision, this line is not anticipated to be moved until July 20th, 2019. This date seems to conflict with addenda #1 which allows work on the project to start earlier. The 90 day restriction on causeways require them to be removed by August 12, which would only leave 3 weeks to install/remove cofferdam, drive piling, construct pier 1 and set span 1 and 2 girders. This is not feasible. | Wisconsin Public Service Gas per the special provision should have had it completed by July 20, 2018, not 2019 as you have noted. We followed up with WPS and have found they are behind in their relocation, but will be completed with it by December 31, 2018. Therefore construction in 2019 will not be impacted. | Fred Schunke | 6 | 2018-11-06 14:58 | 2018-11-07 10:19
20181113 | 20181113026 | 26 | Traffic Control Project 6320-08-62, B-71-0018, STH 73 | Special provisions sheet 3/26 & 4/26 state that for this project the contractor must maintain minimum of 2 lanes of traffic in each direction and provide temporary pedestrian access for duration of project. There is no mention of temporary lane closures. What was the intent for delivery of materials, removal of debris, setting up of debris containment. Can daily flagged temporary lane closures allowing 1 lane of traffic through the construction zone be added as an option. | Temporary traffic control for lane closure with flagging operation following the standard details contained in the plan would be allowed. | Fred Schunke | 2 | 2018-11-06 15:07 | 2018-11-08 07:45
20181113 | 20181113025 | 25 | Possible rock at surface for guardrail installation on sheet 30 | From station 206+15 LT - 207+37 LT, there is a note that says possible rock near surface. We may need to drill to install guardrail. My question is, can this be broken out into its own bid item, so that everyone involved is protected incase there isn't a need to drill? | Please bid with the information and materials as provided â€“ no additional bid item will be added. | Fred Schunke | 4 | 2018-11-06 15:33 | 2018-11-07 14:58
20181113 | 20181113020 | 20 | Structural Approach Concrete Quantities | What items are included in the structural approach concrete quantities? Assuming sleeper slab, approach slab and 2 runs for 32SS parapet I am coming up 20cy short for each on totals shown in the Estimated Quantities table. | We have confirmed our quantity calculations for the Concrete Structural Approach Slabs. The quantities include the footing, approach slab, and parapets. Structural Approach Slab is for the roadway only and does not extend to the trail. | Fred Schunke | 7 | 2018-11-07 07:54 | 2018-11-07 10:40
20181113 | 20181113026 | 26 | Epoxy Injection means & methods Intent. Structure B-35-2 | The estimated quantities show 25 LF of epoxy injection at both pier 1 & 2. In the general notes It states "Repair cracks in "abutment" or pier footings using epoxy injection crack repair at locations approved by the engineer". The observed water elevation on the general plan sheet is (or appears to be) above the top of the footings. There are file pictures that show the top of the footings at the piers above water during possibly low or normal water stage. Is it the intent that the epoxy injection be determined & accomplished during a water stage when the tops of the footings are above water? OR will the contractor need to cofferdam and dewater the repair areas or use underwater forces (IE:divers) to accomplish the repairs. How will the repair locations be determined & documented prior to the repairs and who will be responsible for that? | The epoxy injection shall be placed on surfaces and in conditions based on the specifications and manufactures recommendations. The methods for placing the material are dependent upon the contractorsâ€™ operations and are incidental to the item. The engineer in the field will document improvements. | Fred Schunke | 3 | 2018-11-07 10:35 | 2018-11-08 14:35
20181113 | 20181113021 | 21 | Landmark reference monuments | My question is in regards to line item number 64. Landmark reference monuments. Per page 48 of the plans, will the monuments need to be concrete or can the aluminum monuments be used? | Standard Detail Drawing 16A 1-7 Landmark Reference Monuments and Covers, General Notes state: â€œMonument shall be cast-in-place concrete unless Precast concrete or aluminum monuments are specified in the contract or permitted by the engineer.â€ Per this note, precast concrete or aluminum monuments are not allowed. | Fred Schunke | 3 | 2018-11-07 15:01 | 2018-11-08 07:49
20181113 | 20181113026 | 26 | Error or missing quantities | 1.) On structure B-71-18 there is 6 SY of Joint Repair but 5 "CY" of Concrete masonry deck repair {the concrete going back in} see sheet 73 or 3 of 4 section C-C thru slab. Is there more deck repair elsewhere? or is this quantity incorrect? 2.) On structure B-21-15 there is 49 SY of Joint repair but no quantity listed for Concrete masonry deck repair { the concrete going back in} How is the replacement concrete paid for? 3.)On structure B-21-15 sheet 66 or 4 of 5 the S505 rebar listed as "Adhesive Anchor No.5 bar" - how is the drilling and adhesive paid for? This is typically a separate pay item? | An addenda is being prepared based upon the responses below. 1.) The quantity is correct. 2.) Concrete Masonry Overlay Deck should be included. 17 CY 3.) Adhesive Anchor No. 5 Bar should be included. 112 EACH | Fred Schunke | 4 | 2018-11-07 15:04 | 2018-11-08 15:09
20181113 | 20181113018 | 18 | Borrow / Embankment | Will payment for erosion control, fertilizing and seeding for off site borrow pits be paid for as in 628.5.1 since embankment replaces the borrow item? | Each item listed will be paid for separately. | Fred Schunke | 6 | 2018-11-07 16:29 | 2018-11-09 08:20
20181113 | 20181113030 | 30 | Temporary Structure | What is the required span length for the temporary structure? | The temporary structure design is to be provided by the contractor per Section 526 of the standard specifications. Note also hydraulic data for a temporary structure is available and provided on the structure plans for B-55-257. | Fred Schunke | 2 | 2018-11-07 17:44 | 2018-11-09 08:17
20181113 | 20181113025 | 25 | Temp Signals | Is it the intent to complete the 3 culverts requiring temp traffic signals to be done consecutively or concurrently? | The intent is they are worked on consecutively -- one at a time. After one is completed then move to the next. The work was organized like that so the other two remain open to accommodate flow between the Fox River and the adjacent wetlands, if necessary. The last paragraph in Prosecution and Progress in the Special Provisions addresses this for the culvert work between CTH A and South Street. | Fred Schunke | 5 | 2018-11-07 20:14 | 2018-11-08 12:11
20181113 | 20181113025 | 25 | Possible rock at surface for guardrail installation | As a follow up question, what if there is 700 feet of rock at the surface rather than the 150', who would be responsible for paying for this in this situation? The way the plan shows I will figure for the 150 feet but if there is more, will the state compensate me for the extra footage of rock drilling for the guardrail? The way its called out in the plan the state nor the contractor isn't protected. | There is processes in the specification book â€“ for example section 104 -- to deal with changed conditions, if appropriate, that addresses both the state and the contractor interests. In this instance, we observed rock in the area identified on the plans and wanted to alert the contractor that rock may exist in this area so they could adjust their bidding accordingly. This is a location where we are replacing an end terminal and changing the beam guard location slightly from the existing installation. Standard Detail Drawing 14 B â€“ 42 5a note 3 addresses what is needed to be done if rock is encountered for post installation. | Fred Schunke | 6 | 2018-11-07 20:45 | 2018-11-08 12:10
20181113 | 20181113020 | 20 | Utility pole at the new CTH R bridge | Can the utility pole at the Northwest corner of the New CTH R bridge structure be held during construction and guy wires be removed, to move equipment in and out of this area? | The utility pole at the northwest corner of the New CTH R structure cannot be held and guys cannot be removed, the tension on overhead line is too great to be held with a pole truck. | Fred Schunke | 8 | 2018-11-08 07:37 | 2018-11-08 07:38
20181113 | 20181113006 | 6 | Clearing, Grubbing, and Restoration at Parcel 2 | 1. For Parcel 2, does the Removing Buildings bid item include clearing and grubbing of the trees on the parcel, and restoration items (seed, mulch, fertilizer, e-mat)? 2. Also is there a well on the property, or is it hooked up to the municipal water system? | 1. Tree clearing and grubbing is not expected to occur on this parcel. Any tree clearing needed in order to remove the building would be considered incidental to the Lump Sum â€œRemoving Buildingsâ€ bid item. Restoration items are included in the bid items shown in the Misc. Quantities sheets and will be paid for under their respective bid items. 2. According to municipal records, the building is connected to the municipal water system. | Fred Schunke | 3 | 2018-11-08 08:26 | 2018-11-08 08:26
20181113 | 20181113005 | 5 | Nesbitt Road Closure | We have heard that Nesbitt Road is going to be closed for this project. We would like to confirm this as this will affect our haul routes. | No closures will occur on Nesbitt Road under this project with the exception that the contractor may close the McKee Road and Nesbitt Road intersection for up to two days as specified in the Prosecution and Progress. As stated in Other Contracts in the special Provisions the City of Fitchburg is proposing the reconstruction of the Nesbitt Road and Fitchrona Road intersection in 2019 under a separate construction contract. Contact the City to obtain the latest information on their plans. | Fred Schunke | 11 | 2018-11-08 08:29 | 2018-11-09 08:31
20181113 | 20181113023 | 23 | Landmark reference monuments | My question is in regards to line item number 132. Landmark reference monuments. Per the SDDâ€™s in the plan, will the monuments need to be concrete or can the aluminum monuments be used? | Standard Detail Drawing 16A 1-7 Landmark Reference Monuments and Covers, General Notes state: â€œMonument shall be cast-in-place concrete unless Precast concrete or aluminum monuments are specified in the contract or permitted by the engineer.â€ Per this note, precast concrete or aluminum monuments are not allowed. | Fred Schunke | 6 | 2018-11-08 09:40 | 2018-11-08 09:40
20181113 | 20181113018 | 18 | Culvert Pipe Trench Depth | Does the "Detail for Installation of Pipes" in the Construction Details only apply to culvert pipes, and how they can determine the depth of the vertical section of the trench (immediately below the subgrade; so they know how far up the 2:1 extends)? | This detail applies only to culvert pipes. Due to the shallow nature of culvert pipes on the project, the vertical depth is zero. | Fred Schunke | 7 | 2018-11-08 12:17 | 2018-11-08 12:18
20181113 | 20181113030 | 30 | IRI Ride | Will the 9â€ HMA Pavement on the east end of both the WB & EB lanes be considered part of the IRI ride? The HMA pavement section itself is only 350 ft +/- long on each side. | For the Incentive IRI Ride bid item, the pavement sections considered for inclusion will follow section 440 of the standard specifications. | Fred Schunke | 3 | 2018-11-08 14:24 | 2018-11-09 08:22
20181113 | 20181113030 | 30 | Asphaltic Surface Temporary | The plan specifies the HMA mix type, Asphalt Cement type and lift thicknesses for the Asphaltic Surface Temporary. Is there a reason for this? | The Asphaltic Surface Temporary needs to last two construction seasons and carry a higher volume of interstate traffic. Therefore, specific temporary pavement is included in the plan. | Fred Schunke | 4 | 2018-11-08 14:26 | 2018-11-09 08:19
20181113 | 20181113030 | 30 | Permanent Asphalt Shoulders | On the permanent asphalt shoulders the plan calls for a 4MT58-34H. Typically we have used a 4LT on the shoulders with a 58-34S | The HMA mixture for permanent shoulders shown on the plan is correct. | Fred Schunke | 5 | 2018-11-08 14:28 | 2018-11-09 08:19
20181113 | 20181113018 | 18 | Underdrain | The typical sections show underdrain in the corner of the roadway of the excavation in both lanes in the median and outside. Note 6 says to place it 50' upstream of the inlets. Which way is the correct way to install? Entire job or just 50' upstream of the inlets? Either way, I believe the quantity may be incorrect. | The intent of pipe underdrain is to be placed for 50â€™ upstream of each inlet, between flanking inlets and not the entire length of the project. The estimated length of pipe underdrain was based on the number of inlet covers and low spots. The installed pipe underdrain may be little less than the estimated quantity. | Fred Schunke | 8 | 2018-11-08 15:43 | 2018-11-09 09:29
20181113 | 20181113025 | 25 | Intent on shoulders | Referencing pages 8-11, is the intent to mill the asphalt shoulders full depth and then remove the base aggregate to the bottom of the pulverized (6") and the bottom of the CIP (3-1/4" after milling of 1-3/4")? | Yes. The goal is to construct the new paved shoulder on uniform pulverized/CIP material and to do that the shoulder material needs to be removed both asphalt and gravel to the same depth as pulverized/CIP material. | Jill Fehrman | 7 | 2018-11-08 17:13 | 2018-11-09 14:47
20181113 | 20181113025 | 25 | Vertical pavement option? | Prosecution and progress states â€œPlan and execute daily work operations for milling, pulverizing, and paving so STH 49 mainline lanes at center line in each direction match at the end of the work day to avoid a vertical pavement edge parallel to traffic flowâ€. Due to a notched wedge being used per spec 450.3.2.8 (3) can the mainline lanes at centerline not match at the end of the days paving? | Region work zone traffic control preference is to have pavement match up at the end of each day. Please bid as Prosecution and Progress indicates. | Jill Fehrman | 8 | 2018-11-08 17:24 | 2018-11-09 14:50
20181113 | 20181113025 | 25 | Cross section for Sta 79+24 - 87+00 | Sheet 59 gives verbiage for climbing / taper construction, could we get a cross sections for the area from Sta 79+24 to Sta 87+00. | STH 49 has wide shoulders. The work these notes refer to are shoulder only work and cross sections would not be necessary. Both notes relate to adjustment in the climbing lane tapers â€“ which have been lengthened â€“ and is contained on the existing shoulders. | Jill Fehrman | 9 | 2018-11-08 17:24 | 2018-11-09 14:55
20181113 | 20181113025 | 25 | Flagging Distance | Due to the constructability of mill / pulverize/ grade and pave and also the mill / cold in place / and pave, could the maximum flagging distance be increased to 4 miles instead of 2? | This is a region work zone traffic control consideration. Please bid with the 2 mile maximum flagging distance as indicated in the Prosecution and Progress. | Jill Fehrman | 10 | 2018-11-08 17:25 | 2018-11-09 14:59
20181113 | 20181113025 | 25 | Rail in Widening Areas | The guardrail areas addressed in sheets 13 and 14, appears to need to be widened prior to the mill / pulverize and mill /CIR. Is the intention for the guardrail to be placed back after widening and if it needs to be adjusted after pavement is placed, then an item for adjusting beamguard will be needed? |  |  | 11 | 2018-11-08 17:26
20181113 | 20181113018 | 18 | Undistributed Asphalt Surface | What is the intent of the undistributed quantity in the Asphaltic Surface (#465.0105) bid item? | The existing CTH KR roadway will remain open to traffic while we construct the westbound lanes, and the Asphaltic Surface will be used as needed to maintain the existing roadway. The undistributed quantity is intended for that work. | Fred Schunke | 9 | 2018-11-09 08:24 | 2018-11-09 08:25
20181113 | 20181113025 | 25 | Base Aggregate Quantties | It seems that Base Aggregate Dense table in the plan only shows quantities through STA 330+27, and locations of the pipes at STA 378, 389 and 398 are missing along with other pipe locations to the south. Could updates table be provided? |  |  | 12 | 2018-11-09 14:15