## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20191112 | 20191112001 | 1 | Cad files | Can you please make the cad files available for this project? Thank you. | The metadata files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112001/ | Mike Coleman | 1 | 2019-10-16 09:51 | 2019-10-23 08:25
20191112 | 20191112001 | 1 | Proposal 1 - Temporary Barrier Pinned | In miscellaneous quantities it states that stage two barrier is pinned. Is that referring to the anchoring barrier on bridge or the 14,749 of installed? | For Stage 2, both the 14,749 feet of installed barrier and the barrier on the existing bridge should be pinned. | Mike Coleman | 2 | 2019-11-06 11:09 | 2019-11-11 08:06
20191112 | 20191112002 | 2 | CAD Files | Could you please provide the CAD Files for this project? Thank you | The files can be found in the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112002/ | Mike Coleman | 1 | 2019-10-14 09:54 | 2019-10-16 14:00
20191112 | 20191112002 | 2 | Hillside Drive Road Closure | State project ID 1067-02-74 Hillside Dr. I cannot find any reference to the closure status of Hillside Dr itself during construction. Please point me in the right direction or advise on status | The intent is to close Hillside Dr. during construction. | Mike Coleman | 2 | 2019-10-15 16:26 | 2019-10-16 09:43
20191112 | 20191112002 | 2 | 204.0110 Removing Asphaltic Surface | In Miscellaneous quantities plan sht. 99, Removing Asphaltic Surface, lists CTH D and CTH X. Shouldn't the asphalt on Hillside Drive be included? Please Clarify. | No, the removal of the asphaltic surface on Hillside Dr is covered as part of excavation common. | Mike Coleman | 3 | 2019-10-17 07:59 | 2019-10-17 08:33
20191112 | 20191112002 | 2 | 204.0110 Removing Asphaltic Surface | In Miscellaneous quantities plan sht. 99, Removing Asphaltic Surface, lists CTH D and CTH X. Shouldn't the asphalt on Hillside Drive be included? Please Clarify. | No, the removal of the asphaltic surface on Hillside Dr is covered as part of excavation common. | Mike Coleman | 4 | 2019-10-17 08:00 | 2019-10-17 08:33
20191112 | 20191112002 | 2 | Hillside Dr Guardrail | The typical section for Hillside Dr shows an approximate widening in the guardrail of 1-foot, with a guardrail block depth of an extra 4-inches. Does the Department feel that the footings for the bridge caissons will potentially interfere with post placement? Will this fall under "contractor risk" if the existing structure interferes with guardrail post placement? | There are two issues here which are as follows: Structure B-28-31 will be removed. On sheets 274 and 275 there is a special note that indicates the existing footings should be removed. We anticipate that if the existing footings are not removed, they would interfere with the new guardrail posts. To reinforce this the std spec indicates: 104.7 Removing Structures and Obstructions (1) Remove from within the roadway all or parts of existing culverts, bridges, and miscellaneous structures designated for replacement or that interfere with new construction. B-28-30 (Existing structure to remain) â€“ there is a potential the new guardrail posts could interfere with the existing footings. To avoid this potential interference, we will be revising the plan to include MGS long span via an addendum. | Fred Schunke | 5 | 2019-10-21 11:43 | 2019-10-25 15:11
20191112 | 20191112002 | 2 | Pavement Markings | With a completion date of 11-20-20 just wondering why cold weather markings are not considered? Is there a possibility for this item to be included? | Cold weather marking should have been considered. We will be adding the item via an addendum next week. | Fred Schunke | 6 | 2019-10-21 15:19 | 2019-10-25 15:08
20191112 | 20191112002 | 2 | Please clarify article 16 of the Special Provisons page 13 of 21 | Article 16 is titled "Debris Containment Structure B-28-25 & B-28-27." The first paragraph of section C third sentence states "Do not start work over Johnson Creek until engineer approves debris containment plan." Structure B-28-25 is CTH X over IH 94 and B-28-27 is CTH D over IH 94. Please clarify. Debris containment for the Johnson creek structures is covered under article 17, Correct? | Article 16 is for Structures B-28-25 & B-28-27 which are over IH 94. Johnson Creek is a typo and should be IH 94. "Do not start work over IH 94 until engineer approves debris containment plan." A future addendum will clarify this. | Mike Coleman | 7 | 2019-10-28 08:52 | 2019-10-28 10:01
20191112 | 20191112003 | 3 | Marking Line Replace Wet Reflective Epoxy Spec | Line items 0200 and 0204 are for replacing wet reflective epoxy. The spec calls for the removal of any loose markings, and replacing the marking without painting over any black if there is contrast markings. Should this bid item be Replace Contrast Wet Reflective markings? Will we have to remove the black markings if there are any loose contrast markings? Or are we just replacing them with White and Yellow Wet Reflective Epoxy, and no black? | The items are correct. The intention is to replace the white and yellow markings and leave the black in. | Mike Coleman | 1 | 2019-10-15 10:02 | 2019-10-21 07:36
20191112 | 20191112003 | 3 | Overhead Sign Supports S-32-70 & S-32-71 | In the drawing of the two structures it shows only one center pole that connects the two structures.Is this the correct design that the DOT wishes to use? | Yes, that is the correct design. See page 44 of the plans for an overhead view of the structures. | Mike Coleman | 2 | 2019-10-22 08:21 | 2019-10-22 12:13
20191112 | 20191112003 | 3 | Schedule | Can the design schedule be provided? | The time charts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112003/ | Mike Coleman | 3 | 2019-10-27 06:49 | 2019-10-28 13:49
20191112 | 20191112003 | 3 | Concrete Pavement | Will a concrete pavement be required for full width pavement over 300 feet in length? | There are no areas of concrete repair over 300 feet in length. | Mike Coleman | 4 | 2019-10-27 06:50 | 2019-10-29 06:32
20191112 | 20191112003 | 3 | 0326 - Pedestrian Push Buttons | I have only been able to locate 1 push button in the plans on sheet 66, intersection CTH SS & Crossing Meadows. Schedule of items shows quantity of 3. Can you please advise what intersections the other 2 buttons are located in the plans, and if they need left or right arrow R10-3E signs? | The other 2 push buttons are at the STH 157 and STH 16 intersection, pg 57. They are missing from the signal detail but are correct in the quantities. They are located at SB 14 & SB 22, both will need right arrow signs. The other push button at SB401 will need a left arrow sign. An addendum will be issued to clarify. | Mike Coleman | 5 | 2019-10-28 11:16 | 2019-10-29 06:43
20191112 | 20191112003 | 3 | 0324-Pedestrian Signal Face 16 inch | Which intersection location are the two 16 inch pedestrian signal faces going on? I do not see them marked in the plans. Thank you. | As stated in the MQ tables for CAT 0020, they go on SB3 and SB14 at the STH 16 and STH 157 intersection. However; they are not drawn on the signal detail on sheet 57. | Mike Coleman | 6 | 2019-10-29 09:57 | 2019-10-30 09:53
20191112 | 20191112003 | 3 | Schedule | Does the signal work need to fall into the days as outlined by the stages or is the staging more related to paving? | Signal work that does not require lane closures can be completed at any time prior to the stage being completed. Signal work requiring lane closures shall be completed during the defined stages. | Jill Fehrman | 7 | 2019-11-01 09:22 | 2019-11-04 09:30
20191112 | 20191112003 | 3 | Schedule | When will the notice to proceed be given for construction to start in the spring? | A start work notice will be issued per paragraph two of the Prosecution and Progress in the Special Provisions which states: Provide the start date to the engineer in writing within a month after executing the contract but at least 14 calendar days before the preconstruction conference. Upon approval, the engineer will issue the notice to proceed within ten calendar days before the approved start date. | Jill Fehrman | 8 | 2019-11-01 09:25 | 2019-11-05 09:44
20191112 | 20191112003 | 3 | Schedule | Are "days" as shown on the schedule calendar days or work days? | Days shown on the schedule are Working Days. | Jill Fehrman | 9 | 2019-11-01 09:26 | 2019-11-04 09:50
20191112 | 20191112003 | 3 | Signal Installation | We have a concern regarding concrete bases for completing work associated with large pole structures. Is temporary signal work required between the time when existing poles and signals are removed to create "space" for new pole bases? | One far indication must remain energized at all times, which is possible utilizing existing median signal heads. In most locations, existing mast arm signals can be maintained while building monotubes. Where existing mast arms cannot be maintained while completing monotube bases, the existing median signals must remain energized. | Jill Fehrman | 10 | 2019-11-01 09:30 | 2019-11-04 09:51
20191112 | 20191112003 | 3 | Signal Installation | Are DOT Electricians as part of their work, going to complete temp signal work at existing intersections wher the large 9,10, 3 concrete bases and structure are to be installed? | There should not be any additional temporary signal work not already outlined in the plan sheets. | Jill Fehrman | 11 | 2019-11-01 09:33 | 2019-11-04 09:52
20191112 | 20191112003 | 3 | Signal Installation | Would our electricians be working with DOT electricians to keep signals up and operating during construction? | Yes, DOT electricians will be available to coordinate with during construction. | Jill Fehrman | 12 | 2019-11-01 09:34 | 2019-11-04 09:53
20191112 | 20191112003 | 3 | Signal Installation | During construction are existing signals / new signals on the old or new control cabinet? | This depends on the method of construction. Once the new control cabinet base is installed, WisDOT can run signals out of the new cabinet if contractor desires. | Jill Fehrman | 13 | 2019-11-01 09:35 | 2019-11-04 09:54
20191112 | 20191112003 | 3 | Schedule | Is it possible to have DOT supplied signal structures type 9,10,13 along with associated mono tube arms delivered February before start of construction in the field? | The monotubes are not expected to be available by February. | Mike Coleman | 14 | 2019-11-01 09:38 | 2019-11-11 09:09
20191112 | 20191112003 | 3 | Concrete Pavement | This is not a question about concrete repair. It is a question about the concrete pavement. Will the concrete pavement area on CTH SS require a paver for areas over 300 feet in length? | There is nothing in the plans or specials that requires a paver on CTH SS. Refer to the Standard Specifications. | Mike Coleman | 15 | 2019-11-10 12:15 | 2019-11-11 09:10
20191112 | 20191112005 | 5 | MGS 3 QS | In the SDD 14B42-06b drawing, note 2 states that 25 feet of MGS 3 HS is required on either side of MGS 3 QS. Will this note be eliminated for this project? If not, will each system lengthen by 50 feet or will some of the MGS 3 QS be changed to MGS 3 HS? | An addendum will be issued to clarify. | Mike Coleman | 1 | 2019-10-21 11:50 | 2019-10-28 08:40
20191112 | 20191112005 | 5 | 0220 SPV.0195 Special 01. 16" x 2" select crushed material | Can this material be classified as WI DOT section 606.2.1 riprap stone, light riprap? | The material must conform to the specs called out in article 29 of the special provisions. | Mike Coleman | 2 | 2019-10-21 12:02 | 2019-10-22 09:52
20191112 | 20191112005 | 5 | Soil Borings | Are there soil borings available for this project | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112005/ | Jill Fehrman | 3 | 2019-11-04 16:52 | 2019-11-08 10:33
20191112 | 20191112006 | 6 | Cable Barrier Borings | Are there any borings available for the cable barrier locations? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112006/ If you have questions about the borings, please contact Melissa Markquart at (608) 799-0480 | Mike Coleman | 1 | 2019-10-29 14:22 | 2019-10-30 09:50
20191112 | 20191112006 | 6 | Removing Temporary Crossovers | Are there any estimated quantities associated with each of these removals? | There are not any estimated quantities for the crossover removals | Mike Coleman | 2 | 2019-11-05 09:50 | 2019-11-06 10:15
20191112 | 20191112007 | 7 | HMA Mix type for the project | Should the HMA mix type be changed from LT to MT mix? From our experience an LT mix will not handle the traffic loading on this Highway and it is my understanding that the new FDM 14.10.10 for HMA Pavement Design dated 8/15/19 Section 10.7.2 Traffic Category Selection has changed the ESALs for LT mix to a maximum of 1 million. This job has 1.7 million ESALs. | An addendum will be issued to change to MT mix. | Mike Coleman | 1 | 2019-10-11 09:22 | 2019-10-14 10:25
20191112 | 20191112007 | 7 | Geo-technical Reports | Could you please supply the geo-technical data used for design on this project. | The Geo-Technical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112007/ | Jill Fehrman | 2 | 2019-10-31 15:22 | 2019-11-08 13:04
20191112 | 20191112007 | 7 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112007/ | Mike Coleman | 3 | 2019-11-04 16:53 | 2019-11-05 10:45
20191112 | 20191112007 | 7 | Centerline Paving in Stage 2A | Plan sheet 136 shows stage 2A construction limits paving HMA 2' past centerline with a crown. I don't believe this is constructible and I definitely don't know how we would compact this 2'. Should this 2' of HMA that extends past centerline be constructed at the same slope as the adjacent lane and then saw or mill and remove the 2' prior to paving the match up lane? | In stage 2A the grading and paving operation should utilize the same slope across the entire limits including the 2â€™ east of the centerline. In stage 2B a sawcut should occur at the centerline of the roadway and remove the 2â€™ shelf built in stage 2A. A traffic control drum will be required adjacent to the northbound traffic lane. During the final grading and paving operation the contractor will need to take appropriate actions to keep traffic control drums adjacent to the northbound traffic lane while performing their operation. The contractor will be required to have a 2â€ drop or less adjacent to the northbound traffic lane after each day of work. | Mike Coleman | 4 | 2019-11-05 17:08 | 2019-11-07 16:43
20191112 | 20191112007 | 7 | Stage 4 Traffic Control | There is no Stage 4 traffic control plan in the plan set. What is the plan for traffic during construction of STH 82 and Tilmar Ave. intersections and turn lanes? | In Stage 4 all areas that are milled and paved (Existing HMA pavement on STH 80, Tilmar Ave, and STH 82) should utilize a moving operation with flaggers. The turning lanes and shoulders should utilize standard detail drawing 15D28 Traffic Control, Work on Shoulders or Parking Lane, Undivided. The installation of 24â€ culvert pipe and turning lane island should utilize traffic control drums and/or flagging operation with temporary lane closures on Tilmar Avenue and temporary turning lane closures on STH 82. | Mike Coleman | 5 | 2019-11-06 11:16 | 2019-11-07 09:25
20191112 | 20191112007 | 7 | 4' Polymer Coated Chain Link Fence | Looking at page 18 of the plans, there is a call out for Fence Special Split Rail in the same location as the 4' Polymer Coated Chain Link Fence. There is no bid item for the spit rail fence, so we are assuming that the note is wrong and that it should say 4' Polymer Coated Chain Link Fence instead of the Special Split Rail Fence. Can you please confirm? | You are correct. Fence Special Split Rail has been replaced with 4â€™ Polymer Coated Chain Link Fence. Note is wrong in plans and should be replaced with 4â€™ Polymer Coated Chain Link Fence. | Mike Coleman | 6 | 2019-11-06 14:23 | 2019-11-07 10:31
20191112 | 20191112008 | 8 | QC lab placement | why would the QC lab need to be placed within 30 miles of this project? There are only 5 or 6 tests to take for qmp. Wether the lab is 30 miles or 230 miles, the requirements for processing the sample doesn't change. I know of no other projects that this is required including interstate and major roadway projects that testing is done almost every day. This requirement makes no sense | The department will be issuing an emergency addenda to remove Article 10 of the Special Provisions which requires the QC Laboratory for base aggregate placement sampling to be within 30 miles of the project. All eligible bidders on the proposal will need to acknowledge the receipt of the addenda. | Jill Fehrman | 1 | 2019-11-08 09:56 | 2019-11-08 12:40
20191112 | 20191112008 | 8 | Special Provision #10 | Requesting clarification on the need for the requirement to have the QC Laboratory for base aggregate placement sampling to be within 30 miles of the project? | The department will be issuing an emergency addenda to remove Article 10 of the Special Provisions which requires the QC Laboratory for base aggregate placement sampling to be within 30 miles of the project. All eligible bidders on the proposal will need to acknowledge the receipt of the addenda. | Jill Fehrman | 2 | 2019-11-08 10:20 | 2019-11-08 12:42
20191112 | 20191112012 | 12 | Structure Backfill | Is the Structure Backfill for the area at the box culverts where attaching new beam guard? | Yes, it is to fill in after having attached new beam guard to the box culvert. | Mike Coleman | 1 | 2019-10-29 06:45 | 2019-10-29 06:45
20191112 | 20191112012 | 12 | traffic control restrictions | Since the road is going to be closed to through traffic can the window of time between milling/mill & Relay and mill & relay/HMA paving be increased? Having only 72 hours between milling and mill & relay, then an additional 72 hours between mill & relay and HMA lower layer will slow the pace of construction and add unnecessary cost. This is especially true for the less mobile mill and relay operation. Thanks. | There are concerns about the subgrade being exposed to excessive moisture, but with the road closed to through traffic, we would allow up to 5 days between the mill & relay and HMA lower layer being placed. The other restriction between milling and mill & relay is not necessary and was entered in error. | Mike Coleman | 2 | 2019-11-05 14:25 | 2019-11-07 09:20
20191112 | 20191112013 | 13 | Printing the plans | Is anyone else having trouble printing the plans for this project? Cannot print the second part of the job. SP 1000-54-73 | A glitch in the uploaded plan was discovered late yesterday. A new and printable version of the plan has been uploaded. Please let us know if you have further problems. | Mike Coleman | 1 | 2019-10-10 15:23 | 2019-10-11 06:38
20191112 | 20191112013 | 13 | SPV.0165 - Special 01. Fiber Wrap Reinforcing Structural | Sheet 315 (11 of 12 Structure B-40-392): Must the Fiber Wrap sheets be placed at 8" wide with 2" clear spacing between sheets or can wider strips (12" or 24") be installed? If wider strips are allowed to be installed, is a clear space between strips still required? | Alternate designs for strips larger than 8â€ wide may be presented to WisDOT for review and acceptance. The 2â€ clear spacing between strips must be held for future inspection purposes. | Mike Coleman | 2 | 2019-10-16 13:47 | 2019-10-17 07:38
20191112 | 20191112013 | 13 | Structure B-66-99 | Structure B-66-99 Can't be found in the plan set. Will a plan set be added by addendum? | The missing plan sheet (B-66-99) has been sent out via addendum and a full-size sheet (11x17) can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112013/ | Mike Coleman | 3 | 2019-10-21 16:36 | 2019-10-22 12:09
20191112 | 20191112013 | 13 | Bridge B-30-65 | According to proposal page 32 of 57, states 974 square feet of steel to be painted on Bridge B-30-65. Can you please confirm the amount of steel to be painted? This seems like a small amount of steel for the size of the bridge. Thank you. | B-30-65 is a weathering steel bridge. The intent is for the steel surfaces within the end 8 feet of the girder to be painted. The square footage area to be painted, as shown on the plans, is 1,211 SF (the calculation of this area is also at the tail end of the quantity exhibit for this structure). | Mike Coleman | 4 | 2019-10-28 12:36 | 2019-10-29 08:02
20191112 | 20191112013 | 13 | Fiber Wrap | In the special provisions it states that prepping (surface repair) to the areas that will have Fiber wrap is incidental to Fiber wrap. However in the plans it states that area is paid under the concrete surface repair bid item. How will the repair area be paid? | An addendum will be issued to clarify. | Mike Coleman | 5 | 2019-10-29 09:18 | 2019-11-05 10:53
20191112 | 20191112013 | 13 | HMA OVERLAY POLYMER-MODIFIED | Specification states that the Polymer modifier manufacturer personnel must be present at each location for this work, some of these bridges are only taking between 16 to 33 ton of mix so I wanted to clarify that they must be present for all 9 bridges | Yes the representative must be present at each location for this work. Each site may have different characteristics/contractor crews/etc that may require the expertise to be present. | Mike Coleman | 6 | 2019-10-30 15:18 | 2019-10-31 12:12
20191112 | 20191112015 | 15 | PWL Paving | 1) The misc quantities show 4000 tons of undistributed binder patching. How is the removals and other associated items paid for? How is the mix tested for density and volumetrics? 2) The 2â€ overlay on Pell Lake Drive is shown as PWL testing for density. However, surface is over a milled surface unlike the other PWL density surface items on the project. A new test strip would be needed but the tonnage for the area is below the 750 tons needed for a test strip. Would density testing on Pell Lake Drive be completed as department acceptance? 3) On Walworth St the binder is acceptance testing for density but PWL density testing for surface. Since all the work is done under flaggers and smaller scale of work compared to STH 12 mainline PWL, could all the density testing on Walworth St be completed under department acceptance? | Answers to these questions will be addressed in a future addendum: 1) The 4000 tons of undistributed binder patching will be removed from HMA Pavement 3 MT 58-28 S. The item Asphaltic Surface will be used for shoulder repair and will be a reduced quantity from the 4000 tons. PWL is not required for Asphaltic Surface. Removing Asphaltic Surface Milling quantity will be increased to include the removals at the shoulder repair locations. 2) PWL Mixture Use Table was updated so Pell Lake will be completed under department acceptance for density. 3) No, Walworth Street is also USH 12 mainline and density acceptance will be by Incentive Density PWL HMA Pavement 460.2005. Walworth Street was incorrectly shown in PWL table as Base Aggregate for underlying surface. Table will be updated to show Milled Existing HMA Surface for underlying surface. | Jill Fehrman | 1 | 2019-10-28 11:41 | 2019-11-05 09:18
20191112 | 20191112015 | 15 | HFST | It is unclear what phase the High Friction Surface Treatment will take place, will it be done with a single lane closure or full closure? Also will the rumble strips be milled in after the HFST is installed or will they be filled with the HFST? Thanks | HFST will be done under single lane closures. There will be an updated specification issued with an addendum which will limit the HFST to only the lane, not the shoulder, therefore there will not be an issue between which will be completed first HFST or rumble strips. | Mike Coleman | 2 | 2019-10-29 10:40 | 2019-11-07 09:24
20191112 | 20191112015 | 15 | Concrete Pavement 9 1/2" Doweled | Project ID 1080-19-70 Concrete Pavement 9 ½ inch doweled quantities for Station 448+64 to Station 456+46 and Station 492+05 to Station 499+40 do not equal the length between stations x 24â€™ (width shown in typical sections). Are the quantities shown in misc. quantities correct? | No, the quantities are not correct. An addendum will be submitted to update. | Mike Coleman | 3 | 2019-10-30 12:31 | 2019-10-30 12:33
20191112 | 20191112015 | 15 | Existing Pavements | The plan typical existing section states pavement is reinforced and rubblized. The proposed typical section claims continuously reinforced crack and seated pavement. These are not the same. Which is accurate? In in fact pavement is continuously reinforced, where is contractor supposed to assign costs for the removal of these areas? With the uncertainty of the Excavation Common quantity, it would seem more rational to have a Removing Pavement item to account for the labor intensive cost of this work, provided crack and seated continuously pavement is still considered rigid pavement due to the continuous reinforcement. If there is low moisture present in the subgrade of these replacement areas and the engineer determines breaker is not required as the plan states, will WisDOT allow a revision the Excavation Common price even though it wouldn't qualify under 104.2.2.4.3 Changed Quantities? Will WisDOT pay for the sawing of these areas per number 3 of 690.4(2) to make the removal of these areas more conducive? | 1. The existing pavement on USH 12 is rubblized reinforced concrete pavement, except at the stations shown on sheet 8 and 11 for ID 1080-18-70 and sheet 7 and 12 for ID 1080-19-70 which shows existing and proposed typical sections under the structures on USH 12. The pavement under the structures is crack and seated reinforced concrete pavement as labeled on the typical section. The note on these 4 sheets incorrectly states that the concrete pavement is continuously reinforced. 2. The pavement is not continuously reinforced and WisDOT is not considering this rigid pavement or rigid base, the contractor should assign removal costs for this in the Excavation Common item. 3. Standard specification 104.2.2.4.3 should be followed for this. â€œIf the quantity is decreased more than 50 percent from the original contract quantity for that bid item. Either party to the contract may submit a request for a revision to the contract unit price for that bid item.â€ 4. The plans include Sawing Asphalt for each end of the proposed concrete pavement areas. This is shown on the plan details and miscellaneous quantities (sheet 147, â€œCONCRETE PAVEMENT SECTIONSâ€). | Mike Coleman | 4 | 2019-11-08 11:12 | 2019-11-11 07:58
20191112 | 20191112015 | 15 | Culvert Replacements and 45 hr closure | How is 6.5" SHES concrete pavement getting paid in culvert replacement detail? Should this SHES pavement be constructed at the same thickness as existing roadway cross section, rather than what is detailed? After milling of 2.5", there will be only 4" of concrete pavement remaining. Is this accurate? Would a SHES concrete base patching item be more conducive for this work provided a sizable portion of the culvert replacement work is during the 45 hour closure? If not, how is removal is existing pavement and base volume from top of pavement to top of proposed granular backfill getting paid? Will this SHES pavement be placed from edge of shoulder to edge of shoulder? If not, what are limits? Can these SHES replacement areas be constructed at the same skew as the culvert, rather than transverse with roadway? Can the manhole at STA 108+96, that is included in the 45 hour closure, being prior to the closure? |  |  | 5 | 2019-11-08 14:36
20191112 | 20191112017 | 17 | Soil Stabilizer Type A and B | Article 14, Permanent Restoration, reads as though this project was supposed to go over a winter shutdown period. Specifically, it mentions using Soil Stabilizer Type B before winter shutdown. Can you confirm that the quantity for Soil Stabilizer Type A and B are still applicable with a November letting date and a September completion date? | Soil Stabilizer Type A and B will be needed even though there will not be a winter shutdown. | Mike Coleman | 1 | 2019-10-21 15:19 | 2019-10-22 09:53
20191112 | 20191112017 | 17 | CAD Files | Could the CAD Files be made available for this project? Could you also provide the earthwork tables and miscellaneous quantities data in excel format? Thank you. | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112017/ | Mike Coleman | 2 | 2019-10-25 09:21 | 2019-10-28 12:16
20191112 | 20191112017 | 17 | Pavement Markings | Good morning. Can you clarify when and where the pavement marking removal and temporary paint items will be utilized? Thank you. Also, what is the agencies plan to delineate the center line once the surface layer of asphalt is applied? It appears that the surface layer can be constructed after stage 2 when the road is open and it appears that there is not same day or temporary epoxy item included in the proposal. Thank you. | Pavement Marking Removal and Temporary Paint items will be needed for Stage 1, when the traffic is shifted for shoulder access. An addendum will follow to add â€œMarking Line Same Day Epoxy 4-Inchâ€ for the centerline. | Mike Coleman | 3 | 2019-10-26 09:49 | 2019-10-29 06:33
20191112 | 20191112017 | 17 | PWL Paving | 1) The work in Stage 1 over the Enbridge pipe line is not enough tonnage for each mix type to complete a 750 tons test strips for PWL testing. Would the paving in Stage 1 be completed under regular QMP for both density and volumetric testing? 2) Per FDM 19-21-10, PWL testing is to be used when a contract has at least 12,000 tons per each mix type. The surface quantity for the project is only 10,312 tons. Does PWL testing apply to the surface mix on this project? | 1) Yes 2) Although the FDM recommends 12,000 tons, as long as there are 3 QV volumetric tests completed on the project, the PWL calculations will work. This tonnage works out to 9,750 to get 3 QV samples. PWL will be used for the surface layer. | Mike Coleman | 4 | 2019-10-28 11:45 | 2019-10-29 14:30
20191112 | 20191112017 | 17 | Culvert Patching | 1) Culvert detail on sheet 11 shows asphaltic surface temporary patching at culvert pipe crossing locations. There is not a asphaltic surface temporary bid in the project. Will one be added? Also, the detail doesn't show any culvert/pipe trench patching between sta 217+00 to 242+00 but there is new storm sewer being placed. Do those runs of storm sewer need to be patched? | Asphaltic Surface Temporary is needed and will be added to the plan for the patching over trenched areas. Patching will be needed for culverts and storm sewer trench areas that are not within the shoulder areas. An addendum will be issued. | Mike Coleman | 5 | 2019-10-31 13:33 | 2019-11-05 10:57
20191112 | 20191112017 | 17 | Pavement Markings | Thank you for addressing my previous question. Will you be issuing another addendum to add back the 4" epoxy item that will need to be placed after the center line rumble strips are installed? | An upcoming addendum will remove the Marking Line Same Day Epoxy 4-Inch that was added in Addendum 1, restore the Marking Line Epoxy 4-Inch to its original quantity, and add the item Temporary Raised Pavement Markers, Type II. | Mike Coleman | 6 | 2019-11-02 07:24 | 2019-11-06 08:36
20191112 | 20191112018 | 18 | Addenda 1 - Schedule | Has a schedule been put together for this project since the addendum 01 change to start date? The revised dates only gives 9 weeks to do all work to open traffic back up on the bridge. The schedule demand on this project is dangerous. Can the WDOT schedule be provided? Can the start date be revised to make sure the project is buildable in the time provided? |  |  | 1 | 2019-11-07 15:27
20191112 | 20191112019 | 19 | Pavement Markings | What is the agencies plan to delineate the striping after milling and paving? I do see some temporary tape included but I do not see any quantities for laying out the center and/or edge line rumbles prior to the rumble operation as there is no same day or temporary epoxy bid items included in the proposal. Thank you. | An addendum will be issued to clarify. | Mike Coleman | 1 | 2019-10-28 11:00 | 2019-10-29 06:41
20191112 | 20191112019 | 19 | Earthwork Quantities | The earthwork quantities do not seem to accurately reflect the cross sections. Numerous cross sections indicate fills where no fill quantity is noted in the Earthwork Quantities table. Can you verify that the Earthwork Quantities are correct? | An addendum will be issued to address these earthwork questions. | Jill Fehrman | 2 | 2019-10-28 14:11 | 2019-11-05 09:55
20191112 | 20191112019 | 19 | Traffic Control | 1) The traffic control plans state that work at the bridge will be completed using a single lane closure. However, the road is only one lane in each direction and the detail is for a multi lane road. How will a single lane closure be completed? Additional, the traffic control plans states that 13' lanes must be maintained and the bridge is only 44' wide. Could you provide clarification on how the staging will be for the bridge work. 2) How is the will the traffic control be handled for the mainline culvert crossing at sta 167+00? 3) Will the turnlane widening/construction be completed under a shoulder closure? | 1) Work on the bridge to be completed using the standard detail: â€œTraffic Control for Lane Closure with Flagging Operationâ€. 2) Work at the mainline culvert crossing at STA 167+00 will be completed in 2 stages using the standard detail: â€œTraffic Control for Lane Closure with Flagging Operationâ€. 3) Yes. | Jill Fehrman | 3 | 2019-10-31 13:26 | 2019-11-05 09:24
20191112 | 20191112021 | 21 | Bridge & navigation closed date needed | What is the earliest date that both roadway & waterway traffic can be permanently stopped for required winter work? | An addendum will be issued to clarify | Mike Coleman | 1 | 2019-10-29 14:01 | 2019-10-30 10:01
20191112 | 20191112021 | 21 | As-Built Drawings | Are As-Built Drawings available for this project? If so, how can they be obtained? | The as-built plan can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112021/ | Mike Coleman | 2 | 2019-10-29 14:32 | 2019-10-30 10:26
20191112 | 20191112021 | 21 | The "NTE" in stream work date 3/1/20 contradicts the prosecution & progress 4/10/20 completion date | The two dates are contradicting of one another. Which date has precedence? Reason for question; A barge will most likely be needed for the approach spans exterior beam painting. This work would be more economical to perform in the warmer month of March. Please explain, Thank You | A barge sitting in the river is not considered in-stream work. | Mike Coleman | 3 | 2019-10-30 10:29 | 2019-10-31 10:50
20191112 | 20191112022 | 22 | Excel Files | Can we get the Misc Quantity Sheets and Earthwork Data sheets in Excel Format? | The Excel Files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112022/ | Mike Coleman | 1 | 2019-10-17 16:58 | 2019-10-22 07:29
20191112 | 20191112022 | 22 | line work | Can we get the electronic line work or any files available for staking data. | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112022/ | Mike Coleman | 2 | 2019-10-28 11:28 | 2019-10-28 13:01
20191112 | 20191112022 | 22 | Culvert Pipe Excel Sheets | Can the Culvert Sheets included in the MQ be updated to include length? Currently just has an X | The Culverts.xls file was uploaded in error and has been removed. Please use the file called D_Bid Items 500s_STH 76.xls that can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112022/ExcelFiles | Mike Coleman | 3 | 2019-10-28 14:48 | 2019-10-29 09:56
20191112 | 20191112022 | 22 | Construction Schedule | Can the construction schedule that was developed with the design be uploaded to the ftp site? | The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112022/ | Mike Coleman | 4 | 2019-10-29 07:21 | 2019-10-29 09:56
20191112 | 20191112022 | 22 | Shrubs in Roundabouts | The typical sections for the roundabouts show 3-Inch mulch is incidental to shrub bid items, but there are no bid items for shrubs for this project. Is this to be done by others? | The center islands for the roundabouts are receiving Low Maintenance Seed Mix, item SPV.0085.01. This was accounted for in the quantities. We will be submitting an addendum to correct the 2 typical section sheets for the appropriate call out. | Mike Coleman | 5 | 2019-10-29 07:24 | 2019-10-29 14:29
20191112 | 20191112022 | 22 | Utilities - WE Energies Asbestos | In the utilities section of the specials show that if asbestos wrap is encountered during construction the contractor is to give WE energies 10 days notice to test the material, and an additional 5 days to remove the material. How would this be handled if this is encountered during stages 2B or 2C there is only 25 calendar days to finish these stages and there would be only 10 calendar days for the contractor to finish their work? | We believe that the contractor should be able to provide the 10 days advance notice such that it doesnâ€™t delay the operations of the controlling work item. This will need to be a schedule item that the contractor and the engineer discuss at the weekly meeting. Is the asbestos wrap is found, then the 5 additional days that WE Energies needs to remove the pipe would be treated as an excusable, non-compensable delay per standard spec. 108.10.2.1. | Mike Coleman | 6 | 2019-10-29 07:43 | 2019-10-29 14:27
20191112 | 20191112022 | 22 | Earthwork Expansion | Sheet 187 of the Misc Quantities shows an expanded fill factor of 1.42 while the note on the bottom says 1.25. The actual calculation on the sheet is 1.42. How did the designer determine this factor? | 1.42 is the correct fill factor, so the calculated material is correct. We will plan to correct the note at the bottom of the table so that these match in an upcoming addendum. | Mike Coleman | 7 | 2019-10-30 09:36 | 2019-10-30 11:16
20191112 | 20191112022 | 22 | 1.42 Earthwork Expansion Factor | How did the designer determine that 1.42 is the correct expansion factor for the unexpanded fill? | The design team reviewed the soils report and the NCRS Soils Series contained within the report. It was estimated that the soils in the area would have a shrinkage factor of approximately 30% which corresponds to the 1.42 expansion factor that was used in the design calculations. You should adjust the expansion factor accordingly to address the characteristics of the fill material you intend to use on the project. | Jill Fehrman | 8 | 2019-10-31 15:08 | 2019-11-01 10:09
20191112 | 20191112022 | 22 | ADDITIONAL SPECIAL PROVISIONS 5 - FUEL COST ADJUSTMENT | Why is there no Additional Special Provision 5 - Fuel Cost Adjustment included within the Proposal? | An addenda will be issued to add Additional Special Provision 5 - Fuel Cost Adjustment. | Jill Fehrman | 9 | 2019-11-04 12:44 | 2019-11-05 10:00
20191112 | 20191112022 | 22 | SP Article #44 Cleaning Ditch | SP Article #44 Cleaning Ditch, will the Landscaping items (seed, fertilizer, mulch, E-mat, etc.) be paid for separately? | That is correct, the landscaping items are to be paid separately. | Mike Coleman | 10 | 2019-11-04 13:26 | 2019-11-05 13:32
20191112 | 20191112022 | 22 | Soil Boring Logs | Is a copy of the soil boring logs available? | The geotechnical report can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112022/ | Jill Fehrman | 11 | 2019-11-06 13:54 | 2019-11-08 15:52
20191112 | 20191112022 | 22 | QMP Base Aggregate Dense 1-1/4" Compaction | The proposal includes a bid item for QMP Base Aggregate Dense 1-1/4" Compaction, however an outdated version of the Special Provisions are referenced. Will the Department provide an Addendum to include the correct Special Provision? | Addenda #4 for this proposal was issued to insert the updated special provision. | Jill Fehrman | 12 | 2019-11-07 17:19 | 2019-11-08 15:55
20191112 | 20191112023 | 23 | Contract Completion Date | Question regarding contract completion date. With in-stream restrictions in effect beginning May 1st and County road weight restrictions in early Spring; is a May 23rd completion date feasible? | Schedule of operations will need to take into effect the instream restrictions and the early completion date. Oconto County does not put spring restrictions on CTH H. | Mike Coleman | 1 | 2019-10-30 14:55 | 2019-10-31 10:52
20191112 | 20191112023 | 23 | Select Borrow | The spec for Select Borrow does not seem to be in the specials or anywhere else in the plan? Can you provide this please | Select Borrow. Conform to standard spec 208 as modified in this special provision. Material Furnish and use material that consists of granular material meeting the following requirements: No more than 25% P-200 of that portion of the #4 sieve. stp-208-005 (20031103) | Mike Coleman | 2 | 2019-11-08 08:39 | 2019-11-11 07:59
20191112 | 20191112024 | 24 | Guardrail Removal @ B-63-10 | It appears that this bridge has existing guardrail that is called out on p.52 to be removed. Is the bid item missing for this? | An addendum will be issued to include that item. | Mike Coleman | 1 | 2019-10-22 08:37 | 2019-10-22 11:19
20191112 | 20191112024 | 24 | Removing Asphaltic Surface & Asphaltic Surface Patching Bid Items | At structures B-63-13 & 14, Asphaltic Surface Patching is shown via the hatching on Sheet 50 to the full limits of the roadway and paved shoulder to extend approx. 150-ft to 200-ft beyond the end of each of the respective bridge decks. The miscellaneous quantities tables identify 868 SY of Removing Asphaltic Surface beyond the limits of the concrete approaches for these structures, and 198 tons of Asphaltic Surface Patching within these same limits. Based on the correlation of removal items to asphaltic surface patching quantities, it appears that the patching is intended to be full depth replacement for any asphaltic surface removed for construction of the approaches, though it is not clear from the plans what the desired limits for removal and replacement are, or what the scope of work is that is intended by these items. Can you please clarify the scope of the Removing Asphaltic Surface and Asphaltic Surface Patching items. | Addenda #2 was issued on this proposal to clarify the question asked. | Jill Fehrman | 2 | 2019-10-30 13:49 | 2019-11-08 12:57
20191112 | 20191112024 | 24 | Asphaltic Surface to Accommodate Traffic Staging | Per Sheet 49, Structure B-63-7 has 8 tons of Asphaltic Surface between Stages 2 & 3, and per Sheet 51, Structure B-63-17 shows 12 tons of Asphaltic Surface in Stages 1 & 2, to accommodate traffic phasing, and replace the pavement surface to match the new deck and approaches back to the existing asphalt roadway, prior to the following stage for full width milling and overlaying. Structures B-63-8 & 10 will have the concrete masonry deck overlay and approach cleaning & overlay performed in stages prior to stage for the mill & overlay work, but no asphaltic surface is included in the quantities for matching the existing roadway to the new concrete approach and deck at each of these structures. It appears plausible that the height of the roadway may change due to the masonry overlay, and that asphaltic surface may be required at these structures to accomodate the traffic phasing. Please advise whether additional quantities will be included to address the traffic phasing at these structs | Addendum #2 was issued for this proposal to clarify the questions asked. | Jill Fehrman | 3 | 2019-10-30 14:02 | 2019-11-08 12:58
20191112 | 20191112024 | 24 | Concrete Pavement Partial Depth Repair - Maximum width of mill | Special provision #11 indicates that the maximum width for joint repair is 12 inches and that the removal is to be performed by a milling machine. Most milling contractors have a minimum drum width of 20" or 24". The provision also indicates that air chippers are only to be used for final preparation of the area, not all removals. Are there other alternatives for this work? Is the mill head required to have a parabolic shape per standard detail sheet 13c8? | The mill width will remain as is, following the special provision and standard detail. | Mike Coleman | 4 | 2019-11-06 07:29 | 2019-11-07 09:18
20191112 | 20191112024 | 24 | Traffic control | B-63-7,8,10,17 all call out milling and paving in stages 3 or 4, open to traffic one lane at a time with flaggers, then the following stage says set temp lights with barrels to perform polymer overlays one lane at a time, can the lights and drums be utilized for the milling and paving as well? | The temp signal spacing is setup specifically for the intended stages. The temp signal spacing does not provide adequate space for the milling and paving work. Perform staging as indicated in plan. | Jill Fehrman | 5 | 2019-11-06 13:25 | 2019-11-07 12:23
20191112 | 20191112024 | 24 | Stage 1 Shoulder Paving | How is the shoulder grading for the stage 1 shoulder paving being paid for? Items 205.0100 or 211.0400 aren't included in the plan. | An addendum has been issued to include 211.0400. | Mike Coleman | 6 | 2019-11-07 08:13 | 2019-11-07 16:39
20191112 | 20191112026 | 26 | Temporary Water Diversion | Would bypass pumping be allowed to be used as part of the temp water diversion? | Part of the 5th paragraph under â€œConstructionâ€ for the item â€œTemporary Water Diversionâ€ states: Base flow water into the construction area can be pumped, diverted thru a channel, or some other approved method to protect the work area for the new culverts. Therefore, bypass pumping is allowed, however the contractor must maintain a minimal base flow as stated in the 3rd paragraph under â€œConstructionâ€ for the item â€œTemporary Water Diversionâ€ which states: Divert stream with impermeable barrier. A minimum base flow rate 6 cfs shall be maintained up to and around the construction area. Additional stream flow in excess of 6 cfs may be blocked off/diverted to minimize flow thru the construction area. This additional stream flow will be redirected east, north, then west in existing ditches on private property (cranberry bog). Quantity and control of excess flow not being maintained up to and around the construction area must be coordinated and approved by Steve Steward, Marsh Manager for Wood-U Marsh (715-213-8102). Provide a minimum of 10 daysâ€™ notice to project staff and property owner/manager before blocking or diverting any portion of the stream. | Mike Coleman | 1 | 2019-10-30 08:21 | 2019-10-30 10:30
20191112 | 20191112026 | 26 | Geo-technical Data | Could you please provide the geo-technical data that was used for design on this project. | The Geo-Technical Report cam be found at the following location: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-nc.aspx | Jill Fehrman | 2 | 2019-10-31 15:27 | 2019-11-04 09:15
20191112 | 20191112026 | 26 | 30" Concrete Curb & Gutter | Will Intergal Curb and Gutter be allowed on the project? | Integral curb and gutter is acceptable, provided access is maintained for drives and sideroads per the â€œTrafficâ€ section of the Special Provisions. | Jill Fehrman | 3 | 2019-11-01 15:30 | 2019-11-05 10:14
20191112 | 20191112026 | 26 | 12" Watermain Direction Bore | What is the intent behind the design to directional bore the northern portion of the project? | There was a significant number of existing utilities (both underground and overhead) to contend with, as well as the existing roadway and wetlands. As such, it was decided to require the contractor to directional bore in the new line. | Mike Coleman | 4 | 2019-11-07 11:34 | 2019-11-07 16:35
20191112 | 20191112026 | 26 | ULO's | There is no bid item for ULO's on the project. Based on the scope of the work, we are questioning if this was an item that was overlooked. | Not included in the contract, as we did not anticipate that they would be needed. Utilities were field located with survey crews and cross checked during design. | Mike Coleman | 5 | 2019-11-08 13:28 | 2019-11-11 07:21
20191112 | 20191112027 | 27 | Butt Joint/ Milling | Sheet 7 of the plans indicates that all side roads are to have butt joints presumably 25' in length. Sheet 46 of the plans (misc qty) defines butt joint at STH73 (BOP), CTH K, Owen Ave and STH95, the balance of the side road appear Not to have butt joints. Could this please be clarified. | The side roads listed in the miscellaneous quantity sheets under item 204.0115 are the only side roads that require butt joints. The other side roads within the project limits (not listed under item 204.0115) do not have a paved surface and will not require a butt joint to compensate for the profile raise. Milling of the asphalt around the radius at these unpaved side roads will be paid under item 204.0120. | Mike Coleman | 1 | 2019-10-23 15:44 | 2019-10-24 07:23
20191112 | 20191112027 | 27 | culvert work | The cross section at each culvert shows a fill being constructed. How will this fill be paid? Secondly, the ditch cleaning item references a 10' width maximum for the work. How long will the ditch cleaning be limited to? | There is not a set length for the ditch cleaning. The intent is to remove sediment from the inverts of the culvert pipes, at the locations shown in the plan, to provide drainage to/from the pipes. | Jill Fehrman | 2 | 2019-10-31 11:58 | 2019-11-04 09:47
20191112 | 20191112027 | 27 | Soil Borings | Are there soil borings available for this project? | No soil borings are available for this project. | Mike Coleman | 3 | 2019-11-04 16:53 | 2019-11-05 12:49
20191112 | 20191112027 | 27 | Culvert Pipe Installation | Please clarify how the pipe trench backfill will be paid for the culvert pipe installation if the existing on-site material is found to be unsuitable. | If existing material is determined to be non-suitable per 520.2.5.3, material is paid per section 520.5.2(2). If applicable contract items are not available, this will be paid as extra work. | Mike Coleman | 4 | 2019-11-05 08:52 | 2019-11-05 13:31
20191112 | 20191112027 | 27 | Centerline Joints | Will the region consider eliminating the Joint Heater Item and add the Joint density spec that has been on the majority of the PWL projects. Also is running a Notch Wedge Joint going to be considered as matching up on this project as central office has indicated in a question and answer to WAPA? | Bid the centerline joint as shown in the contract documents. A notched wedge joint is not considered matching up as required by the special provisions. | Mike Coleman | 5 | 2019-11-05 16:28 | 2019-11-07 16:37
20191112 | 20191112027 | 27 | centerline joint | will the region consider a 24hr restriction on an uneven lane during paving with the use of a notched joint, match up next day? | Page 2 of the Special Provisions require the centerline elevations of both lanes match at the end of each day for milling and paving. Without reason, the Department will not waive this requirement. | Mike Coleman | 6 | 2019-11-11 09:05 | 2019-11-11 10:06
20191112 | 20191112029 | 29 | Request DVD or Video | Cured in Place Pipe Lining 36-inch, Item SPV.0090.04 (C. Inspection of Pipelines - DVD's are available upon request). Can you please provide DVD or link to the videos. | There are no DVDâ€™s or video available. An addendum will be issued to remove that language. | Mike Coleman | 1 | 2019-10-16 15:59 | 2019-10-21 11:06
20191112 | 20191112030 | 30 | Soil Borings | Are there soil borings available for this project? | There were no soil borings. Pavement cores can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191112030/ | Mike Coleman | 1 | 2019-11-04 16:54 | 2019-11-07 09:36
20191112 | 20191112030 | 30 | Lane Shift | The SPV item states that temporary asphalt is included for the item, the detail on plan sheet 26 shows base aggregate as the final riding surface. Will HMA be required for the lane shift item? | Follow the detail, HMA is not required. HMA is not included in the quantiles for these areas. | Mike Coleman | 2 | 2019-11-06 18:33 | 2019-11-07 11:39
20191112 | 20191112034 | 34 | Topsoil | Is it really supposed to be 13,800 CY of Topsoil? The plan shows the unit as SY, proposal shows it as CY. | Correct, the quantity should be 13,800 SY, not cubic yards. An addendum will be issued to correct. | Mike Coleman | 1 | 2019-10-28 15:55 | 2019-10-29 09:58
20191112 | 20191112034 | 34 | B-50-32 Steel Diaphragms | In regards to Structure B-50-32, the plan shows the steel diaphragms skewed. Normally, diaphragms are in-line or staggered. Please confirm a skewed diaphragm configuration is required. | These are in-line along the skew. Normally we stagger these but the skew is so small and the bolts would have been about 6" apart. So instead of having two sets of bolts we are doing them in-line along the skew. The only thing missing is showing that the diaphragm support needs to be angled to account for the skew on the leg protruding from the beam. It is to be skewed 3 degrees, 32 minutes. An addendum will be issued to add a detail showing the skew. | Mike Coleman | 2 | 2019-11-01 09:43 | 2019-11-05 10:53
20191112 | 20191112036 | 36 | Temp Vertical Clearance during const over BNSF tracks for Painting work in Span 5 - Clarification | The existing vertical clearance over the BNSF track(s) is listed on the existing plans is 23'-7". The minimum clearance listed on the plan set is 23'-3 1/2". Special Provision 7 A.6 lists the "temporary clearance during construction" vertical must be 21'-6" plus 1.5 inch for SE tracks. Best case this leaves approx 2'-1" to 1'-8" worst case for access over the tracks. With 44 trains per day at 55 mph what was the intended access and procedure to do the 2237 sf of Cleaning and priming for bid item 0048 Structure Overcoating Cleaning and painting B-12-5? Plan sheet 60 (2 of 4 set B-12-5) cross section through Span 5 is the only deck cross section that shows the note for Structure Overcoating and Painting. The estimate quantity in the special provisions of 2237 sf is close to the total exposed sf of all the girders in span 5. It appears that all the work for this bid item is in span 5. | For the access part of the question, there are various ways to access the area. The contractor shall determine their Means & Methods of Construction. The procedure part of the question is defined in the Special Provisions. See Article 23. In addition, approximately 15-percent of the 2,237 Sq Ft total is estimated to be in span 5 of this bridge. The remaining estimated 85-percent is located in spans 1, 2, 3, & 4. | Mike Coleman | 1 | 2019-10-16 10:37 | 2019-10-23 09:50
20191112 | 20191112036 | 36 | Bearing Repair SPecial Provision | The special provision for the Bearing Repair on B-12-5 indicates that new anchor bolts are to be furnished and installed but there are no details on what size the new anchor bolts are supposed to be. There is also no indication on how to install them when they will be in conflict with the existing bolts. The provision also states that furnishing and placing shims is included but gives no details on which bearings will require shims, what the shim sizes need to be, or what criteria would mandate shimming. | The intent is to replace anchor bolts with same size as existing. All anchor bolts are 1 ¼â€ Dia. x 1â€™-0â€ long. Pier 5 bearings only require cleaning and painting â€“ existing anchor bolts will remain. New anchor bolts will be placed in opposite corners of existing anchor bolts to avoid conflict. Shim plates should not be required. | Mike Coleman | 2 | 2019-11-04 12:33 | 2019-11-06 11:00
20191112 | 20191112036 | 36 | Joint Repair Removal limits on CIP Girders | Is there any concrete removal at the CIP girder areas in the joint repair on B-12-5? The plan view on sheet 4 of 4 appears to show construction joints at each CIP girder and there does not appear to be any new reinforcing steel in these areas. | Joint repair does not include concrete girder removal. The concrete diaphragm and deck is called for removal but not the girders. There is concrete surface repair called for along the bottom of girder. | Mike Coleman | 3 | 2019-11-04 13:22 | 2019-11-06 11:03
20191112 | 20191112036 | 36 | Confirmation of bearing repairs at Pier #1 | Notes on the plan state that bearing 1,2 & 4 at pier 1 require repair. Pier 1 has 4 bearings for the span 1 girder span and 2 bearings for the truss span side (span 2). Please confirm that bearings 1, 2 & 4 are the girder span bearings at pier 1 | It is confirmed the bearing repair at Pier 1 includes bearings 1, 2, & 4 of the girder span. | Mike Coleman | 4 | 2019-11-04 17:09 | 2019-11-06 11:04
20191112 | 20191112036 | 36 | Concrete surface repair question | On sheet 61 B-12-5 Detail "Pier Column Repair Detail (typ.) - (in Water) shows concrete surface repair "as required" determined in field. The detail shows concrete surface repair occurring underwater. Dry concrete surface repair and underwater concrete surface repair are significantly different scope & cost. To be fair to the department and to to contractor please consider adding a separate contract item for underwater concrete surface repair, similar to the way the fiber wrap repair is bid. | The area of Concrete Surface Repair below water is less than 10% of the total area required and is located right at the water line. Separating into two items is not warranted. | Mike Coleman | 5 | 2019-11-05 15:53 | 2019-11-07 07:55
20191112 | 20191112036 | 36 | Concrete Surface Repair & Underwater Concrete Surface Repair | Pier 1 and Pier 3 require fiber wrap and concrete surface repair to be performed below the surface of the water. Please add a bid item for underwater concrete surface repair similar to the bid item for fiber wrap reinforcing non-structural (wet). Having the payment for both above and below water concrete surface repair in the same bid item will make it extremely difficult for the contractor and its subcontractors to be fairly compensated. | The area of Concrete Surface Repair below water is less than 10% of the total area required and is located right at the water line. Separating into two items is not warranted. | Mike Coleman | 6 | 2019-11-06 09:55 | 2019-11-07 07:56
20191112 | 20191112036 | 36 | Concrete Repairs under Fiberwrap areas | The special provisions for the fiberwrap items indicate that loose/spalled concrete removals, concrete patching, and epoxy injection are all included in the 'Surface Preparation' portion of these items. Plan sheet 3 of 4 for structure B-12-5 indicates areas of Surface Repair in the Fiberwrap areas, which would indicate they are paid separately. Please clarify how the concrete repairs will be paid. Also clarify if the intent of Fiberwrap (wet) is to mean all areas on the piers in the water or if it is the areas that are at or below the waterline. The work at/below the waterline is significantly different than the 'dry' work above the waterline. Different pay items for the different conditions would make this easier to bid. | Concrete surface repair and epoxy injection will be paid separately. All fiberwrap repairs on Piers 1-3 will be included in the â€œwetâ€ item, though no repairs are anticipated at Pier 2. | Mike Coleman | 7 | 2019-11-06 10:11 | 2019-11-07 09:16
20191112 | 20191112036 | 36 | Bearing repair, south truss bearing at pier 4 | Does the department have a plan for how the jacking operation is to be performed for the bearing repair work on the south truss bearing at pier 4? Looking at the pictures available in the inspection reports it does not look like there will be any adequate location to jack and support the structure while this work is taking place. It also appears that this work will have to occur during the full closure timeframe. Is that the intended timeframe for this to work to occur so traffic is not on the structure while it is being temporarily supported? | No plan has been determined for jacking at Pier 4. However, there is a floor beam connecting the trusses that could potentially be used. Jacking should be done during road closure. | Mike Coleman | 8 | 2019-11-06 10:52 | 2019-11-07 09:17
20191112 | 20191112036 | 36 | Structure overcoating cleaning And Priming | Plans only show spot cleaning and painting on railing is thee also painting in truss portion? | There is spot painting of the truss and girders required. | Mike Coleman | 9 | 2019-11-06 11:34 | 2019-11-07 09:29
20191112 | 20191112036 | 36 | Cleaning painting girder ends | The paint systems listed are not designed for SSPC-SP3 Power tool cleaning and can not be applied to old paints? Need minimum SSPC-SP6 Cleaning for the coatings. | The surface preparation for Item SPV.0105.01, Cleaning and Painting Girder Ends should be SSPC-SP6/Commercial blast cleaning. | Mike Coleman | 10 | 2019-11-06 11:39 | 2019-11-07 09:31
20191112 | 20191112036 | 36 | Girder Ends | If blast cleaning is performed you will need containment item also this would be removing lead based paint which would require Negative pressure containment. | The surface preparation for Item SPV.0105.01, Cleaning and Painting Girder Ends is correct as listed in the Special Provisions as SSPC-SP3/Power Tool Cleaning. In regard to the painting system required for Item S SPV.0105.01, Cleaning and Painting Girder Ends, the contractor should furnish an epoxy coating system from the departmentâ€™s APL for Paint- structure maintenance. The listed coal tar coating systems should be disregarded. The surface preparation and painting system will now be in sync. An addenda will be issued to address this issue. | Jill Fehrman | 11 | 2019-11-07 10:34 | 2019-11-08 15:47
20191112 | 20191112036 | 36 | Fiber Wrap Reinf Dry - Pier 5 - Excavation Requiremnet & method of payment | How is the excavation for the bid item "Fiber Wrap Reinf - Dry" Paid for? It is not listed in the payment portion of the Special Provison. Payment for Fiber Wrap Reinforcing Non-Structural (Dry) is full compensation for preparing required submittals, cleaning and preparing the surfaces of elements to be strengthened, furnishing, transporting, handling, and installing the fiber fabric, finish coat of epoxy, the final protective coating system, field testing, and required remediation. No extra measurement or payment will be made for overlap areas. Sheet 61 has a detail Pier Column Repair (at Dry Ground) . It shows 6" max excav at the front with the wrap going back horizontal at the point. The back face at pier 5 has could be as much as 5 ft of excavation with potential for shoring near the existing timber crib wall. Please clarify the Required excavation intended plus how it will be paid for. | Pier 5 - There are no repairs required that close to the ground. No excavation is required at pier 5. | Mike Coleman | 12 | 2019-11-08 13:49 | 2019-11-11 11:01
20191112 | 20191112036 | 36 | Bearing Repair | The response to question #2 indicates that new anchor bolts would be placed in opposite corners of the masonry plates to avoid conflicts. Existing bridge plans show anchor bolts in all 4 corners of existing masonry plates. Existing plans also indicate 1-1/4" anchor bolts or 1-1/2" anchors. Were the bearings replaced once already, and if so have all potential anchor bolt conflicts been reviewed. | No, the original bearings have not been replaced. (Additionally, only bearings at Piers 2 & 3 have 1-1/2 inch anchor bolts. These are not being repaired.) | Mike Coleman | 13 | 2019-11-08 14:53 | 2019-11-11 10:08