## qandasearchletting_results
Date: | 2020-02-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200211 | 20200211001 | 1 | Geotechnical Report | Please provide a copy of the Geotechnical Report. | The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211001/ | Mike Coleman | 1 | 2020-01-16 12:19 | 2020-02-03 06:33
20200211 | 20200211001 | 1 | Design Files | Can the Department Provide: 1. Design Schedule 2. All Design files (ie prop dwgs, existing & proposed surfaces, structure linework etc.) | The design schedule and design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211001/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-01-23 08:56 | 2020-02-03 06:32
20200211 | 20200211001 | 1 | Girder Removal and Replacement | In the special provisions it states that the contractor is only allowed 2 rolling stops each direction for girder removal and 3 rolling stops each direction for girder erection. Are these numbers representing the number of nights allowed for rolling stops or is it showing the number of rolling stops? If it is showing the number of rolling stops the project can not be done safely. | There are 4 existing girders and 6 proposed girders. We feel that it is appropriate to have 1 rolling closure for the removal of each existing girder and 1 rolling closure for the installation of each new girder. The table is updated below: Girder Removal and Placement The Distribution of Allowable Rolling Stops for specified activities are shown below: Distribution of Allowable Rolling Stops Activity EB IH 94 at CTH Q WB IH 94 at CTH Q Existing Girder Removal 4 4 Girder Placement 6 6 During the removal of existing girders and placement of the new girders for B-28-186, â€œrolling stopsâ€ on IH 94 may be used for periods not to exceed 15 minutes during allowable times for lane closures as listed in the Traffic article. This will involve slowing interstate traffic and then allowing it to proceed behind a line of state patrol cars that will coordinate the procession with the construction crew at the bridge site. Traffic will proceed in groups timed to allow for the removal and placement of the girders overhead. Allow all vehicle backups to clear the project area prior to setting up the next road closure during the above timeframe. The allowable number of closures are specific to the activity, direction, and location specified above. Cost for Wisconsin State Patrol services associated with IH 94 rolling stops will be the responsibility of the department. Cost for any additional Wisconsin State Patrol services that are requested by the contractor will be the contractorâ€™s responsibility. Arrangements for implementing â€œrolling stopsâ€ on IH 94 shall be through Kyle Hemp with the Departmentâ€™s Southwest Region office at (608) 246-5367, with the WisDOT Southwest Region, the Wisconsin State Patrol, and the Jefferson County Sheriffâ€™s Department, at least five days prior to any stoppage. | Fred Schunke | 3 | 2020-02-03 07:05 | 2020-02-04 14:06
20200211 | 20200211001 | 1 | SPV.0045 SP 01 Basic Traffic Queue Warning System | You have 120 days in the proposal and estimated quantities but not in the miscellaneous quantities. Without a clear understanding of the intent it is hard to put a bid to this. There could be multiple closures each night and each would need this system according to the lane closure detail. Is the intent for milling and paving operations? Etc thanks | This item is intended to be used for ID 1067-04-71 only. The system is required to be used for the first lane closure set up in a direction of travel. If multiple lane closures are used in the same direction of travel, the system is only required on the first lane closure set up and Standard Detail Drawing â€œTraffic Control, Lane Closure, Speed Reductionâ€ should be used for the next lane closure set up. | Fred Schunke | 4 | 2020-02-05 09:44 | 2020-02-07 14:14
20200211 | 20200211001 | 1 | CONCRETE BASE PATCHING SPV.0180.01 | The material specified under the base patching references standard spec 715 and requires an opening strength of 2000 psi within 4 hours of placement, or prior to opening to traffic. Standard specification 715 does not allow for chloride to be added to the concrete. The 2000 psi strength will not be obtained without a chloride additive. Was this an oversite in the specification? | Standard Specification 715.2.3.1 Section (5) states, â€œDo not use chloride based accelerators in mixes for new construction.â€ The Concrete Base Patching item is meant to repair existing pavement and is not considered new construction. | Mike Coleman | 5 | 2020-02-05 17:39 | 2020-02-10 13:26
20200211 | 20200211001 | 1 | Addendum #1- Notice to Contractor- Interstate Work Restriction | With the revised notice to contractor in addendum #1, why is the contract completion date not extended? |  |  | 6 | 2020-02-06 10:40
20200211 | 20200211001 | 1 | Staging | Is there a typo in the second and third bullet points below? How can you not start work on stage I of a project until post-stages of that same project are complete? ID 1067-04-71 - IH 94 Overlay General â€¢ See INTERIM AND FINAL COMPLETION OF WORK section of these special provisions for work requirements on eastbound IH 94. â€¢ No work can take place in the 1067-02-76 - Rock Creek work zone until Stage 2 of ID 1067-02-76 is complete. â€¢ Complete Stages 1A, 1B, 2A, and 2B in the work zone along IH 94 for ID 1066-06-72 prior to beginning Stage 1 of ID 1066-06-72. â€¢ Stages 3A, 3B, 4A, and 4B cannot be constructed within the work zone along IH 94 for ID 1066-06-72 until Stage 9 of ID 1066-06-72 is completed. | The stage number is unique to the individual ID and not for the project as a whole. Stage 1 for ID 1066-06-72 is the not the same as Stage 1 for 1067-04-71, so Stage 1 for one ID can occur before Stage 1 for a different ID within the project. | Jill Fehrman | 7 | 2020-02-07 15:55 | 2020-02-10 15:28
20200211 | 20200211001 | 1 | sawing for concrete base patching | Detail and bid item show only saw cutting the depth of the HMA for the concrete base patch removals. The existing rubbilized concrete should be saw cut full depth as the particle size of rubbilized concrete may be small at the surface however could be +8" in diameter at the bottom. Not sawing the rubbilized concrete full depth may result in undermining of the base patch excavation and interference of the adjacent pavement structure. | Note 2 on Sheet 16 of ID 1067-04-71 states that saw cutting the concrete is not required, however, it does not say that it isnâ€™t allowed. Full depth saw cutting through the existing HMA and underlying concrete pavement may be allowed with approval of the engineer. As stated in Note 2, â€œSawing asphalt and sawing concrete are incidental to the item Concrete Base Patching.â€ | Jill Fehrman | 8 | 2020-02-07 16:15 | 2020-02-10 15:32
20200211 | 20200211001 | 1 | Sawing. | Sheet 16 of the plans disallows the use of Vermeers/rock saws for cutting concrete. This apparently is due to the rubbilization of the existing pavement. Vermeer/rock saws have been used in the past successfully. Using a diamond bladed saw and then removing the rubblized pavement will result in far more undermining than when a Vermeer/rock saw is used. As a result, can the note on Sheet 16 of the plan be removed and Vermeers/rock saws be allowed? | As stated in the plans, use of a Vermeer/rock wheel will not be allowed for the item SPV.0180.01 Concrete Base Patching. | Jill Fehrman | 9 | 2020-02-08 13:08 | 2020-02-10 15:31
20200211 | 20200211001 | 1 | Design Schedule | Can the design schedule be provided? |  |  | 10 | 2020-02-10 04:42
20200211 | 20200211001 | 1 | Use of a Vermeer/Rock Wheel | Can a Vermeer/Rock Wheel be used on the Base Patches? Rock wheels have been used very successfully when asphalt covers existing concrete without any problems. | As stated in the plans, use of a Vermeer/rock wheel will not be allowed for the item SPV.0180.01 Concrete Base Patching. | Jill Fehrman | 11 | 2020-02-10 11:33 | 2020-02-10 15:30
20200211 | 20200211002 | 2 | Crack Sealing | What does the state expect to do with the joints/cracks that are over one inch in width and the alligatored cracking on this section of road? | Per the special provision, the engineer will determine if those less than 1/4-inch or greater than 3/4-inch will benefit from a route and seal. The Region's Maintenance Engineer and Pavement Design Engineer agree that those cracks greater than 3/4-inch should be cleaned and filled with sealant (i.e. routing is not necessary). Do not prefill with crumb rubber or other filler material. In the alligator cracked areas, the contractor will be expected to fill the wider cracks. The department will seal the remaining areas as needed after the project is complete. | Mike Coleman | 1 | 2020-01-20 15:40 | 2020-01-21 13:13
20200211 | 20200211002 | 2 | Closure length | If we are to cover 40 miles (20 miles inside and outside) in 30 days, that requires 7,040 linear feet per day. If the maximum closure length is 1000 LF, are you expecting this to be a rolling operation or are we supposed to set up multiple closures each day? What is the required distance between 2 closures? | The expectation is that work will be performed with a moving operation around a maximum working area of 1000-feet during daylight hours. A moving operation will be used on both mainline IH 43 and ramps. Single lane closures on SB or NB IH 43 will be allowed during weekday (Monday - Friday) daylight hours. On ramps, traffic will be shifted to utilize the existing paved shoulder while work occurs on 1/2 of the ramp. Traffic will then be switched to the other paved shoulder to route and seal the other half of the ramp. Temporary ramp closures shall be limited to weekdays and off-peak hours. Temporary ramp closures may be allowed only if approved by the engineer with proper notification and signed detours. For freeways, a 3-mile minimum distance between the end of one work zone and the start of the next work zone is required. When using multiple operations in the same directions, the contractor will be required to close the same lane. We will issue an addendum to this contract to add SDD15D43-01, Traffic Control, Short Duration, Mobile Operations. | Fred Schunke | 2 | 2020-01-23 11:46 | 2020-01-29 14:01
20200211 | 20200211002 | 2 | Hours of Work | With the uncertainty as to whether traffic backups will lead to multiple shut downs during the day, could this project be completed at night instead. If night work would be approved, could closures be extended to 2 miles in length - matching previous WIDOT projects of similar roads? Also, question number 1 is showing question marks where the numerals should be, could that be corrected? | The expected volumes and capacity of the roadway yield conditions that construction activities may be conducted during daylight hours. These conditions were meant to be permissible, not restrictive. The work restrictions will be modified to the following. Work Restrictions Performing construction activities during daylight hours Monday through Friday is allowable. The single-lane work zone length (i.e. work area on SDD 15D43-01) can be longer than 1000-feet if authorized by the engineer. The length of the work zone should be based on the safety of the construction staff and traveling public (i.e. expected traffic volumes will likely not be the limiting factor). Response to Question #1 will be modified. | Jill Fehrman | 3 | 2020-01-29 14:32 | 2020-02-06 20:28
20200211 | 20200211002 | 2 | Lane Closure | Based on the fact that youâ€™ve added 500 drums/day as a bid item are we to infer that you will allow the contractor a single lane closure for up to the entire length of the project per day, if they choose to do so? |  |  | 4 | 2020-02-07 11:47
20200211 | 20200211003 | 3 | Mill and Relay | Would the Department consider a pulverize and relay operation instead of the mill and overlay? Both the pulverizer and the mill can use an upcut to process the asphalt. The mill is approx. 20% heavier than the pulverizer. During the mill operation the front tracks will ride on the existing asphalt and the back tracks ride on the milled out grade. During a pulverize operation the front tires on the existing asphalt and the back tires will be on the pulverized material surface, which would provide more support over the existing tile. The pulverizer is designed to size the material in its operation. The mill is not designed to size the material and another process has to be done to size the material. This introduces more material loss through the addition of an additional process. The elimination of the additional process for using a pulverizer would make that option more economical for the tax payer and provide a product that is comparable in quality to the proposed method. | No, we want the Mill and Relay item/operation to be used for this project. | Fred Schunke | 1 | 2020-01-28 07:50 | 2020-01-29 14:04
20200211 | 20200211003 | 3 | Cold Mix | Cold Mix is specified as a MC 250 in the plans. In the past a more common SC â€“ 250 or QPR (Quality Pavement Repair) has been an acceptable substitution on DOT projects. Would these materials be an acceptable substitution for the small tonnage for this project? If not, is there another cold mix that would be an allowable substitution? | Yes, those materials would be acceptable substitutions for the Cold Mix. | Fred Schunke | 2 | 2020-01-28 07:51 | 2020-01-29 14:04
20200211 | 20200211003 | 3 | Rumble Strips | For the Asphaltic Surface Rumble Strips would the contractor be allowed to sweep the material to the shoulders after the completed shoulder as occurred on a couple of projects last year? | No, the millings from the rumble strips should be disposed of following the Standard Specifications for the Asphaltic Shoulder Rumble Strips item. | Fred Schunke | 3 | 2020-01-28 07:52 | 2020-01-29 14:04
20200211 | 20200211003 | 3 | Traffic/Safety | During staged construction when crews are working in the outside lanes, traffic control drums will necessarily encroach on the median travel lane reducing the width available to traffic. With the reduced lane width and narrow median shoulder, the â€œbail outâ€ path for traffic is into the work zone. This puts contractors labor, DOT staff and the traveling public in an unsafe situation. This will most likely be the case during concrete patching and asphalt paving. Would the Department implement measures to slow traffic such as workzone speed reductions, portable speed trailers, or State Patrol/County Sheriff presence? | The first construction stage widens the median shoulder pavement with a mill and overlay to allow extra room for traffic when the contractor is working in the outside lane. When working in the outside lane, the contractor is expected to remove the traffic control drums from the median travel lane once the construction operation is through in that area. This is noted on the Construction Staging typicals in the plan. The speed limit is to be reduced to 55 MPH when a lane is closed to traffic, per the special provisions. | Fred Schunke | 4 | 2020-01-31 13:17 | 2020-02-03 13:08
20200211 | 20200211003 | 3 | Common Excavation | How will the quantity of Common Excavation be calculated for measurement. There is minor scratch grading throughout the project. Will you be doing a survey or will you be paying plan qty.? | The common excavation will be calculated by doing a survey. | Fred Schunke | 5 | 2020-02-06 11:51 | 2020-02-07 14:12
20200211 | 20200211003 | 3 | Common Excavation | Station 1585+50 to 1597+00 shows no grading but has Common excavation and fill shown in the earthwork tables. How will this area be calculated and paid in the final qtys? Station 1642 to 1649 also? Station 1752 to 1770? These qtys are included in the bid qty and we want to make sure they will be included in the final calculation. | The estimated quantities are calculated through the engineering software. Survey in the field will be used to calculate the final quantities. | Jill Fehrman | 6 | 2020-02-07 16:02 | 2020-02-10 16:18
20200211 | 20200211003 | 3 | Design Schedule | Can the Design Schedule be provided? |  |  | 7 | 2020-02-10 05:06
20200211 | 20200211003 | 3 | Base Patch size and locations. | Can the Base Patch size and locations be provided? We need this information to perform accurate steel calculations. If we don't have this information we will be required to interpolate the quantities of steel based on the limited information provided. | The base patch size and locations will be marked in the field at the start of the project. | Jill Fehrman | 8 | 2020-02-10 06:55 | 2020-02-10 16:19
20200211 | 20200211003 | 3 | Base Patching | Confirming that base patching requires a high early strength B-Mix, per 710.4 (6), and not a straight B-Mix. |  |  | 9 | 2020-02-10 10:56
20200211 | 20200211004 | 4 | Bridge Agreement | Can you post a copy of the bridge agreement? | The bridge agreement can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211004/ | Mike Coleman | 1 | 2020-01-21 13:24 | 2020-01-21 13:25
20200211 | 20200211004 | 4 | Geotechnical Reports | Can you please provide geotechnical reports for this project? The plans do not have soil borings located by the new piers which require cofferdams. The reports will need to be review to see if the piling can be driven and the cofferdam installed | The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211004/ | Mike Coleman | 2 | 2020-02-03 15:03 | 2020-02-06 14:18
20200211 | 20200211004 | 4 | Contract Schedule | Has a schedule been prepared showing how this project can be done in 50 working days? If a schedule has been put together can it be provided? | An addendum will be issued to revised the contract time for completion from a 50 working day contract to a 70 working day contract. | Mike Coleman | 3 | 2020-02-04 06:43 | 2020-02-06 10:13
20200211 | 20200211006 | 6 | Culvert Pipe Cleaning B-52-0249 | Can you please provide the as-built for this structure? | The as-builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211006/ | Mike Coleman | 1 | 2020-01-23 09:51 | 2020-01-27 10:56
20200211 | 20200211006 | 6 | Mill and Relay/ Shaping Shoulders? | On sheet 6 and 7 of the Plans the Typical sections indicate that the existing HMA Pavement (22' to 24" Wide) is to be Milled 5" and then Relay 4.25" (28' to 30') wide. How is the existing CABC to be handled? Is the existing CABC to be removed or bladed out onto the fore slope? What bid items pays for this work? | An addenda will be issued to add the item Shaping Shoulders to the contract to handle the existing CABC outside the existing pavement. | Fred Schunke | 2 | 2020-02-03 10:09 | 2020-02-04 11:57
20200211 | 20200211006 | 6 | Butt Joints / Mill and Relay | On sheet 10 of the plans, lower half of the sheet- "Side Road Detail". Left hand side of detail shows the Mill and Relay stopping the Edge of Paved Shoulder and then a ~30' butt joint being milled. The right hand side of the detail shows Mill and Relay being completed for the entire intersection. Please clarify. Note that it would be very difficult to complete Mill and Relay in intersections due to the train of equipment used in the Mill and Relay operation. | An addenda will be issued to clarify the detail, the sideroads will have a ~30â€™ butt joint. | Fred Schunke | 3 | 2020-02-03 10:18 | 2020-02-04 11:58
20200211 | 20200211006 | 6 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211006/ | Mike Coleman | 4 | 2020-02-04 07:00 | 2020-02-10 12:59
20200211 | 20200211006 | 6 | Backfill Structure Type B | Will the department allow the use of 3/4" or 1 1/4" dense graded base course in place of backfill structure type B for the box culvert backfill similar to standard specification 520.2.5.2? | The Department will allow the use of ¾â€ or 1 ¼â€ dense graded base if all the material requirements of Section 210 of the Standard Specifications are met. | Fred Schunke | 5 | 2020-02-04 08:16 | 2020-02-04 15:32
20200211 | 20200211007 | 7 | Bid Item Structural Carbon Steel - Approved Fabricators | Is the structural carbon steel material (approved fabricators) for this project governed by Fabricated Bridge Components https://wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/appr-prod/ap-current/bridge-fabrications-2-1-2019.pdf OR Primary Steel Members https://wisconsindot.gov/Documents/doing-bus/eng-consultants/cnslt-rsrces/tools/appr-prod/ap-current/primary-members-11-29-2018.pdf | A fabricator from the â€œApproved Fabricators, Primary Steel Membersâ€ list will be required. The DT2333 form with a P.E. stamp will also be required. | Fred Schunke | 1 | 2020-01-27 14:14 | 2020-01-29 13:42
20200211 | 20200211007 | 7 | Steel pedestals | The ears for mounting the steel pedestals to the bridge abutment, can they be welded rather than the 2" bend radius it calls for? | Yes, ¼â€ bevel-groove welds ground flush on the side that abuts the concrete, and a ¼â€ fillet welds on the exterior/exposed side would be acceptable. The welds would be required full length. | Fred Schunke | 2 | 2020-01-28 15:02 | 2020-01-30 13:17
20200211 | 20200211008 | 8 | Removing Asphaltic Wedge Milling | Where on the project will the 6,400' of asphaltic wedge milling take place? The Misc. qty's list the entire limits of the project. Is this item only used on the surface lift of HMA? Please advise. | On page 146 of the project drawings under â€˜LEGEND: SYMBOLS ALL STAGESâ€™ there shading is for â€˜ASPHALTIC SURFACE TEMPORARY WEDGE AND ASPHALTIC SURFACE MILLING (SEE CONSTRUCTION DETAILS - STAGING AND TRAFFIC CONTROL PLANS)â€™. The anticipated locations of the asphaltic surface temporary wedge and asphaltic surface milling are indicated with the shading shown in the legend in the subsequent traffic control drawings. Details are provided on page 149 of the project drawings. | Fred Schunke | 1 | 2020-01-21 15:33 | 2020-01-24 13:15
20200211 | 20200211008 | 8 | Earth work table | Can we get clarification on the earth work table in the misc. quantities section. Not one part of it makes any sense. | Drawing sheet 229 includes the miscellaneous quantity earthwork summary table. The earthwork summary table includes footnotes 1-8. Please provide a specific question if the footnotes provided do not clarify the values listed in the table. | Fred Schunke | 3 | 2020-01-23 14:50 | 2020-01-27 08:16
20200211 | 20200211008 | 8 | Asphaltic Surface Temporary Wedge Detail | On plan sheet 149 the Asphaltic surface temporary wedge is shown. Is the intent to install this wedge/ramping while paving binder (monolithically) with berm extension or to install the wedge on top of the binder in a separate operation? If wedge is installed while paving binder will the density gauge be placed outside of the wedge area to remain on a flat surface during testing? | The contractors means and methods shall dictate how the asphaltic surface temporary wedge is paved. The density requirements in the project specifications shall apply to the binder and surface layers as shown in the drawings. | Fred Schunke | 4 | 2020-01-28 10:12 | 2020-01-29 13:47
20200211 | 20200211008 | 8 | Soil Borings | Are there soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211008/ | Mike Coleman | 5 | 2020-02-04 07:01 | 2020-02-10 13:06
20200211 | 20200211008 | 8 | Recycled Base | Will WisDOT allow recycled aggregate products on this project or will city of Fitchburg specifications supersede? | Recycled base will be allowed by the City of Fitchburg with restrictions and conditions. The restrictions and conditions are provided in Addendum #1 for project 5849-02-02. | Jill Fehrman | 6 | 2020-02-04 09:02 | 2020-02-06 20:22
20200211 | 20200211008 | 8 | Signal Control Cabinet | A signal control cabinet is shown on the PD & Marketplace Drive intersection. There is a type P base for this on the estimate of quantities list however the control cabinet is not on the list. Is this control cabinet to be included in the project or is this being supplied by the city ? | The traffic signal control cabinet at this intersection will be provided by and installed by the City of Madison. | Fred Schunke | 7 | 2020-02-06 07:16 | 2020-02-07 14:13
20200211 | 20200211009 | 9 | Prep for Asph Shoulders & Shaping Shoulders | The quantity under the prep foundation for asphaltic surface item looks like it includes stations of the roadway that are not getting widened out (~101+00 to ~595+00), is the intention to pay for those stations the same as the areas where the shoulders will be widened? Similarily, the shaping shoulders item seems to be 1.5x what the proper stationing should be, is there a reason for this? | An addendum will be issued to clarify these questions. The quantities and locations for item 305.0500 Shaping Shoulders and item 211.0400 Prepare Foundation for Asphaltic Shoulders will be revised to address the questions below. The section from Sta ~101+00 to ~595+00 will be removed from the quantity on bid item 211.0400 Prepare Foundation for Asphaltic Surface. The quantity for item 305.0500 Shaping Shoulders was incorrect was will be revised as part of the addendum. | Fred Schunke | 1 | 2020-01-23 15:41 | 2020-01-29 14:05
20200211 | 20200211009 | 9 | Items 305.0110 and 305.0504.S breakdowns | Can the designer show how they are coming up with 14,700 tons of new 3/4" BAD and 2,280 CY of excess material? Item 305.0504.S, Hauling Excess Shoulder Material states that all the excess existing suitable shoulders are to be loaded, hauled and placed along the roadway to areas of deficiency as the engineer directs. How do we know what is suitable and what we need to haul off the project for bidding purposes? There is not an item to haul this material off the project. | An addendum will be issued to clarify these questions. The bid items and quantities will be revised to address the questions below. The quantity for bid item 305.0110 Base Aggregate Dense ¾-Inch will be revised (lowered) to better reflect field conditions. Bid item 305.0504.S Hauling Excess Shoulder Material will be removed from the contract as part of the addendum and replaced with a new item SPV.0035.02 Removing Excess Shoulder Material that describes that the excess shoulder material is to be hauled offsite. The quantity for this new item will be increased from what was shown for the Hauling Excess Shoulder Material item. | Fred Schunke | 2 | 2020-01-27 16:29 | 2020-01-30 13:11
20200211 | 20200211009 | 9 | Grade, Shape, Finishing Intersection | Are there quantities for the intersection work? There is other grading work being done at each of these intersections with work being paid by the applicable grading and restoration items. Where is the cutoff of what is incidental to the intersection and what will be paid under the items? Thanks | The intent of these 2 items is that they include the work necessary to widen and grade the intersection and grade for the beam guard in the radius areas shown in the details (from the labeled saw cuts to the necessary slope intercepts behind the beam guard. This work is not intended to include any grading or finishing work required for the end terminals of the beam guard. That is covered in other bid items. The quantities for the 2 intersections are estimated as follows: Grading, Shaping and Finishing Intersection Dorset Avenue, Item 205.9015.S.01 Excavation Common: 50 CY Salvaged Topsoil: 135 SY Seeding Mixture No. 20: 4 lb Seeding Temp: 2 lb Erosion Mat Class II, Type C: 135 SY Grading, Shaping and Finishing Intersection Copper Road, Item 205.9015.S.02 Excavation Common: 150 CY Salvaged Topsoil: 300 SY Seeding Mixture No. 20: 8 lb Seeding Temp: 4 lb Erosion Mat Class II, Type C: 300 SY | Fred Schunke | 3 | 2020-01-29 09:20 | 2020-01-30 13:17
20200211 | 20200211009 | 9 | Tack Quantity | The tack quantity seems to be overstated by quite a bit. Could this be reviewed for accuracy | The tack quantity was reviewed and an error was found. An addendum will be issued with a revised quantity. The revised tack quantity will be approximately 41,080 gallons. | Jill Fehrman | 4 | 2020-02-04 07:45 | 2020-02-06 19:45
20200211 | 20200211009 | 9 | Covering milled surface | In the special provisions it talks about waving the 48 hours to cover the milled surface in Juneau County under the road closure, but doesn't address Monroe county. With the closure of the entire section could this same provision hold true for Monroe county or if a particular section is what is warranting this be called out specifically. With the undistributed quantity on distressed pavement milling and not being able to plan for this appropriately with a 48 hour time frame, this could come at a much higher cost than if there was more time to accommodated the work and a far less chaotic work zone. | The design team and the Department feel this provision needs to remain as written. - It is anticipated that a higher volume of local traffic using the Monroe County section as access from STH 21 to Mather during the detour period. The intent is to manage the time length that this local traffic has to drive on the milled surface. - After milling, the remaining asphalt pavement in the Monroe County section is approximately 2-inches. In Juneau County, the portion remaining is approximately 5-inches. The intent is to manage and minimize the time traffic has to drive on the remaining 2-inch layer in Monroe County before the new asphalt is added. - The project schedule anticipates that the Monroe County portion could be under construction prior to closing the Juneau County portion in June, which could result in high traffic volumes on the milled surface. | Jill Fehrman | 5 | 2020-02-04 07:52 | 2020-02-06 19:50
20200211 | 20200211009 | 9 | Extra Depth HMA Pavement | On the SPV item removing distressed pavement milling the quantity is for 43,400SY. To fill that back in it is paid under the Extra Depth HMA pavement SPV. That quanity is 1670 tons. calculating out the HMA quantity using 43,400SY would yield 4900 tons. There appears to be a discrepancy between the 2 items | After a review of the quantity computations for these 2 items, we feel that the quantity of 1670 tons shown for the Extra Depth HMA Pavement SPV is the better representation of field conditions. The SPV item for removing distressed pavement milling was over estimated and we expect that quantity to under-run the amount listed in the plans. | Fred Schunke | 6 | 2020-02-04 14:39 | 2020-02-07 14:30
20200211 | 20200211009 | 9 | Geotech Reports | Can you send or post the Geotech reports for the three structures? C-29-62, C-29-63, C-29-64 | The Geotech reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211009/ | Mike Coleman | 7 | 2020-02-06 08:36 | 2020-02-10 13:21
20200211 | 20200211012 | 12 | Mobilizations Erosion Control | The standard mobilization item allows 72 hours from initial order. In addition to the elevated penalties on this project, has the arrival time also been reduced? Please confirm that the 48 hour language is accurate for this project. | The Mobilizations Erosion Control article 14 and the Mobilizations Emergency Erosion Control article 15 will be removed in an addendum. | Fred Schunke | 1 | 2020-01-23 11:34 | 2020-01-27 08:24
20200211 | 20200211012 | 12 | Railroad Crossing and special training | If we are installing fence and working within 25 feet of the railroad crossing, do we need any special training prior to working that close to the crossing? | Yes, the employees installing the fence will be required to obtain e-railsafe training as described in section 9.D. This is because the fence will be on Canadian Pacific property near the crossings. D Rail Security Awareness and Contractor Orientation Prior to entry on railroad right-of-way, the contractor shall arrange for on-line security awareness and contractor orientation training and testing and be registered through "e-RAILSAFE" for all contractor and subcontractor employees working on railroad right-of-way. See e-railsafe.com "Information". The security awareness and contractor orientation training is shown under the railroadâ€™s name. The department has secured right of entry to railroad property; neither the contractor nor subcontractors or their employees will be required to sign a right of entry form. 1009-86-18 15 of 20 The security awareness and contractor orientation certification is valid for two year(s) and must be renewed for projects that will carry over beyond the 2 year period. Contractor and subcontractor employees shall wear the identification badge issued by e-RAILSAFE when on railroad right-of-way. Costs associated with training and registration are incidental to other items in the contract. stp-107-034 (20170615) | Jill Fehrman | 2 | 2020-02-04 16:20 | 2020-02-06 20:07
20200211 | 20200211013 | 13 | Contractor Data Request | Can you provide the Existing Ground CAD Surface, Design CAD Files (Subgrade & Base Aggregate Surfaces with Alignments & Linework), Excel Earthwork Sheets, Design Schedule and Soils Reports? | The design schedule and geotechnical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211013/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. All electronic files will be transmitted upon completion of an upcoming Addendum. We will advise when the files have been uploaded. The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211013/ | Mike Coleman | 1 | 2020-01-17 08:36 | 2020-01-27 10:49
20200211 | 20200211013 | 13 | Stage 1B Earthwork | Stage 1B shows work in the median between the crossovers and there are quantities for aggregate and asphalt but the Earthwork Summary/Earthwork Data sheets/cross sections don't show any CYs. Can the Cross Sections/Earthwork Data Sheets/Earthwork Summary Sheets be updated to include Stage 1B? | The crossover earthwork has been added to the plans and will be included in Addendum #1. | Fred Schunke | 2 | 2020-01-17 15:33 | 2020-02-04 12:00
20200211 | 20200211013 | 13 | Stage 4A & 4B Earthwork | There are no Earthwork Qtys for the removal of the temporary roadways shown in the traffic control plans for Stage 4A & 4B. Can this work be added to the Earthwork Summary and Earthwork Data Sheets? | The earthwork for the removal of the temporary crossover has been added to the plans and will be included in Addendum #1. | Fred Schunke | 3 | 2020-01-17 15:38 | 2020-02-04 12:03
20200211 | 20200211013 | 13 | CAD Files | Could you please provide the following: 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .DWG or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .DWG or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .DWG or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .DWG or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .DWG or .DGN) | The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211013/ | Mike Coleman | 4 | 2020-01-20 11:06 | 2020-02-03 06:46
20200211 | 20200211013 | 13 | Schedule - Award & Contract Execution Dates | This project has a very aggressive schedule. What date does the Designer expect construction to start to complete all work within the Interim/Final Completion Dates? When will this project be awarded? Some projects from the December letting are still not awarded, so if that happens on this project the schedule will not be met. Why does the restoration/landscaping need to be completed by the interim completion date? This seems impossible for all of the interim completion dates. Can the restoration/landscaping items be excluded from these dates (as long as traffic is switched = no liquidated damages)? Please provide a design schedule with all work items included within it. Also please state how many weather days are included in the schedule. | Project will be awarded within normal WisDOT guidelines. Contract execution is dependent on the contractorâ€™s ability to submit complete and fully executed paperwork that meets the Departments requirements. Work can start no earlier than April 1, 2020. Stages are expected to be completed in their entirety in accordance with the specifications. In accordance with contract documents, a stage must be completed in its entirety. No lane closures will be allowed for any contractor to remobilize to complete restoration. Regardless of whether lane closures are required for restoration or not, the interim LDs will continue to accrue for all work that is specified to be complete for that stage that is not complete. This is a completion date contract with all work to be complete by December 11, 2020. | Fred Schunke | 5 | 2020-01-21 17:00 | 2020-01-24 13:56
20200211 | 20200211013 | 13 | Design Schedule | Can the Design Schedule be provided? |  |  | 6 | 2020-01-22 08:10
20200211 | 20200211013 | 13 | Design Schedule | Can the Design Schedule be provided? |  |  | 7 | 2020-01-22 08:10
20200211 | 20200211013 | 13 | Overhead Sign Supports | Between pages 62-70, it appears that either some structure numbers are incorrect, duplicated, or a couple of structures are missing. | There are nine proposed sign structures. Sheets 1 of 9 and 2 of 9 were inadvertently included in the plans twice and sheets 8 of 9 and 9 of 9 were inadvertently not included in the plans. The details for S-51-249 (sheet 8 of 9) and S-51-250 (sheet 9 of 9) will be added to the upcoming addendum. | Fred Schunke | 8 | 2020-01-23 11:58 | 2020-01-27 11:03
20200211 | 20200211013 | 13 | 4' Concrete Pavement Widener. | Is a construction joint required for where the 4' widener meets the through lanes in the 11.5" Concrete Pavement areas. This joint has been eliminated entirely on most pavements in the area. We do not see 4'wideners through turn lanes in the area and when they have been designed they have been eliminated prior to construction. Is it possible to get the planned construction joint where the 4' widener meets the through lanes prior to bid rather than after? | The maximum concrete panel width is 15â€™. As a result, the joint cannot be eliminated. A general note has been added to the plans to note the maximum concrete panel width. | Mike Coleman | 9 | 2020-01-27 10:41 | 2020-02-03 06:50
20200211 | 20200211013 | 13 | Can more detail be provided on where HES concrete will be used on the project. | Given the extremely tight schedule and the large number of pours and cure times needed as a result of the project design, can more precise location for where HES concrete will be used be provided? Also, can a HES curb and gutter item with significant quantity and locations for use also be provided? | HES curb and gutter has been added to the project and will be included in Addendum #1. The high early strength concrete and high early strength curb and gutter can be used by the contractor with approval by the engineer at locations that are considered necessary to meet the project schedule along with the requirements of the prosecution and progress. Precise locations are not given since they will be specific to individual contractor's means and methods. | Fred Schunke | 10 | 2020-01-28 06:20 | 2020-02-04 12:03
20200211 | 20200211013 | 13 | Pavement Design Report | Is there a PDR available for this project? | The Pavement Design Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211013/ | Jill Fehrman | 11 | 2020-02-04 09:56 | 2020-02-10 16:27
20200211 | 20200211013 | 13 | Design Schedule Missing Information | The Design Schedule that was provided doesn't have the detail below the Ghantt Chart as other provided schedules. Other provide schedules usually have work items with quantities and productions showing all the work items can be completed within the time allowing in the contract at the bottom of the schedule. Can an updated schedule be provided showing this detail? | This will be addressed via addendum | Fred Schunke | 12 | 2020-02-04 11:31 | 2020-02-07 14:20
20200211 | 20200211013 | 13 | Addendum #2 Clarification | Please provide clarification on the addenda # 2 issued February 6, 2020 regarding the interim completion date being accelerated to September 30th. The department provided Gantt chart shows stage 3 concrete paving from early to late October. We do not feel this acceleration is actually achievable, please provide a revised schedule showing greater detail with regards to excavation, storm sewer, aggregate, concrete paving, and electrical/signal items. Has the Department eliminated any work items or adjusted staging to accommodate this acceleration to the schedule? The work site is not large enough to support â€œextraordinary forcesâ€, without sacrificing quality, and safety. | The Gantt chart provided by the Department is an approximation. The contractor shall submit their schedule indicating provision of adequate forces, equipment, and material to meet the interim and final completion dates as specified. | Fred Schunke | 13 | 2020-02-06 15:37 | 2020-02-07 14:32
20200211 | 20200211013 | 13 | Addendum #2 Clarification | Please provide clarification on the addenda # 2 issued February 6, 2020 regarding the interim completion date being accelerated to September 30th. The department provided Gantt chart shows stage 3 concrete paving from early to late October. We do not feel this acceleration is actually achievable, please provide a revised schedule showing greater detail with regards to excavation, storm sewer, aggregate, concrete paving, and electrical/signal items. Has the Department eliminated any work items or adjusted staging to accommodate this acceleration to the schedule? The work site is not large enough to support â€œextraordinary forcesâ€, without sacrificing quality, and safety. |  |  | 14 | 2020-02-06 15:37
20200211 | 20200211013 | 13 | Add#2 - Schedule Change | Is addendum #2 a mistake? The schedule was nearly impossible before this addendum. Now its definitely impossible. This addendum removed another 30 days from stage 3 and stage 4. Why? Can we get the 30 days back? Can weather days be added back into this contract? We can't control the weather. Or aleast tell us how weather days we should estimate in our bid schedule? | The contactor shall submit their schedule indicating provision of adequate forces, equipment, and material to meet the interim and final completion dates as specified. Severe weather exclusion language was removed in addendum #2. Contractor shall consult Section 108 of the Standard Specifications for information regarding severe weather days on this completion date contract. | Jill Fehrman | 16 | 2020-02-07 09:47 | 2020-02-07 18:14
20200211 | 20200211013 | 13 | Milling | Item 014 Removing Asphaltic Surface Milling. In the miscellaneous quantities page 449 it references milling in SY however on the bid form it is bid the same quantity as TON. I assume this is by the SY as the area ties off and assuming the bid form needs to be modified? Also for milling, there is some additional milling noted for the temp widening at STA 265+00 LT. These quantities are not noted in the quantities and assuming this will be paid under the milling item? |  |  | 17 | 2020-02-10 09:31
20200211 | 20200211013 | 13 | Addendum #1 - CPM Schedule Specification Change | Addendum #1 revises the monthly CPM schedule item to state that: "The department will retain 10 percent of each estimate until the Department accepts the monthly CPM Update". What will be the process for payment in the event that the contractor and Department are in disagreement on the schedule? |  |  | 18 | 2020-02-10 09:56
20200211 | 20200211014 | 14 | Video Detection | The proposal states that the video detection system will be state furnished. What model video camera system is being furnished? | Video system being furnished is the Autoscope Vision. | Fred Schunke | 1 | 2020-01-23 14:56 | 2020-01-27 15:16
20200211 | 20200211014 | 14 | Dynamic Late Merge System | Question 1 For the dynamic late merge system, it is unclear if the temporary flashing will be needed on the left shoulder or just on one side of the road. The shoulder on the left looks very narrow and plans say final locations will be determined in the field. Will there be three or six temporary flashing beacons needed? Question 2 In the proposal for Dynamic Late Merge System, Item 643.1110.S under section B.2 Portable Traffic Sensors it reads that the PTS needs to only capture vehicle speed in MPH. In section C.2 Reports it reads the report must include speed, volume, and classification. Please clarify what is actually needed. | This was clarified in addendum #02. | Mike Coleman | 2 | 2020-02-03 15:53 | 2020-02-10 13:08
20200211 | 20200211014 | 14 | Traffic Control Plan Sheets | Will the traffic control plans be revised to match the changes made to the prosecution and progress in addendum #1? Conflicts listed below: 1. No work on NB until off ramp is complete. 2. No work on SB until stage 1B Can NB be in a different traffic stage than SB at the same time? ie. NB in 1B and SB in 1A? | Plan sheets will not be reissued. An addendum will handle any changes needed. Per 105.4 (3) addenda and the special provisions take precedence. | Fred Schunke | 3 | 2020-02-04 13:49 | 2020-02-07 14:20
20200211 | 20200211014 | 14 | Project Schedule | Please provide the anticipated project schedule used in the development of the proposal. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211014/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2020-02-04 14:57 | 2020-02-10 13:23
20200211 | 20200211014 | 14 | Bid Item #670 - Bridge Joint Repair | This is an SPV item but there is not a Special Provision for it in the proposal. | An emergency addendum was issued on 2/10/2020 to add the SPV for Bridge Joint Repair. | Jill Fehrman | 5 | 2020-02-04 15:10 | 2020-02-10 16:06
20200211 | 20200211014 | 14 | Area to be cleaned and painted. | Structure B-40-586 has four girders. The estimated area to be cleaned appears to only included three girders. Can that be corrected? |  |  | 6 | 2020-02-07 17:38
20200211 | 20200211015 | 15 | Cross overs | I do not see a detail for building the crossovers, or a temporary asphalt item for the pavement | Key layout points are provided in the plan sheets for Stage 1. An addendum will be forthcoming for the temporary asphalt pavement and cross sections that better show the crossover. | Fred Schunke | 1 | 2020-01-22 08:45 | 2020-01-27 09:08
20200211 | 20200211015 | 15 | IRI ride | Is this a Ride spec job, I see no item | IRI Ride is needed and will be added. An addendum will be prepared for IRI Ride and Temporary Asphalt Pavement (Question #1) in the near future. | Fred Schunke | 2 | 2020-01-22 08:46 | 2020-01-27 09:08
20200211 | 20200211015 | 15 | Video Detection | The proposal states that the video detection system will be state furnished. What model video camera system is being furnished? | There is no video detection on this project. There is a Cohu observation camera for the temporary signal at STH 164 & CTH ES. | Fred Schunke | 3 | 2020-01-23 14:57 | 2020-01-27 09:09
20200211 | 20200211015 | 15 | Storm Sewer | I do not see items for the storm sewer work shown on sheet 109. | There will be an addendum coming to address missing items brought to light. | Fred Schunke | 4 | 2020-01-31 11:09 | 2020-02-04 09:21
20200211 | 20200211015 | 15 | storm sewer | please clarify what is incidental to the inlet adjust/reconstruct and what is paid for. sheet 18 refers to payment of 31" curb and gutter, however there is no 31" curb and gutter item on the contract. | The detail on page 18 is applicable to all adjusting/reconstructing inlets and manholes, regardless of size. Addendum 1 added a section to make the No. 4 bars incidental. Other incidental items are called out on the detail. | Jill Fehrman | 5 | 2020-01-31 12:40 | 2020-02-03 08:14
20200211 | 20200211015 | 15 | Storm Sewer | Is the curb and gutter removal and replacement shown on sheet 18 paid for? If so, under what items or is it incidental to the reconstruction/adjustment? | There will be an addendum coming to address missing items brought to light. Although the detail gives a curb and gutter type, 31-inch, it is for all curb and gutter adjusting/reconstructing for any size. The â€œ31-inchâ€ will be crossed off in the next addendum. Curb and gutter adjacent to the inlets, removal and replacement, and the Tie Bars will be paid under their respective items. Addendum #1 added the No. 4 bars as incidental. The Detail on Page 18 indicates that the items described below are incidental. This does not impact anything else that may be incidental as called out for under the specific items as described in the Wisconsin Standard Specifications Manual. Plan View â€œ**â€ - call out that pavement removal and replacement is incidental to Adjusting or Reconstructing Inlets or Manholes. Above the ** note, â€œConc. Pavt Removalâ€ has the â€œ**â€ and the area indicated is any section of roadway that would need to be removed, adjacent to the flange line, to allow work to be done. The description will be changed to â€œPavt Removalâ€¦â€¦â€ in the next addendum. Section A â€“ A The same section called out by the â€œ**â€ in the plan view is shown below in the â€œSections A-A Inletsâ€ drawing with an arrow stating that that the cost of replacing the material in the roadway, adjacent to the edge of structure, is incidental. The mention of â€œconcreteâ€ in that note will be changed to â€œHMA pavementâ€ in order to match the adjacent pavement type. | Fred Schunke | 6 | 2020-02-03 09:14 | 2020-02-04 09:20
20200211 | 20200211015 | 15 | 42 Inch Cones | What is the intended use for the 42 inch Cones? There is a large quantity shown in the miscellaneous quantities, however they are not shown in use on any Traffic Control typical sections or Traffic Control staging plans. Thanks | The 42-inch cones were removed from the plan when the staging was changed to allow for echelon paving. Their removal was missed in the quantities. An addendum will be issued to remove this item. | Mike Coleman | 7 | 2020-02-04 12:27 | 2020-02-05 13:30
20200211 | 20200211015 | 15 | 36'' TYPE D CURB | The plan does not show any pavement removal and replacement for the curb installation. The curb cannot be installed against existing asphalt. Will there be items added for sawing, asphalt removal, and asphalt patching against the new curb and gutter? | The pavement adjacent to the new curb should not be disturbed during its removal and construction. An addendum will be issued to add quantities for the material disturbed behind the curb (sidewalk, common excavation, topsoil) | Jill Fehrman | 8 | 2020-02-04 14:47 | 2020-02-06 20:19
20200211 | 20200211015 | 15 | Poles type 12 | Are these poles required? Misc quantities show them on the same bases as the transport & Install Poles type 9 special |  |  | 9 | 2020-02-07 11:49
20200211 | 20200211015 | 15 | HMA Joint Density Incentive ITem | Item #460.2007 is an HMA joint density incentive item that should have a predetermined unit price of $1.00/DL. The predetermined unit price for this item is $0.40/DL Is the intent to only pay 40 cents on the dollar for any HMA joint density incentive that is achieved? Why????? |  |  | 10 | 2020-02-09 23:06
20200211 | 20200211018 | 18 | Design Schedule and CAD files | Can a design schedule and CAD files be provided | A link has been created on SE preliminary plans page to the file location, ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211018/ https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Fred Schunke | 1 | 2020-02-06 09:53 | 2020-02-07 14:33
20200211 | 20200211018 | 18 | Overlapping of Stages. | Can various stages be overlapped so that the project can be expedited and coordinated more efficiently? |  |  | 2 | 2020-02-10 06:04
20200211 | 20200211020 | 20 | soil borings | Are there soil borings for this project | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211020/ | Mike Coleman | 1 | 2020-01-30 09:03 | 2020-02-03 06:54
20200211 | 20200211022 | 22 | Asphlatic Surface | With the Asphaltic Surface carrying temporary traffic, could the contractor place the asphalt in 1 lift? | Yes, the asphalt will be placed in one lift. | Fred Schunke | 1 | 2020-01-28 07:53 | 2020-01-29 13:44
20200211 | 20200211022 | 22 | Traffic Queue Warning System | In regards to the length of the system, typical application is to place a PCMS every mile extending approximately three miles out from the start of the project (3 Total PCMS). The Misc Quantities for this project states the length of the Queue systems as 9 and 10 miles, which places the start of the system before WI-441. Is the intent of the Queue Warning System to place three PCMS signs before WI-441 and then place no additional PCMS leading up to the project, or is the intent to place 9 or 10 PCMS in each direction (one every mile)? Thanks | Place 9 or 10 PCMS in each direction (one every mile). This is the potential queue length that may be generated. The contractor is to present the department with their findings for queue lengths for each direction prior to setup of the system, so that we can verify the lengths and the ultimate placement of the boards along I-41 they plan to layout. | Jill Fehrman | 2 | 2020-02-04 12:18 | 2020-02-06 19:58
20200211 | 20200211022 | 22 | Portable Automated Real-Time Traffic Queue Warning System | Can you please provide a device layout for the above Real Time QWS? Nothing for a layout in Plans 22 | See Article 18. in the Special Provisions: C Construction C.1 General Install and reposition Portable Automated Real-Time Queue Warning System per plan with PCMS spaced every one mile starting one mile upstream of the taper or as the engineer directs. Provide plan to the engineer 14 calendar days in advance of construction. The spec language requires the contractor to provide the plan to the engineer 14 calendar days in advance of construction. | Jill Fehrman | 3 | 2020-02-05 12:27 | 2020-02-07 07:37
20200211 | 20200211022 | 22 | Portable Automated Real-Time Traffic Queue Warning System | -Can you please provide a device quantity for the Real Time QWS? Nothing for specific quantities in proposal 22 | See Article 18. in the Special Provisions: C Construction C.1 General Install and reposition Portable Automated Real-Time Queue Warning System per plan with PCMS spaced every one mile starting one mile upstream of the taper or as the engineer directs. Provide plan to the engineer 14 calendar days in advance of construction. The spec language requires the contractor to provide the plan to the engineer 14 calendar days in advance of construction. Anticipated queues are represented in the miscellaneous quantities on sheet 29 of the plans (9 to 10 miles in respective direction)â€¦.1 mile = need for 1 PCMS setup. The contractor will need to verify this within their respective plan. | Jill Fehrman | 4 | 2020-02-05 12:27 | 2020-02-07 07:40
20200211 | 20200211023 | 23 | HMA Quantities | The typical sections show a 2.5â€ layer of 3 LT and a 1.75â€ layer of 4 LT. The quantities reflect a 2.5â€ layer of 4 LT and 1.75â€ layer of 3 LT. Which one is correct? | These inconsistencies will be fixed with an addendum. | Fred Schunke | 1 | 2020-01-23 09:18 | 2020-01-28 10:04
20200211 | 20200211025 | 25 | Earthwork Summary | On the earthwork summary. 4 - Salvaged unusable pavement is 0 CY is this shown correctly? 7 - Expanded EBS Backfill shows 12855 CY is this number correct? If so what is it representing? | The earthwork table will be updated via Addendum to include the unsalvaged/unusable pavement and to make corrections to the calculations for EBS Backfill. | Fred Schunke | 1 | 2020-01-24 13:43 | 2020-01-30 13:15
20200211 | 20200211025 | 25 | Staking | There are no items for staking subbase or base? Will these items be added? | Yes, Item 650.5000 Construction Staking Base, 3,625 LF will be added to the contract in an addendum. | Fred Schunke | 3 | 2020-01-24 13:54 | 2020-01-30 13:16
20200211 | 20200211025 | 25 | Work By Others | Brown County will be performing the asphalt paving. Will they be doing the fine grading? Also they will be doing night time paving. There is a Nighttime Work Lighting Stationary #23 Special Provision. Will Brown County be performing this due to their work? | Brown County will complete the fine grading just before paving but the Contractor will need to have some base material available, if needed, and someone available to haul away excess base material during fine grading. The Contractor will need to provide the Nighttime Work Lighting-Stationary described in the Special Provision. The work by others article of the Special Provisions will be updated in an Addendum to include this additional information. | Fred Schunke | 4 | 2020-01-24 14:01 | 2020-01-30 13:16
20200211 | 20200211025 | 25 | EBS/Common Quantites | With EBS quantities being undistributed and 20% of the Cut amount, how potential changes in the quantities be handled in case if EBS is not what shown in a plan. Common Excavation is a blended unit price item and any extra waste is a most expensive part of the item, therefore any deviation from the plan quantities will have an impact on the overall unit price. Would it be handled as a change of conditions in case if EBS quantities are different from what plan shows? |  |  | 5 | 2020-02-07 09:15
20200211 | 20200211027 | 27 | Temporary Pavement Markings | On similar projects, the temporary paint item would be placed on the milled surface and a same day or temporary epoxy item would be placed on the upper layer so that removal of the temporary paint item is not required (if it is placed on the surface layer) after rumbles and prior to placing the permanent markings. Will the agency issue an addendum to add the temporary or same day epoxy item for the upper layer and reduce the quantity of the temporary paint item to what is needed on the milled surface? Thank you. | No addendum would be issued. Once the surface has been placed, the temporary pavement marking would need to be placed. Construction of the centerline rumble strips would follow, the construction of the rumble strips would remove the temporary pavement marking. Permanent pavement marking would then be placed. | Fred Schunke | 1 | 2020-01-30 08:47 | 2020-02-03 13:08
20200211 | 20200211027 | 27 | Soil Borings | Are there soil borings available for this project? | Soil borings arenâ€™t available for this project | Jill Fehrman | 2 | 2020-02-04 07:03 | 2020-02-06 19:53
20200211 | 20200211027 | 27 | Pavement Markings | Good morning and thank you for the response on my previous question. While I agree that the temporary markings would be partially removed, I do not feel they would be totally removed and there would still be temporary paint left on the surface where the permanent markings are to be placed. The spots that the rumble strip operation removes would not have residual temporary paint left over but there will still be temporary paint on the surface where the rumbles operation does not remove the asphalt (in between the rumbles). I would ask that you reconsider this matter and issue an addendum switching the temporary paint to temporary epoxy or same day epoxy so that there are no issues going forward. Thank you. |  |  | 3 | 2020-02-04 07:38
20200211 | 20200211029 | 29 | Pile Points | Pile Points are listed on the Estimate of Quantities in the bridge plan, but there is not an item for the Pile Points listed on the Proposed Schedule of Items nor is there any information regarding them in the Foundation Data in the bridge plan. Please advise. | The use of pile points is correct, and the bridge plans are correct. This will be addressed in the Schedule of Items in an addendum. | Fred Schunke | 1 | 2020-01-21 14:34 | 2020-01-27 09:06
20200211 | 20200211032 | 32 | Pier Construction | Will concrete poured underwater be allowed to construct the piers? | Concrete poured underwater will be allowed to construct the piers. An addendum will be issued to add language to the special provisions. | Mike Coleman | 1 | 2020-02-04 08:26 | 2020-02-06 10:15
20200211 | 20200211032 | 32 | timber piling removal, existing pier footings in conflict with new | Hi, Can you please note which timber piling you want removed? Does that include the pier? In reviewing the as built plans, the new piers appear conflict with the old pier footing, which means the entire pier and pier footing will have to be removed. Would the Department entertain shifting the bridge 2' to the north to avoid this substantial removal cost? |  |  | 2 | 2020-02-10 14:44
20200211 | 20200211035 | 35 | Pre-boring on structure B-3-209 | Pre-boring plan quantity for this structure is 60 lineal feet, or 30' per abutment. However, the bottom elevations of the abutments are roughly 16-17.25' above bedrock. If pre-boring 5' into bedrock is the goal, that would yield a quantity closer to 300 lineal feet for the project. Can you please review this quantity and confirm what it should be? Thank you. | The correct plan quantity for this item is 250 LF. An addendum is being submitted to correct the quantity and pertinent plan sheet. | Fred Schunke | 1 | 2020-01-23 13:54 | 2020-01-29 13:48
20200211 | 20200211038 | 38 | Contractor Data Packet Request | Can you provide the Existing Ground CAD Surface, Design CAD Files (Subgrade & Base Aggregate Surfaces with Alignments & Linework), Excel Earthwork Sheets, Design Schedule and Soils Reports? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211038/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-01-14 13:04 | 2020-01-21 07:03
20200211 | 20200211038 | 38 | Contractor Data Packet | Can you provide the original ground and design surface files in LandXML format? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211038/ In addition to the XML files, raw data files of the design surfaces are also provided in AutoCAD format. Note that these CAD files are simply a graphic representation of the engineering hardcopy plans and are being provided for informational purposes only. In the event of a conflict, the data in the plans presides over these CAD files. | Mike Coleman | 2 | 2020-01-24 15:14 | 2020-02-03 08:07
20200211 | 20200211038 | 38 | Item 144 Bar steel reinforcement coated quantity error | It appears there is an error in the total quantity for bid item 144, coated rebar. Total bid quantity is 123,030 lbs but there is a quantity of 144,720lbs on B-30-139 and 8,310 lbs for C-30-07. Total quantity for this item should be 153,030 based on the structure plans. | Total quantity for Bid Item 505.0600, Bar Steel Reinforcement HS Coated Structures, shall be 153,030 LB under this contract. An addendum will be issued to clarify this correction in the Schedule of Items. We are currently assembling an addendum for this revision as well as a couple other updates for submittal to WisDOT later this week. | Fred Schunke | 3 | 2020-01-28 10:00 | 2020-01-29 14:03
20200211 | 20200211040 | 40 | Lane Closures - Entrance to JC Penney | Will we be allowed to close one of the lanes of the entrance and exit to JC Penney to install SB3 and SB4? | There is a 2 night closure for the mall entrance, but there will be other opportunities for single lane closures of the mall, during the STH 157 Southbound and Northbound closure stages. | Jill Fehrman | 1 | 2020-01-17 10:30 | 2020-01-23 08:14
20200211 | 20200211040 | 40 | Design Schedule | Can the Design Schedule be provided? | Yes, the link, ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200211040/, can be found on the Southwest Preliminary Plans page. | Fred Schunke | 2 | 2020-01-27 21:26 | 2020-01-31 11:49