## qandasearchletting_results
Date: | 2020-12-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20201208 | 20201208002 | 2 | Pcc Base Course Pavement | Will the 9" pcc base course 9" and 9-1/2" base course pavement be a doweled pavement ? per standard detail drawings. | Yes, the 9â€ and 9 ï¿½â€ concrete base items will be a doweled pavement per the standard detail drawings. | Mike Coleman | 1 | 2020-11-04 15:18 | 2020-11-05 09:47
20201208 | 20201208002 | 2 | Design File Request | Can the Department provide the Meta-Data files for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208002/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2020-11-18 08:23 | 2020-11-18 13:46
20201208 | 20201208002 | 2 | Question | Will the Department be supplying additional equipment if there are discrepancies between the Estimate of Quantities for Department Furnished Equipment and the actual number of items to be installed? | The Department will supply the necessary Department-Furnished equipment as indicated in the plans and specifications for the project. | Jill Fehrman | 3 | 2020-11-19 11:30 | 2020-11-20 14:33
20201208 | 20201208002 | 2 | Question | Are power supplies and SFPs included with the department furnished Ethernet Switches? (Item 678.0600 - Install Ethernet Switches) | The necessary SFPs will be provided by the Department with the Department-Furnished switches. Power supplies will be provided by the Department with the Department-Furnished switches. | Jill Fehrman | 4 | 2020-11-19 11:31 | 2020-11-20 14:33
20201208 | 20201208002 | 2 | Question | There is no description regarding Item 674.020 - Cable Microwave Detector in the proposal or the plans. Is this supplied with the Department furnished Microwave Detector Assembly? | In the locations on the plans that have serial microwave detectors where the Cable Microwave Detector bid item is identified, the cable is to be supplied by the contractor as specified in the standard specifications for this bid item. | Jill Fehrman | 5 | 2020-11-19 11:32 | 2020-11-20 14:34
20201208 | 20201208002 | 2 | Questions | Are the appropriate device mounting brackets included with the department furnished Camera Assemblies and the Microwave Detector Assemblies? | Please refer to article 22 and article 23 of the special provisions. | Jill Fehrman | 6 | 2020-11-19 11:32 | 2020-11-20 14:35
20201208 | 20201208002 | 2 | Questions | On sheet 313 of the plans, the existing cabinet EXCB4-1 (at Verona Rd.) is shown with a new Ethernet Switch being installed along with (3) new FO laterals. However, there are no new SFPs shown. Are any needed for this location? | The necessary SFPs will be provided by the Department with the Department-Furnished switches. | Jill Fehrman | 7 | 2020-11-19 11:33 | 2020-11-20 14:36
20201208 | 20201208002 | 2 | Questions | On sheet 313 of the plans, the existing cabinet EXCB9-1 (at Fish Hatchery Rd.) is shown with a new Ethernet Switch being installed along with (2) new FO laterals. However, there are no new SFPs shown. Are any needed for this location? | The necessary SFPs will be provided by the Department with the Department-Furnished switches. | Jill Fehrman | 8 | 2020-11-19 11:33 | 2020-11-20 14:36
20201208 | 20201208002 | 2 | Questions | On sheet 316, the Seminole Hwy traffic signal cabinets are shown with a new SM fiber interconnect being installed. There is no mention of any new interface devices in order to connect the existing traffic signal controllers to the new SM fiber. Will this be Department furnished or is it the responsibility of the contractor to provide? | Department-Furnished. | Jill Fehrman | 9 | 2020-11-19 11:34 | 2020-11-20 14:37
20201208 | 20201208002 | 2 | Permanent Barrier Wall Excavation/Backfill | Per Section 603.5.2(3) Excavation and Backfill for roadside retaining wall is paid under Excavation (Common) and Backfill Structure bid items. 1. In the retaining wall areas it appears there is no quantity for over excavating the back of the wall to allow room for forming/slipping the wall and/or footing, is this considered incidental or will this over-excavation be paid as common? 2. There is no backfill structure included in the contract for retaining wall areas. Will this be added to the contract? | 1. Excavation at retaining wall barriers will be paid as excavation common. Revisions to excavation common quantities at these locations will be included via addendum. 2. Backfill Structure Type B for retaining wall barrier locations will be added via addendum. | Mike Coleman | 10 | 2020-11-23 14:36 | 2020-11-25 05:55
20201208 | 20201208002 | 2 | Weight and size of VMS signs | Can you please give the weights and measurements of the VMS signs going on the sign structures? | The large DMS (VMS) dimensions are shown on structure plan sheets for structures S-13-423, S-13-538, S-13-541, S-13-2033, and S-13-2040. Maximum dimensions and weight for the large DMS (VMS) signs are also noted on pages 1151, 1175, and 1190 of the plans. Smaller DMS (LCS) sign dimensions and maximum weights are noted on the respective structure plan sheets. | Mike Coleman | 11 | 2020-11-24 08:04 | 2020-11-24 10:21
20201208 | 20201208002 | 2 | Existing Barrier Wall | Can the Department provide as-builts for the permanent existing CL barrier wall? | The as-builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208002/ | Mike Coleman | 12 | 2020-11-24 13:57 | 2020-12-01 09:06
20201208 | 20201208002 | 2 | Subgrade Files | In the meta-data files provided on the pre-lim page, it appears there are a few subgrade files missing. It looks to be the xml files for "Median 03 thru 06" may be missing. Could the Department add these files to the pre-lim page? | Median_01-02 Subgrade.xml files were provided because the median shoulders are being reconstructed between Seminole Rd. and Fish Hatchery Rd. Median_03-06 Subgrade.xml files were not created because the existing concrete shoulders are only being replaced with new concrete base shoulders of similar depth. The Median_07 Subgrade.xml file was not intended to be provided for the same reason. Therefore, Median_03-06 Subgrade.xml files will not be provided. | Mike Coleman | 13 | 2020-11-25 07:43 | 2020-12-01 06:55
20201208 | 20201208002 | 2 | Schedule | On the pre-lim page, the pdf version of the P6 schedule is provided. Could the Department also provide the .xer file for this schedule? | The .xer file can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110024/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 14 | 2020-11-25 07:45 | 2020-11-30 12:55
20201208 | 20201208002 | 2 | VMS size and weight and dimensions | More specifically we need the depth and the weight per square foot on the 4â€™ x 5â€™ LCS sign on structure S-13-2011 Thanks | LCS sign cabinet depth is approximately 6â€ and cabinet weight is not to exceed 300 lbs. There will most likely be a z-bracket or c-channel on the back of the housing to facilitate mounting it to the structure, which would stick out another 3-4â€. Note that structures are designed for a 750 lb. maximum LCS sign as shown in the respective structure plans. | Mike Coleman | 15 | 2020-11-25 09:02 | 2020-12-01 05:44
20201208 | 20201208002 | 2 | SDD 13B02 -09a | The standard detail has #6 bars placed longitudinally spaced 6 inches c-c. The #6 longitudinal bars are normally placed 12 inches c-c. Is this a typo or a new standard detail? | SDD 13B02-09a is correct. The spacing of the #6 bars placed longitudinally 6 inches c-c is not a new standard. | Mike Coleman | 16 | 2020-11-29 12:32 | 2020-11-30 12:43
20201208 | 20201208002 | 2 | Fish Hatchery Crash Investigation Pavement Type | On sheet 28 the typical proposed cross section has 11 inch concrete in the accident investigation area on the Fish Hatchery EB off ramp. Sheet 72 construction detail has 5.5 inch HMA pavement. Which is correct? | The Fish Hatchery EB offramp typical section shown on page 28 accurately shows 10-inch concrete pavement for the ramp pavement adjacent to the crash investigation site. This is separate from the 5.5â€ HMA pavement for the crash investigation site which is accurately shown in the typical section on page 30 and the construction detail shown on page 72. | Mike Coleman | 17 | 2020-11-29 14:37 | 2020-11-30 12:48
20201208 | 20201208002 | 2 | HMA Pavement Longitudinal Joint Density | I have not seen HMA Joint density when there is not PWL Density for the HMA. Should the HMA longitudinal Joint density item/ incentive be removed for this project? | No, the HMA longitudinal joint density item/incentive will not be removed from this project. This item was coordinated with BTS during design. | Mike Coleman | 18 | 2020-11-30 09:16 | 2020-11-30 13:47
20201208 | 20201208002 | 2 | Prepare Foundation for Asphaltic Shoulder | The plan item quantities show 37 STA for the Prepare Foundation for Asphaltic shoulder. Can you let me know where this work occurs on the project? I.E. Station, inside outside shoulder and plan sheet this is on. | This item is for the mainline outside shoulder widening between Todd Drive and Fish Hatchery Road. Approximate limits are STA 582+10 â€“ 603+40 EB and STA 583+95 - 598+40 WB. Limits are shown on pages 287-288 of the plan set. | Mike Coleman | 19 | 2020-12-01 16:05 | 2020-12-02 13:33
20201208 | 20201208002 | 2 | 9. 9.5 and 10 Inch PCC Base Pavement | PCC base pavement along the wall is variable width and recessed below the existing asphalt, will the department allow the PCC Base pavement to be placed by hand methods, truss, roller or laser screen...? | The bid items will be administered/enforced per the specifications. | Mike Coleman | 20 | 2020-12-02 08:17 | 2020-12-02 13:32
20201208 | 20201208002 | 2 | B-13-311 Missing pages? | On Structure B-13-311 page 1055 is showing the west half of the bridge, but not showing he east section. Is there a missing page? | The pier is symmetrical about the C/L as noted in the bottom right of lower detail on page 1055. The east half will be identical to the west half. | Mike Coleman | 21 | 2020-12-02 11:40 | 2020-12-02 16:31
20201208 | 20201208002 | 2 | Soil Borings | Are there soil borings that can be provided for this project? | The soils information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208002/ | Mike Coleman | 22 | 2020-12-04 12:59 | 2020-12-07 06:32
20201208 | 20201208002 | 2 | barrier wall | Does the barrier wall work, have to be done at night? | All contract work shall be performed according to the allowable lane closure hours as stated in the special provisions. | Mike Coleman | 23 | 2020-12-05 07:31 | 2020-12-07 09:29
20201208 | 20201208005 | 5 | Incentive Density? | Due to the small quantities, will QMP mix and density be waived on the project? | Please bid the project as shown in the plans and specs. | Mike Coleman | 1 | 2020-11-23 09:03 | 2020-12-02 16:33
20201208 | 20201208005 | 5 | B-14-7 Barrier Block Removal | Existing bridge deck B-14-7 currently has 16 pieces of barrier block protecting traffic from the edge of deck. Is the contractor responsible to remove this barrier block and if so what item is this paid under. | We have discussed it, and Dodge County will perform the removal operation. The County contact for the contractor is as follow: Nathan Kempke, PE Assistant Commissioner Dodge County Highway Department 211 E. Center Street Juneau, WI 53039 Phone: 920-386-3655 Email: nkempke@co.dodge.wi.us | Mike Coleman | 2 | 2020-12-01 07:45 | 2020-12-01 14:11
20201208 | 20201208006 | 6 | plan designer bidding on projects | Since the plan Designer bids on projects as sub-contractor. does then other contractors have the ability to get whatever information that is asked from the designer, since the state has already paid the designer for that information. | This was discussed with Consultant Services and Bureau of Project Development. Because they are the designer and are giving quotes for staking, this is not deemed a conflict of interest. You should have access to the same information they have as far as staking the structure. | Mike Coleman | 1 | 2020-11-23 06:40 | 2020-11-23 09:06
20201208 | 20201208008 | 8 | Construction Staking Structure Layout | Should there be an bid item for structure layout? | An addendum is being issued to add the item. | Mike Coleman | 1 | 2020-11-11 13:37 | 2020-11-13 06:31
20201208 | 20201208008 | 8 | Pile Points | There is a bid item for Pile Points for structure B-52-277, however the detail on sheet 2 of the structure plan shows standard end plates. Which is correct? | The geotechnical engineer recommended pile points and the bid item is included for their usage. If the contractor chooses not to use pile points the standard end plate detail is shown. | Mike Coleman | 2 | 2020-11-16 15:26 | 2020-11-17 12:57
20201208 | 20201208008 | 8 | Utility conflicts | This is more of a comment than a question... The special provisions indicate the overhead power line crossing the road at the west end will either be dropped or temporarily de-energized. This arrangement is not workable- the line will have to be moved for safe construction to occur. If you dig the structure out in order to drive piling, the crane will be either directly under the power line, or the power line will be damaged by the crane. The contractor must have enough room to raise the boom and lay/down, pick up the pile driver, etc. From a dirt working perspective, the power lines will conflict with a quad axle dump truck dumping its contents. Will the Department address this utility conflict prior to bid? | Alliant Energy will de-energize the OH utility and drop the line as needed during construction. Alliant Energy requires a two week notice in order to de-energize and temporarily drop the line. The Alliant Energy contact for this work is: Matthew Hosler, (608) 963-3655, MatthewHosler@alliantenergy.com The de-energized "dropped" line is not directly in conflict with the new structure. The contractor will be able to work around the utiltiy and construct the structure. | Mike Coleman | 3 | 2020-11-18 13:08 | 2020-11-19 11:53
20201208 | 20201208009 | 9 | Construction Staking Structure Layout | Should there be an bid item for structure layout? | An addendum is being issued to add the item. | Mike Coleman | 1 | 2020-11-11 13:38 | 2020-11-13 06:32
20201208 | 20201208010 | 10 | Construction Staking Structure Layout | Should there be an bid item for structure layout? | An addendum is being issued to add the item. | Mike Coleman | 1 | 2020-11-11 13:39 | 2020-11-13 06:32
20201208 | 20201208013 | 13 | WALL NEAR STA 444+00 'T' | I am seeking information regarding the general note on sheet 18 of the plans for the, C. Platteville, Business 151, Staley Avenue to Commercial Drive/5996-00-77, WISC 2021 029 project. Specifically; WALL APPEARANCE SHALL REASONABLY MATCH BLOCK COLOR AND STYLE OF THE EXISTING. Can a physical address for this station or location of these walls to be matched be provided? | The existing wall being referenced is shown on the plan and profile sheets between approximately STA 443+90'T' and 445+20'T'. The existing wall is 100â€™-200' west of the intersection of Business 151 and Eastside Road on the south side of Business 151. The address for the closest adjacent property is 50 Eastside Road. | Mike Coleman | 1 | 2020-11-12 07:34 | 2020-11-13 06:28
20201208 | 20201208013 | 13 | Modular Block Retaining Wall design question | We have a design related question on the modular block retaining wall. The plans & profiles are showing only 6â€ embedment is required, but the specs are the usual WI/DOT requirements of 1.5' of embedment. What should we follow for design? | The wall should be designed for the 6" minimum embedment. The Special Provision for the wall bid item includes the language "or as given on the plans" in reference to the minimum embedment. The notes on the retaining wall plans of a 6" minimum embedment for the wall are intended to govern. | Jill Fehrman | 2 | 2020-11-19 12:45 | 2020-11-20 12:10
20201208 | 20201208013 | 13 | RRFB System Questions | This is regarding the RRFB systems that are included in Job #13. While there are certain parts of the spec that allow for different products to be bid, there are certain parts that are proprietary. I would like to submit the spec with pop notes on where the system we would bid differs, with the hopes that it will be approved as an "or equal". Aleigha Burg, LPPM, has a copy of this document already. Should I send it to someone else as well? Thanks | Thermal detection will be required for the proposal. | Jill Fehrman | 3 | 2020-12-02 13:44 | 2020-12-04 12:49
20201208 | 20201208014 | 14 | Storm Sewer Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2020-11-09 13:25 | 2020-11-12 06:01
20201208 | 20201208014 | 14 | Soil Reports | Does the Department have soil reports/borings for the project? If so, could the department provide them? | The Geotech Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208014/ | Mike Coleman | 2 | 2020-11-10 14:28 | 2020-11-12 05:56
20201208 | 20201208014 | 14 | Asphalt Items | For line 88 Density Incentive and line 466 Ride Incentive the bid quantity listed and the unit price listed need to be switched around. Unit Prices for these should be $1.00. The Asphalt Items Quantities in the plan show that there is 40 tons of Asphaltic Surface located at BOP Warrens Street. Can You please clarify where this mix goes? What does BOP stand for? I am not seeing any asphalt surface on the plan and profile or the construction details along Warrens St. Should there be a pay item for temporary asphalt patching over plated manholes? Is the asphalt for patching around manholes after final manhole adjustment paid as HMA or asphalt surface? | The incentive items have been revised by addendum. Asphaltic Surface mix is for the TOW Path/Ice Age National Scenic Trail labeled as MP-3 on the plan details sheets located at the Portage Canal. BOP is Beginning of Project. Asphaltic Surface is shown on the plan detail sheets as MP-3 for the TOW Path/Ice Age National Scenic Trail. Legend for the Plan Detail Sheets: MP-3 Multi-Use Path should also say (Asphaltic Surface required). All asphalt placed on roadways should be paid as HMA. Plans do not dictate contractor means and methods for adjusting manholes to final grade. Construction details show a HMA wedge required at manholes. All asphalt placed on roadways should be paid as HMA. Plans do not dictate contractor means and methods for adjusting manholes to final grade. | Mike Coleman | 3 | 2020-11-30 15:05 | 2020-12-02 11:39
20201208 | 20201208014 | 14 | Asphalt Alley Hookups | Is the asphalt pavement for paving the alley connections part of the asphalt surface driveways bid item or is it part of the HMA bid item? | Yes, as shown on the Plan Details sheets and legend areas shaded grey shall be paved with Asphaltic Surface Driveways and Field Entrances bid item, which includes the alley connections. | Jill Fehrman | 4 | 2020-12-02 09:54 | 2020-12-04 12:51
20201208 | 20201208015 | 15 | WISDOT ITEM # 15 - 75TH ST. Kenosha, WI | 1) Please provide CAD files & Surfaces in .XML format for both Existing & Proposed tops of Subgrade. 2) Please provide Earthwork tables & end areas in .excel format 3) Please provide Drainage tables in .excel format. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 1 | 2020-11-04 10:57 | 2020-11-11 10:20
20201208 | 20201208015 | 15 | Drainage Details/Tables | 1)Special Provision #79 â€“ Storm Sewer Backfill states â€œBackfill all trenches and excavations, not occupied by slurry backfill, immediately after completing sewer construction as shown in the storm sewer backfill construction details of the plans.â€ We are unable to locate the Storm Sewer Backfill construction detail in the drawings. Please provide. 2)Previous WisDOT projects have supplied proposed storm sewer pipe and structure data tables in Microsoft Excel format. Could these be provided on this contract? | 1) Special provision will be updated to remove the reference to the detail. Issue will be resolved with Addendum 1 (transmitted 11/10) 2) The storm pipe and structure data tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 2 | 2020-11-05 12:25 | 2020-11-11 10:24
20201208 | 20201208015 | 15 | Design Scheduel | Can the design schedule be provided? Does the Department see the single season construction time frame as extremely aggressive? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2020-11-06 04:39 | 2020-11-10 14:55
20201208 | 20201208015 | 15 | Storm Sewer Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | For the 1310-10-71 ID, the drainage pipes and items should be bid per plan due to existing local agreements and staging considerations. For the 1310-10-70 ID, drainage pipes shown in the plans and quantities will be adjusted from Class III RCP Pipe, to show Class IIIA/IIIB. An addendum will be issued to correct this. | Mike Coleman | 4 | 2020-11-09 13:29 | 2020-11-16 06:06
20201208 | 20201208015 | 15 | Additional Document Request | 1. Special Provision Article 14 references the USACE Section 404 Permit which is not currently included with the Bid Documents and we request access to this information. Please provide the permit. 2. Special Provision Article 15 references the WPDES General Construction Storm Water Discharge Permit which is not currently included with the Bid Documents and we request access to this information. Please provide the permit. 3. Special Provision Article 17 references available Geotechnical Investigation Information which is not currently included with the Bid Documents and we request access to this information. Please provide the Geotechnical Report for all walls and Bridges as well as and Technical Memorandum for subgrade improvement. 4. Special Provision Article 41 reference Copies of Determinations in relation to Airport Operating Restrictions and has a link to access the information,ftp://ftp.dot.wi.gov/dtsd/hcci/project documents/20180522001/, but this link does not work. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ The link in the special provisions will be updated via addendum. | Mike Coleman | 5 | 2020-11-10 10:09 | 2020-11-11 10:28
20201208 | 20201208015 | 15 | Pre-Bid Meeting | Can you post the power point presentation from the Pre-Bid Meeting? | An updated presentation has been uploaded to the same location below. The Pre-Bid Meeting information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 6 | 2020-11-13 08:42 | 2020-11-13 08:49
20201208 | 20201208015 | 15 | Storm Sewer Structures | 1) After reviewing the storm sewer plans and referencing the structure and pipe tables, it appears that there are several structures (+/- 50) that appear on the plans and pipe tables, but are not shown in any of the structure tables. Without this information we are unable to perform a proper take off. Please advise. | We have reviewed the drainage plans, and have found a few structure numbers did not have a letter designation in profile view (ex. 1918A, 1918B, etc). We have made the correction and will be issuing the updates as part of addendum 2 that will be issued. | Mike Coleman | 7 | 2020-11-13 15:21 | 2020-11-19 11:54
20201208 | 20201208015 | 15 | B-30-32 Turbidity Barrier | Is turbidity barrier truly needed through the entire length of this existing box culvert? We're skeptical as to how to install through this structure. If it is needed as shown on page 370 of the plan, please provide the as-built drawings for this structure, B-30-32. | In reviewing the plans and question, we misinterpreted DNRâ€™s request after reviewing their comments/guidance further. The turbidity barrier is to be parallel with STH 50 to protect a pond, not Kilbourn Road Ditch/box culvert as its currently drawn. Plan sheet and MQâ€™s will be updated accordingly with an upcoming addendum. | Mike Coleman | 8 | 2020-11-16 09:54 | 2020-11-16 12:32
20201208 | 20201208015 | 15 | S - 42 Conc Barrier | Is the 4'-0" conc pad below the S-42 Barrier incdental to the Barrier or the 8-1/2' concrete pavement. If it's paid for under the 8-1/2' pavement will it have dowel baskets in it? | Concrete pavement is measured out to the back of concrete barrier wall. So the pad is NOT incidental to the barrier wall. It is also not incidental to concrete pavement as concrete pavement quantity is provided to account for this width under the barrier wall. This section of pavement beyond the saw cut under the barrier will not have dowel baskets. | Mike Coleman | 9 | 2020-11-16 10:07 | 2020-11-16 12:31
20201208 | 20201208015 | 15 | Backfill Slurry | Under article 80 Storm Sewer is says, Use of backfill slurry to be determined by engineer based upon location and work location requiring reopening for traffic. Use of backfill slurry incidental to storm sewer installation, and to be used in locations where adequate compaction cannot be obtained with standard granular backfill materials. Then there is a item of Backfill Slurry, Item SPV.0035.0201 which pays for this slurry. Can the incidental under Article 80 be removed? | An addendum will be issued to clarify. | Mike Coleman | 10 | 2020-11-16 14:45 | 2020-11-17 10:38
20201208 | 20201208015 | 15 | Material Stockpile and Equipment Storage - 5' ??? | Article 28. Material stockpiles and equipment storage on throughout corridor is limited to a height of five feet and 14 calendar days unless the engineer approves otherwise in writing. 5' is unrealistic. This means all equipment will have to be hauled off the project every night, including cranes at the bridges. Also all material will be required to be hauled offsite to be reprocessed and re-hauled back to the project. This requires a lot of unnecessary trucking (increasing the safety risk) and added cost. Pickup trucks are higher than 5'. Please remove this requirement. | In talking with region construction, we will modify the special provision to reflect more of the intent on avoiding business sign obstruction and access. Then also adjust the stockpile height from 5â€™ to 12â€™. This will be addressed as part of addendum 2. | Mike Coleman | 11 | 2020-11-18 10:38 | 2020-11-19 11:55
20201208 | 20201208015 | 15 | Soils Report | Can the soils report be provided? | The Geotech reports were already posted. They can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 12 | 2020-11-19 10:26 | 2020-11-19 12:11
20201208 | 20201208015 | 15 | Milled Asphalt | Can milled asphalt be used for base or does it have to be crushed or screened to 1.25" minus? | Per spec book, see 305.2.2.2 Reclaimed Asphalt requirements. â€œThe contractor may use reclaimed asphalt with 100 percent passing a 1 1/4-inch sieve as 1 1/4-inch base. The engineer will assess gradation primarily by visual inspection but may test questionable material.â€ | Jill Fehrman | 13 | 2020-11-19 10:27 | 2020-11-20 12:29
20201208 | 20201208015 | 15 | Breaker Run | Can the existing breaker run be used for breaker run in the new construction? | Material meeting the gradation and specification requirements for breaker run can be placed as breaker run. Refer to section 311.2 for sourcing. | Jill Fehrman | 14 | 2020-11-19 10:28 | 2020-11-20 12:25
20201208 | 20201208015 | 15 | Traffic Control - Stage 3 Paving Trackline | Will the Department require the pavement adjacent to lanes constructed in Stage 2 to be constructed at night under single lane closures? The traffic control typical section on sheet 1027 shows 2 feet from the edge line to the edge of pavement. Will the Department require the joint between stage 2 and stage 3 pavement to be edged? It is unsafe to have a finisher in a 2-foot buffer area only protected by cones. The plans as drawn do not allow adequate track line and buffer between traffic and the work zone. | Nighttime lane closures are allowed as defined in the special provisions and are encouraged to be applied to Stage 3 paving operations if the contractor requires additional space for equipment and finishing. The joint between pavement placed in stages 2 and 3 shall be finished in accordance with the standard specifications. | Jill Fehrman | 15 | 2020-11-19 11:07 | 2020-11-20 12:11
20201208 | 20201208015 | 15 | Drop off protection | Does the Department intend to require ramping/drop off protection in stage 3 where traffic is 2-feet from the work zone. Will installation/removal of drop off protection be paid under applicable base aggregate pay items? | Drop off protection is required. Page 1411 of the plans addresses this work showing the use of BAD 1 ï¿½â€ and its payment under those items for this purpose. Use of material will be addressed as part of an upcoming addendum. | Jill Fehrman | 16 | 2020-11-19 11:11 | 2020-11-20 12:18
20201208 | 20201208015 | 15 | Traffic | With two lanes of traffic immediately next to construction operations with no barrier wall dividing construction and traffic, will traffic in one lane veer into the second lane causing accidents where construction activity is occurring? Wouldn't it make more sense to place all traffic on one side of the roadway, like most urban reconstructs, without barrier wall? | The traffic staging as prescribed is within allowable standards when coupled with the speed reduction to 40MPH throughout the corridor per the traffic control and staging plan. Adjustments to the traffic control and staging plan can be considered as long as the interim/final completion dates and associated scope of work with those dates are met. | Jill Fehrman | 17 | 2020-11-20 06:58 | 2020-11-20 13:33
20201208 | 20201208015 | 15 | Clay Liner Specification. | The Clay Liner specification requires a static compactor that exceeds 30,000 pounds. Can a lighter vibratory sheep's foot compactor be used that is capable of achieving specified compaction? | The language concerning the size of the compaction equipment has been in the special provision for awhile and it comes from the WisDNR 504 requirements for clay liners. | Mike Coleman | 18 | 2020-11-20 07:34 | 2020-11-24 13:53
20201208 | 20201208015 | 15 | Excavation | Can a Miscellaneous Quantity sheet for the Excavation be provided by stage as the plan contains for the Substructure section has for Base, Breaker Run, etc.? | With the project being a cut/fill approach and no balancing (borrow, etc), the plans only show the total qty in the MQâ€™s with assumed staged limits in the cross sections. However we have estimated quantities as part of the contract time of completion form. Here is our assumed CY quantities as part of that exercise. Stage 1 â€“ 10,7000 Stage 2- 115,900+4,000 (74ID) Stage 3 â€“ 112,600 Stage 4 â€“ 12,200 Stage 5 â€“ 75,800 Stage 6 â€“ 101,900 Stage 7 â€“ 23,700 Stage 8 â€“ 300 Adding in the approximate qty of 4,000 CY for the 74ID (addâ€™l Stage 2 qty) gives an approximation of excavation quantities by stage as shown in the plans. | Jill Fehrman | 19 | 2020-11-20 11:24 | 2020-11-20 14:44
20201208 | 20201208015 | 15 | Embankment Volumes per Stage | Can the Embankment volumes per stage be provided? | Similar to the Excavation question, with the project being a cut/fill approach and no balancing (borrow, etc), the plans only show the total qty in the MQâ€™s with assumed staged limits in the cross sections. However we do have an assumed breakout for embankments for information purposes only. Essentially Stage 2 embankments and excavation balance very closely. Stage 2 â€“ 110,500 CY Stage 3 â€“ 11,400 CY Stage 5 â€“ 19,700 CY Stage 6 â€“ 11,600 CY Stage 7 â€“ 6,500 CY These are assumptions and these numbers can slide between stages where there is workzone overlap. The earthwork files and miscellaneous quantities files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 20 | 2020-11-22 23:27 | 2020-11-23 06:55
20201208 | 20201208015 | 15 | Crushed Aggregate Base Course Under Sidewalks. | What width beyond the edge of the sidewalk will the crushed aggregate base course be paid? Realistically the base will need to extend 1' beyond the edge of walk for forms and stability. | Limits of sidewalk base course to be paid as shown on the plans. Means and methods for base installation and form setting for concrete sidewalk are for the contractor to determine. | Mike Coleman | 22 | 2020-11-22 23:30 | 2020-11-23 14:32
20201208 | 20201208015 | 15 | Topsoil Excavation. | Will Topsoil Excavation be paid as part of common excavation if it is not reused as salvaged topsoil? | Article 65. Roadway Excavation of the special provisions describes this. Essentially, yes, any topsoil removal was factored into our Earthwork quantities and accounted for in the totals. â€œReplace standard spec 205.3.2(2) with the following: Salvage topsoil from excavation areas and the roadway foundation. Remove topsoil present below the subgrade in cut sections and excess topsoil from embankment areas not required to cover side slopes as excavation common. Dispose of excess topsoil according to standard spec 205.3.12. Utilize Roadway Embankment to backfill areas of topsoil removal as directed by the engineer. The engineer may require EBS Backfill to fill shallow areas at cut-fill transitions to address stability issues related to underlying soils.â€ | Mike Coleman | 23 | 2020-11-22 23:31 | 2020-11-23 14:29
20201208 | 20201208015 | 15 | Stage 1 Crushed Aggregate Base Course | Does quantity for Stage 1 Crushed Aggregate Base need to be added? | Page 1411 as part of the MQâ€™s shows assumed quantity and intended use as part of temporary paving operations, shouldering, etc. | Mike Coleman | 25 | 2020-11-22 23:41 | 2020-11-23 14:25
20201208 | 20201208015 | 15 | Stage 2 Pavement Removal. | Will Pavement Removals in Stage 2 be allowed to encroach into Stage 3 enough to create a 4 foot track line for the concrete paver? If not, how will the Concrete Paver track line, grade stakes and stringline be accommodated? | Stage 1 operations provide for temp widening into the median to move traffic away from Stage 2 paving. The typical section shows 6â€™ from edge of travelled away shown in Stage 1, to paving operations in Stage 2. Removal of 4-feet of existing pavement adjacent to the Stage 2 proposed lanes can be allowed for contractor paving operations, provided that a 1â€™ minimum buffer between the edge of travel lanes and all traffic control devices can still be provided, and drop-offs adjacent to travel lanes are protected as required in the standard specifications 104.6.1.2.3. We recognize paving will be tight here, which is why Stage 2 has temp BAD qtyâ€™s associated with it as well to address any dropoff protection. (Page 1411 of the plans) | Mike Coleman | 26 | 2020-11-22 23:55 | 2020-11-23 14:27
20201208 | 20201208015 | 15 | Common Excavation Payment for Existing Topsoil Excavation. | Will Common Excavation be paid in areas where Topsoil and Topsoil EBS occur that is not used as salvaged Topsoil? | Article 65. Roadway Excavation of the special provisions describes this. Essentially, yes, any topsoil removal was factored into our Earthwork quantities and accounted for in the totals. â€œReplace standard spec 205.3.2(2) with the following: Salvage topsoil from excavation areas and the roadway foundation. Remove topsoil present below the subgrade in cut sections and excess topsoil from embankment areas not required to cover side slopes as excavation common. Dispose of excess topsoil according to standard spec 205.3.12. Utilize Roadway Embankment to backfill areas of topsoil removal as directed by the engineer. The engineer may require EBS Backfill to fill shallow areas at cut-fill transitions to address stability issues related to underlying soils.â€ | Mike Coleman | 27 | 2020-11-22 23:56 | 2020-11-23 14:30
20201208 | 20201208015 | 15 | Stage 1 Sawing Asphalt | Will the existing Asphalt be sawed and paid as Sawing Asphalt in stage 1? | Stage 1 operations is to address temp widening needs in the median. As much of this work is adjacent to an existing shoulder/joint/etcâ€¦we felt the sawing would be an optional item and it would depend upon the contractors level of comfort on if they wanted a clean joint here for the first few months of construction. To address this uncertainty, we do have undistributed Sawing Asphalt show for the 70ID on page 1394 of the plans. | Mike Coleman | 28 | 2020-11-22 23:59 | 2020-11-23 14:31
20201208 | 20201208015 | 15 | Design Files - Existing Surface Files | Circling back to question #1 for this Call No. (Call No. 15) - it appears there have been 2 Existing Surface Files provided in response to that question: - 'WIS 50 Exist_East.dtm' - 'WIS 50 Exist_West.dtm' Can XML files please be provided that represent the existing topography of the project location in lieu of these DTM files? | The existing DTM files are both over 300MBâ€™s and exporting to XMLâ€™s are unfortunately not working out for us. We have been able to export them to a TIN file. The TIN files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208015/ | Mike Coleman | 29 | 2020-11-23 08:33 | 2020-11-24 09:41
20201208 | 20201208015 | 15 | Material Stockpile and Equipment Storage - 12' ??? | From the previous question and answer, the limit is now going to be 12'. If you are in a 3-5' car/truck and have 12' pile next to you what are you going to see over that 12' pile? Why limit the pile to 12'? There should be no difference between a 12' pile or a 40' pile, you can't see anything anyways. So please remove the height limit. The shorter the height limit equals more pile length, causing more blockage. How is the contractor suppose to determine where we can stockpile or not? This effects our costs? The way it currently is written a business owner can direct the contractors methods of construction by telling them to haul that material farther down the road or more that piece of equipment every night. This will cause cost impacts and could require additional time on the schedule. Please remove this entire article. #28 Material Stockpile and Equipment Storage | Please bid according to plans and specs | Mike Coleman | 30 | 2020-11-23 15:14 | 2020-12-03 17:03
20201208 | 20201208015 | 15 | #28 Material Stockpile and Equipment Storage - Written Permission | How is the contractor going to get written permission from all the business owners and local government on the project? This will not happen. No business owner will give the contractor permission. This is cause major delays in the construction schedule. Please remove this requirement. | Please bid according to plans and specs. | Mike Coleman | 31 | 2020-11-23 15:25 | 2020-12-03 17:03
20201208 | 20201208015 | 15 | Clay Liner. | If a non-static/vibratory 84 inch sheeps foot compactor is used to place the clay liner like is commonly used in landfills to achieve density on slopes, can a non-static/vibratory 84 inch sheeps foot compactor be used? Vibratory sheeps foot compactors are superior to static compactors in achieving density. | After further discussion with BTS, we will adjust the specification allowing for contractor interpretation for equipment usage, while still requiring engineer approval. This will be added to addendum 3 | Mike Coleman | 32 | 2020-11-25 05:46 | 2020-12-02 11:46
20201208 | 20201208015 | 15 | Sign Structures - Reinforcing Steel Bid Items | How is the reinforcement in the Sign Structures to be bid? Is this now incidental to the Sign Structure Bid Item? Example, Bid Item 531.5130.0001 â€œFoundation Single Shaft Type MC-III (S-30-265)â€, I see that it is a Type MC-III, I see what Reinforcement is needed, I can come up with a quantity, but what Bid Item doe the Reinforcement get bid to? It does not say that the Reinforcement is Incidental. Prior Lettings had a Bid Item No. 636.1500 Sign Supports Steel Coated Reinforcement HS, I do not see this on this letting. | See standard spec 531.5 (5) Payment for the Foundation bid items is full compensation for providing concrete foundations; for anchor rod assemblies; for reinforcing steel; and for embedded conduit and electrical components. | Mike Coleman | 33 | 2020-11-25 11:48 | 2020-11-30 13:11
20201208 | 20201208015 | 15 | Sweeping | Can an hourly pay item for sweeping be added? | Article 150 of the special provisions provides this very item for all 3 project IDâ€™s to be paid on an hourly basis. | Mike Coleman | 34 | 2020-11-27 19:54 | 2020-11-30 12:59
20201208 | 20201208015 | 15 | Stage 6 Traffic. | Can the rationale be provided why in Stage 6 at 52nd St. there is a large space between the west bound and east bound traffic. This large area seems to serve no noticeable purpose and adds a number of complexities for the construction of the 52nd St. intersection. | Page 1147, in the typical section explains the intent behind this additional width as an emergency bypass/left turn lane due to the single lane in each direction configuration. It is similarly shown during Stage 7 of the project on page 1186. | Mike Coleman | 35 | 2020-11-28 07:43 | 2020-11-30 12:58
20201208 | 20201208015 | 15 | Stage 1 Lane Closure. | Will a lane closure be provided for the work in Stage 1? What time of the day will a lane closure be allowed? | Lane closure timeframes, lane rental assessments, and work restrictions are all described in the prosecution and progress, traffic, and lane rental articles in the specifications. They are allowed during stage 1, but just need to fall within the prescribed timeframes in the special provisions. | Mike Coleman | 36 | 2020-11-28 09:24 | 2020-11-30 12:58
20201208 | 20201208015 | 15 | Topsoil | Seed Mix No. 40 is specified. Will the Topsoil need to be screened and pulverized as provided for in the Standard Specifications when Seed Mix No. 40 is used? This standard makes sense possibly in businesses and residential front yards but not on the entire project including ditch lines, roadway slopes, medians, ramps, etc. Please specify specific areas of the project where screened and pulverized topsoil will be required to meet the related Standard Specification. | As stated in the question, this is a standard specification. The majority of this project will be left in an urbanized setting with sidewalk in all locations, many of which will abut business, homes, etc. Regardless of the location, the standard specification should be used for bidding purposes. | Mike Coleman | 37 | 2020-11-29 08:29 | 2020-11-30 12:59
20201208 | 20201208015 | 15 | Staging. | Can Stage 6 be started east of the Stage 5 STH 50 crossover prior to Stage 5 being complete? Is there anything in the special provisions or plans that prevents working in two stages at the same time as long as the work and traffic control does not conflict? | There is nothing in the specifications stating that the contractor has to wait until Stage 5 is completed prior to beginning Stage 6. The depicted staging is only showing a feasible way to build the stage 5, stage 6 interface. | Mike Coleman | 38 | 2020-11-30 08:42 | 2020-12-01 05:45
20201208 | 20201208015 | 15 | 77th Ave Traffic | SPV 6 requires access to be maintained on 77th Ave on a paved surface at all times. Please advise as to how B-30-35 and B-30-36 are supposed to be demoed if traffic must be maintained at all times. | The intent was to make sure that traffic would not be forced to ride on gravel, but we will be revising the traffic article to clarify the intent on allowable nighttime full closures of 77th Avenue to facilitate bridge demolition and falsework placement/removal activities. This will be provided with addendum 3. | Mike Coleman | 39 | 2020-11-30 16:23 | 2020-12-02 05:43
20201208 | 20201208015 | 15 | Embankment - MSE Backfill | It appears the Embankment quantity has not been reduced where the MSE Wall backfill is located in fill sections. Please confirm and adjust Embankment to reflect the actual dirt fill on this project. | There will be a reduction in embankment quantity for those locations behind retaining walls and will be covered in addendum 3. | Mike Coleman | 40 | 2020-12-01 09:27 | 2020-12-01 14:23
20201208 | 20201208015 | 15 | Temporary Wire Faced Wall Quantity | Do you have details for limits of excavation for the temporary wire faced MSE? Is the estimated quantity generated using finished grade and the minimum 3' toe bury depth? (FYI - Using the DOT's FTP CAD files and 3' toe bury depth we generated very different qty) Thank you | The assumed depth of embedment for the temp walls beyond finished grade are as follows. The deviation from the standard 3â€™ for the 51 and 53 walls is due to the deeper footing depth to accommodate future potential grading. 49 wall â€“ 3â€™ embedment below finished grade 51 wall â€“ 9â€™ embedment below this projects finished grade (due to deeper wall foundation) 53 wall - 9â€™ embedment below this projects finished grade (due to deeper wall foundation) | Mike Coleman | 41 | 2020-12-01 10:26 | 2020-12-01 14:09
20201208 | 20201208015 | 15 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch and Breaker Run? | A uniform 2.0 conversion factor was used for BAD ï¿½â€, BAD 1-1/4â€, and Breaker Run. | Mike Coleman | 42 | 2020-12-01 14:03 | 2020-12-01 15:11
20201208 | 20201208015 | 15 | Article #25 - Public Convenience and Safety | Please remove Article #25, night work is required on all roadways to achieve the DOT's provided schedule. Those productions rates will require multiple crews working day and night. There is not enough work area to work all those crews just during the day. A night shift is required. | Local coordination and outreach was part of the process to develop these timeframes as part of the public convenience and safety article. This doesnâ€™t suspend work activities at night, but designates allowable roadway locations, types of work activities, and necessary approvals from the engineer to work at night. The prosecution and progress references the expedited work schedule and extraordinary forces needed to meet the assumed production rates. | Mike Coleman | 43 | 2020-12-01 15:11 | 2020-12-02 11:44
20201208 | 20201208015 | 15 | Railing Steel Pedestrian Type C1 | The detail on plan sheet 93 provides no details for the railing. For example: height, pipe size, base plate size, anchor bolt size, railing finish, etc. Are we to match pipe railing on structure R-30-55? | The Intent of the Railing on Page 93 (Used on small modular block walls as fall protection) would be to use similar or the same Railing used on Wall R-30-55 (Page 2433). This would match aesthetically and provide the necessary fall protection. | Mike Coleman | 44 | 2020-12-02 14:51 | 2020-12-03 10:23
20201208 | 20201208015 | 15 | Drain slotted vane | is there a detail showing length and configuration of the 2 proposed drains | Location: Shown in Planview (Page 466) - Will be running longitudinal along back of Proposed Barrier Detail: Follow SDD (Page 1869) - Top of Drain and Finished Concrete Surface should be flush with pedestrian walking surface/Sidewalk - See Wall R-30-51 Plan for additional configuration information (Page 2392) Length: Shown in MQs As Comment (Page 1558) - Each, 24FT Long | Mike Coleman | 45 | 2020-12-03 07:01 | 2020-12-03 10:25
20201208 | 20201208015 | 15 | Drain slotted vane temporary | The special provisions indicate there should be steel reinforcement conforming to standard spec 415.2.2. The SDD on sheet 1869 does not show any reinforcement. | Sheet 956 of the plans shows the construction detail for the temporary vane drain, not the SDD on sheet 1869. The detail on sheet 956 shows the reinforcement for the temporary vane drains (Item SPV.0090.0300). The SDD on sheet 1869 is for the permanent vane drains (item 611.9900.S). Monitoring the vane drain for performance and necessary repairs is part of Special provision 161. | Mike Coleman | 46 | 2020-12-03 07:06 | 2020-12-03 10:25
20201208 | 20201208015 | 15 | Excavation for Structure Items Missing | Please add items for Excavation for Structures Bridges (structure) B-30-131 & Excavation for Structures Bridges (structure) B-30-132. | Page 2390 and 2406 delineate assumptions for wall excavation. As these bridges have MSE wall abutments, any structure excavation is actually behind the walls and is covered by these two detail sheets and the associated wall bid item. | Mike Coleman | 47 | 2020-12-03 09:53 | 2020-12-03 10:53
20201208 | 20201208015 | 15 | Addendum #3 - Article 28. Material Stockpile and Equipment Storage. | Please remove this language. How does the 70,000+ LF of Pipe on this project get installed? The contractor can't side cast spoils? They must be loaded directly into a truck? The contractor needs to stockpile material in every stage along the entire length of the project to maintain this very aggressive schedule at the lowest cost to the tax payers. This project will more than likely not finish on time. It appears in this language the contractor can't do anything until it is approved on where they can stockpile any material at any height now. And if the engineer decides to not allow any stockpiles on the project they have that right. So the contractor should assume no stockpiling of material is allowed on the project at bid time? Please provide a plan sheet showing where stockpiles are allowed or not allowed if the language stays in the contract. | Plans and specifications should be bid as shown. | Mike Coleman | 48 | 2020-12-03 10:39 | 2020-12-03 16:05
20201208 | 20201208015 | 15 | Curb & Gutter Removal | Will the curb and gutter be paid as shown in the Miscellaneous Quantity Sheets? | Curb and Gutter Removal will be measured and paid in accordance with WisDOT 2021 Standard Specifications 204.4 Paragraph (3) & (5). The Miscellaneous quantities provided for Curb & Gutter Removal is based on the current staging plan and anticipated construction sequence. Variations to the staging plan or Contractor means and methods may influence how Curb & Gutter Removal is measured and paid. | Mike Coleman | 49 | 2020-12-04 21:37 | 2020-12-07 10:49
20201208 | 20201208016 | 16 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, there appears to be numerous runs of SSPRC Class IV that have adequate cover for Class IIIA and IIIB bid items. Will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV in areas that meet this design guidance? | The bid items will remain as shown. The City requested this material based on local preference. | Mike Coleman | 1 | 2020-11-09 13:51 | 2020-11-13 06:24
20201208 | 20201208016 | 16 | Soil Boring Logs and Cad Files | Can you please provide the soil boring logs and CAD files for this project. | It has come to ou attention that the soils report that was previously provided did not include the attached soils report Addendum A, that includes additional soil borings and recommendations at the proposed box culvert (B-67-380) location on the project. The file has been uploaded and you can find it at the link below. The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208016/ | Mike Coleman | 2 | 2020-11-12 13:48 | 2020-11-16 09:43
20201208 | 20201208016 | 16 | Storm Sewer Excel Files | Can the storm sewer excel files be provided for this project? | The storm sewer excel files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208016/ | Mike Coleman | 3 | 2020-11-23 14:33 | 2020-11-23 15:47
20201208 | 20201208016 | 16 | 10' x 6' Box Culvert | Will dual single cell precast 10' x 6' box culverts be an acceptable product on this project. | After further discussions on this bidder question, we would like to revise the response. Please update the response to this question to the following: As noted under the General Notes on sheet 2 of the plans for B-67-380, placement of a precast culvert in lieu of the cast-in-place design is acceptable. The contractor shall be aware that approval of the alternative is subject to the WisDOT structures design section. Changes to the structure layout shall not be permitted without written approval from the engineer. Furthermore, the contractor shall be aware the construction of the structure is staged, and the staging limits of this construction shall not be modified without written approval from the engineer. Quantities and payment for a precast structure, including excavation, backfilling and concrete masonry â€“ culverts, shall be based on the cast-in-place option. Two separate precast cells may be considered. If the contractor proposes to install two separate precast cells, the design shall conform to requirements of Chapter 36 of the Bridge Manual, which provides design standards for wall thickness and space between cells. Installation of two separate precast cells will result in a wider structure footprint. The contractor is responsible for verification that utilities are clear of the wider structure. | Mike Coleman | 4 | 2020-11-25 08:38 | 2020-11-30 12:49
20201208 | 20201208016 | 16 | Select Borrow | The Special Provisions state that material meeting the specifications for Grade 2 Granular Backfill is required for the Select Borrow Item. Will material meeting the specifications for either Base Aggregate Dense 1 1/4", or Table 37 of the Standard Specifications for Sewer and Water Construction in Wisconsin be allowed? | Substitutions may be made for the Grade 2 Granular Backfill as long as the material conforms to the requirements of Section 209 of the standard specifications. If Base Aggregate Dense is considered for substitution, do not use crushed concrete or reclaimed asphalt, as noted in Section 209.2.1 of the standard specifications. | Mike Coleman | 5 | 2020-11-30 08:59 | 2020-12-02 11:50
20201208 | 20201208016 | 16 | Precast Twin Endwalls | Will Precast Twin Endwalls be allowed for proposal line # 104 & 106? 60" CMP & 95" x 67" Pipe Arch Steel. | The masonry endwalls for the twin 60â€ and twin 95â€x67â€ corrugated steel pipes shall conform to the dimensions shown in the plans and shall meet the requirements of the standard specifications for the bid items involved. Precast endwalls may be considered if they conform to the plan dimensions and specifications. Standard apron endwalls may not be substituted. | Mike Coleman | 6 | 2020-11-30 09:53 | 2020-12-01 05:46
20201208 | 20201208016 | 16 | Utility Compaction Testing | Many of the sanitary sewer and water main items for the City of Brookfield note that density tests on backfill materials will be as specified or as directed by the engineer. Also, the contractor will provide for all compaction testing. Is compaction testing required for all of the sanitary sewer and water items? If so, how often is the testing required? | Backfill density testing will be performed by the engineer on sewer and water items that have compaction testing noted in the special provision article. Where the articles state â€œthe contractor will provide for all compaction testingâ€, the intent is that the contractor is to provide the time and space for the engineer to complete the testing. As noted in the articles, the contractor will be responsible for subsequent re-testing of failed density tests. The frequency of testing will be determined by the engineer and will depend on the magnitude of the work and the compaction effort being put forth. | Mike Coleman | 7 | 2020-11-30 16:09 | 2020-12-01 14:13
20201208 | 20201208017 | 17 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Additionally, breaker run can be counted towards sub-grade cover when used for stabilization (FDM 13.15.9). Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and IV? | No. Most of the storm sewer is Class IV reinforced concrete because the pipes do not meet the minimum requirement for cover and that is why the Class IIIA and IIIB were not used. In addition, this is a STP Rural local program project and the county requested the use of concrete pipe. | Mike Coleman | 1 | 2020-11-09 13:57 | 2020-11-12 05:59
20201208 | 20201208017 | 17 | Soils Report | Is there a soils report available for this project that can be shared with the contractors? | The reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208017/ | Mike Coleman | 2 | 2020-11-13 11:08 | 2020-11-16 10:54
20201208 | 20201208017 | 17 | Frost Heave Detail | The plan has a frost heave detail shown on plan sheet 15. Does this only apply to the culvert at station 43+54? Is this frost heave are to be backfilled with material that complies with specification 520 or imported granular backfill? | Yes, this detail is for the culvert on the east end of the project, station 43+54. The backfill material will follow specification 520. | Mike Coleman | 3 | 2020-11-13 11:26 | 2020-11-16 10:16
20201208 | 20201208017 | 17 | DBE Participation | Now that I have the standard Specifications for the Sewer and Water, it appears the Village has secured funding for their portion of the work. There are requirements for DBE Participation as part of these specifications. Is the contractor required to comply only with the DOT DBE requirements only or both? What if there is a conflict between the two? | There should be no conflict between the DOT & DNR requirements regarding DBE requirements. There are different forms for the DNR that need to be signed with the bid, which are included in the separate Standard Specifications for the Sewer and Water. | Mike Coleman | 4 | 2020-11-13 15:16 | 2020-11-17 06:50
20201208 | 20201208018 | 18 | Storm Sewer and Culvert Pipe Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2020-11-09 13:59 | 2020-11-12 08:10
20201208 | 20201208018 | 18 | Soils Report | IS there a soils report available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208018/ | Mike Coleman | 2 | 2020-11-13 14:04 | 2020-11-16 09:57
20201208 | 20201208018 | 18 | Schedule | Is there a design schedule available for this project? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2020-11-13 14:05 | 2020-11-16 09:56
20201208 | 20201208018 | 18 | Street Lighting | Who is responsible for the removal of the existing street lights? | The existing street lights are not part of the contract. They are to be relocated by the utility in an agreement with the utility and the village of Campbellsport. | Mike Coleman | 4 | 2020-11-19 14:14 | 2020-11-25 14:20
20201208 | 20201208018 | 18 | Contaminated soils and water | Special provisions say " All costs associated with dewatering activities within contaminated groundwater areas shall be considered incidental to construction" Since the Village will not take it, how is the contractor to quantify the amount of dewatering involved and determine appropriate hauling and disposal fees? Is all this risk to be born by the contractor? | We keep management of contaminated groundwater incidental. Maybe a bit unique in this situation because the municipalities are usually willing to accept. Data in DNR files showed it to be below our excavation limits. However, groundwater levels are very high lately, so we included it. | Mike Coleman | 5 | 2020-11-23 13:53 | 2020-11-25 14:22
20201208 | 20201208018 | 18 | Rock Excavtion | There is an item for Rock Excavation for Storm sewer but reviewing the plans for the Village work it would look like rock might be encountered while performing some of the water main. Is it safe to assume any rock encountered during this work would be considered extra work and compensated as such? | An addendum will be issued to include rock excavation for the village utility work. | Mike Coleman | 6 | 2020-11-23 14:17 | 2020-11-30 12:40
20201208 | 20201208018 | 18 | Phase 2.5 | Can you post the Phase 2.5 environmental? | The Phase 2.5 can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208018/ | Mike Coleman | 7 | 2020-11-25 14:31 | 2020-11-25 14:32
20201208 | 20201208018 | 18 | Pipe bursting 16" Forcemain | The specifications for the Village of Campbellsport has a Pipe Bursting Spec 330523 Pipe Bursting Sanitary Sewers which addresses the laterals. It also has a spec 333123 Sanitary Sewer Force Main which addresses the open cut work and using Ductile Iron pipe. The problem is that there is no spec for the Sanitary Force Main Pipe Bursting. As I see it is the plan appears to require the contractor to upsize and install 16" DI pipe for the 80' river pipe burst. From what I am hearing this would be extremely difficult if not impossible to construct using Ductile Iron pipe. Can the size be changed or the use of HDPE allowed? | The pipe size and material will be reviewed and addressed via addendum. | Mike Coleman | 8 | 2020-11-30 12:28 | 2020-12-01 05:36
20201208 | 20201208018 | 18 | Force main | The contractor has to connect to the existing force main at 4 locations. Can we get the pumping rates for the current lift station and the cycle time since we are required to bypass flows for the duration of these four connections. | The average daily wastewater flow in the force main is 200,000 gallons per day during dry weather. During wet weather, peak daily wastewater flow can reach 1,000,000 gallons per day. | Jill Fehrman | 9 | 2020-12-01 10:23 | 2020-12-04 13:51
20201208 | 20201208018 | 18 | Sewer aand Water Bedding and Cover | detail in plan shows clean soil up to 12" over the top of the pipe and compacted to 95%. The Village of Campbellsport specifications for S & W in STH 67 calls for the 1# stone to be 12" over the top of the pipe Which is it? The specifications also call for the bedding (1# stone) to be compacted to 95% while the detail says tamped, and the 95% compacted refers to the clean cover soils. Typically the 1# bedding stone is not tested because getting accurate results is difficult if not impossible. Will the bedding be tested for compaction by the Village? | The detail in the plans is correct and the bedding would not be tested for density. The Village specs need to be modified to match the detail. We will work with the Village to make this happen. | Mike Coleman | 10 | 2020-12-02 13:26 | 2020-12-03 12:52
20201208 | 20201208018 | 18 | Open cut Force Main work | The majority of the open cut Sanitary Force Main is thru an open field. I see no items for turf restoration in these areas. further when I read the village specifications for 67 Sewer and Water Work it tells me that include din my work is to strip and stockpile the topsoil, it does not tell me to respreads the topsoil, reseed and place mulch or emat. Does the contractor assume that this will turf restoration will be paid as additional quantitates? | The Village spec currently shows turf restoration as incidental in the General section but is not included in the Payment section. The spec needs to be modified to include this work in the Payment section and we will also reference WisDOT specs in the Construction section. This will include application rates and types for restoration. | Mike Coleman | 11 | 2020-12-02 15:54 | 2020-12-03 16:06
20201208 | 20201208018 | 18 | Special 110 Reinstall Sanitary Sewer Lateral At Main | The Village specifications (pg 15-21, 3.4 Connections, B.1.a.) state "Reinstate and reconnect service connections to the sewer main before sewer main is slip lined". Does the contractor have to cut in a new wye prior to slip lining and make the connection to the pipe burst lateral? Or shall the connection of the pipe burst lateral be made at the outside of the existing sanitary main and the liner would extend into the lateral past the connection point of the pipe burst lateral. If the reconnections can be made after the sewer main slip lining has occurred, saddle wyes could be installed at the time of pipe bursting | This issue has been discussed with the Village and the Village would like to proceed with the current construction process as stated in the Village specifications. | Mike Coleman | 12 | 2020-12-02 16:25 | 2020-12-03 12:53
20201208 | 20201208018 | 18 | Excavation Common vs Excavation Waste | Could you explain the difference between the excavation common and excavation waste items? It seems that the marsh excavation and rock excavation items are included in the excavation waste item. | Per the waste SPV, any excavation material hauled off the project limits and not utilized on the project is to be paid as waste. Common, marsh, rock are all included in this item. If the material is utilized onsite within the right of way, then the waste item is not paid and only the standard bid item is paid. | Mike Coleman | 13 | 2020-12-03 10:13 | 2020-12-03 10:19
20201208 | 20201208018 | 18 | Underground staging | In reviewing the design schedule and the special provisions it mentions that it anticipated Stage 1A and Stage 2 will begin shortly after Stage 1 with work occurring concurrently. With the overall time frame of the project and the concern with asphalt paving in late October (Stage 4) can the underground crews continue with installation on site until they are completed or is there a gap is needed as shown between Stage 2 and Stage 3 in the schedule? | The winning contractor can submit a revised staging plan for the Department to review, but the bid should reflect the work as shown in the plans and special provision staging. | Mike Coleman | 14 | 2020-12-03 10:34 | 2020-12-03 16:01
20201208 | 20201208018 | 18 | Street lighting | Per the response that the street lighting will be relocated by the utility and village. Is it anticipated to install during the staging of the project? | As noted in the previous questions, this work is being done by others. I reached out to WE Energies for their scheduled completion of this work. They hope to have lighting relocated by March 15th. | Mike Coleman | 15 | 2020-12-03 10:39 | 2020-12-03 16:07
20201208 | 20201208018 | 18 | Sanittary laterals | Because of the depth of the sanitary sewer main in some areas one would assume that there are sanitary risers the exist. Because the laterals are being replaced back to the wye in the main one would assume that you will be paid to this point. My question is can this riser pipe be replaced with conventional pipe materials such as SDR 35 or SCH 40 the existing riser will most likely have been removed to access the wye in the mainline? | Yes, the riser can be replaced with standard materials (PVC SDR 35). | Mike Coleman | 16 | 2020-12-03 11:19 | 2020-12-03 16:04
20201208 | 20201208018 | 18 | Sanitary laterals | Some of the sanitary laterals on the plan show that there maybe deflection in the alignment. While pipe bursting in most cases should work thru these deflections some of the them might not because if the angle is to severe the pipe bursting cable might try to shortcut the angle point and snub out pipe advancement. If this happens and the contractor is forced to excavate in a second location on property will this be considered extra work? | Yes. That would be considered Extra Work. | Mike Coleman | 17 | 2020-12-03 11:45 | 2020-12-03 16:02
20201208 | 20201208018 | 18 | Measurement/Payment of Retaining Wall | How is the wall going to be measured for payment? Is it from the bottom of the base block below grade or is it from the bottom of the exposed grade to the top of cap? | The measurement for SF payment is from the theoretical pay limits shown in the plans. The detail on sheet 22 of the plans shows the pay limits from the first block on the leveling pad to the top of the cap. | Mike Coleman | 18 | 2020-12-03 12:48 | 2020-12-03 12:49
20201208 | 20201208018 | 18 | Force Main Pipe Bursting | What is the existing force main material that we will be pipe bursting? | The existing force main that will require pipe bursting consists of ductile iron pipe. | Jill Fehrman | 19 | 2020-12-03 14:30 | 2020-12-04 13:52
20201208 | 20201208018 | 18 | Water Main Fittings | What material are the bolts for the water main fittings? In the special provisions addressing the water main it talks about Tee head bolts. If you make the jump to reviewing the force main spec ( which isn't water but the pipe material is DI like the water main ) it refers to using 304 stainless material for the bolts. | The water main fittings shall use stainless steel bolts. | Mike Coleman | 20 | 2020-12-04 10:07 | 2020-12-07 06:06
20201208 | 20201208019 | 19 | Adjusting Steel Plate Beam Guard | The areas listed in the plan for adjusting guardrail are the 4 SPBG EAT's at Mud Creek. Under the new spec, adjusting the height by more than 3 inches will require new posts. Can you confirm that the intent for these areas is to adjust the rail up by no more than 3 inches? Also, if new posts are needed, are the new posts incidental to the adjusting guardrail bid item? If posts are incidental, should EAT's, being proprietary systems, be included for adjusting under this bid item at all? | The intent of the adjusting guardrail is to adjust less than 3-inches for the EATâ€™s. This is due to changing cross slope within 5-ft of the EATâ€™s from 4% gravel shoulders to 2% paved shoulders. This is an expected change of 2% over 5-ft. From field inspection the beam guard meets height requirements as is. | Mike Coleman | 1 | 2020-11-16 11:38 | 2020-11-17 13:02
20201208 | 20201208022 | 22 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2020-11-09 14:01 | 2020-11-13 06:01
20201208 | 20201208022 | 22 | Miscellaneous Quantities Mixture Use Table & Typical Proposed Sections | The Miscellaneous Quantities Mixture Use Table on sheet #51 states that in station range 297+76 - 562+88 there should be 3.75" of HMA on the shoulder (1.75" Lower Lift and 2" Surface) meaning there would be full depth milling on the shoulder. The Proposed Typical Sections on sheet #9 state that station range is to mill 2" and overlay the mainline and shoulder with 2" with no full depth milling. Is there a missing Proposed Typical Section that states in that station range that the full depth milling and 3.75" of paving is being done or is it to follow the Proposed Typical Section on sheet #9? | An addendum will be issued to clarify this. | Mike Coleman | 2 | 2020-11-11 16:21 | 2020-11-13 06:03
20201208 | 20201208022 | 22 | Base Aggregate 1 1/4" | Cross Drain Installation Construction Detail shows 18" of 1 1/4" Base Aggregate Dense over the pipe trench and pipe transition area, but there is no quantities in a bid for this material. | The bid item 305.0120 Base Aggregate Dense 1-1/4 inch will be added via addendum. | Jill Fehrman | 3 | 2020-11-16 10:04 | 2020-11-20 12:54
20201208 | 20201208022 | 22 | DBE Goal | This project has a DBE participation goal of 11%. This project consists of primarily asphalt milling, asphalt paving, culvert pipe replacement, and a minor amount of guard rail work. From our experience with projects, in this area of the state, with these work types, it will be difficult to achieve 11% DBE participation. Can the DOT please review the DBE goal for this project? | The DBE office has reviewed this project's goals. An addendum is being issued to changed the DBE goal from 11% to 3%. | Mike Coleman | 4 | 2020-11-16 11:07 | 2020-11-17 12:29
20201208 | 20201208022 | 22 | Intersections and Driveway Quantities | This project has a total tonnage of 27,525 tons when you add the asphaltic surface for the (shoulder widenings and culverts patches) and mainline. If you hand calculate that tonnage out you come pretty close to same total tonnage for the asphaltic surface and 4LT Pavement. Looking at sheet #12 there is a Paving Detail At Intersections that states the butt joints for the intersections will be back 10' from the radius end. When you look at sheet #45 of the Miscellaneous Quantities Removing Asphaltic Surface Milling there is no quantity for milling the sideroads/driveways, but there is a quantity for Removing Asphaltic Surface Butt Joints at each sideroad. Then you look at sheet #46 for HMA Pavement there is no quantity for sideroads/driveways/field entrances. So is the plan to follow sheet #12 mill sideroads/driveways 10' back from radius end or mill through existing sideroads/driveways and match sideroads/driveways with edge as we pave the mainline overlays? | The sideroad and driveway milling quantities are included in the milling and paving quantities, for sideroads it was measured back 10 ft from the largest radius, driveways were calculated at 5ft from the shoulder edge. For project ID 6054-06-72 the estimated tonnages separated out from the asphalt paving in the miscellaneous quantities are as follows: Side Roads: 336 tons, Driveways 5.8 tons For project ID 6054-06-73 the estimated tonnages separated out from the asphalt paving in the miscellaneous quantities are as follows: Side Roads: 230 tons, Driveways 10.3 tons | Jill Fehrman | 5 | 2020-11-17 12:37 | 2020-11-20 12:00
20201208 | 20201208022 | 22 | milling quantities and no shaping shoulders Item | Sheet#8 shows each shoulder being milled 3.5" at 6 feet wide between 0+26 to 182+/-. The existing typical shld consists of 3 ft of asphalt and 3 feet of base. Is the total 6 feet of each shoulder going to measured and paid under the SY's of the milling item? Is there a detail on what is expected for milling and butt joints on the side roads and driveways. Does not appear that there is milling in the side roads according to the MQ's. Should there be a shaping shoulders item to cover the areas that are not covered by the prep foundation for Asphalt shoulders item? | For the shoulder widening: the existing 3 ft of asphalt is measured under the bid item 204.0120 Removing Asphaltic Surface Milling, the remaining 3 ft of the shoulder is measured under the bid item 211.0400 Prepare Foundation for Asphaltic Shoulders. Bid item 305.0500 Shaping Shoulders will be added via addendum. See question number 5 for the answer to where the sideroad and driveway milling quantities are located. | Jill Fehrman | 6 | 2020-11-18 08:41 | 2020-11-20 12:08
20201208 | 20201208022 | 22 | Construction Schedule | Can the Department provide the schedule developed during design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208022/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2020-11-19 07:33 | 2020-11-23 06:38
20201208 | 20201208022 | 22 | Lane Shifts | The Misc. Quantities show 4 Lane Shifts for the seven culvert pipe. The four locations all correspond to pipe that have a Depth greater than 7â€™ as described in the specials. There are also two more pipe that after 1-1/4â€ BAD is placed will have fills greater than 7â€™ that do not have lane shifts identified. Lastly, there is only 1 Lane Shift per pipe location. Generally, a 2 lane shifts are paid for per pipe location to complete the pipe installation. | The quantity for lane shifts is correct. The intent is to build the lane shift on one side of the roadway with an adequate offset to install the culvert pipe past the centerline of the road so the second half of the cross the pipe can be installed with traffic in the normal lane location. The pipes located at 112+97, 295+86, and 388+77 are shallow pipes (<6 ft in depth) therefore no lane shift was anticipated to be needed. The culvert at station 200+30 is not being replaced and only concrete masonry endwalls are being added. | Jill Fehrman | 8 | 2020-11-19 07:34 | 2020-11-20 13:02
20201208 | 20201208022 | 22 | Temporary markings on the milled surface | Good morning. With the milled surface allowed for a maximum of 72 hours, will the department overrun the 4" temporary epoxy item to cover this scenario if the paving contractor follows the 72 hour rule or will there be a temporary paint item added via an addendum? Thank you. | The contractor will be paid for pavement markings required. | Mike Coleman | 9 | 2020-11-23 11:33 | 2020-11-25 05:52
20201208 | 20201208022 | 22 | Barrier System Grading Shaping | On sheet 47 the Barrier System Grading, Shaping, and Finishing item has a station range that only includes the EAT. The grading limits are shown throughout the entire length of the guardrail. 1. How is the grading paid for between the EATs shown? 2. Could a more detailed Earthwork table be provided with stationing and cut and fill volumes? 3. Could slope staking be added for these areas? The Item for the Regrade Cattle Pass only includes payment for removing excavated material. It appears that there is some fill that would be required. How is that paid for? | 1. Grading will be paid for with the Borrow bid item. 2. A detailed table will not be provided due to the small quantities. 3. Yes, Construction Staking Slope Staking will be added. 4. Payment for fill in the cattle pass will be paid under the Borrow bid item. | Mike Coleman | 10 | 2020-11-30 14:49 | 2020-12-02 16:37
20201208 | 20201208022 | 22 | Lane Shift |  | there was no question attached to this. | Mike Coleman | 11 | 2020-12-02 08:03 | 2020-12-02 08:10
20201208 | 20201208022 | 22 | Lane Shift | the special provision for a lane shift say that the furnishing and installing of Temporary Asphalt is included in the cost work required. So the lane shifts have to be paved prior to used? I do not see where the culvert patches have to be paved in under any sort of time line. There is a plan note on Plan sheet 13 that says the asphalt surface has to be paved in after the culverts are installed and prior to the 4LT. Can local traffic be maintained on CABC? And for how long? | The intent is that asphaltic surface will be placed within 24 hrs of the completion of the culvert installation. | Mike Coleman | 12 | 2020-12-02 08:17 | 2020-12-02 16:40
20201208 | 20201208023 | 23 | Electronic Data Request | Please provide the following files below: - Existing ground surface file, in LandXML format. - Reference line alignments and proposed profiles, in LandXML format. - Superelevation transition information, .csv format. - Proposed roadway features, 2D DWG file. - Proposed structure horizontal features, 2D DWG file. - Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format - Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files - Slope stake report, .csv format. - Earthwork data, Excel spreadsheet xlsx file(s). - Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. - Design Schedule - Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208023/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-11-09 13:02 | 2020-11-13 08:29
20201208 | 20201208023 | 23 | Storm Sewer Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III in areas not located under the divided segment of USH 53? | : The project storm pipes, both storm sewer and culverts, have been evaluated to see if non-metal pipes should be used. Under the revised FDM guidance, a number of pipes qualify for the option of contractor choice in materials, allowing for a wider range of acceptable pipe material. An addenda will be issued that will modify the bid items of the qualifying pipes. | Mike Coleman | 2 | 2020-11-09 14:09 | 2020-11-16 06:10
20201208 | 20201208023 | 23 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? Also, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | The project storm pipes, both storm sewer and culverts, have been evaluated to see if non-metal pipes should be used. Under the revised FDM guidance, a number of pipes qualify for the option of contractor choice in materials, allowing for a wider range of acceptable pipe material. An addenda will be issued that will modify the bid items of the qualifying pipes. | Mike Coleman | 3 | 2020-11-09 14:14 | 2020-11-16 06:10
20201208 | 20201208023 | 23 | QMP Base Aggregate Dense 1 1/4" | The Special provision â€œQMP Base Aggregate Dense 1 ï¿½ - Inch Compaction, Item 371.2000.Sâ€ is in the proposal but there is not a quantity indicated. | This special provision is not needed and will be removed from the proposal via addendum. No change to the schedule of items. | Mike Coleman | 4 | 2020-11-13 07:39 | 2020-11-13 07:40
20201208 | 20201208023 | 23 | Soils Report | Is there any soil boring information related to this project that can be shared? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208023/ | Mike Coleman | 5 | 2020-11-16 08:53 | 2020-11-16 10:10
20201208 | 20201208023 | 23 | New Type I Sign Spec Items | There is an item for coated reinforcement, which may not be needed. There is not an item for Structural Steel Sign Supports, which may be needed. It is possible to move structural sign supports, if the grades are identical at the new location. However, the footings are paid separately and there is not any quantity for those. | The quantities for the new footings for Sign 4-1A are located in the Signs Type I table (page 357 of 1150). This table indicates the sign should be moved and includes bid items/quantities for concrete, steel and drilling shaft for the new footing. Via addendum, bid item 531.1160 Steel Reinforcement HS Coated Ancillary Structure Type NS will be updated to item 635.0200 Signs Supports Structural Steel HS. | Mike Coleman | 6 | 2020-11-17 08:39 | 2020-11-18 09:24
20201208 | 20201208023 | 23 | Removal of C-65-05 Clarification | Removal of existing structure C-65-05 is referenced under two different special provisions. #21 Removing old structure over waterway station 913+59SB Item 203.0500.S.01 and under #22 Removing Old Structure over waterway with minimal debris station 169+08 WF Item 203.0600.S.02 - Please clarify. | The bid items referenced in the structure plans are correct. Special provision #22 inadvertently states C-65-0005 as removal with minimal debris under bid item 203.0600.S.02. An addenda will remove the irrelevant language from the specials. There is no change to the plans or bid items/quantities. | Mike Coleman | 7 | 2020-11-23 14:33 | 2020-11-25 05:57
20201208 | 20201208023 | 23 | Concrete Retaining Wall - Volume Measurement & Payment | Will the concrete volume that infills the sheeting be measured and paid or will only the 8 1/2" minimum wall thickness be measured for payment? | The concrete that infills the sheets will be considered incidental to the sheeting. Notes will be added to the structure plans clarifying the payment. Revised plan sheets will be included in Addenda #1. | Mike Coleman | 8 | 2020-11-24 11:30 | 2020-11-25 14:23
20201208 | 20201208023 | 23 | Waste Site Location - SE Quadrant | Is there a surface file that shows the intended grades for this waste area? | The areas of WisDOT R/W that will be allowed for waste material will be clarified in Addenda #1. Proposed contours or a surface file will not be provided to the contractor, but the approximate volumes and general grading guidelines will be shown in the plan sheet. All final contours will be approved through the ECIP process during construction. | Mike Coleman | 9 | 2020-11-24 16:37 | 2020-11-25 14:24
20201208 | 20201208023 | 23 | Waterway Marker | Will waterway markers be required in the Namekagon River during the removal of P-65-6? | Waterway markers are required for the Namekagon River. The required use is referenced in special provision #3, Prosecution & Progress, and #71, â€œSPV.0105.02, Floating Boomâ€. Article #12 identifies the Namekagon as a navigable waterway. The cost for the waterway markers is incidental to the bridge removal items. | Mike Coleman | 10 | 2020-12-01 13:56 | 2020-12-02 11:34
20201208 | 20201208027 | 27 | Type II Signs | The miscellaneous quantities show several "BEAM GUARD REFLECTIVE END MARKER" being paid as Type II signs. Is that really the case or will they be incidental to the EAT? | These markers should not be paid as type 2 signs and should be considered incidental to the MGS terminals. We will be preparing an addendum to address this item. | Mike Coleman | 1 | 2020-11-17 08:28 | 2020-11-18 09:35
20201208 | 20201208027 | 27 | CIR/Shouldering/Hma Thickness | Question #1 Is the 3â€ CIR to extend to the limits of 2â€ Paving? This does not appear to be the case in some stations we go from exiting 26â€™ to paved 28â€™ width but does not show the CIR to go beyond 26â€™ In some sections is shows and existing width of 22â€™ a relay width of 22â€™ and a paved surface of 28. Our concern is that we will be paving a 1â€™ or 3â€™ additional width beyond the CIR process. We would propose reduced milling depth or no milling and increases the depth of 3 CIR to incorporate enough material to reach the extend of paving limits. Just some thoughts. Question #2 The shaping shoulder item on the CIR/widening in order to get the 28â€™. We question the structure stability of material left after blading this excess material off the side of the road to using on the slope. Question #3 Thickness of shoulder Paving 2â€? We do not believe that 2â€ of HMA shoulder is not sufficient when being installed on existing roadway material after the blade preps for HMA paving. Question #4 We feel that a single lift 2â€ paving lift limits us from any correction of slope and effects ride. Will the department consider a leveling layer? Questions #5 What is the requirement of the shoulder material prior to the CIR/Milling? Shall this material be picked up and hauled offsite out used on the slopes and wasted. Will virgin aggregate be supplemented for the use in shouldering? Questions #6 Will the 5MT Hma within CIR projects will be subject to PWL requirements? Very small quantity withing this portion of the project very possible to happen at a different time as the west portion of the job and possible a different plant as well. | 1. The CIR will extend out to the 3â€™ beyond the lane. The pre-mill will be reduced to allow for the excess material required. This will be addressed with an addendum. 2. The CIR will extend 3â€™ under the paved shoulder and the Prepare Foundation for CIR Pavement is included. This will be addressed with an addendum. 3. The CIR will extend out to 3â€™ beyond the lane to help provide a better based for the shoulder. This will be addressed with an addendum. 4. The leveling layer is not required for this project. 5. Base on the CIR Asphalt Base layer bid item the existing shoulder material will be bladed off to avoid contamination for CIR. The item Shaping Shoulders will be updated in the addendum to include all CIR areas to pay for this. The existing based will be allowed to be pulled up on the new shoulders. Supplemental virgin base has been included in the plan to account for areas wither the existing shoulder has sloughed off and to match the new pavement depths. The quantities will be updated in the addendum for these items. 6. This mix will be subject to PWL requirements. | Mike Coleman | 2 | 2020-11-19 13:53 | 2020-12-01 12:21
20201208 | 20201208027 | 27 | Anchoring Concrete Barrier | What is the reasoning for anchoring the temporary barrier on the bridge and approaches for this project. The deck remains in place on the bridge and the are not significant drops on the approaches. Are these items required? | The quantity for anchoring temporary barrier will be reduced and the revised quantity will be included in the addendum for the project | Mike Coleman | 3 | 2020-11-23 20:48 | 2020-11-24 11:51
20201208 | 20201208027 | 27 | Common Excavation | The plan for SP#8630-03-82 shows common excavation quantities at the several of the culvert replacements. The cross sections seem to show most of that quantity comes from directly above the pipe. Will the department actually pay for that excavation as common ex or will it end up being incidental to the pipe installation? | An addendum will adjust the earthwork data tables and common excavation quantities to eliminate the common excavation for the culvert pipes for the 8630-03-82 project. | Mike Coleman | 4 | 2020-12-02 07:35 | 2020-12-03 16:00
20201208 | 20201208027 | 27 | Follow up Question - Shaping Shoulders/Prep.... | This is a follow up Question to one that I asked and received and answer as number 5. I believe the in widening the road in the CIR portion of this project there is little to no room for the 1' to 3' widening. This material for the most part will not be able to be bladed onto the slope. Can you tell me underwhich item the removal of excess material will be paid? "Prep of Foundation for Asphaltic Shoulder" or a new Item such as "Haul Excess Shoulder Material". This material when hauled off will not be brought back onsite. Additional 3/4" should material maybe needed. | An addendum will increase the item common excavation to account for removal of excess shoulder material. This material will be able to be used to reduce the Borrow required for the project. The Base Aggregate Dense ï¿½ - Inch will also be increased in the addendum. | Mike Coleman | 6 | 2020-12-02 19:35 | 2020-12-03 16:00
20201208 | 20201208028 | 28 | Culvert Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) Min/max cover heights are less than 15 feet for Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPCS? | We will develop an addenda for the project that will allow the use of Class III pipes based on FDM guidelines. | Mike Coleman | 1 | 2020-11-09 14:19 | 2020-11-16 06:13
20201208 | 20201208028 | 28 | pulverize and relay | Is there any core data available to confirm pavement thickness? thanks | The geotechnical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208028/ | Mike Coleman | 2 | 2020-11-13 15:33 | 2020-11-17 14:03
20201208 | 20201208028 | 28 | Temporary Shoring | Does WisDOT have a detail showing how the shoring will be used to replace the pipe and for excavating the 3:1 slopes to the top of the pipe, while maintaining traffic? It seems a detour would be fairly easy to set up and much more cost effective. Thanks | A detail for Lane Shift for the construction of the pipes half at a time will be added to provide additional detail as to the pipe construction and use of temporary shoring. | Jill Fehrman | 3 | 2020-11-18 13:36 | 2020-11-20 12:24
20201208 | 20201208028 | 28 | Traffic - Lane Closure Limit | Under the Traffic section it states "Lane closures shall not exceed 1/2 mile in length unless authorized by the engineer." While it does allow leeway for the engineer; note that it is not possible to, prep, tack, pave HMA, roll and density test within a 1/2 mile lane closure while paving consistently to meet the PWL specification. Can we remove the 1/2 mile limit and follow the standard detail for lane closures with flagging operations? | It is anticipated that the contractor will be able to increase the lane closure to greater than ï¿½ mile, provided that they can do so in a safe manor without creating excessive delays (over 15 minutes) for the traveling public. If there are any safety issues or excessive delays caused by longer lane closures longer than ï¿½ mile, the lane closure will be limited to a length that limits delays and does not create safety issues. | Mike Coleman | 4 | 2020-12-01 15:11 | 2020-12-02 11:47
20201208 | 20201208002 | 2 | SOIL BOARINGS | Are soil borings available for the sign structure foundations? | No, we did not get borings at each individual sign structure foundation. A combination of historical borings and a few strategically located additional borings were used to evaluate general soil conditions and foundation design parameters for each sign structure. The borings available have been posted to the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208002/ | Mike Coleman | 24 | 2020-12-06 08:51 | 2020-12-07 08:08
20201208 | 20201208002 | 2 | Soils Report. | Can the soils report be provided? | The soils information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201208002/ | Mike Coleman | 25 | 2020-12-07 08:08 | 2020-12-07 08:25
20201208 | 20201208002 | 2 | Are there restrictions to the hours that traffic can leave the median areas. | Are there hour restrictions when construction traffic and trucks can enter and leave the areas that are protected by temporary barrier walls? | Access to areas protected by temporary barrier wall shall follow the restrictions stated within the â€œWorkzone Access and Work Hoursâ€ section of the â€œProsecution and Progressâ€ special provision. | Mike Coleman | 26 | 2020-12-07 08:11 | 2020-12-07 08:45
20201208 | 20201208015 | 15 | Bid Item # 0952 - Railroad Flagger Reimbursement | Bid Item #0952 - Railroad Flagger Reimbursement does not have a set Unit Price of $1.00 Dol. Please clarify if $1.00 should be used for Bid Item # 0952. | An emergency addendum has been issued to change this to a pre-established unit price of $1. Thank you for bringing this to our attention. | Mike Coleman | 50 | 2020-12-07 10:56 | 2020-12-07 12:47
20201208 | 20201208015 | 15 | Response 49. | The curb and gutter removal shown in the Miscellaneous Quantity sheet is largely for curb and gutter tied to existing concrete pavement and both will be removed. For example all the curb and gutter on STH 31 is tied to Existing Concrete Pavement but is included in the plan and bid quantities as being paid for as curb and gutter removal. Standard Specification 204.4 (3) and (5) do not include payment for curb and Gutter removal as shown in the plans but as Pavement Removal. This is a conflict with the plan and the standard specifications provide payment for the curb and gutter removal as Pavement Removal. The Standard Specifications are clear that when there is a conflict between the Plans and the Standard Specifications the plan overrules. Should we bid the curb and gutter that is tied to concrete pavement at a penny being WisDOT is not going to pay for work as clearly shown in the plan? | In locations where Concrete Curb & Gutter is removed separate from the Concrete Pavement due to staged constructions (ie existing pavement to remain for staged traffic), Curb & Gutter Removalâ€™s were listed in MQâ€™s as this activity is independent of Concrete Pavement removal, thus paid as C&G Removal per WisDOT 2021 Standard Specifications 204.4 (5). Along STH 31 for example the Median C&G is removed independently from the Pavement for Staged Construction and listed in the C&G Removal MQs. While the C&G Removal on the outside shoulders is removed at the same time as the Concrete Pavement, thus included with the Concrete Pavement Removal Area, and Not listed in the C&G Removal MQs. The intention of the Curb &Gutter MQâ€™s and interpretation of the Standard WisDOT 2021 Standard Specifications 204.4 (3) only applies when both pavement and Curb & Gutter are removed in the same stage/sub-stage, if staging operations require C&G removal in an independent staged/sub-stage compared to the Pavement, Payment would follow WisDOT 2021 Standard Specifications 204.4 (5). | Mike Coleman | 51 | 2020-12-07 11:21 | 2020-12-07 14:41
20201208 | 20201208023 | 23 | bid items 204.0240.01/.02/.03 Site Clearance. | What work was to be included for bid items 204.0240.01/.02/.03 Site Clearance? | Additional guidance is as follows: 204.0240.01, Clear any remaining structure items for existing â€œicoâ€ sign located on Parcel 11 204.0240.02, Clear any remaining bollards located on Parcel 12 204.0240.03, Clear any remaining bollards located on Parcel 21 | Mike Coleman | 11 | 2020-12-07 12:57 | 2020-12-07 12:58
20201208 | 20201208004 | 4 | Signal Questions | 1. Sheet 10 & 11 call us to bring a 2" & 3" out of PB-5 and to Adjust PB-5. Sheet 32 calls to remove PB-5? 2. Sheet 11 Calls out PB31 but is not Sheet 32 3. Sheet 11 shows Signal head 7 as 5 Section but Sheet 12 in Construction Notes4. says change to a 4 Section? | 1. There are 2 sets of conduit coming from PB-5. Sheet 10 is on the lighting plan which shows 2 inch conduit and Sheet 11 is the Signal Plan which shows 3 inch conduit. These are called out on Sheets 31 and 32 of the misc quanitity sheets. PB-5 should be removed and replaced. The removal and new pull box are called out in the misc quantity tables on Sheet 32. 2. This pull box should have been included in the Pull Boxes misc quantity table on Sheet 32. 3. This signal head should be a 4-section. The 4 heads should show left arrows for red, yellow, flashing yellow, and green. | Mike Coleman | 1 | 2020-12-07 14:47 | 2020-12-07 14:48