## qandasearchletting_results
Date: | 2021-04-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210413 | 20210413001 | 1 | Shaping Shoulder - Missing item | On sheet 323 of 426 on the plans the detail calls out ""shaping shoulders - blade off shoulder gravel to maintain drainage" however there is no pay item for this. Is this intended to be a paid item or is this being considered incidental? Thanks, | The â€œShaping Shouldersâ€ language was not intended to be a paid bid item, but direction to the contractor to maintain drainage during construction, which is incidental per Standard Specification 204.3.2.2.2 Removing Asphaltic Surface Milling. | Mike Coleman | 1 | 2021-03-15 10:57 | 2021-03-18 07:53
20210413 | 20210413001 | 1 | Rem HMA Notched Wedge - Missing Item | On sheet 326 of 436 it calls out for "removing HMA pavement notched wedge longitudinal joint milling" however there is no item for this. Is this a paid item, incidental or should this be removed? Thanks, | We have confirmed with the Region that the note should be removed and the notched wedge joint be left in place and handled per the updated SDD 13C19 that is included in the Let plan. An addendum will be issued to address this. | Mike Coleman | 2 | 2021-03-15 10:59 | 2021-03-18 08:13
20210413 | 20210413001 | 1 | Design Files | Can the Department provide the design files for project (ie staking packet, orig/final surfaces, prop lines/alignments, schedule, soils report, etc.)? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413001/ | Mike Coleman | 3 | 2021-03-15 11:12 | 2021-03-19 06:57
20210413 | 20210413001 | 1 | B-28-18/19 Bearing anchor bolts | In the notes for the bearing details on B-28-18 and B-28-19 it states to "REUSE EXISTING ANCHOR BOLTS" at certain girders for each structure. What is the intent of this? Typically all anchor bolts are cut off flush, and new ones installed. Removing the nuts, and bearings without damaging the threads of the existing anchors will be difficult. | The existing bridges had the original bearings replaced in 1989 and then were widened in 2001. From field inspections the 2001 bearing anchor bolts appear to be in good condition and are planned to be reused. The existing bearings from 1989 are to have new adhesive anchors installed. | Mike Coleman | 4 | 2021-03-19 11:11 | 2021-03-22 12:11
20210413 | 20210413001 | 1 | #85 temp pavement removal | Which item(s) will payment for Removal of temp. pavement from project #85 be under? | For project 1067-01-85, the pavement widening is permanent. Traffic will be on it for temporary stages, but this pavement will not be removed on this project. | Mike Coleman | 5 | 2021-03-22 12:17 | 2021-03-23 06:21
20210413 | 20210413001 | 1 | Cable Barrier SDD's | On pages 235 and 236, the SDD's for the cable barrier are showing details not historically used in cable barrier installations. Several drawings for the cable barrier anchors and line post footings show a multitude of rebar and all of the rebar being epoxy coated. In the General Notes, it states, "Drawings are general in nature. See manufacturer's information for more detail.". And it also states, "Provide a Wisconsin Professional Engineers stamped analysis that the line post and cable barrier end terminal footings are designed for the soil conditions present." My question is, if the manufacturers stamped and signed drawings show less rebar and/or rebar that is not epoxy coated, will the Department defer to the manufacturer's stamped drawings as determined by the manufacturer or will the Department require the manufacturer to follow these SDD's instead? | The contractor shall provide a cable barrier system that is on the approved product list for Jefferson County. Provide a Wisconsin Professional Engineerâ€™s stamped analysis that the line post and cable barrier end terminal footings are designed for the soil conditions present. | Jill Fehrman | 6 | 2021-03-29 14:28 | 2021-04-12 14:43
20210413 | 20210413001 | 1 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413001/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2021-03-30 06:32 | 2021-03-30 11:31
20210413 | 20210413001 | 1 | Rubblization of Existing Pavement. | In the Existing Cross Sections it is noted, "CONTRACTOR TO DETERMINE SIZE AND CONDITION OF RUBBLIZED CONCRETE." Can WisDOT Explain how the Contractor is supposed to do this prior to bid and construction? Does WisDOT have records of the condition of the Existing Pavement Rubblization that it can share with the bidders? Is there any reason to expect the existing rubblized concrete is in a condition other than the gradation provided in the Rubblization Standard Specification? | Addendum #2 removed the note and added another to clarify. | Jill Fehrman | 8 | 2021-03-30 06:40 | 2021-04-12 14:25
20210413 | 20210413001 | 1 | SPV.0105 Salvage and reinstall beam guard rail LS | If you look on sheet 9 and sheet 12 it shows small stretches of rail being taken down at the bridge parapet walls is this correct? In the misc quantities it says lump sum from station 674+10 - 625+29 Which is 4881 linear feet, we would like some clarification on how much rail has to be salvaged and reinstalled. | The Salvage and Reinstall Beam Guard Rail bid item is intended so the Contractor can remove beam guard as necessary to complete the pavement replacement adjacent to it. This amount was revised in Addendum #2, but it should be the length of the shoulder paving or as determined in the field. | Jill Fehrman | 9 | 2021-03-31 07:27 | 2021-04-12 16:00
20210413 | 20210413001 | 1 | 614.0905 Temporary Crash Cushion | In the Miscellaneous Quantities table for Temporary Crash Cushions on project ID 1067-01-85, the "Back Width" column shows widths of 8' up to 15' for the crash cushion to protect; however under the "Crash Cushion Shields" column the hazard protected by the crash cushion is temporary barrier wall which is typically only 2' wide. Please clarify if the crash cushions will be protecting standard temporary barrier wall (2') or if the contractor should plan on utilizing extra-wide bay crash cushions up to 15' wide. Thanks | The Temporary Crash Cushion column â€œback widthâ€ has been removed from the MQ table in Addendum #2. The crash cushions are intended to protect concrete barrier ends, either a single barrier or 2, depending on the stage. | Jill Fehrman | 10 | 2021-03-31 13:50 | 2021-04-12 15:58
20210413 | 20210413001 | 1 | Rubblization | Can the precise records that show where the existing concrete pavement was rubblized to gradation, cracked or seated or no rubblizing or cracking and seating was performed please be provide which show the precise location of these three existing pavement treatments? | The as-built plans show that all underlying concrete was rubblized. The department has no additional information. | Jill Fehrman | 11 | 2021-04-03 06:17 | 2021-04-12 14:58
20210413 | 20210413001 | 1 | Temporary Pavement Markings | Good afternoon, Can you please elaborate on what the 3' line/9' gap 4" temporary markings are for on the mainline in stages 1 & 2? I know there are a 3'/9' few dotted areas coming off of ramps but the quantity seems to be way more than is needed to place these markings. Will this be clarified and, if needed, will an addendum be issued to include corrected quantities? Thank you. | We will address the ID 1067-04-72 temporary pavement marking question via Addendum for this proposal. The computed quantity totals for the bid item in question are correct in the MQ table, but there are unnecessary quantities in the mainline rows that will be removed for the addendum sheet and these did not factor into the total. Again, no SOI update needed for this change for ID 1067-04-72. | Mike Coleman | 12 | 2021-04-05 13:40 | 2021-04-06 10:21
20210413 | 20210413001 | 1 | Permanent Pavement Markings on Ramps | Good afternoon, Can you please take a look at the note on page 7 of 54 stating that a ramp may be closed for "up to one hour when placing pavement markings" and clarify if that statement is meant for temporary and permanent markings or just the temporary markings? Being that the ramps will get grooved in wet reflective and tape markings, if this statement pertains to permanent markings, it isn't realistic to expect the permanent markings to be placed within this time frame. Can you please clarify the intent and, if this is the case for the permanent markings as well as the temporary, address the permanent markings and allow more time for said permanent markings? Thank you. | Typically one nighttime closure per ramp per stage is allowed to complete this work. | Jill Fehrman | 13 | 2021-04-05 13:58 | 2021-04-12 14:18
20210413 | 20210413001 | 1 | OPENING STRENGTH OF CONCRETE BASE | Section 35 paragraph B states, Furnish concrete according to standard spec 715 that meets the required opening strength of 2000 PSI within 4 hours of placement or prior to opening to traffic. Obtaining 2000 PSI of strength within 4 hours can be an issue but obtaining 2000 PSI of strength prior to opening to traffic will not. If 2000 PSI of strength is obtained prior to opening the roadway to traffic but it takes longer than 4 hours will there be a material penalty on the material? | There will be no penalty as long as an opening strength of 2,000 psi is achieved prior to opening to traffic. | Mike Coleman | 14 | 2021-04-05 17:26 | 2021-04-06 10:23
20210413 | 20210413001 | 1 | Dowel Bars and Tie Bars | The plan does not have dowel bars or tie bars for the base patches. Is the intent on this project to not use tie bars or dowel bars on the base patches? | The construction detail on page 16 of the plan for Project ID 1067-04-72 indicates the existing concrete pavement has been rubblized (typical). It is not anticipated that dowel bars or tie bars will be required to complete this work. | Jill Fehrman | 15 | 2021-04-06 12:02 | 2021-04-12 14:04
20210413 | 20210413001 | 1 | Concrete Masonry Deck Repair, Item 509.2100.S. | Is the Preparation Decks Type 1 & 2 removal supposed to inclusive to this item? This special provision describes providing concrete masonry on the sawed deck preparation areas of the concrete bridge deck, but doesn't include the removals. | New concrete at the joint repair is paid for as â€œ509.2100.S Concrete Masonry Deck Repairâ€. This includes concrete to replace sections of the parapet within the joint repair limits. Any excavation required to complete the joint repairs at the abutments to be considered incidental to the bid item â€œ509.2100.S Concrete Masonry Deck Repairâ€. No deck repair has been included in this work. | Mike Coleman | 16 | 2021-04-06 16:17 | 2021-04-07 13:19
20210413 | 20210413001 | 1 | Crown Point between Lane 1 & inside shoulder | If the Lane 1 and inside shoulder lower layers are not paved at the same time; would we be allowed to leave a standing joint at the crown point (transition from Mainline to shoulder)? Or would we be required to install a Michigan joint? | If Lane 1 and the inside shoulder lower HMA layers are not paved at the same time, a standing/vertical joint will not be allowed. | Jill Fehrman | 17 | 2021-04-07 15:51 | 2021-04-12 15:39
20210413 | 20210413001 | 1 | Temp Barrier Anchoring Requirements | The miscellaneous quantities call for 225â€™ of anchored barrier in stage 1C on WB and nothing during the mirror stage for stage 2C. The bridge plans show anchoring of barriers to the deck on both bridges. 2 questions, 1. What are the limits for anchoring of the temp barrier as shown in the quantities on sheet 42 of the plans? 2. Is the anchoring of the barrier on the deck required since there is a clear zone on each side and if so, is it incidental or included in the bid item 603.8500 - Anchoring Concrete Barrier Temp Precast | For Stage 1C, the barrier is anchored from the west end of the parapet, 225â€™ (18 segments), from station 673+64â€™WBâ€™ Lt to 675+89â€™WBâ€™ Lt. This is because the pavement only allows 1â€™ behind the barrier, and there is a long slope beyond that. The same is not true of the eastbound for stage 2C. | Jill Fehrman | 18 | 2021-04-08 15:21 | 2021-04-12 15:11
20210413 | 20210413001 | 1 | Addendum -Pending | When can we expect to see the addendum referenced in my question regarding removal of the notched? Thanks, | This was addressed in addendum #1. The notched wedge will remain. Please follow the standard detail drawing. | Jill Fehrman | 19 | 2021-04-08 17:19 | 2021-04-09 16:21
20210413 | 20210413001 | 1 | Anchoring Temp Barrier on Bridge | The notes on the pages 129 and 139 of the plans call for temp barrier to be anchored to the bridge deck in stages 1B and 2B. Is this anchoring of the barrier on the deck required since there is a clear zone on each side and if so, is it incidental or included in the bid item 603.8500 - Anchoring Concrete Barrier Temp Precast. |  |  | 20 | 2021-04-12 15:31
20210413 | 20210413004 | 4 | Design Files | Can the Department provide the design files for the project (ie staking packet, orig/final surfaces, prop lines/alignments, schedule, soils report, etc.)? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413004/ â€¢ Per FDM standards, because of the type of project (resurfacing mill & overlay), surface files are not required, however they were prepared and are included for the three culvert replacement locations. The proposed concept for mill & overlay matches the existing surface elevation and cross slope of the asphaltic pavement, including areas of superelevation and cross slope transition. The Detail for Typical Supelevation Transition is included with the Construction Details in the plan to show the intent for superelevation. â€¢ Due to the limited scope of construction, no soil borings were taken for the project. â€¢ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-03-15 11:13 | 2021-03-17 08:59
20210413 | 20210413005 | 5 | Road Closure | A couple of questions regarding the road closure. Will the department allow the in town curb & gutter and sidewalk repair work to occur while the section of road is closed? Does the 48 hour mill-pave rule apply in this closure? | No. Per the Prosecution and Progress Article of the Special Provisions, â€œDo not begin contract work under Project ID 5939-01-60 and between STH 80 and Bigelow Hill Road under Project ID 5940-02-60 until all contract work between Bigelow Hill Road and STH 130 is complete.â€ The 48 hour mill-pave rule does apply in this closure. | Jill Fehrman | 1 | 2021-03-26 09:48 | 2021-04-09 16:09
20210413 | 20210413005 | 5 | 5940-02-60 Beam Guard | The typical on sheet 6 shows the milling going to the face of the beam guard. In the past we have been permitted to mill as close to the face of the rail as the equipment will allow. Will this be permitted on this project also? Thanks | The intent of the project is to mill/pave as close to the face of existing guardrail (to remain) as allowed using standard milling equipment without causing damage to the existing guardrail (to remain). | Jill Fehrman | 2 | 2021-03-26 10:09 | 2021-04-09 16:10
20210413 | 20210413006 | 6 | Polymer Resin Supply | The polymer resin industry is experiencing unprecedented supply chain disruptions caused by the recent weather in Texas which accounts for a significant portion of petrochemical production in the U.S. Most of the Houston area affected facilities are the primary suppliers of the base resin and amines which are the key ingredients needed to produce epoxy products used for bridge deck polymer overlays. This has resulted in an extreme material shortage with no current outlook as to when supply will be back to normal. This project would require immediate and consistent supply of polymer resin to meet construction schedule and required completion date of 9/14/21. All polymer resin suppliers have not been able to provide certainty as to when supply will be available for current demand or future opportunity. Most estimations have been out to Q4 and likely into 2022. Please consider extending polymer overlay completion requirement through 2022 due to supply issue. | The contract completion time will remain unchanged. The contract should be bid to meet the specifications in the plans and special provisions. | Mike Coleman | 1 | 2021-03-30 12:50 | 2021-04-06 12:16
20210413 | 20210413006 | 6 | Polymer Liquid Binder Price Volatility | Due to raw material supply issues for polymer liquid binders there has been significant price volatility in the market. Price increases and surcharges have been implemented, however these prices are not guaranteed will fluctuate with the raw material costs based on the date the product is manufactured or shipped. We are confident we can obtain supply, but there is significant price risk that is out of our control which may result in higher unit prices for the project. Is the department willing to consider an escalation clause due to price volatility on polymer liquid binders? | The Department will not provide an escalation clause. | Mike Coleman | 2 | 2021-04-01 14:45 | 2021-04-06 12:17
20210413 | 20210413007 | 7 | Thermoplastic Bid Items and a Tape Specificaiton | The bid items for Preformed Thermoplastic, #'s 0284, 0292, 0294, & 0296 have a specification in the proposal for Tape. (Pages 40, 41, & 42 of 53) Can you confirm that you want thermoplastic and not tape on this project? Will the correct specifications be provided in the proposal for the thermoplastic, or will this be switched to tape? | Preformed thermoplastic markings will be required. Specifications will be updated via an addendum. | Jill Fehrman | 1 | 2021-03-22 07:34 | 2021-03-25 06:32
20210413 | 20210413008 | 8 | Signing | Can a better breakdown of signs be provided? Page 146 of the MQs only lists the total square footage of signs per street. In addition, pages 134 through 136 are showing a total of 7 folding stop signs that don't have a quantity for that bid item listed. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-04-05 09:11 | 2021-04-06 08:11
20210413 | 20210413008 | 8 | Special 07 Curb Ramp Grading Shaping and Finishing | Does the Design engineer have a take off on the Quantities for the Excavation, Earth Backfill, Topsoil, Fertilizer and Sod broken out for this item? This has been broken out and provided on previous projects that have been let, and included in the MISC QTY'S. Trying to Verify qty's for this combined item. | With the urban nature of the project, the amount of work for the items in question are minor and these items were not broken out and provided. For curb ramp and pedestrian curb installations, restoration varies for installations adjacent to existing sod and existing landscaped areas (mulch) as shown on the plan. A special provision is provided in the proposal that includes items of work required including restoration incidental to the pay item. However based on review of the plans and specials, we plan to issue a clarification via addendum. Regarding breakdown of breakdown of restoration items, prospective bidders will need to employ due diligence in reviewing the plans, and if needed, perform a field review of the conditions for bidding purposes. | Mike Coleman | 2 | 2021-04-05 11:27 | 2021-04-06 08:33
20210413 | 20210413009 | 9 | Railroad insurance | Looking at the plans, and locations of the striping, can you tell me where the railroad crossings are located in regards to the striping on this project? I do not see any crossings within the project limits of the plans. Is the Railroad insurance needed? | The railroad insurance article will be removed by addendum. | Mike Coleman | 1 | 2021-03-22 11:06 | 2021-03-24 12:34
20210413 | 20210413009 | 9 | 8" Epoxy | Looking at the bid item for 8" Epoxy. It has a total of 121,861' as the bid item, but the miscellaneous quantities only show 5,965', which I am assuming is the correct quantity. Can you verify the quantity for 8" Epoxy? | You are correct. It should be 5,965. An addendum will be issued to correct this. | Mike Coleman | 2 | 2021-03-22 11:16 | 2021-03-23 10:18
20210413 | 20210413009 | 9 | Addendum #03 | Good morning. In looking at addendum #03, I am concerned with that, with the late addition of this requirement, it will be difficult to find space that meets these requirements on such short notice and that has the flexibility for short term occupancy. In addition, I am curious why this was added to a pavement marking contract seeing as these types of projects do not have the need for a field office, especially one of this size. I would think that the significant potential cost that will be added would be a deterrent and, with COVID 19 still abundantly in play, most state agencies and contractors alike would not be inclined to gather in a space such as this as it would violate most, if not all, companies protocols and COVID awareness plans. I would think anything that is usually done in a field office can be, as it is being done on most projects, done remotely using Teams or Zoom. Can this requirement be withdrawn in the interest of safety and economics? | The Field Office requirement will not be withdrawn from the proposal. | Jill Fehrman | 3 | 2021-04-08 06:31 | 2021-04-09 16:05
20210413 | 20210413010 | 10 | Design Files | Can the Department provide the design files for the project (ie staking packet, orig/final surfaces, prop lines/alignments, schedule, soils report, etc.)? | The soils report has been added to the same link. The requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413010/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. The soils report will be provided soon. | Mike Coleman | 1 | 2021-03-15 11:13 | 2021-03-17 08:12
20210413 | 20210413010 | 10 | Signing | A couple of concerns with the signing plan: The chevrons are called out to be doubled up on a single 2 x 2 steel post. One concern is the ability to angle the signs correctly toward oncoming traffic this way. It appears the current installation has 2 posts in some instances because of this. It appears that one directions signs will not be at state minimum heights. Please confirm. The night arrows are 4 foot wide and also on a single 2 x 2 post. Please confirm this is desired. | For W1-8 chevrons, an addendum will be issued to call for separate posts for each sign. For W1-6 night arrows, the addendum will reflect 2 posts per sign per sign plate A4-9. Mounting heights for these signs are per sign plate A4-3. | Mike Coleman | 2 | 2021-04-05 09:35 | 2021-04-06 12:15
20210413 | 20210413011 | 11 | Electronic Data Request | Please provide the following files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413011/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-03-10 11:54 | 2021-03-12 08:06
20210413 | 20210413011 | 11 | 616.0120.S Fencing Small Animal | Does the DOT have any knowledge of where this type of fence can be purchased? Do you have more info on what type of posts are needed? Also it seems that finding this fence in stainless steel is about impossible, how do we know when we bid this item if we bid it for a galvanized type of fence that the dot will accept this product as long as this type of fence meets spec? | We have not done specific research on locations where this small animal fence can be purchased. However, the specification for the small animal fence is basically for chicken coop wire and should be readily available. Based on the material requirement for the Fencing Small Animal requirement (attached below), if stainless steel is not available, the contractor can document and substitute appropriately. If it meets all specifications, WisDOT will accept. | Mike Coleman | 2 | 2021-03-16 09:54 | 2021-03-17 06:10
20210413 | 20210413011 | 11 | 5' Chain Link Special | Bid item #0438 - Fence Chain Link 5' Special - In the proposal on page 41 of 57 it states that the 5' fence should be buried 1' into the ground. Does that mean 4' of chain link fence is showing, or do you want a 6' fence with 1' of fence buried? Please advise on how much fence you want showing above the finished ground. | The Fence Chain Link 5â€™ Special item should have 4â€™ of the chain link fence showing with 1â€™ buried. Buried fence is due to environmental commitment within this area. | Mike Coleman | 3 | 2021-03-18 12:13 | 2021-03-22 06:23
20210413 | 20210413011 | 11 | Item # 10 & 12 | Why is there a Removing Old Structure and a Removing Old Structure Over Waterway with Minimal Debris item for the same location / station? | There are duplicate items for the structure removal at STA 339+40. The correct item is 203.0060.S Removing Old Structure over Waterway with Minimal Debris. An addendum will be forthcoming to remove the duplicate 203.0200 Removing Old Structure item. | Mike Coleman | 4 | 2021-03-19 08:50 | 2021-03-22 13:00
20210413 | 20210413011 | 11 | Temporary Haul Road Crossings | What will be the requirements for contractors crossing any roads with construction equipment, mainly between stations 372+00 to 390+00? | Contractors are required to follow all applicable portions of Section 100 and 618 of the Standard Specifications for hauling operations. In addition, if they are proposing to directly cross any existing local/county roads that intersect the corridor with off-road equipment, they are responsible to protect the underlying roadway prior to crossing it to prevent damage to the pavement/substructure of respective local/county road. Any proposal by the contractor would be subject to approval by the engineer but this approval would not absolve the contractor from ultimate responsibility for protecting the local/county road. Any crossing of local/county roads would only be allowed during daylight hours and contractor should make every effort to minimize impact on local traffic. Contractor is also responsible for any signing/flagging operations to ensure safe crossing of vehicles. Signing would be subject to engineer approval and should at a minimum conform to SDD 15D29 â€“ Traffic Control, Vehicle Entrance/Exit or Haul Road. | Mike Coleman | 5 | 2021-03-19 08:57 | 2021-03-22 12:15
20210413 | 20210413011 | 11 | Select Borrow | Can DOT provide a station to station listing (like cut and fills) of how the select borrow quantity was calculated? Also, in the earthwork summary it states that EBS excavation to be backfilled with select borrow material. Where is that quantity of select borrow accounted for? | The quantity of select borrow material is shown in the miscellaneous quantity listing on page 73. There is an estimated quantity shown for the select borrow in each of the three identified marsh excavation areas. In order to get a station-to-station breakdown for select borrow similar to cut/fill, our designer would need to create a special select borrow surface layer and this was not created in design. Therefore, we are not able to provide a station-to-station listing. | Mike Coleman | 6 | 2021-03-19 10:51 | 2021-03-23 08:50
20210413 | 20210413011 | 11 | Pipe End Grate | Will the Department consider changing the current "Pipe End Grate" detail to a grate which is placed over the endwall? | Yes, the Department will change the â€œpipe end grateâ€ detail to have the grate placed over the endwall. An addendum will be forthcoming to revise the pipe grate detail. | Mike Coleman | 7 | 2021-03-23 08:27 | 2021-03-24 08:45
20210413 | 20210413011 | 11 | Eco Passage Structure | Will the Department allow the eco passage structure to be precast, instead of cast in place? | Given the complexity of the eco-passage structure, we felt that cast-in-place would be a better and less expensive option. Also, a cast-in-place option was used on a previous project with a similar eco-passage structure. That being said, the Department would allow a precast option if the contractor can meet all plan requirements for the eco-passage structure. | Mike Coleman | 8 | 2021-03-23 13:54 | 2021-03-24 07:56
20210413 | 20210413011 | 11 | Select Borrow # 2 | The questions asked in the initial "Select Borrow Question" where not answered in the response. #1: If a station to station listing is not able to be provided, then how was the select borrow "estimated quantity" listed on page 73 of the miscellaneous quantities (for the marsh backfill) calculated by DOT? #2: In the earthwork summary it states that EBS excavation to be backfilled with select borrow material. Where is that quantity of select borrow accounted for? | #1: Select borrow was calculated using a surface to surface computation between the marsh surface and the existing surface, minus the breaker run depth. It was not done by average end area. #2: The amount of select borrow to backfill the EBS areas was omitted from the quantities. An addendum will be forthcoming to include this additional quantity of select borrow. | Jill Fehrman | 9 | 2021-03-24 08:00 | 2021-03-25 06:43
20210413 | 20210413011 | 11 | Culvert Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | As shown on the plan title sheet, the design ADT for WIS 15 is 21,600 and is above the threshold referenced in FDM Chapter 13. As such, we are requiring CPRC Class III as specified in our plan documents and contractors should bid accordingly. | Jill Fehrman | 10 | 2021-03-24 12:59 | 2021-03-26 05:35
20210413 | 20210413011 | 11 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | Storm sewer locations are limited to the CTH M and Nash Street areas. In these areas, the storm sewer falls into one of two categories: â€¢ It is too shallow (not enough subgrade cover) to allow for alternate storm sewer items â€¢ The storm sewer is not installed under the pavement and has less than 4â€™ cover. Per FDM 13-1-17.5, â€œWhere high groundwater and fully saturated soil conditions are anticipated, the minimum cover for storm sewer outside the roadway shall be 48 inches for thermoplastic pipe, otherwise reinforced concrete pipe should be specified.â€ Based on the above, the appropriate storm sewer items are shown in the plan and it should be bid accordingly. | Mike Coleman | 11 | 2021-03-24 13:01 | 2021-03-29 10:02
20210413 | 20210413011 | 11 | Item # 178 - Culvert Pipe | Is the culvert pipe RCCP 19x30" on CTH MM (120 LF) needed? Its not shown on the plan. | Line #178 in the schedule of items which references bid item 522.2319 for the 120 LF of RCCP 19â€x30â€ on CTH MM is not needed and an addendum will be forthcoming to remove this item. | Mike Coleman | 12 | 2021-03-25 14:53 | 2021-03-29 12:37
20210413 | 20210413011 | 11 | Item # 180 - Culvert Pipe | I believe there is 126 LF too many in this item as it seems to be accounted for in item # 186 with the correct Class IV. | Line 180 in the estimate of quantities for bid item 522.2324 CPRCHE Class III 24â€x38â€ does have an extra 126 LF shown for this quantity. An addendum will be forthcoming to decrease the quantity. | Mike Coleman | 13 | 2021-03-25 15:36 | 2021-03-29 12:44
20210413 | 20210413011 | 11 | Select Borrow QTY | The select borrow quantity listed for station 450+00 to 458+00 on page 73 of plan shows 24000 CY. Per takeoff it should only be about half the quantity listed. | The Department has reviewed the select borrow quantity from Station 450+00 to Station 458+00 on page 73. Based upon our review, the 24,000 CY quantity is accurate. Per note (4) on page 80, the material used to backfill the marsh excavation is not included in the roadway embankment item. The select borrow quantity used for marsh backfill has a 1.50 expansion factor applied. | Mike Coleman | 14 | 2021-03-29 17:40 | 2021-03-31 13:18
20210413 | 20210413011 | 11 | Interim Completion Date Clarification | In the special provisions under interim completions, it states to â€œComplete topsoil placement and final restoration from Station 339+00 to Station 341+00 prior to September 1, 2021â€. Which is the work by Black Otter Creek proposed bridges. This date is unreasonable to obtain given the other environmental protection dates that have to be followed and the amount of work that needs to occur. First the other environmental protection dates. 1. There shall be no instream disturbance (of all the locations given in the special provisions) from March 1 to June 15 in order to avoid adverse impacts upon the spawning of various fish species. 2. Clearing and grubbing between Stations 346+00 to 372+00 shall be done outside of the nesting season of April 1 through July 31 both days inclusive. Given the existing topography each side of Black Otter Creek, how the existing creek channel lays, and how the proposed must be constructed (logically and per the plan / construction details) you have to first gain access to the creek (+/- 340+00) from the east side. In order to get access to Black Otter Creek on the east side you have to clear and grub between stations 346+00 to 372+00, complete marsh excavation, select borrow backfill, breaker run backfill just to get access to creek. Then temp shoring needs to be installed, followed by creek realignment, followed by pier (x2) and abutment (x2) construction, followed by all the final restoration items including riprap, topsoil, etc. Once the previous is complete the west side of the creek must be constructed. Which would include switching staging of temp shoring finishing marsh excavation, backfills of select borrow / breaker run, constructing piers (x2) and abutments (x2) and all the final restoration items. The above paragraph lays out the proposed construction that needs to occur to satisfy the above interim completion date of â€œComplete topsoil placement and final restoration from Station 339+00 to Station 341+00 prior to September 1, 2021â€. None of this work can even be started until August 1, 2021 per the special provision concerning clearing and grubbing between 346+00 to 372+00 over the nesting of the Red Shouldered Hawk. This gives you about 4 weeks to complete all of the work stated above, which is unfeasible under any circumstances. Rough estimates, given the quantity of clearing and grubbing, marsh excavation, select borrow, breaker run, channel realignment process, pier & abutment construction, and all the misc. finial restoration items that need to occur would be 4 to 5 times the amount of time currently allotted in the special provisions. It is realized that the interim completion date only encompasses stations 339+00 to 341+00 (200â€™), but given the location of the proposed many other construction operations must occur first to gain access to the previous stated location. Please clarify the intentions of the above stated interim completion date. Please clarify what can be changed, deleted, relaxed to make the current interim completion date manageable. | The Department agrees the referenced September 1, 2021 interim completion date needs to be revised given the current environmental restrictions on clearing and grubbing from Station 346+00 to Station 372+00 related to the Red Shouldered Hawk. An addendum will be forthcoming that revises the interim completion date to October 29, 2021 for topsoil placement and final restoration from Station 339+00 to Station 341+00. There will also be language added that expedited forces may be necessary to achieve this date. The Department is also working to complete a field survey of the right-of-way from Station 346+00 to Station 372+00. If that survey indicates the Red Shouldered Hawk is not present within our corridor, it is possible that clearing and grubbing operations may be allowed to begin prior to August 1, 2021. Any allowable date change would be a part of a negotiated contract change order. Information from the survey is not anticipated until June 2021 so the contractor should submit their bid under the assumption that the April 1 to July 31 work restriction for the Red Shouldered Hawk will remain in place. | Mike Coleman | 15 | 2021-03-30 08:08 | 2021-04-01 05:27
20210413 | 20210413011 | 11 | Railroad Flagging Cost Participation - Hauling Operations | For construction activities occurring between ~STA 280+00 (WI Central LTD. RR) and STA ~340+00 (Black Otter Creek), access options are limited due to no temporary easements existing from Givens Rd (or any other potential sideroads) to the project limits. Accessing this workzone by crossing the railroad will be a necessity for hauling-in embankment, aggregates and other materials required by the project. Although subsection B in article 9 of the special provisions does not specifically name these hauling operations, it is safe to assume that the Department will be participating in 50% of the flagging costs that are borne by these operations â€“ correct? | Yes, the Department will participate in 50% of the railroad flagging costs. | Mike Coleman | 16 | 2021-03-31 08:29 | 2021-03-31 13:16
20210413 | 20210413011 | 11 | Select Borrow QTY 450+00 to 458+00 | Select Borrow QTY 450+00 to 458+00 The quantity listed for the above station range does not add up. Please clarify. - How is the Select Borrow item going to be measured and paid? In its original position, in its final position, etc.? - In the previous question and answer is stated that â€œthe select borrow quantity used for marsh backfill has a 1.50 expansion factor appliedâ€. Is that true for all the entire select borrow quantity for marsh or ebs backfill? Where in the plan or specials does it state that the select borrow expansion factor is 1.50? Obviously per addendum posted the select borrow listed for ebs backfill is not expanded as itâ€™s the same as the ebs quantity? Per takeoff of other marsh excavation areas it is believed that there is no expansion factor on the select borrow. - The 24,000 CY of select borrow for marsh backfill for the above area still does not add up. Per plan marsh excavation between 450+00 to 458+00 shows +/- 21530 CY. Per construction detail on page 16 of plan breaker run would be placed in the top 2 feet, thus reducing the select borrow quantity to approximately just less than half of what is currently listed (@ 24,000). Please clarify how the math works at 24,000 CY listed? |  |  | 17 | 2021-03-31 17:07
20210413 | 20210413011 | 11 | EBS | Per plan EBS listed is from approximate station 432+00 to 436+00; 21,671 CY. What is anticipated in this location for EBS as nothing is shown for EBS excavation in the cross sections / details and it seems to be in the same location as the Landfill Excavation? Is EBS needed in this location? In turn is the Select Borrow quantity listed for EBS backfill needed? | The 21,671 CY of EBS shown from Station 432+00 â€“ 436+00 is not required. An addendum will be forthcoming to adjust the quantities for related earthwork items. | Mike Coleman | 18 | 2021-04-01 07:14 | 2021-04-06 08:19
20210413 | 20210413011 | 11 | Bridge approach quanties | Miscellaneous quanties on sheet 75 list bridge approach for EB sides total of 45 sy.I measured and calculated 116 sy per side full width with a 62.6 skew angle for the east bound approaches.are the approaches only 1/2 width of the adjacent payment? | There was an error in the miscellaneous quantities for the bridge approaches. The 116 SY per side for the eastbound approaches at B-44-289 referenced in question #19 is the correct quantity. An addendum is forthcoming to revise the bridge approach quantities. | Mike Coleman | 19 | 2021-04-01 10:39 | 2021-04-06 07:39
20210413 | 20210413011 | 11 | Landfill Excavation | What is the landfill excavation to be backfilled with, assumed to be embankment? Is that quantity of embankment needed to backfill the landfill excavation included in the embankment quantity? | Yes, the landfill is backfilled with embankment above the new clay cap and this quantity is included in the embankment item. | Mike Coleman | 20 | 2021-04-01 11:06 | 2021-04-06 07:03
20210413 | 20210413011 | 11 | Black Otter Creek / Pike Scrapes | Where does the Black Otter Creek Channel Realignment and Pike Scrapes excavations get paid? If incidental, to what item? | All excavation will be paid through the common excavation or marsh excavation bid items as applicable. This work is not incidental. | Jill Fehrman | 21 | 2021-04-08 08:22 | 2021-04-08 15:09
20210413 | 20210413011 | 11 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch, Breaker Run, Select Crushed & Shot Rock? | CY to TON conversion factors used for design computations were: â€¢Base aggregate dense ï¿½â€ â€“ 2.1 â€¢Base aggregate dense 1 ï¿½â€ â€“ 2.0 â€¢Breaker run, select crushed, shot rock â€“ 1.75 | Jill Fehrman | 22 | 2021-04-08 10:55 | 2021-04-09 16:06
20210413 | 20210413011 | 11 | ECO Pass Structure I-beam | Are the I-beams in the ECO Pass structure considered part of the structure or part of the Galvanized Steel Grating? | The I-beams in the ECO Pass structure are considered part of the structure. | Mike Coleman | 23 | 2021-04-12 09:07 | 2021-04-12 10:49
20210413 | 20210413012 | 12 | Base Aggregate Dense 1 1/4" | Could quantity for base aggregate dense 1 1/4" be verified? Miscellaneous quantity table doesn't show any of that material for culvert pipe locations. Also typical section for culvert pipe bedding detail doesn't show thickness of base aggregate dense under pavement (pavement thickness is not shown either). Thanks | We have reviewed the quantity for Base Aggregate Dense, 1 ï¿½-Inch and confirmed that the material for the culvert pipe locations was not included. It appears the quantity should be increased approximately 1,000 ton for the base aggregate above the culvert pipes. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-03-16 11:41 | 2021-03-18 09:51
20210413 | 20210413012 | 12 | Culvert Replacement Bedding Detail | Please Confirm That HMA Pavement Replacement Will Not Be Necessary For The 4 Mainline Cross Culvert Replacement Areas Shown In The Plans. CTH R Is Detoured And The Roadway Will Be Pulverized And Relayed After The Culverts Are Installed. Thank You. | It is not be necessary to place HMA at the culvert pipe replacement areas on a temporary basis before pulverizing and relaying the roadway. | Jill Fehrman | 2 | 2021-03-25 07:35 | 2021-03-26 05:38
20210413 | 20210413012 | 12 | 8" paint bid item | Good morning. Item 0104, marking line paint, appears to be a 6" epoxy item on plan sheet 20 which there is no bid item for. Should this be changed to an 8" epoxy item typical of other turn lane markings on similar projects or is there another use for this 8" paint item on this project? Thank you. | There was an error on Sheet 20 of the plan set where a callout incorrectly referenced 6-inch pavement markings with no accompanying bid item. The correct callout should have said 8-inch epoxy pavement markings as the existing bid item implies. This will be addressed via an upcoming addendum. | Mike Coleman | 3 | 2021-03-30 07:46 | 2021-03-30 11:49
20210413 | 20210413012 | 12 | 8" Bid Item | Good morning. Thank you for clarifying and changing the plan sheets to call out the 8" epoxy rather than 6". Will you also be changing the 8" paint bid item to 8" epoxy? | It will be revised via an upcoming addendum. | Mike Coleman | 4 | 2021-04-01 10:54 | 2021-04-05 06:28
20210413 | 20210413012 | 12 | Bid Item 36-40 | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB culverts shall be used at every opportunity possible, up to 20,000 design ADT, when installations are: â€¢ 12-36 inches in diameter â€¢ located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) â€¢ Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA culvert pipe. â€¢ Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culverts Class IIIA and/or IIIB in lieu of the sole specified corrugated polyethylene culvert pipe? | This project is a local program project and the local unit of government has elected to use the pipe material specified. | Jill Fehrman | 5 | 2021-04-08 10:30 | 2021-04-08 15:10
20210413 | 20210413012 | 12 | Deflection Testing item 36-40 | Will the Department require deflection testing per 520.3.7 Deflection Testing; Test 100 percent of the installed length of 24 inches or greater in diameter. Ensure that mandrel passes through the entire section in one pass when pulled by hand without using excessive force. If the Designated length of pipe fails, the engineer may require additional testing. For pipe less than 24 inches in diameter, the engineer will designate at least 10 percent of the installed length of pipe for testing. Ensure that mandrel passes through the entire section in one pass when pulled by hand without using excessive force. If the Designated length of pipe fails, the engineer may require additional testing. Relay or Replace pipe that does not pass deflection testing. Retest all relayed or replaced pipe. | Yes, Deflection testing should be conducted per the standard specification. | Jill Fehrman | 6 | 2021-04-08 10:37 | 2021-04-08 15:11
20210413 | 20210413013 | 13 | Asphaltic Surface Patching | The miscellaneous quantities show 50 tons of patching the length of the job and there is no detail or note for that item. What is the expectation of work to complete that item? | The undistributed quantity for asphalt surface patching is intended for any minor repairs (potholes or pop outs that occur under traffic) of the shoulders. | Mike Coleman | 1 | 2021-04-02 09:03 | 2021-04-07 06:35
20210413 | 20210413015 | 15 | Traffic Signal Plan/Proposal - Controller | What traffic controller type is being used at the project intersection? | According to the information we have the controller is an EPAC 300. | Mike Coleman | 1 | 2021-03-16 10:18 | 2021-03-18 07:54
20210413 | 20210413015 | 15 | Structure Adjustments | For the Gate Valve and Manhole Adjustments: 1.) Is the sawcutting being paid separately? 2.) In areas of existing concrete pavement, does concrete need to be poured back around the structure after adjusting? If so, will that be paid separately like the HMA is? 3.) There is not any quantity designated in the HMA misc quantities for the structure adjustments. | Sawcutting required for those adjusting items is considered incidental, so it is not paid separately. Based on the small areas of pavement required for the structure adjustments it was assumed that HMA would be used. The HMA quantity for the structure adjustments is included in the roadway quantity. | Jill Fehrman | 2 | 2021-04-07 12:29 | 2021-04-08 15:03
20210413 | 20210413015 | 15 | Contaminated Soils | Typically when there is an SPV for Contaminated Soils, there is a bid item for dealing with those contaminated soils. Will an item be added? | The contaminated soils SPVs were included due to the potential presence of contaminated soils in the general area, but are anticipated to be outside of the construction limits, so an item was not included. | Jill Fehrman | 3 | 2021-04-08 07:02 | 2021-04-08 15:05
20210413 | 20210413017 | 17 | Milling and Paving | The plan shows the existing pavement structure to be 5" deep. The proposed section calls for 4" to be milled out, leaving 1" of HMA. In the Specials it states to not pave the lower layer on the milled surface for at least 48 hours. Guessing that this is being done to help clean the roadway for the tack to stick, which is a good idea, but in this application there is a real concern that the 1" remaining has a great chance of blowing up. THis should really be looked at as milling and filling the lower layer if that proposed milling depth needs to stay or lessen the depth of milling to leave more existing pavement. | The department would like to run traffic on the milled surface. Provisions and bid items are included in the contract to repair any damage to the milled surface as outlined in the article for Prepare Foundation for Asphaltic Paving. | Mike Coleman | 1 | 2021-03-23 13:07 | 2021-03-24 06:56
20210413 | 20210413017 | 17 | Milling Item | Will the department consider adding an item for Distressed Milling to cover the work that is referenced being done in the Special Provisions under the Prep Foundation Item so this will not be done under the Asphaltic Surface Milling item that is for the milling of the Highway? | We are submitting an addendum to address this question and will be adding the distressed milling item. | Mike Coleman | 2 | 2021-03-30 17:46 | 2021-04-01 05:24
20210413 | 20210413025 | 25 | Pipe at 174+90 | Has the Department considered lining this existing CMP? The pipe at 184+35 may be able to be installed with the lane shifts. The pipe at 174+90 is too deep to maintain traffic while replacing the pipe and excavating the 3:1 slopes without shoring and the shoring options are limited considering the road needs to be opened to 2 lane traffic every night. Given that this project was already rejected once, that may be a good option to reduce overall cost. | It is understood that the pipe at 174+90 will require shoring to construct with lane shifts. Shoring quantities are included in the plan. The existing pipe is being upsized from an 18â€ to a 24â€. | Mike Coleman | 1 | 2021-04-08 06:46 | 2021-04-08 11:23
20210413 | 20210413026 | 26 | Electronic Data Request | Please provide the following files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. Due to the number of structures, no roadway soils report was created. All areas are covered by the structure soil reports. | Mike Coleman | 1 | 2021-03-10 11:54 | 2021-03-22 06:19
20210413 | 20210413026 | 26 | Electronic Data Request | Could the Department please provide the storm sewer tables in excel format? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ Please note that an addendum is being prepared that will make changes to this information. | Jill Fehrman | 2 | 2021-03-11 14:19 | 2021-03-26 15:48
20210413 | 20210413026 | 26 | Temp. Wire Wall Sta. 954+00 - 963+00 | It appears there are no construction drawings for the Temporary Wire Wall from Station 954+00 to 963+00. Could they please be provided? | The intent of the temporary wall in that station range is for it to be Temporary Shoring (511.1100), as shown in the Miscellaneous Quantities page 606 | Mike Coleman | 3 | 2021-03-15 08:16 | 2021-03-15 12:41
20210413 | 20210413026 | 26 | Information Request | Please provide geotechnical report, DNR/404 permits, DOT's anticipated construction schedule. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ | Mike Coleman | 4 | 2021-03-17 08:59 | 2021-03-22 06:20
20210413 | 20210413026 | 26 | Pedestrian Tunnel Lights | Sheet 295 shows a 4"x4"x6" junction box behind the light fixtures in the C-40-111 pedestrian tunnel. Sheets 1225-1227 calls for 4"x4"x4" junction boxes behind the light fixtures in this pedestrian tunnel. Please advise as to what size junction box is supposed to be installed behind the light fixtures. | 4â€x4â€x4â€ is the correct junction box. This will be updated in the lighting plan via an upcoming addendum. | Mike Coleman | 5 | 2021-03-19 08:03 | 2021-03-29 13:58
20210413 | 20210413026 | 26 | C-40-111 Precast Option | Can the C-40-111 structure be precasted in lieu of cast in place? | Allowance for a precast alternative is not suitable for this structure (C-40-111), due to unique and complex geotechnical soil conditions, the need to limit the number of vertical construction joints, and the complexity of staging and construction between MSE retaining walls and pavement above. In addition, cast-in-place sections are preferred for pedestrian underpasses for improved long-term serviceability. | Mike Coleman | 6 | 2021-03-19 11:32 | 2021-03-22 12:16
20210413 | 20210413026 | 26 | NB Exit Ramp to Green B Ave/Capitol. - Ramp GBA2 - closure clarification | Please clarify when this ramp can be closed. Specials call for a closure in Stage 2A with reopening by 10-14-21, but the staging plans call for it to be open during this stage. Stage 2C2 staging plans show the ramp being closed, but the stage 2C2 overview sheet says it is to remain open. | The stage 1 overview states that the ramp is closed for the noise wall construction which takes place from 9/3/2021-10/14/2021. The 2C2 staging does show the ramp being closed in the details, we will remove those barrels and signing. The 2D stage overview states that Ramp GBA2 may have short term closures for work on B-40-1014. The notation of the closure from the detail sheets for stage 2C2 will be removed as part of an upcoming addendum. | Jill Fehrman | 7 | 2021-03-19 11:56 | 2021-03-29 16:40
20210413 | 20210413026 | 26 | barriers | On the Concrete S-42 barrier is the 4'-0" footing part of the Barrier or the adjacent concrete pavement. Are the dowels for the high performance concrete be high performance style dowels per APL list ? | The 4â€™ footing is part of the barrier. Design intent is to use Standard Detail Drawings to construct. The detail in question will be removed as part of an upcoming addendum. | Jill Fehrman | 8 | 2021-03-22 11:59 | 2021-03-29 16:29
20210413 | 20210413026 | 26 | Ramp HAB Structure B-40-67 | Sheet 422 of the plans indicate that in Stage 2D, "Construct IH 43 SB Deck Replacement Rehabilitation of Entrance Ramp Over Milwaukee Structure (Ramp HAB)." No plans are given for this structure, please advise if this structure gets rehabed in this project or not. | The work on this bridge was removed from the project and will be LET as a separate project within this contract's timeline. The note on Stage 2D will be removed as part of an addendum to be issued approximately April 1st. | Mike Coleman | 9 | 2021-03-22 13:05 | 2021-03-30 08:39
20210413 | 20210413026 | 26 | Hampton Ave Traffic Control | Please advise as to the exact lane designation (lane 1, lane 2, etc.) that traffic will be in on WB & EB Hampton Ave as depicted on sheets 501 & 502. Is the traffic control layout as shown on sheets 501 & 502 to be installed for the duration of the contract? | Clarification on Traffic control will be provided via an addendum to be issues approximately April 1st. Design intent is for this staging to remain in place until construction is complete at Hampton Avenue. | Mike Coleman | 10 | 2021-03-22 13:15 | 2021-03-30 10:34
20210413 | 20210413026 | 26 | Glendale Ave Traffic Control | Please define closure restriction hours for Glendale Ave traffic control as shown on sheet 500. Will existing structure removal and girder setting operations over Glendale Ave be allowed full closures per sheet 500? | Local Road Closure restriction hours will be provided in an addendum to be issued approximately April 1st. Full Closure will be allowed for removal and girder install with coordination with the engineer in the field. | Mike Coleman | 11 | 2021-03-22 13:29 | 2021-03-30 10:58
20210413 | 20210413026 | 26 | Glendale Ave Plan Details | Glendale Ave plan details sheet 104 only indicates that Glendale Ave receives a mill and overlay at the end of the contract. Storm sewer removals, storm sewer install and the new MSE walls along Glendale Ave will impact numerous areas of curb & gutter and sidewalk, please advise as to how these ancillary concrete and removal items are to be paid for. | Additional details will be provided in an addendum to be issued approximately April 1st. Additional Curb and Gutter and sidewalk work will be added. | Mike Coleman | 12 | 2021-03-22 13:44 | 2021-03-30 10:59
20210413 | 20210413026 | 26 | HPC Pavement Joint Details | Sheet 61 of the plans shows HPC Pavement Joint Details for several shoulder widths except 10-FT. Is the intention to utilize standard 12-inch spacing in the 10-FT shoulders. The Special Provisions do not mention HPC concrete or HPC dowels. Can the joint details on Sheet 61 be used with non-HPC dowels? | Design intent is to use Standard Detail Drawings to construct. The detail in question will be removed as part of an upcoming addendum. | Jill Fehrman | 13 | 2021-03-24 08:26 | 2021-03-29 16:32
20210413 | 20210413026 | 26 | Milwaukee County Parks Permit | Please provide a copy of the draft Milwaukee County Parks permit as discussed in SPV 14. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ | Jill Fehrman | 14 | 2021-03-24 08:31 | 2021-03-26 15:54
20210413 | 20210413026 | 26 | Silane Sealant | There is a note (4) on Sheet 61 of the plans calling for Silane Joint Sealant on all sawed joints in the concrete pavement. Is the Department only requiring this on sawed joints and not on construction joints? Why is this note buried in the plans and not called out in the Special Provisions for Concrete Pavement as is typical when required? | Design intent is to use Standard Detail Drawings to construct. The detail in question will be removed as part of an upcoming addendum. | Jill Fehrman | 15 | 2021-03-24 09:44 | 2021-03-29 16:34
20210413 | 20210413026 | 26 | Concrete Paving - Track Line | The Typical Sections at MSE Retaining walls show no room for concrete paver track line on the coping. This is in the shoulder lane where pavement is placed over the moment slab. Will the Department allow for hand placement in these areas and waive any IRI requirements? There are no details showing a bond breaker between the moment slab and the concrete shoulder pavement. Will a bond breaker be required in these areas? | The details shown in the plans follow Standard Details that have been utilized in other areas of the state without need to modify IRI requirements. The Department will not waive IRI requirements for this project. A bond breaker will not be required outside of the rubberized membrane waterproofing items that are included in the contract for the retaining wall(s). | Jill Fehrman | 16 | 2021-03-24 09:57 | 2021-03-26 05:43
20210413 | 20210413026 | 26 | Temporary Causeway - Stage 2 limits | Plan sheet 508 shows causeways and cofferdams 4, 5 and 6 installed under ramp HAB, however no work is expected to take place on this structure with this project. Please clarify if all cofferdams and causeways shown on sheet 508 are to be installed as part of the Temporary Causeway Lump Sum Bid Item. If they are all not being installed, what are the revised limits of the causeways? | Causeway drawing will be modified via Addendum 2. | Mike Coleman | 17 | 2021-03-24 14:41 | 2021-04-05 06:43
20210413 | 20210413026 | 26 | 643.1100.S Dynamic Late Merge System | Will the DLMS be required on Southbound I-43 during Stage 2A when there is still three lanes open to traffic? All other stages that the DLMS is required traffic is limited to two lanes. Thanks | DLMS is not required when there is no lane reduction. | Mike Coleman | 18 | 2021-03-25 09:05 | 2021-04-05 06:45
20210413 | 20210413026 | 26 | High Performance Concrete Pavement and Dowels | Three questions: 1. Sheet 61 of the plan refers to High Performance Concrete. There is no definition in the plan or proposal of what high performance concrete is. Was it the intent to insert a special provision for high performance concrete like the other mega projects and the previous ZOO Interchange project? Was it forgotten? 2. Previous HPC projects in the southeast region included high performance concrete pavement dowels. The standard specifications now include HPC dowel language and there is an approved product list for the dowels. But you have to insert a special provision specifically calling for HPC dowels. Do you have the intent of using HPC dowels? 3. The typical sections call for dowels in the two feet of concrete pavement next to the concrete barrier. Two-foot baskets are problematic and it can be argued that this pavement is never loaded and these dowels would never be put to work. Significant dollars could be saved if they were eliminated. | Design intent is to use Standard Detail Drawings to construct. The detail in question will be removed as part of an upcoming addendum. | Jill Fehrman | 19 | 2021-03-25 17:10 | 2021-03-29 16:39
20210413 | 20210413026 | 26 | Hampton Ave Full Closure | Please advise if full closures are allowed on Hampton Ave for demo, girder setting and decking. If so please advise what time frame requirements apply to this full closure. | Local Road Closure restriction hours will be provided in an addendum to be issued approximately April 1st. Full Closure will be allowed for removal and girder install with coordination with the engineer in the field. | Mike Coleman | 20 | 2021-03-26 12:58 | 2021-03-30 11:00
20210413 | 20210413026 | 26 | B-40-1016/1018 Pier 1 & 2 | Please advise that all rebar shown in the bill of bars tables for piers 1 & 2 for structures B-40-1016 and B-40-1018 is supposed to be uncoated as shown and that non of this rebar is to be epoxy coated. | The plans show uncoated rebar correctly for Piers 1 & 2. | Mike Coleman | 21 | 2021-03-29 14:04 | 2021-03-30 08:37
20210413 | 20210413026 | 26 | B-40-116 existing structure plan | Are the existing structure plans for B-40-116 available and can they be provided? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ | Mike Coleman | 22 | 2021-03-30 08:16 | 2021-04-05 06:38
20210413 | 20210413026 | 26 | Lake Tower Pond & Oak Leaf Pond | Are the earthwork quantity's for the two ponds(Lake Tower / Oak Leaf) included in the Common Excavation Qty? If so please show the qty for each pond and what stage they need to be completed in. | Oak Leaf Pond earthwork will be included in Addendum 2, tentatively scheduled to be issued on April 8th. The Lake tower pond earthwork is included in the mainline earthwork and Ramp HAA Earthwork. | Mike Coleman | 23 | 2021-03-31 15:59 | 2021-04-05 06:42
20210413 | 20210413026 | 26 | EXPANSION BEARING QUESTION | On Sheet# 1037: Please verify the dimensions in the EXPANSION BEARING TABLE. The current sizes will not allow for the required movements. | This will be addressed in an upcoming addendum. | Mike Coleman | 24 | 2021-04-01 07:58 | 2021-04-05 06:41
20210413 | 20210413026 | 26 | DOT Owned Sites Adjacent to Project | There appears to be several properties adjacent to existing structure B-40-115 notably properties East and West of IH43 from STA 940+00 to STA 955+00. Will crushing, borrow excavation, storing and wasting be available on these sites? Additionally are there any restrictions on these sites? | The Department does not own any additional properties in the areas mentioned. Utilize the plat to determine DOT owned areas. Specific sites will be evaluated on a case by case basis. | Mike Coleman | 25 | 2021-04-01 15:42 | 2021-04-05 06:47
20210413 | 20210413026 | 26 | Schedule - Procurement | Was this project originally scheduled to be let earlier than April 2021? The dates in the department's schedule suggest that the start of the project would be sooner than typical for an April let project. If this is the case, please adjust the schedule to reflect the April let date. Stage 1 should be extended through the winter of '21-'22 allowing for concrete paving to be performed in the spring of 2022. Please also consider design, review and fabrication lead times for MSE Walls and Noise Walls. We are seeing 3 month minimum leads at this time, (6 weeks for design and 6 weeks for fabrication). | The Department will not be extending stage 1 interim dates or issuing a new schedule. The detailed schedule provided is for information only. The contractor will need to meet the interim and final schedule dates as shown in the proposal. | Mike Coleman | 26 | 2021-04-01 17:13 | 2021-04-08 06:06
20210413 | 20210413026 | 26 | Traffic Control for Bridge Painting, B-40-116 | It is assumed that bridge painting would not start until all joint repair and overlay work is completed in stage 4. Notes on traffic control staging sheets show ramp GBA2 open to traffic during both stages 4 and 5. How is the bridge painting to be completed with the ramp open? | Bridge painting for B-40-116 may be performed in stage 4 after deck and joint work is completed. Bridge end span girder painting behind roadway barrier can be completed while ramp traffic is open and protected from painting operations. The bridge middle span over ramp lane, shoulders, and concrete barriers can be completed with nighttime closures of ramp GBA2. Ramp GBA2 is required to be open to traffic each morning before peak hour traffic. | Mike Coleman | 27 | 2021-04-06 07:34 | 2021-04-08 06:08
20210413 | 20210413026 | 26 | B-40-116, Removing Loose Concrete | Where are the locations for Loose concrete removal expected? If all underdeck removals, will the ramp be closed to perform this work? | The B-40-116 Removing Loose Concrete work is for the underside of the deck within Span 2 (over the ramp) and may be performed in stage 4 prior to bridge painting work. Removal work can be completed with nighttime closures of ramp GBA2. Ramp GBA2 is required to be open to traffic each morning before peak hour traffic. | Mike Coleman | 28 | 2021-04-06 16:21 | 2021-04-08 11:24
20210413 | 20210413026 | 26 | Contaminated Soils | Based on information provided in Addendum 1 can you please clarify the following: 1. Will you be adjusting the tonnage for the Contaminated Soils bid item? It appears as though that has changed. 2. Will you be adjusting the available materials in the earthworks table to reflect the 8030 cy of soils that are to be reused in the project?? or will you just be adding this to the actual common excavation item? 3. There is conflicting info as to how to dispose of this material. There is mention of roll off containers being provided by others. Is the intention for the State to provide these containers just for a temporary storage until the materials are tested? Once tested will "others" then be dumping the material out of the dumpsters for us and we then need to reload material and either use on the grade as common or haul to a DNR approved disposal facility? | For the bid Item SPV.0165.0001, Management of Contaminated Soil and Contaminated Sediment, it is estimated that the contractor will have to excavate and segregate 32,464 tons (19,097 CY, a 1.7 tons/CY conversion rate was used for this number). Within this number, 13651 tons (8030 CY) is estimated as low-level impacted soil that is to be reused onsite and 18,813 tons (11,067 CY) is estimated as hazardous material (contaminated soil and sediments) that will need to be disposed of appropriately offsite. Of the 18,813 tons (11,067 CY), an estimated 15,431 tons (9077 CY) of hazardous material will need to be loaded and transported by the contractor to a WDNR-licensed landfill facility for disposal. The contractor is responsible for all costs to dispose of this material. The remaining estimate of 3382 tons (1990 CY) of hazardous material is characterized as hazardous solid waste soil that the contractor will need to load into roll-off containers supplied and delivered to project site by State of Wisconsin master contract solid waste contractor. Once these roll-off containers are loaded, the State of Wisconsin master contract solid waste contractor will haul the hazardous solid waste soil off the project and dispose appropriately offsite. The bid Item SPV, 0165.0001 Management of Contaminated Soil and Contaminated Sediment will be measured by the estimated 15,431 tons hazardous materials accepted by the disposal facility and as documented by weight tickets. Concerning the 13,651 tons (8030 CY) of reusable material, the material will need to be loaded, hauled, and capped with 2-foot clay layer. All materials should be placed in accordance with embankment earthwork requirements. This 8030 CY was included in the earthwork tables as useable material. The Department will not be issuing updated earthwork tables for bid. | Mike Coleman | 29 | 2021-04-07 08:03 | 2021-04-12 09:36
20210413 | 20210413026 | 26 | Earthwork Summary | Page 566 Earthwork Summary, Division 1 the available Material is higher quantity than the common excavation, this shouldn't be the case. Looks like the Contaminated Soil was added to the available material. Can the Contaminated Soil be used in the fills on this project? | For the bid Item SPV.0165.0001, Management of Contaminated Soil and Contaminated Sediment, it is estimated that the contractor will have to excavate and segregate 32,464 tons (19,097 CY, a 1.7 tons/CY conversion rate was used for this number). Within this number, 13651 tons (8030 CY) is estimated as low-level impacted soil that is to be reused onsite and 18,813 tons (11,067 CY) is estimated as hazardous material (contaminated soil and sediments) that will need to be disposed of appropriately offsite. Of the 18,813 tons (11,067 CY), an estimated 15,431 tons (9077 CY) of hazardous material will need to be loaded and transported by the contractor to a WDNR-licensed landfill facility for disposal. The contractor is responsible for all costs to dispose of this material. The remaining estimate of 3382 tons (1990 CY) of hazardous material is characterized as hazardous solid waste soil that the contractor will need to load into roll-off containers supplied and delivered to project site by State of Wisconsin master contract solid waste contractor. Once these roll-off containers are loaded, the State of Wisconsin master contract solid waste contractor will haul the hazardous solid waste soil off the project and dispose appropriately offsite. The bid Item SPV, 0165.0001 Management of Contaminated Soil and Contaminated Sediment will be measured by the estimated 15,431 tons hazardous materials accepted by the disposal facility and as documented by weight tickets. Concerning the 13,651 tons (8030 CY) of reusable material, the material will need to be loaded, hauled, and capped with 2-foot clay layer. All materials should be placed in accordance with embankment earthwork requirements. This 8030 CY was included in the earthwork tables as useable material. The Department will not be issuing updated earthwork tables for bid. | Mike Coleman | 30 | 2021-04-07 11:36 | 2021-04-12 09:36
20210413 | 20210413026 | 26 | Anchoring Temp. Barrier | Standard bid item 603.8500 - Anchoring Concrete Barrier Temporary Precast was not included in this contract. With the number of stages and traffic shifts it seems likely that barrier wall will need to be pinned somewhere at some point. Should this item be added with an arbitrary quantity? | Standard bid items 603.8500 - Anchoring Concrete Barrier Temporary Precast and 603.8505 Anchoring Concrete Barrier Temporary Precast on Bridge Decks will be added via addendum. | Mike Coleman | 31 | 2021-04-07 17:20 | 2021-04-08 12:02
20210413 | 20210413026 | 26 | Select Crushed Material - UOM | Why is it necessary to have two units of measure for the Select Crushed Material work? These two items cover the same scope of work, utilizing the exact same means and methods of construction. The only difference is the physical location of the work on the jobsite. For this item, we suggest using the TON item for all the locations. | Bid Item 312.0115 Select Crushed Material paid by CY will be removed and quantities added to Bid Item 312.0110 Select Crushed Material paid by TON in an addendum. | Jill Fehrman | 32 | 2021-04-08 11:49 | 2021-04-08 15:12
20210413 | 20210413026 | 26 | Schedule | Can the design schedule be provided? | The schedule is posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210413026/ | Jill Fehrman | 33 | 2021-04-09 12:43 | 2021-04-09 16:43