## qandasearchletting_results
Date: | 2021-05-27
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210511 | 20210511001 | 1 | Concrete Surface Repair | Is there a detail as to what needs to be done for this item? Is this on the masonry flume going into the 60" pipe? Thanks | No, there is no detail for the concrete surface repair areas. The concrete surface repair is to be used for the spalling found inside the 60â€ pipe and to fill any lift holes found to be open. | Mike Coleman | 1 | 2021-04-22 07:54 | 2021-05-03 13:11
20210511 | 20210511001 | 1 | 643.1205.S Basic Queue Warning System | In the Miscellaneous Quantities for Traffic Control, the item 643.1205.S Basic Queue Warning System is only allocated to the Eastbound lane closures. Does this mean that the QWS will only be required for EB I-90, or will a system also be required for WB I-90? Thanks | Only the EB will require the QWS | Mike Coleman | 2 | 2021-04-23 14:57 | 2021-05-03 13:12
20210511 | 20210511002 | 2 | Borrow | WOULD TOPSOIL BE ACCEPTABLE TO USE IN THE BORROW AREAS? THIS HAS BEEN ALLOWED ON OTHER SIMILAR PROJECTS. | No, we will not allow Topsoil to be used in place of Borrow. | Mike Coleman | 1 | 2021-05-04 20:22 | 2021-05-06 13:19
20210511 | 20210511003 | 3 | Seeding Mixture 70A | Please check the plan quantity for the 70A seed and verify that 70A is the seed that's needed for the median. If 70A is the correct seed, our math is showing about 52 lbs needed based on the erosion mat quantity. | For item 630.0171 the correct quantity is 52 lbs as mentioned below instead of the plan 350 lbs. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-05-03 09:28 | 2021-05-03 13:17
20210511 | 20210511003 | 3 | Traffic | -Will project 1161-00-67 and 1161-02-67 have their own separate lane closure operations? Or will they ever have to be combined into one? | The two separate project IDs 1161-00-67 & 1161-02-67 are approximately 5 miles apart. Both projects have separate traffic control plans and are not intended to be combined. | Mike Coleman | 2 | 2021-05-05 20:42 | 2021-05-06 09:49
20210511 | 20210511003 | 3 | Earthwork Summary | The earthwork tabulations show all of the incremental cut volumes as salvaged/unusable pavement material. Is that accurate? | Yes, all cut volumes are assumed salvaged/unusable. Due to the cut operations being in close proximity to the existing shoulder or within the median, which is likely saturated material, the cut material is considered to be unusable for fill. | Mike Coleman | 3 | 2021-05-06 09:17 | 2021-05-06 11:36
20210511 | 20210511004 | 4 | Existing HMA Thickness vs. Milling Thickness | Plant Sheet 4 indicates 3'' HMA Pavement existing for the majority of the lot. Plan sheet 5 indicates 3.5'' removing asphaltic surface milling and 3.5'' new HMA to be installed. Is the intent to remove an additional .5'' of Gravel during the milling or is existing HMA thickness 3.5''? | The pavement structure thicknesses indicated are approximate and may vary. The intent is to remove 3.5â€ of material which may also include gravel beneath the existing asphaltic pavement. | Mike Coleman | 1 | 2021-04-29 21:10 | 2021-05-03 13:19
20210511 | 20210511004 | 4 | Drainage | Can additional detail be provided for the parking lot drainage? Are there any areas that are not 1.5% across or flowlines that are not shown? | The intent is to replace the cross slope in-kind that is approximately 1.5% as shown on sheet 5, the cross slope will need to be field verified. No slope corrections or improvements are required. | Mike Coleman | 2 | 2021-04-29 21:24 | 2021-05-03 13:14
20210511 | 20210511005 | 5 | Questions regarding Bid Item 208.0100 Borrow | 208.0100 According to the quantities, there are 173 cy yards of Borrow between STA 32+00 â€“ STA-287.62. Can we get better clarification on where this borrow is intended to be placed. Is crushed stone acceptable as borrow? | See construction detail on sheet 14 and cross sections for clarification on location(s). Crushed stone may be an acceptable substitute for borrow, but proper compaction procedures will be required. | Mike Coleman | 1 | 2021-04-27 14:22 | 2021-04-30 08:06
20210511 | 20210511005 | 5 | Paving Operations | Paving Operations Under the Paving Operations section of the Special Provisions, it states that â€œLoaded trucks will not be allowed to operate on a milled surface at any timeâ€. We assume that means that shuttle buggyâ€™s will be required to place asphalt mix into the pavers from the un-milled lane or bindered lane on the first lift. Since both lanes will now occupy paving equipment, how did the department anticipate getting loaded trucks into position to place material into the shuttle buggyâ€™s (both paving and patching)? Would the shuttle buggy be permitted to move into the milled lane as needed to let trucks pass, then return to the un-milled lane? Does the department feel itâ€™s safe to try and have loaded trucks and local traffic diverted to the outside shoulder and ditch in order to pass trucks in line to pave? Some clarification would be helpful. | A shuttle buggy or material transfer machine will be required to keep loaded trucks off the milled surface during paving operations. The unloaded material transfer machine will be permitted to operate on the milled surface for the purpose of letting trucks and local traffic pass. As on all projects, the contractor is required to safely maintain local traffic on detoured highways during construction. It will be the contractorâ€™s responsibility to determine if the existing shoulder is suitable for loaded trucks and local traffic. Any damage to the existing shoulder will be at the contractorâ€™s expense | Mike Coleman | 7 | 2021-04-27 14:23 | 2021-04-29 08:21
20210511 | 20210511006 | 6 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-20 12:37 | 2021-04-21 06:09
20210511 | 20210511006 | 6 | Traffic Signal Controller | We were unable to locate in the plans or special provisions any specification for what type of Controller is required in the traffic signal control cabinet other than a NEMA TS2 Type 2. Can you please confirm what traffic signal controller is required or if this is open to any manufacturer's controller? | The controller and the MMU are both state-supplied. Thatâ€™s written in B.2.3 of SPV.0060.07. | Mike Coleman | 2 | 2021-04-21 14:21 | 2021-04-26 09:03
20210511 | 20210511006 | 6 | Traffic Signal Controller | Which manufacturers traffic signal controller is being used/provided for this projects cabinet? (ie. Econolite, EPAC, etc.) | The state will be supplying an Econolite Cobalt controller and a Reno A&E MMU2 monitor. However, the TS2 control cabinet does not need to be manufactured by Econolite. | Mike Coleman | 3 | 2021-04-26 09:23 | 2021-04-27 08:23
20210511 | 20210511006 | 6 | Sawcuts. | There seems to be a lot of sawing concrete on the sidewalks. These cuts may be designated by the usual xxxx mark, but in the 'legend' on the sheets, that is not the case. Can you clear this up? Also, it seems unfortunate to me that with this seemingly large quantity of cuts not possible to do with a road saw that they do not have their own item #. It is really a different animal. | Yes, the â€œXâ€â€™s bring attention to a sawcut line. The plans include sawing per WisDOT standard specification 690. Please bid accordingly. | Mike Coleman | 4 | 2021-05-05 16:08 | 2021-05-06 09:52
20210511 | 20210511006 | 6 | longitudinal Joint Repair. | The related special provision is conflicting in B Materials. It calls for High Early strength in words but specifies a number of B mixes which are base mixes with only 4 bag cement contents. Can this be clarified? | The mix should follow the specifications for Base Patching Concrete SHES (which follows SHES concrete repair and replacement 416.2). | Mike Coleman | 5 | 2021-05-08 10:54 | 2021-05-10 12:58
20210511 | 20210511007 | 7 | Geotechnical Report | Would the department please provide any geotechnical report prepared for this project. | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511007/ | Mike Coleman | 1 | 2021-04-19 08:56 | 2021-04-20 07:44
20210511 | 20210511007 | 7 | Earthwork Tables | Can the Excel files for the earthwork table be made available? | The earthwork Excel files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511007/ | Mike Coleman | 2 | 2021-04-29 08:04 | 2021-04-30 07:13
20210511 | 20210511007 | 7 | Design Files | Can the Department provide the meta data for this project? | The metadata can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511007/ | Mike Coleman | 3 | 2021-05-03 11:49 | 2021-05-04 10:35
20210511 | 20210511007 | 7 | Milling Restrictions | The proposal states allowing both 24hrs & 48hrs between milling and paving. Please indicate which is allowed. Also given that this will be a road closed setting could a slightly longer period be allowed such that project limits could be milled prior to paving? | Cover the milled surface with at least one layer of HMA within 48 hours of milling, as indicated on page 4 of the Special Provisions. The engineer can reduce to 24 hours if deemed necessary due to the condition of the milled surface. A longer period will not be allowed. | Mike Coleman | 5 | 2021-05-03 11:55 | 2021-05-04 11:47
20210511 | 20210511007 | 7 | Stage 2 & 3 - 4MT Asphalt Testing Requirements | During stage 2 & 3 4MT asphalt paving will be required for the round-about reconstruction. This work will take place prior to the PWL test strip required during stage 4. Can the testing requirements for the 4MT asphalt under stage 2 & 3 be changed to QMP? | All asphalt for the roundabout construction (ID 5155-00-79) falls under QMP guidelines. Limits for the roundabout project are shown on the Project Overview plan sheet. PWL applies to the mill and overlay project (ID 5155-04-81), up to Station 352+00, as indicated in the PWL Miscellaneous Quantities table. For contractor convenience, the USH 14 asphalt structure through the roundabout limits will be changed to a 2 ï¿½-inch lower layer and two 1 ï¿½-inch upper layers to align with the mill and overlay lifts. An addendum will be issued with this change. | Mike Coleman | 6 | 2021-05-03 11:58 | 2021-05-04 11:48
20210511 | 20210511007 | 7 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch and Select Crushed? | Base Aggregate Dense ï¿½ Inch = 2.1 Tons/CY Base Aggregate Dense 1 ï¿½ Inch = 2.0 Tons/CY Select Crushed Material = 1.9 Tons/CY | Mike Coleman | 7 | 2021-05-06 19:48 | 2021-05-07 08:54
20210511 | 20210511008 | 8 | Traffic | -Are the daily lane closure restrictions for all stages or only after the King and Badger St closures are done in stage 1A and 1B? If the daily lane closure restrictions are for all stages, do the temporary pavement markings stay in place overnight? | The lane closures are for all stages. You may not need to utilize the Temporary Pavement Marking in all instances according to applicable SDDâ€™s. If Temporary Markings are needed they will need to be removed when lane closures are not permitted. | Mike Coleman | 1 | 2021-05-05 20:41 | 2021-05-07 06:16
20210511 | 20210511010 | 10 | ITEM SPV.0090 CULVERT HORIZONTAL ELLIPTICAL PIPE | THE CLASS V PIPE IS A SPECIAL DSIGN. WOULD A STANDARD D LOAD DESIGN OF 2000 D BE ACCEPTABLE FOR THIS PIPE PRODUCT? IF NOT CAN YOU FURNISH THE D LOAD THAT WOULD BE NEEDED FOR THESE PIPES SO WE CAN QUOTE THE PROPER PRODUCT? | Please see Addendum No. 1 issued on 4/21/2021. | Jill Fehrman | 1 | 2021-04-22 06:51 | 2021-04-22 09:33
20210511 | 20210511010 | 10 | Erosion Control Filter Bag | For bid item 106, SPV.0060.001, I believe that the wrong bid item is specified for the application needed for this work on this project. The Special reads as though it is similar to rock bags. However, the plan pages show a need for a dewatering bag inside of a settling basin. Please verify what is needed. | Dewatering bag should be used for the settling basin application. | Mike Coleman | 2 | 2021-04-26 11:12 | 2021-05-03 06:39
20210511 | 20210511010 | 10 | Culvert Pipe Checks | On plan page 7, it shows that sand bags are allowed for culvert pipe check installations. Please verify that sand bags will be allowed for the bid item concerning culvert pipe checks. | Per WisDOT Spec 628 and WisDOT SDD 8E15-01, rock bags are to be used for culvert pipe checks. | Mike Coleman | 3 | 2021-04-26 11:16 | 2021-04-28 07:36
20210511 | 20210511010 | 10 | 643.1050 PCMS | For item 643.1050 Traffic Control PCMS, what is the intent of having 20 PCMS/280 days included as "Undistributed"? This undistributed quantity seems slightly excessive for a 14 day project. | PCMS is included as an undistributed quantity to direct motorists to an alternate detour route if ramp closures on the I-43 project (1090-16-70) conflict with the posted detour. | Mike Coleman | 4 | 2021-05-06 13:00 | 2021-05-10 12:57
20210511 | 20210511011 | 11 | 643.0500, 643.0600 Flexible Tubular Markers | Items 643.0500 and 643.0600 Flexible Tubular Marker Posts & Bases are counted by the "DAY" on this project; most past projects count these as "EACH" installed. Please confirm that these will be paid by the "DAY". Thanks | The units for the two items; 643.0500 (Flexible Tubular Markers Posts) and 643.0600 (Tubular Marker Bases) should be â€œEACHâ€ not â€œDAYSâ€ and the quantities should also be changed from â€œ1,806 DAYSâ€ to â€œ43 EACH. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-04-20 15:43 | 2021-04-21 11:58
20210511 | 20210511011 | 11 | Longitudinal deck Joints | Stage 1 and stage 2 will require ~17' wide deck pours based on 18' working area shown in the traffic control details. Plan sheet #80 shows a transition from 2% to 3% cross slope at a point 12' from the curb face. Since the low-slump finishing machines can only finish at a constant slope, Stage 1 and Stage 2 will require 2 deck pours and a longitudinal joint at the slope transition point. The same is true for Stage 3 pour which will require a longitudinal joint at the crown. Does the owner really want 5 longitudinal joints in this deck? |  |  | 2 | 2021-05-07 10:37
20210511 | 20210511012 | 12 | Mosaic Tile | There is a note on the structure plan calling out mosaic tile insets on the four corners of the structure, but there is no detail or payment for the call-out. Could the Department please provide detail and mechanism for payment? | Mosaic panel details are included on sheet 62 of the bridge plan. This work is to be covered under the Concrete Staining bid item. | Mike Coleman | 1 | 2021-04-21 10:01 | 2021-04-22 06:56
20210511 | 20210511012 | 12 | Request for Existing Structure Plan-Set | Could the Department provide the original structure plan-set showing the Sub-Structure and Super Structure detail? The inventory website only has the rehab plans from 1983. | The structure as-built plan can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511012/ | Mike Coleman | 2 | 2021-04-21 10:05 | 2021-04-22 07:08
20210511 | 20210511012 | 12 | Pre-Bid Meeting Attendance Roster | Please post the attendance roster for the Pre-Bid Meeting. | The attendance roster has been posted at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511012/ | Jill Fehrman | 3 | 2021-04-23 07:27 | 2021-04-23 07:30
20210511 | 20210511012 | 12 | Request for information listed in special provisions | Can you please provide the following: . Bridge Asbestos Inspection Report . FAA Coordination Information . Incidental Take Permit . Section 404 . TCGP Certificate . Temporary Causeway flood plain permit | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511012/ An addendum will be issued to clarify that the City will not be obtaining the temporary causeway floodplain permit. | Mike Coleman | 4 | 2021-04-26 09:38 | 2021-04-26 09:56
20210511 | 20210511012 | 12 | Existing Abutments | On page 5 of the existing P-51-709 planset, there is a note/ detail stating an alternate to use wood piling in the abutment footings. Can the Department clarify which option was used either wood or concrete? | It is not known which pile option was used. | Mike Coleman | 5 | 2021-04-26 10:45 | 2021-04-27 06:50
20210511 | 20210511012 | 12 | Existing Plans for the Split Block Retaining Wall | Are plans available for the existing split block retaining wall that the new wing #3 ties into? | The existing wall plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511012/ | Mike Coleman | 6 | 2021-05-04 11:06 | 2021-05-04 13:24
20210511 | 20210511012 | 12 | Excavation, Hauling, and Disposal of Sediment | How was the tonnage of sediment to be excavated, hauled, and disposed of determined? Location is noted as Causeway. Is the causeway material, once placed into the river, going to be classified as contaminated? | The quantity includes excavation of Root River sediment including any causeway material that may mix with river sediment materials. Special Provision Article Notice to Contractor â€“ Root River Excavation provides additional guidance on this. | Mike Coleman | 7 | 2021-05-07 13:14 | 2021-05-10 08:09
20210511 | 20210511013 | 13 | SPV.180.01 Hydroseeding | Couple of Questions: In the Specials for this item, Section B Materials lists a type of 'hydromulch' for covering the hydroseed. The payment for this item includes the seed mix, fertilizer, and water. I can't find a bid item for the 'hydromulch'. Please clarify if the 'hydromulch' bid item is missing or if it is incidental to the hydroseeding. In Section C Construction, it states to mix the seed, fertilizer, and 'hydromulch' in the tank and apply all of this together. Generally, to get a good seed-soil contact, the seeding and covering are done in separate steps so the seed is in contact with the soil. Can these applications be separated due to this concern or must it be bid for applying as written? If they can be separated, is the real intent of this specification for applying 'hydromulch'? Perhaps normal seeding and fertilizing bid items are appropriate with a 'hydromulch' special instead of the hydroseeding special? | An addendum will be issued to clarify. â€¢ The mulch is incidental to the hydroseeding bid item. An addendum is being prepared to revise the special provisions to clarify that the mulch is included. â€¢ The construction application of the hydroseed should be bid as written. | Mike Coleman | 1 | 2021-04-26 13:42 | 2021-04-28 06:09
20210511 | 20210511013 | 13 | CAD files | Are earthwork CAD files available? | No 3D models are available for this project. | Mike Coleman | 2 | 2021-05-04 09:42 | 2021-05-04 13:34
20210511 | 20210511014 | 14 | 649.0150 Temporary Tape | What is the intended use of item 649.0150 Temporary Removable Marking Tape, 4-Inch? There is quantity of 15,410', but there isn't an application for this item shown in the plans. Thanks | Item 649.0150 Temporary Marking Line Removable Tape 4-Inch will be deleted. Item 649.0105 Temporary Marking Line Paint 4-Inch is to remain. The item # for this paint was incorrectly identified in MQ sheets. An addendum will be issued. | Mike Coleman | 1 | 2021-04-20 13:24 | 2021-05-05 13:39
20210511 | 20210511014 | 14 | SPV.180.01 Hydroseeding | Couple of Questions: In the Specials for this item, Section B Materials lists a type of 'hydromulch' for covering the hydroseed. The payment for this item includes the seed mix, fertilizer, and water. I can't find a bid item for the 'hydromulch'. Please clarify if the 'hydromulch' bid item is missing or if it is incidental to the hydroseeding. In Section C Construction, it states to mix the seed, fertilizer, and 'hydromulch' in the tank and apply all of this together. Generally, to get a good seed-soil contact, the seeding and covering are done in separate steps so the seed is in contact with the soil. Can these applications be separated due to this concern or must it be bid for applying as written? If they can be separated, is the real intent of this specification for applying 'hydromulch'? Perhaps normal seeding and fertilizing bid items are appropriate with a 'hydromulch' special instead of the hydroseeding special? | An addendum will be issued to add mulch to the general and payment portion of the article. It will be incidental to the item. | Mike Coleman | 2 | 2021-04-26 13:46 | 2021-05-05 13:42
20210511 | 20210511014 | 14 | BASE PATCHING ASPHALTIC | There is no typical section for Base Patching Asphaltic. Please provide a typical section. | Base patching will occur prior to milling. In the past, Waukesha County has done the base patching prior to milling â€“ this generally provides for a better surface lift even though we end up paying for the wasted asphalt. The thickness of the asphalt varies throughout the project. The specification states the thickness shall match the existing abutting pavement. Variable sizing of patches should be expected and will be at direction of engineer. We do take into account equipment to be used as well as the patch that provides for the best repairs (usually a foot or two beyond the distressed area). | Mike Coleman | 3 | 2021-05-06 09:59 | 2021-05-10 07:00
20210511 | 20210511014 | 14 | Base Patching Asphaltic | Is there a minimum patch size or width? | Again, this is an undistributed item. Per the specification removal locations will be located as engineer directs in the field. So, short answer would be no minimum. | Mike Coleman | 4 | 2021-05-06 14:19 | 2021-05-10 06:39
20210511 | 20210511015 | 15 | Steel repair clarifications | I have a couple of questions regarding the steel repair work on P-40-589: 1. What work is being paid for under bid item 50, Structural Steel Carbon? It appears to be the work related to the new moment plates on sheet 5? 2. Item SPV.0105.597- Cross Bracing Adjustment: there is no detail shown for this work or a detail on how the existing H2 (5x5) bracing is currently attached to the bottom flange of the girders. Could more detail be provided for this item? | 1. Structural Steel Carbon bid item 506.0105 is for the new moment plates including the required plates, washers, and bolts. 2. See the cross brace shim details on sheet 5 (lower right side of sheet) and the STSP for Cross Bracing Adjustment P-40-589, Item SPV.0105.597. Note- at each cross brace/girder shim location install four bolts and two shims. The 3" wide shims are to be installed parallel to the C/L of each 6" wide girder bottom flange. | Jill Fehrman | 1 | 2021-04-21 13:11 | 2021-04-23 07:15
20210511 | 20210511016 | 16 | Electronic Data Request | Please provide the following files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511016/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-16 09:12 | 2021-04-20 07:15
20210511 | 20210511016 | 16 | Earthwork | Please provide earthwork station to station listings for marsh excavation and select borrow, so the quantities can be verified and locations known. | We are not able to provide specific station to station listings for marsh excavation and select borrow quantities. However, as explained below, there is plenty of information on these quantities in the plan for the contractor to prepare their bids. The limits of Select Borrow (208.1100) are shown in the miscellaneous quantities on sheet 344 of the plan. There are also construction details referencing select borrow on sheets 29 and 30 and a plan view of EBS limits is shown on page 31. Excavation Marsh (205.0400) is shown in the earthwork summary table on page 343 of the plan. The spreadsheet for this table was provided as part of Question #1. Excavation Marsh is not shown in the earthwork data sheets but the quantity was developed in conjunction with the wetland areas which can be found on pages 5 and 6 of the plan. The link below does contain our marsh excavation surface and wetland shapes that we used to calculate the quantities. These files may be useful. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511016/ | Mike Coleman | 2 | 2021-04-16 16:01 | 2021-04-20 09:04
20210511 | 20210511016 | 16 | Roadway Embankment | Per detail in the plan for marsh and ebs excavation it states that in note # 3 "The area of select borrow used to backfill the marsh (or EBS) excavation as shown above is not included in the roadway embankment quantity and will not be paid as roadway embankment." Per further investigation it is believed that the 1 foot of select borrow backfill that goes above the existing ground of the marsh or EBS was NOT removed from the roadway embankment quantity and in currently included in the embankment item. Please revise the plan / roadway embankment so note # 3 in the details are correct, thus reducing the embankment quantity. | Quantities were checked and it was confirmed that the 1 foot of select borrow was not removed from the roadway embankment quantity. An addendum will be issued to revise the incorrect quantity. | Jill Fehrman | 3 | 2021-04-19 15:26 | 2021-04-23 07:13
20210511 | 20210511016 | 16 | Select Borrow | How is the Select Borrow item going to be measured and paid? In its original position, in its final position, etc.? Please confirm that the quantity of Select Borrow is at 1.0 expansion factor. What is the reasoning for such a large amount of undistributed quantity of Select Borrow? Please eliminate the undistributed quantity as DOT has all areas of Select Borrow backfill accounted for in the quantity already without the undistributed quantity. | Select Borrow will be measured in its final position according to standard spec 208.4.4 and an addendum will be issued to add appropriate language to clarify this. Select Borrow is at a 1.0 expansion factor. An undistributed quantity was originally included to cover the potential for marsh areas being larger than anticipated. After further discussion, we agree that all areas are adequately covered in the quantities and there is no need for the undistributed quantity. The forthcoming addendum will remove the undistributed quantity of Select Borrow. | Jill Fehrman | 4 | 2021-04-20 07:54 | 2021-04-23 07:19
20210511 | 20210511016 | 16 | Storm Pipe & Culvert Pipe Excel Data | Can the Storm Pipe & Culvert Pipe data be provided in Excel? | The storm sewer Excel files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511016/ Note that these sheets are provided for information only and the final posted plans should still be considered the official bidding documents. | Mike Coleman | 5 | 2021-04-20 15:39 | 2021-04-21 11:53
20210511 | 20210511016 | 16 | Construction Start 2021? | Can this project be started in 2021? The specials say start April 1, 2022. There is a lot of construction season in 2021 where this project can be accelerated and finished one year early if allowed, saving escalation for labor and equipment. | Completion of 1146-75-72 is directly linked with the completion of the WIS 15 bypass segment that wonâ€™t be open to traffic until Fall 2023. Both segments will open to traffic simultaneously and this coordination is referenced in the Prosecution and Progress article. Since the work for 1146-75-72 only requires two construction seasons, work on is not allowed to begin until April 2022 to minimize the overall duration of impact to traffic and to adjacent properties. | Mike Coleman | 6 | 2021-04-20 15:42 | 2021-04-22 06:51
20210511 | 20210511016 | 16 | Marsh Excavation 3:1 Slopes vs 1:1 | Why does the Marsh Excavation extend to the 3:1 slope off the shoulder point vs to the 1:1 slope off the shoulder point? The EBS detail shows excavation to the 1:1 slope. Can it be changed to the 1:1 slope? | The marsh excavation limits shown in the detail have been used in the Northeast Region for many years and have been shown to provide a stable roadway foundation. The excavation limits are based on recommendation by the Northeast Region soils engineer and these same limits were used on the WIS 15 bypass project ID 1146-75-71 that was let in April 2021. Geotechnical information from the corridor was also considered in using the marsh excavation detail and establishing the limits of marsh excavation. No change will be made to the details shown in the plan. | Mike Coleman | 7 | 2021-04-20 15:48 | 2021-04-22 07:19
20210511 | 20210511016 | 16 | Marsh & EBS Disposal | Why is the Marsh & EBS Disposal limits only allowed outside the 3:1 slope off the shoulder point vs outside the 1:1 slope off the shoulder point? Can it be changed to the 1:1 slope (this has been common construction practice for years)? | The decision to allow disposal only outside of the 3:1 slope off the shoulder point was based on recommendation by the Northeast Region soils engineer. This has been standard practice in the region for many years and was also used on the WIS 15 bypass project ID 1146-75-71 that was let in April 2021. Geotechnical information from the corridor and past construction experiences led to the decision of only allowing disposal outside of the 3:1 slope. No change will be made to the details shown in the plan. | Mike Coleman | 8 | 2021-04-20 15:51 | 2021-04-22 07:20
20210511 | 20210511016 | 16 | Construction Staking Structures | There are a great list of staking bid item in the proposal, but I don't see this item for staking the S-44-115 and S-44-116 structure. Can you please add these bid items for these structures, also? | Staking items for structures S-44-115 and S-44-116 will be added via addendum. | Mike Coleman | 9 | 2021-04-26 14:12 | 2021-04-27 14:03
20210511 | 20210511016 | 16 | Temporary Inlet Covers | Can DOT provide what type of inlet cover would best be suited and approved by DOT further than just the description provided? It would then be easier to try and get prices from suppliers. | Temporary inlet covers are required at the locations shown in the WIS 15 median east of Lily of the Valley Drive and are needed due to temporary crossovers for traffic staging. Existing inlets have a 2â€™ by 3â€™ opening. Intent is to provide a temporary cover that is flush with surface and is traversable for vehicles. There is no standard WisDOT cover that works for this application. There are multiple cover options that could work and we tried to allow maximum flexibility for the contractor in writing this specification. | Mike Coleman | 10 | 2021-04-28 14:15 | 2021-04-30 07:16
20210511 | 20210511016 | 16 | Concrete Pavement Gaps | There are no Concrete Pavement Gaps as a bid item. If access to homes/businesses during construction, shouldnâ€™t there be a bid item for Concrete Pavement Gaps ?? | Concrete pavement gaps should have been included for access and they will be added via addendum. | Mike Coleman | 11 | 2021-05-02 21:01 | 2021-05-04 06:08
20210511 | 20210511016 | 16 | Contract Schedule and Payment for Material Costs | With this project being bid in May, 2021, and work cannot begin until April 2022, upon award of the contract and execution of a signed contract, could contractors begin to receive payment for stockpile / delivered items at the current dollars ?? I know that proper certifications and delivery receipts will be needed, but this could help with the material costs that have recently began to go up quickly, and with no assurance that it will level off, this would allow the contractor to bid without worries of escalating material prices. | In accordance with pertinent parts of Section 106, Section 109, and sections for individual bid items within the Standard Specifications and Special Provisions, the Department will consider requests for payment of stockpile items after the contract is executed. Any request should include information about where and how the material will be stored until it is incorporated into the project. | Mike Coleman | 12 | 2021-05-02 21:03 | 2021-05-03 12:32
20210511 | 20210511016 | 16 | Christus Pond | Where is the Christus Pond within this project ?? There is a bid item for 2000 Ton of Shot Rock, and the miscellaneous quantities say it is located at the Christus Pond ?? | The Christus Pond is the pond on the Christus Church parcel located in the southwest quadrant of the existing WIS 15 & Julius Drive intersection. This pond is also referenced as Julius Pond - STA 40 â€˜JULâ€™+00 (LT) in the construction detail on lower left of page 23 of the plan. An overview of the pond (and overall parcel) is visible on plan and profile page 480 of the plan. | Mike Coleman | 13 | 2021-05-02 21:04 | 2021-05-03 11:08
20210511 | 20210511016 | 16 | Select Borrow Quantity | Per further investigations it is believed that the select borrow quantity listed in the miscellaneous quantities (on page 344 of plan) for stage 1B (525+00 - 626+00EB & 512+00 - 520+00WB) of plan is incorrect if the select borrow is at a 1.0 expansion factor and will be measured in its final position / per spec 208.4.4 and via forthcoming addendum. Right now the quantity listed for stage 1B shows that it has an expansion factor different than 1.0 (higher). Please revise / lower the select borrow quantity to reflect what was stated above. | The select borrow quantity for Stage 1B was checked again and quantities shown are correct with a 1.0 expansion factor. | Mike Coleman | 14 | 2021-05-03 14:56 | 2021-05-04 09:05
20210511 | 20210511016 | 16 | Structure Removal | Please advise as to how the structure excavation and structure backfill involved to remove the existing structures at C-44-125 and C-44-128 is to be paid for. | Both box culverts have the Removing Old Structure, Excavation for Structure, and Backfill Structure items and include notes within the structure plans as appropriate, so we are unclear what this question is asking. Please provide clarification on the intent of the question. | Mike Coleman | 15 | 2021-05-04 07:19 | 2021-05-04 11:46
20210511 | 20210511016 | 16 | Follow Up to Structure Removal | Existing structures at both the C-44-125 and C-44-128 that are called to be removed are not on the same alignment as the new structures. Due to the alignments not being the same, the existing culverts do not 100% completely fall into the structure excavation and backfill zone for the new structures. Please advise as to how the remaining portion of the existing culverts that are outside of the new structure excavation zone are to be dug out and backfilled. | Section 203 of the Standard Specifications addresses the excavation and backfill specifics. As for payment under the Removing Old Structure item, Section 203.5.1(2) states â€œPayment is full compensation for breaking down and removing; costs associated with contractor caused damage; required salvaging, storing, and disposing of materials; and, unless the contract specifies granular backfill, for backfilling.â€ | Mike Coleman | 16 | 2021-05-04 12:18 | 2021-05-05 06:15
20210511 | 20210511016 | 16 | 12-Inch Concrete Pavement Item | The item, Concrete Pavement 12-Inch, has differing information in the plan vs Miscellaneous Quantities. In the Miscellaneous Quantities it shows two station ranges on STH 15 that has Concrete Pavement 12-Inch, but the plan detail on Pg. 56 for the same station range shows Concrete Pavement, 9-Inch (Labeled K1). Which is correct ? If 12-Inch is correct, please explain exactly where it is. | The 457 SY for 12-Inch pavement should have been removed from the MQ sheet and estimate. It was double counted with the truck apron quantity. An addendum will be forthcoming. | Mike Coleman | 17 | 2021-05-04 15:27 | 2021-05-05 13:45
20210511 | 20210511016 | 16 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch, Breaker Run, Select Crushed & Shot Rock? | The conversion factors used are as follows: Base Aggregate Dense ï¿½-Inch = 2.0 Tons/CY Base Aggregate Dense 1 ï¿½-Inch = 2.0 Tons/CY Breaker Run = 1.75 Tons/CY Select Crushed = 1.75 Tons/CY Shot Rock â€“ 1.6 Tons/CY | Mike Coleman | 18 | 2021-05-06 19:49 | 2021-05-10 07:12
20210511 | 20210511018 | 18 | Design Schedule | Could you please provide the design schedule for this project? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-15 12:00 | 2021-04-16 09:49
20210511 | 20210511018 | 18 | HMA Items | Can an asphaltic surface item be added to cover the pipe patches, shoulder widening and railroad full depth areas? | Asphaltic Surface will be added via addendum. | Mike Coleman | 2 | 2021-05-04 09:32 | 2021-05-04 11:25
20210511 | 20210511018 | 18 | Potential Utility Conflicts | One of the Utility companies listed in the Special Provisions has declared bankruptcy. What would be the course of action in case if utility conflict happens and how contractor would be reimbursed in that case? | The utility has resolved its bankruptcy. No utility conflicts are anticipated at this time. Any conflicts identified during construction would be addressed using the current process. | Mike Coleman | 3 | 2021-05-04 09:43 | 2021-05-05 13:25
20210511 | 20210511019 | 19 | Cold Mix | The cold mix specifications call for a MC-250. In the past QPR, UPM and SC-250 have been allowed as suitable substitutions for MC-250. Would they be allowable substitutions for this application? | QPR, UPM and SC-250 are allowable substitutions for the MC-250 material specified in the Cold Patch, Item 495.1000.S | Mike Coleman | 1 | 2021-04-16 08:17 | 2021-04-20 07:31
20210511 | 20210511019 | 19 | Earthwork tables | There appears to be an error on the earthwork tables, specifically on page 323 and 324 for the mass ordinate. Could the department both correct this and provide the tables in earthwork in excel format? | The quantities in the plans are correct. The earthwork tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511019/ | Mike Coleman | 2 | 2021-04-19 10:28 | 2021-04-21 06:21
20210511 | 20210511019 | 19 | 2' Asphalt Shoulder | Currently the plans show that the 2' asphalt shoulder is to paved in 2 lifts. Could the 2' shoulder sections be paved in 1 lift using surface mix to allow for a roller to be used to get better compaction? According to 460.3.2 shoulders can be paved in a max shoulder thickness of 4" for 12.5mm mixes. | A single pass full depth pave for the 2â€™ shoulder section would be acceptable. | Mike Coleman | 3 | 2021-04-23 09:58 | 2021-04-27 06:53
20210511 | 20210511019 | 19 | 404 Permit | Can you provide information on why the contractor is responsible for getting a 404 permit. Isn't this done during design? | The project has been designed and can be constructed without requiring a 404 permit. The slope intercept shown on the plan is a minimum distance of approximately 10-ft from mapped wetlands. As specified in Article 7, If a contractorâ€™s chosen methods of operation, including preparatory work, staging, site clean-up, or storing materials would impact a wetland it is the contractorâ€™s responsibility to determine the requirement of and acquire a 404 permit for that operation. | Mike Coleman | 4 | 2021-04-29 13:47 | 2021-04-29 13:48
20210511 | 20210511019 | 19 | Test pit and Traffic Control | Do the plans traffic control plan include traffic control needed to do the test pit(s) prior to the project starting? | The test pit is planned to be completed in Stage 2 when traffic is crossed over onto existing EB lanes. | Mike Coleman | 5 | 2021-04-30 12:16 | 2021-05-03 12:52
20210511 | 20210511019 | 19 | Potential Utility Conflicts/Issues | One of the Utility companies listed in the Special Provisions has declared bankruptcy. What would be the course of action in case if utility conflict happens and how the contractor would be reimbursed in that case? | The utility has resolved its bankruptcy. No utility conflicts are anticipated at this time. Any conflicts identified during construction would be addressed using the current process. | Mike Coleman | 6 | 2021-05-05 11:04 | 2021-05-05 13:47
20210511 | 20210511020 | 20 | Flagging Distance Restrictions | Due to paving constructability, contractor is requesting a maximum of a 1.5 mile distance for flagging operations, in order to allow adequate distance for paving, rolling, and density testing. Will the department change the maximum flagging distance requirement in the special provisions from 0.6 mile to 1.5 mile during paving operations? | Due to the high seasonal traffic volumes in this segment of USH 51, 0.6 miles was computed in order to minimize traffic disruptions and queues. Please maintain the 0.6-mile flagging distance. | Mike Coleman | 1 | 2021-05-04 22:04 | 2021-05-05 13:45
20210511 | 20210511021 | 21 | Schedule | Contractor requests a copy of the DOT's construction schedule. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511021/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-23 14:58 | 2021-04-26 10:04
20210511 | 20210511022 | 22 | Roadway Details at Beam Guard Areas | Can a typical section be provided for the roadway at the areas where guardrail will be removed and replaced? | We typically we do not do separate typical section for the guardrail areas. Between the Guardrail Details (pages 28-29), Cross Sections, and the SDD, contractors should have what they need to build the section at the guardrail. | Mike Coleman | 1 | 2021-05-04 22:07 | 2021-05-05 13:37
20210511 | 20210511022 | 22 | Asphaltic Surface | Per the Miscellaneous Quantities on Sheet 38 of the plans, is the 50 Ton of Asphaltic Surface from STA 829+03 to 869+94 for paving in back of curb? | Yes, the 50 Ton is intended for the asphalt driveways behind the curb. | Mike Coleman | 2 | 2021-05-04 22:09 | 2021-05-05 13:48
20210511 | 20210511023 | 23 | Asphalt Pipe Patches | Looking at the quantities it is unclear if the asphalt placed in the pipe patches is paid under the 4 MT item or the Asphaltic Surface Patching Item. | Asphalt placed as part of the culvert pipe replacements will be paid for as Asphaltic Surface Patching per construction detail on sheet 7 of the plan. An addendum will be issued to clarify. | Mike Coleman | 1 | 2021-04-23 11:09 | 2021-04-26 10:09
20210511 | 20210511023 | 23 | Temporary markings | Good morning. In looking at the temporary paint quantities, there appears to be enough to mark the milled surface and, potentially, the joint after pass #1 or simply place a double yellow the entire length of the milled surface. Could you please clarify the intent for this bid item? Thank you. | The intent for the Temporary Paint bid item is for the contractor to have enough quantity to place a double yellow the entire length of the milled surface, but engineer in field may direct the contractor to include existing passing lane layouts utilizing SDD 15C8-20a with 4â€™ skips instead of 12.5â€™. | Mike Coleman | 2 | 2021-04-29 08:41 | 2021-04-29 13:49
20210511 | 20210511023 | 23 | Culvert pipe excavation and backfill | Is it the designers intent to reuse the material in the transition cut as trench backfill? Will the foundation backfill item be added for backfill around the pipe as shown in the construction detail? | The material around the pipe is incidental to the pipe. The intention was to use existing material, or use borrow if materials prove unsuitable. | Mike Coleman | 3 | 2021-05-04 08:24 | 2021-05-05 13:35
20210511 | 20210511023 | 23 | Guardrail Layout | In the Construction Details, page 10 of the plan, it shows the guardrail 17 feet off centerline and 4 feet away from some other line. Upon viewing the site, it appears that the existing wooden retaining wall under the bridge may interfere with the post placement in MGS installations. At the very least, it appears that the back of posts through the bridges retaining wall will be to close to the retaining wall for current design standards of guardrail. If this hasn't been vetted already, we'd suggest an MGS 3K option or even an MGS QS through this portion of both stretches. | The existing retaining wall based on surveyed shots is approximately 20â€™ â€“ 21â€™ from the centerline alignment. Per the standard detail drawing and current design standards, this distance does not meet the 2â€™ behind the back of proposed guardrail post to use the bid item 614.2300, MGS Guardrail 3. We will issue an addendum to update the plans and estimate to remove the MGS Guardrail 3 bid item and replace it with the MGS Guardrail 3K bid item. | Mike Coleman | 4 | 2021-05-06 07:54 | 2021-05-06 08:46
20210511 | 20210511024 | 24 | HMA Driveway | Near Station 3+75 there is an existing HMA driveway. The Culvert is to be replaced in the area, but there does not seem to be quantity for that location. Should the item Asphaltic Surface Driveways be added? | The intent is to utilize the mainline HMA mixtures for the driveway paving given the small area. The quantity is included in overall HMA quantities noted for west of the proposed bridge. | Jill Fehrman | 1 | 2021-04-21 08:51 | 2021-04-22 09:28
20210511 | 20210511024 | 24 | 404 permit - RFI | Can the department please post the 404 permit for this project on ftp site | The 404 permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511024/ | Mike Coleman | 2 | 2021-05-09 17:51 | 2021-05-10 09:14
20210511 | 20210511026 | 26 | 3/4" Agg Base | Based on the finish cross sections of sheet 5 and 6, is it the departments intention that the ï¿½â€ agg base go all the way down the side slope to meet the topsoil? | The ï¿½â€ Base Aggregate Dense will go to the point where the side slope grade ratio in the typical sections is met (ie 4:1). | Mike Coleman | 1 | 2021-04-28 12:45 | 2021-04-29 13:44
20210511 | 20210511027 | 27 | Small Animal Barrier | What is the required post spacing for the barrier? | After further discussion and review of other details from old plans, can we are revising this answer to 10-foot maximum post spacing. For this particular project our post embedment is 5-feet (versus 2-feet used on other projects) due to frequent high water conditions. At the 2-foot post spacing and current steel pricing, we could see the bid being cost prohibitive on this item. | Mike Coleman | 1 | 2021-04-27 06:42 | 2021-04-27 10:52
20210511 | 20210511027 | 27 | Schedule of Operations | Under Schedule of operations, in general, it appears the Temporary Roadways and Temporary Structures are to be constructed and ready for use in the 2021 construction season but would not be put into use until 4/18/22. At that point, the traffic would be switched, removal operations would begin but the causeways could not be installed until after June 15th to allow for construction on the new structures. If this is the correct observation, there does not appear to be enough time in the schedule to complete the new structures from the causeways, remove the causeways, remove the temporary structures and remove the temporary roadways prior to the completion date of 10/21/22. Would the Department be able to provide the proposed draft schedule used to design this project? If an alternate schedule would be proposed by the contractor with the traffic on the temporary structures prior to 10/29/21, would the traffic remain on the temporary structures through the winter allowing the contractor to utilize the causeways until March 1st (allowing for causeways to be removed by March 15th) for winter construction of portions of the new structures? The remaining work for the new structures would continue into the summer of 2022 followed by the temporary bridge and temporary roadways by 10/21/22. Would this be considered an approved alternate schedule? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511027/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. The schedule assumes expedited work (as noted in the prosecution and progress) and concurrent work on both bridges in year 2. The special provisions outline when the temporary roadway is allowed to carry traffic before October 29, 2021 and after April 18, 2022. Date restrictions are dependent on weather and construction operations and final dates can be further discussed with the engineer. The department does not desire to allow one lane conditions on STH 35 (east temporary bridge) between October 29, 2021 and April 18, 2022 due to potential adverse weather conditions. The contractor could consider constructing the west bridge B-61-286 in 2021 and providing temporary connections between the new bridge and the existing roadway as an alternate to building both bridges in 2022. | Mike Coleman | 2 | 2021-04-27 16:56 | 2021-04-29 07:54
20210511 | 20210511027 | 27 | Substitute Backfill Granular Grade 2 | Would the Department allow the contractor to substitute Item 209.2500, Backfill Granular Grade 2 with a quarried rock item such as Breaker Run or Select Crushed Material if this option is more cost effective? | WisDOT would allow the substitution with the Select Crush Material. Breaker Run will not be allowed. | Mike Coleman | 3 | 2021-04-29 09:50 | 2021-05-03 06:40
20210511 | 20210511027 | 27 | Small Animal Barrier - Color | Would black be an acceptable color for the fencing, posts, and rails? Multiple suppliers have said they will not be able to quote the green color at this time. Thanks | The department will allow galvanized steel as an alternative to the coated green color. | Mike Coleman | 4 | 2021-04-30 14:00 | 2021-05-04 09:07
20210511 | 20210511027 | 27 | Substitute Backfill Granular Grade 2 | If Select Crushed will be allowed to Substitute the Backfill Granular Grade 2 item will the Select Crushed have to be placed at 30" thick per the Typical Finished Plan Section, or would it be allowed to place Select Crushed Material per the FDM 11-5 Attachment 15.2 at 16" thick? | The contractor should bid the 30â€ of material (either the Backfill Granular Grade 2 item or the allowed alternative of Select Crushed). | Mike Coleman | 5 | 2021-05-03 09:45 | 2021-05-03 12:39
20210511 | 20210511027 | 27 | Line item 294- SPV.0060 Temp. Marking R/R Crossing Removable Tape | Sheet 49 shows the Temp RR Crossing Marking as the "X with 2 bars", the detail plate includes "RR at the base of the "X". Do we not need the "RR" for this item? | Yes, Sheet 49 shows the RR and the SDD should followed for the temporary RR marking. | Mike Coleman | 6 | 2021-05-03 10:36 | 2021-05-03 12:31
20210511 | 20210511027 | 27 | RR Flagging and Insurance for 0 Trains | Article 7, Section A.2 of the Special Provisions state that "Approximately 0 through trains operate daily at up to 0 mph. There are no switching movement at this location." Is this a mistake? If not, is a flagman and those associated costs necessary when there are zero trains moving through the work area? | Yes, the special provision is correct. At this time there are 0 trains at the crossing although the railroad does periodically run maintenance vehicles through here. The contractor will need to bid this based on the necessary coordination in article 7 for Railroad Insurance and Coordination - Wisconsin Central Ltd (CN). The need for flagging will have to be determined based on the traffic present at the crossing at that time. | Mike Coleman | 7 | 2021-05-03 11:14 | 2021-05-04 06:12
20210511 | 20210511027 | 27 | Project Schedule | Per DOT plan, causeway installation, the existing str. removals, new str construction (piers with cofferdams, seals, pda testing, etc), and temp bypass removals are to be completed in a time span of 6-16 to 10-21. In order to meet the DNR minimal debris spec for the removals, the causeways should be in place for equipment access but according to Article 3, this cannot be completed until after the fish spawning is finished 6/15. The causeways shown on sheet 39 & 43 do not extend into where the rivers are during normal flows. Can the causeways be installed prior to 3/15 to facilitate existing structure removals (285 & 286), and cofferdam construction (piers 3 & 4) at structure 285 and can this work continue during the Fish Spawning Period since this is not located in the banks of normal flows? Can the DOT modify the schedule to have traffic on the new structures by 10/21/22 and allow temp str and bypasses to be removed during fall/winter 2022 and seed/finish Spring 2023? | o If water conditions are normal, changes in these dates may be allowed as outlined in the article for Prosecution and Progress subarticle for Fish Spawning since work would technically be out of the water. o The removal of the temporary roadway was set under the conditions of the Section 404 permit to approve temporary wetland impacts. The contractor should bid the project with the proposed completion date. Any extension of the completion date will be per standard spec 108. | Mike Coleman | 8 | 2021-05-03 11:59 | 2021-05-04 06:15
20210511 | 20210511027 | 27 | Temporary Structure Station 45+70 | The Temporary Structure at Sta. 45+70 is listed as a 16 foot wide, single lane structure with temporary signals. Would the contractor be able to substitute a temporary structure that would be a 30 foot wide, bi-directional structure and eliminate the temporary traffic signals? | The contractor would be allowed to provide a wider temporary bridge with no temporary traffic signals to maintain two lanes of traffic. The bridge would need to meet the requirements of article 22. Any changes to the wetland or waterway impacts would need to be amended in the Section 404 Permit with COE and DNR per article 8. Impacts to the adjacent USFWS property are not allowed. | Mike Coleman | 9 | 2021-05-03 13:19 | 2021-05-04 08:12
20210511 | 20210511027 | 27 | Temporary Structure | Should the contractor elect to use a two-lane Temporary Structure at Station 45+70 (East Channel), would the temporary roadway and structures be allowed usage during the winter months? Removing the October 29, 2021 â€“ April 18, 2022 use restrictions? | Yes, the department would consider removing this restriction if two-lane conditions can be safely maintained on the temporary roadway and bridges during the winter months. Any changes to this restriction may require additional effort by the contractor for winter maintenance. Additional coordination with Buffalo and Trempealeau County would be required in addition to the requirements already outlined in the subarticle for Winter Maintenance in the article for Prosecution and Progress. | Mike Coleman | 10 | 2021-05-04 10:05 | 2021-05-05 06:16
20210511 | 20210511027 | 27 | Design Schedule Durations and Logic | The design schedule as laid out has logic that would appear to be incorrect and durations that are not feasible. The demo of the existing structure cannot be finished until after the temporary access road is in place as access to the piers is needed. The demo of the existing structure (6 span prestress) cannot be realistically completed in 5 days, cofferdams are shown for two days to install but schedule doesn't account for removal of cofferdams/backfilling, structure excavation is being completed before the cofferdams are all installed, and proposed schedule provides 9 days to deck, tie rebar, pour deck and cure time a 25,000 sf deck (and structural approaches?). There is nothing accounting for stripping the deck. This is the third question regarding contract time and working schedule has been discussed in the Q&A session. Please review the contract times allotted and make the revisions necessary to make schedule realistic. | These items were discussed and analyzed in detail during NEPA alternative development, 60%, and 90% since the schedule was a driver of environmental issues and permitting. â€¢ The time chart is completed with bid item quantities and WisDOT rates. The time chart shows working days which does not include weekends, holidays, and weather days. A designerâ€™s time chart may not match the level of detail a contractor puts together since it is using bid items which encompass a number of construction activities in those rates. The approach follows WisDOT FDM Chapter 19 guidance using WisDOT items and rates. â€¢ As provided in the special provisions, the contract will require extraordinary forces. Bid the contract per the special advertised proposal and supplemental information that has been posted via BidX. o Some of the bridge removal work may start ahead of June 15 as noted in the schedule. With the existing span lengths, the bridge deck could potentially be removed one span at a time from the existing bridge deck. o The cofferdams are shown at 8 working days, not 2 working days. o The structure excavation item (bridge excavation line) is for the excavation in front of the proposed abutments, due to bridge lengthening, and this is not the quantity of material in the cofferdams. o The structural approach slabs are included in the deck placement SF. o Deck cure time continues into the parapet forming line (it is not fully shown in the schedule). o The superstructure construction timeline is shown at approximately 5 to 6 weeks in the schedule provided. | Mike Coleman | 11 | 2021-05-05 08:36 | 2021-05-06 13:17
20210511 | 20210511027 | 27 | Winter Work Schedule | Will the department allow traffic on temporary bypass and temporary bridges between the dates of October 29, 2021 and April 18,2022, yes or no? | The department does not desire to allow one-lane conditions on STH 35 (east temporary bridge) between October 29, 2021 and April 18, 2022 due to potential adverse weather conditions. The department would remove this restriction if two-lane conditions can be safely maintained on the temporary roadway and bridges during the winter months. See the previous answers in Questions 2, 9, and 10. | Mike Coleman | 12 | 2021-05-06 14:26 | 2021-05-07 06:58
20210511 | 20210511030 | 30 | Asphaltic Surface Mix Type | On sheet 2 in the General Notes it states that the Asphaltic Surface shall be constructed with 1 lift consisting of 2MT 58-34S. We do not believe a 25mm mix will be good for this application. We would suggest a number 4 (12.5mm). The department may want to consider using a LT mix instead of an MT as well since this area will not have traffic on it. | Upon review of this question, we have decided to eliminate the reference to a specific mix type for this project in the General Notes. An addendum will be issued. | Mike Coleman | 1 | 2021-04-28 18:54 | 2021-05-03 06:42
20210511 | 20210511031 | 31 | Westbound I-90 Lane Closures | Two questions regarding lane closures on Westbound I-90: 1. Special provisions state that lane closures are allowed on Westbound I-90 to help streamline construction activities. Will an additional item for 643.4100.S Interim Lane Closure be paid for lane closures set on Westbound? Currently there are only quantities allocated for Eastbound closures. 2. Will item 643.1205.S Basic Traffic Queue Warning System be required on Westbound I-90 when lane closures are present on Westbound? | 1. An addenda will be issued adding additional quantities for the Westbound closures. 2. Yes, a Basic Traffic Queue Warning System will be required on Westbound I-90 when lane closures are present on Westbound. | Jill Fehrman | 1 | 2021-04-20 14:16 | 2021-04-23 07:11
20210511 | 20210511031 | 31 | PWL Mix Use Table - Plan Sheet 55 | Ramp taper, ramp and aux lane paving is completely different than mainline paving. Would the DOT change that tonnage to QMP Density? | An addenda is being submitted that PWL Table shown the Misc. Quantities and update the tonnage to QMP Density. | Mike Coleman | 2 | 2021-04-22 14:26 | 2021-04-26 10:06
20210511 | 20210511031 | 31 | 740.00440 Incentive IRI Ride | There is no pay item listed for incentive IRI ride. Will this be added to the project? | An addenda is being submitted to add the incentive IRI ride bid item. | Mike Coleman | 3 | 2021-04-22 14:33 | 2021-04-26 10:07
20210511 | 20210511031 | 31 | Guardrail Quantities | A Few Questions: 1. Shouldn't there be a quantity of 'Removing Guardrail' for each location that receives a new EAT or MGS Thrie Beam Transition bid item? 2. It appears that each location in the MQ's that shows a quantity of MGS Thrie Beam Transition, but has no remarks in the remark section, doesn't have any existing Thrie Beam present. Please verify that the MGS Thrie Beam Transition quantity is correct. 3. Is there a SDD or can a detail be provided for connecting MGS Thrie Beam Transitions or MGS EAT's to existing Class A rail? One concern we have is how to handle a stretch of 'Adjusting Class A Rail' that can't be raised to MGS tolerances. Also, because MGS post spacing is 'off the joint', what is the correct method for attaching Class A Rail that is 'on the joint' to either MGS bid item? Thank you. | 1. A quantity for Removing Guardrail will be added by addenda. 2. This item will be switched to Steel Thrie Beam and the quantity will be verified by addenda. 3. The item will be switched from MGS to Steel Thrie Beam and Steel Plate Beam Guard EAT. | Mike Coleman | 4 | 2021-04-27 16:06 | 2021-04-29 13:42
20210511 | 20210511031 | 31 | Two Part Question: QMP Density Incentive Quantity & PWL Test Strips | 1. Looking at the Addendum posted the QMP Density Incentives covers all the 4LT shoulders and all of the 4HT mainline quantities which is 22,720 Tons. Shouldn't the QMP Density Incentive just cover the 4LT shoulders - 7,700 Tons and the 4HT ramp/aux lane paving - 752 Tons that was changed in a previous question making the overall quantity 8,452 Tons eligible for QMP Density Incentive? 2. In the Addendum posted the mixture use table on sheet #53 states that the 4HT is still under PWL Incentive for Volumetric and Density. If the PWL Spec still applies the HMA PWL Test Strips (Density & Volumetrics) shouldn't those still be in the project and not eliminated in the Addendum? | 1. The auxiliary lanes, shoulders, ramps, and crossovers that are constructed with 4 HT on the lower lift will fall under the PWL spec since it is the same mix as the mainline driving lanes. Since these are not mainline driving lanes, they will be acceptance tested. The addenda table shows that the lower lift of the mainline driving lanes constructed with 4 HT will fall under PWL for density and volumetrics and receive PWL incentive. The QMP Nuclear Density STSP will only apply to the 4 LT shoulder on the lower lift, and all upper lift pavement, since they are a different mix type that is not covered by PWL. 2. There will be 1 density and 1 volumetric PWL test strip. An addendum will be issued to correct this. | Mike Coleman | 5 | 2021-04-30 10:15 | 2021-05-03 11:13
20210511 | 20210511031 | 31 | On and Off Ramps Mix Type | Looking at the plan it states that the On and Off Ramps will be paved with the Mix Type of SMA. Is this the new standard of paving the On & Off Ramps with SMA instead of using the HT mix like previous projects? | Paving a ramp with SMA varies by project and it was decided to utilize SMA on the ramps for this project. | Mike Coleman | 6 | 2021-05-03 10:00 | 2021-05-03 13:39
20210511 | 20210511031 | 31 | Prep Foundation for Asphalt Paving | In the plan there is no item for Prep Foundation for Asphalt Paving. There is 4,000 LF of Concrete Joint and Crack Cleaning in the plan to be done. Does that quantity cover Prep Foundation for Asphalt Paving for the entire project? If a Prep Foundation for Asphalt Paving will not be included in the project would the extra quantity be ran under the Concrete Joint and Crack Cleaning Item? | The bid item Prepare Foundation for Asphaltic Paving, Item 211.0100 will be added via addenda. | Mike Coleman | 7 | 2021-05-03 10:14 | 2021-05-03 13:40
20210511 | 20210511031 | 31 | Sheet 48 - Clearing and Grubbing | For Item 201.0205 Grubbing, the total stations add up to 23.5 and you have 28 listed. Are the stations listed incorrect or is this quantity overstated? For Item 201.0105 Clearing, is this just in case there are some trees to clear or do you have an area(s) in mind? | The correct quantity is 23.5 and will be corrected in an addenda. This is an undistributed amount. | Mike Coleman | 8 | 2021-05-04 08:13 | 2021-05-04 10:39
20210511 | 20210511031 | 31 | Proposal - Traffic - Table 108-1 | Should the last line of the IH 90/94 lane closures read Friday - Saturday? | The line was accidently added twice and will be deleted via addenda #2. | Mike Coleman | 9 | 2021-05-04 15:43 | 2021-05-05 12:37
20210511 | 20210511031 | 31 | Mixture Use Table for Question #5 | Will there be a revised Mixture Use Table sent out for this project that coincides with Question #5 stating what is PWL testing and what is QMP testing? | The table in Addendum #1 is correct. | Mike Coleman | 10 | 2021-05-06 11:27 | 2021-05-07 06:29
20210511 | 20210511031 | 31 | Guardrail Quantity Follow-Up | Thank you for addressing the guardrail issues from the previous question. The addendum added 105 LF of 614.0230, Steel Thrie Beam. Given the locations and the 21 LF of need at each location, is it possible that the actual bid item needed is 614.0200, Steel Thrie Beam Structure Approach? |  |  | 11 | 2021-05-06 15:36
20210511 | 20210511034 | 34 | N-40-97 Structure Mounted Bracket | Please provide a detail for the bracket that is to connect the new noise wall post to the existing barrier anchor assembly. | Sheet 5 of 8 from the noise wall structure plan includes the following note: â€œNoise barrier posts, bearing plates, and connection plates to be designed as part of the bid item â€˜Noise Barrier Double-Sided Sound Absorptive N-40-97â€™ (11â€™-2â€ or 12â€™-0â€ existing post spacing).â€ This is the normal note that has been included in other recent structure plans for new noise barrier walls. Different wall systems could require varying types of connections, which becomes a means and method issue. The same plan sheet noted earlier includes details of the existing barrier wall anchorage assembly. This provides contractors with sufficient information to design the applicable details to accommodate their specific wall system or systems. | Mike Coleman | 1 | 2021-05-04 10:57 | 2021-05-05 13:27
20210511 | 20210511034 | 34 | Interim Completion Date | Can the Interim Completion Date of November 14, 2021 be pushed back? The Project Completion Date is June 1, 2022. There are current material supply issues due to the large demand for Noise Walls on several projects throughout the state as well as previous COVID-19 set backs. Flexibility to complete all aspects of work by June 1, 2022 instead of November 14, 2021 would ultimately reduce costs to the department by increasing the number of proposals received. | The Interim Completion Date of November 14, 2021 will remain. The completion date of June 1, 2022 is only intended for the native seeding establishment period. It would not be beneficial for the residents nearby the noise wall to have a winter shutdown so that the work could be completed the following year. The current wall is in poor condition as well, so it is not recommended that replacement be postponed to the following year. | Mike Coleman | 2 | 2021-05-05 09:42 | 2021-05-06 06:36
20210511 | 20210511035 | 35 | Department Construction Schedule | Can the Department's construction schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511035/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-26 09:01 | 2021-04-27 06:49
20210511 | 20210511035 | 35 | Guardrail Removal | It appears that each existing terminal in the guardrail sections flare for 38 feet. Shouldn't there be 38 feet of guardrail removal at each location that is receiving a new 'Steel Plate Beam Guard EAT'? | Yes, there should be 50 feet of guardrail removal for each EAT system replacement. This totals 100 LF for 9190-26-71 and 200 LF for 9190-27-71. An addendum will be issued to add this quantity. | Mike Coleman | 2 | 2021-04-27 16:28 | 2021-04-30 07:20
20210511 | 20210511035 | 35 | Hauling Excess Shoulder Material | Will the "Hauling Excess Shoulder Material" item be paid if the material is hauled off site and not placed on the existing shoulder? If not how will this be paid for if there is excess shoulder gravel that is not needed on the job? | It is not anticipated that you will not be able to incorporate material in the shoulder area. If that occurs, a change of conditions per standard spec 104.2 will be utilized. | Mike Coleman | 3 | 2021-04-28 15:43 | 2021-04-30 07:23
20210511 | 20210511035 | 35 | Culvert Patch Asphalt Quantity | Would the department consider changing the 3 MT 58-28 S quantity figured for patching the culverts to an asphaltic surface item as the culverts will need to be paved prior to a test strip being completed? | The Department will revise the Pavement at Culvert Replacement detail to indicate Asphaltic Surface in lieu of 3 MT 58-28 S. | Mike Coleman | 4 | 2021-04-28 15:49 | 2021-04-30 07:24
20210511 | 20210511037 | 37 | Department Construction Schedule | Can the Department's construction schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511037/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-04-26 09:02 | 2021-04-26 11:02
20210511 | 20210511038 | 38 | Guardrail and Mow Strip | The new detail for mow strip requires steel posts in all areas of the mow strip. It appears at stations 436+73 to 437+20 and 521+88 to 522+33 that the only location with mow strip is around the radius guardrail. 1.) Radius guardrail requires wood CRT posts. What posts are required in this application? 2.) If steel posts are required in the mow strip at the radius, are we allowed to use wood posts for the remainder of the stretch of guardrail? | 1.) Wood posts will be required in this application. The mow strip material will be changed to the Emulsified Asphalt item so that wood posts may be used with the mow strip. This change will be addressed in an upcoming addendum. 2.) All of the mow strip material will be changed to the Emulsified Asphalt item so that wood posts may be used within it. | Mike Coleman | 1 | 2021-04-16 14:44 | 2021-04-21 06:12
20210511 | 20210511038 | 38 | Culvert Replacement Schedule | How was the 2 days of closure figured for each lane of culvert replacement? It seems it would take a day to get the shoring, barrier wall, and traffic control set up at the location. Day two would be dedicated to getting the pipe in the ground. The asphalt would have to be replaced so when we switch TC, the barrier wall can be anchored on Stage 2. It seems the schedule is very tight unless night work is to be expected. | Based on the culvert sizes and reducing traffic impacts it was anticipated that the replacements would be possible within the 2 days for each direction. If night work is anticipated then the equipment necessary for night work will be required. | Mike Coleman | 2 | 2021-04-19 15:59 | 2021-04-21 06:13
20210511 | 20210511038 | 38 | Mechanical Anchor for Culvert Repair | Mechanical anchors are required for the overhead portion of the steel plating. Since the steel plating isn't necessarily structural, could mechanical anchors be used for the side plates as well? If so, would a certified installer be required to install mechanical anchors? | - Mechanical anchors are allowed to be used for the overhead portion of the steel plating, not required as stated below. - Certified installers are not required for mechanical anchors (if the contractor chooses to use them for the overhead portion of the steel plating). - Mechanical anchor substitution along the side wall portion of the plating is not acceptable. | Mike Coleman | 3 | 2021-04-19 16:04 | 2021-04-21 11:56
20210511 | 20210511038 | 38 | Temporary Markings | Good afternoon. In looking at this projects pavement markings, it appears there should be a temporary epoxy item to be placed on the surface during paving prior to the rumble strips. Will this be clarified and/or addressed via an addendum? Thank you and have a nice weekend. | Quantities of temporary paint marking were included for the interim milled/lower surface as well as for the final top pavement surface for dashed centerline marking prior to rumble installation. The final markings would be placed after the rumbles have been installed. | Mike Coleman | 4 | 2021-04-23 16:01 | 2021-04-29 13:45
20210511 | 20210511038 | 38 | One Lane Stop Conditions | Can the stop conditions be amended to reflect a stop condition will be allowed for a maximum of 4 days instead of 2 days per direction? Does it matter which direction has the stop condition? Thanks | USH 10 will remain open to both directions of traffic at all times. The 2 day stop condition is intended to allow the replacement of one half of each culvert, closing one half of the roadway and utilizing the stop condition shown on page 186 of the plans. | Mike Coleman | 5 | 2021-04-27 14:54 | 2021-04-29 07:45
20210511 | 20210511038 | 38 | HMA Lane Repair | On sheet 27 there is a detail for USH 10 HMA Lane Repair. It states (see miscellaneous quantity sheets for locations). In the miscellaneous quantities on sheet 60 under Remove Asphaltic Surface Milling it shows 16,000 SY of undistributed Lane Repair. Under the HMA Pavement items on sheet 62 it again shows and undistributed quantity in the Asphaltic Surface item. Due to the unknown locations and quantities related to this work we are asking the department to consider using the Removing Distressed Pavement Milling item or Lane Repair item so that this is paid separately. Thank you. | After discussions with the NW Region the Removing Distressed Pavement Milling and Lane Repair items will not be used. The lane repair information will be updated to list some of the anticipated repair locations. This will be addressed in an upcoming addendum. | Mike Coleman | 6 | 2021-04-28 19:28 | 2021-05-05 06:18
20210511 | 20210511038 | 38 | Temporary Markings | Good afternoon and thank you for your prompt response to the previous question, it is appreciated. If the intent is to place temporary paint on the surface prior to the rumbles, would it be your intent to have the temporary paint contractor remove the temporary paint that is remaining after the rumble strip operation seeing as the permanent epoxy should not be placed on top of temporary paint and, if that is your intent, what method of removal would the temporary paint contractor be required to use? On similar projects such as this, a temporary epoxy bid item is used prior to the rumbles so as to avoid this issue and a potential warranty issue down the road. Will an addendum or further clarification be issued to address this? Thank you. | The temporary pavement marking for the centerline to be used on the final pavement layer prior to rumble installation will be changed to the epoxy type. This will be addressed in an upcoming addendum. | Mike Coleman | 7 | 2021-04-29 14:03 | 2021-05-05 06:17
20210511 | 20210511038 | 38 | Subsurface Info | Were any cores or borings taken on the project? | The pavement cores can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210511038/ | Mike Coleman | 8 | 2021-05-05 11:25 | 2021-05-06 11:46
20210511 | 20210511038 | 38 | SPV Item for filling voids in culverts | Did the Department have a specific product in mind for the expanding foam to fill voids? There are a wide range of materials that can meet the materials spec, but the pressure gauges, etc indicate a much more sophisticated system of delivery. Any guidance, or a list of approved contractors or approved manufacturers for this type of work would be helpful. | One that meets the specification defined in the special provisions would be TerraThane 24-003. I know this product along with some other poly-jacking and void filling foams were used in the development of the special so that multiple products where available for the contractor to choose from. Uretek 486 Star also has a couple different types of foam that would meet specifications in that product line. | Mike Coleman | 9 | 2021-05-06 12:24 | 2021-05-10 07:09