## qandasearchletting_results
Date: | 2021-06-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210608 | 20210608001 | 1 | Project Question - Material Shortages | Good Morning, Most if not all epoxy suppliers are in a current state of Force Majeure with shortages in raw materials. We are seeing increased pricing and an inability from our suppliers to even provide material in a timely manner. Is WISDOT willing to push back the completion date and/or allow a significant percentage of this project to be completed in 2022? Thank you |  |  | 1 | 2021-06-07 09:33
20210608 | 20210608002 | 2 | DESIGN FILES | Can the Department provide the Meta-Data for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608002/ | Mike Coleman | 1 | 2021-05-24 14:18 | 2021-06-03 08:33
20210608 | 20210608002 | 2 | Distressed Milling/Asphaltic Surface | Per the Special Provisions, the distressed milling item states payment for asphaltic surface will be paid separately. Looking in the contract there is no item for Asphaltic Surface. However, the miscellaneous quantities on plan sheet #50 state that there is an undistributed quantity of 907 tons of 4 LT. Furthermore there is a note below the quantities table that states â€œ**Associated with SPV.0180.02- REMOVING DISTRESSED PAVEMENT MILLINGâ€. The next note denotes that the 4 LT used in distressed milling areas are eligible for PWL spec requirements. Is this correct, or should there be an item added to the contract for Asphaltic Surface to avoid unnecessary testing requirements? | A plan addendum is being prepared that will address adding the bid item Asphaltic Surface to be used with SPV.0180.02 â€“ Removing Distressed Pavement Milling to the contract. Revised plan sheets and an updated Miscellaneous Quantities tables will be included with the plan addendum. | Mike Coleman | 2 | 2021-05-26 16:47 | 2021-06-01 05:38
20210608 | 20210608003 | 3 | Temporary pavement markings | Good morning. In looking at the proposal, plan sheet 9, and plan sheet 35, the proposal and plan sheet 9 state to place temporary epoxy same day as paving operations while plan sheet 35 states to place temporary epoxy same day as milling operations and use the regular 4" item after paving operations are complete. If the milled surface is to be left for a certain amount of time before paving, there would typically be a temporary paint item to be placed on the milled surface daily. There does not appear to be center line rumble strips on this project, on similar projects, a same day epoxy item would be used on the surface after paving rather than a temporary epoxy item so that it would not have to be re-traced with a regular epoxy item. If a same day item is added, the regular epoxy footage (4" yellow) would not be needed. Will an addendum or clarification be issued to address these differences? | Epoxy was chosen as the same day temporary marking line to establish the centerline for its durability and visibility. The regular epoxy item is to be used to re-traced the markings after the project paving is complete. | Mike Coleman | 1 | 2021-05-26 08:14 | 2021-06-03 08:34
20210608 | 20210608003 | 3 | Pavement Markings | Thank you for your response to my initial question. As a follow up, tracing over the same day markings would typically only be done if there are center line rumbles on this project. For bidding purposes, can you please confirm that, on this project, the temporary epoxy item will in fact be re-traced with the regular epoxy item after paving even though there does not appear to be center line rumbles? In addition, what is the plan for the milled surface (paved within 24 hours) in terms of temporary markings? Thank you. | An emergency addendum was issued this morning to address this. | Mike Coleman | 2 | 2021-06-03 08:49 | 2021-06-07 08:17
20210608 | 20210608006 | 6 | Pavement Markings | Good afternoon, With the investment the department is making in placing contrast tape lane lines on this project, would it be prudent to also invest in grooved in wet reflective edge lines like similar projects of this stature? I believe there is something in the design manual advocating for such markings on a higher use/profile road. By getting the edge line markings below the surface as well, the department would have long lasting markings on the entire project. Will these markings be changed via addendum? | The statewide policy on multilane roadways is standard epoxy for the edgelines. We use the grooved in wet reflective epoxy for edgelines on two lane roadways. For this project, we will stay with the standard epoxy edgelines. | Mike Coleman | 1 | 2021-05-20 13:45 | 2021-05-24 06:45
20210608 | 20210608006 | 6 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-05-29 13:46 | 2021-06-01 10:55
20210608 | 20210608007 | 7 | DESIGN FILES | Can the Department provide the meta data files for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608007/ | Mike Coleman | 1 | 2021-05-25 15:52 | 2021-05-27 07:03
20210608 | 20210608007 | 7 | Railing Type W Rehab | Are there any plan details on what is required for rehab on the steel railing? | No details are required. The first General Note on the first structure plan sheet indicates the railing will be cleaned and painted. The third from last General Note describes the work required on the railing: â€˜Existing type â€˜Wâ€™ railing to be cleaned, rust removed from bolts and bottom of posts, tighten all bolts and seal post bases with non-staining gray non-bituminous joint sealer. Work is incidental to bid item â€˜Railing Steel Type â€˜Wâ€™; Rehabilitationâ€™. Finally, article/pay item SPV.0105.02, within the basis of payment section, provides additional details to bidders regarding the scope of work, including zinc coating/painting. | Mike Coleman | 2 | 2021-06-01 09:39 | 2021-06-03 08:13
20210608 | 20210608007 | 7 | Railing Painting | What color is the railing to be painted? Are we painting just posts and top channel or is the thrie rail painted as well? | The railing is be natural zinc in color per the Payment section of spec article #31, Railing Steel Type â€œWâ€ Rehabilitation, Item SPV.0105.02. All elements that comprise the Type â€˜Wâ€™ railing shall be rehabilitated and painted. Per Bridge Manual standard drawing 30.02, that includes the rail/thrie beam. | Mike Coleman | 3 | 2021-06-03 12:53 | 2021-06-03 14:14
20210608 | 20210608008 | 8 | paving | Will it be allowed to go from stage two to stage three with paving 4.5" of 3MT, run traffic on the binder till stage three is done and pave the 1.75" 4MT on the whole job with flaggers? Concern is lack of compaction on the second lift of 3MT on centerline, and also the possibility of damage to the 4MT on the inside lanes while stage three is constructed. Thank you | Yes, the region would allow that staging -- all binder paving first for the project, then surface work after the binder is complete with flaggers. | Mike Coleman | 1 | 2021-06-04 08:45 | 2021-06-07 10:52
20210608 | 20210608009 | 9 | Schedule of Items | Seems to be a discrepancy between what is shown in the Proposals Schedule of Items vs. the .EBSX file. Proposal Line Numbers 442 to 448. Bid Express shows 464 items while schedule of items only shows 460 items. | Bid Express shows the correct schedule of items. An addendum will be issued to correct the schedule of items in the proposal. | Mike Coleman | 1 | 2021-05-12 14:48 | 2021-05-18 09:06
20210608 | 20210608009 | 9 | Stage 1A Traffic Control for Bridge Widening B-55-12 | Should there be concrete barrier added to Stage 1A for the B-55-12 Temporary Widening Work to protect the work area? Currently this work as designed is to be completed with drums only protecting the work area in both the EB and WB directions. | Temporary concrete barrier will be added to Stage 1A per addendum. | Mike Coleman | 2 | 2021-05-26 14:16 | 2021-06-03 08:38
20210608 | 20210608009 | 9 | CTH NN Road Closure Durations | Per Article 4 of the Special Provisions, CTH NN closures will be allowed during removal of the center span of the existing bridges and during setting of beams and falsework for new structures. It appears that temporary shoring for the pier excavation and construction may be necessary to open CTH NN to through traffic but there isn't anything called out for shoring for the pier construction in the plans. Could the closure durations be extended to facilitate construction of the piers and, if necessary, maintain 12' width for emergency services on CTH NN through the work zone? This would be a safer, more cost effective option. Building the piers while CTH NN is open to through traffic would be costly and time consuming for schedule that is already tight. | This is being addressed in addendum 4 | Mike Coleman | 3 | 2021-05-26 15:27 | 2021-06-03 12:52
20210608 | 20210608009 | 9 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch & Select Crushed? | CY to Ton conversion factor: Base Aggregate Dense 3/4 Inch = 2.1 Base Aggregate Dense 1-1/4 Inch = 2.0 Select Crushed = 1.9 | Mike Coleman | 4 | 2021-06-01 15:30 | 2021-06-03 08:45
20210608 | 20210608009 | 9 | Federal Wage Rates | The Special Provisions for this project show that no federal funding is being used, however the Davis-Bacon wage rates are still included. Are federal wage rates required to be paid on this project? Thanks | The federal wage rates and federal requirements in the proposal were removed via addendum yesterday. | Mike Coleman | 5 | 2021-06-02 11:18 | 2021-06-03 08:48
20210608 | 20210608010 | 10 | QMP Density | QMP HMA Pavement Nuclear Density is not included in the special provisions. If the department wants the contractor to complete the testing this should be added. Thank you. | QMP HMA Pavement Density was added by addendum. | Mike Coleman | 1 | 2021-05-22 13:11 | 2021-06-04 05:45
20210608 | 20210608013 | 13 | Standard Detail Drawings for Sideroad signing | On page 48 of the plans, you are indicating the use of SDD Traffic Control, Advance Warning Signs 45 M.P.H or Greater Two-Way Undivided Road Open to Traffic for typical sideroad approach warning sign detail at every sidedroad. Is this correct? Or should it be the SDD Barricades and Signs for Sideroad Closures? | An addendum will be issued to change the sideroad signing to SDD 15C03 and adjust the quantities accordingly. | Mike Coleman | 1 | 2021-05-21 06:34 | 2021-05-24 06:50
20210608 | 20210608013 | 13 | Modular Block Wall Repair | Special No. 37 for SPV.0165.01 doesn't read like a wall repair special. It reads like a new wall. The plan states a block replacement. In one area of the wall detail it states that there is a coping, but another location on the same page states that the wall has caps. Does this wall have a coping? Also, does the Department have as-builts for this wall, R-22-7? Who is the original manufacturer? My assumption is that the contractor must match the existing wall system in order for the repair to function properly. Lastly, if the wall is an MSE wall and has geogrid, the means and methods, along with material needed, changes quite a bit. | Special No. 37 (SPV.0165.01) is accurate. There is no coping for this wall, only a cap. The coping label is incorrect. We do no know who the original manufacture is. Replaced wall components shall meet the special provisions and be dimensionally compatible with the existing wall system. Both walls are MSE with geogrid. Asbuilts for both walls can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608013/ | Mike Coleman | 2 | 2021-05-21 10:48 | 2021-05-26 09:27
20210608 | 20210608013 | 13 | R-22-52 Modular Wall | Can the Department provide the bottom of wall elevations for this wall? There are no wall height calculations or base block elevations given. Also, can the Department provide a bid item for Construction Staking for this wall? | We will add standard bid item 650.6500 for structure staking in an upcoming addendum. | Mike Coleman | 3 | 2021-05-21 10:54 | 2021-05-26 11:09
20210608 | 20210608013 | 13 | Traffic staging for B-22-617 | SPV #4 - Traffic indicates that STH 11 will be closed to through traffic and detoured until the major construction operations are completed including all structure repairs, culvert and beam-guard replacements, etc. However, plan sheet 161 shows the work on structure B-22-617 being completed in 2 stages with temporary barrier wall. Will the bridge be closed during construction or completed in stages? | The bridge, like the rest of the roadway will be closed to through traffic, but must remain open to local traffic, so it will be completed with staging. | Mike Coleman | 4 | 2021-06-01 12:55 | 2021-06-02 06:10
20210608 | 20210608013 | 13 | B-22-616 Temporary Shoring limits | Plan sheet 1 of 3 for Structure B-22-616 shows the cofferdam limits encircling the wing replacement area in the plan view. There is also a quantity of 720 sf of Temporary Shoring for this structure shown in the Total Estimated Quantities Table on Sheet 2 of 3. What are the pay limits for temporary shoring. | The horizontal pay limits of temporary shoring are outside of the stream along the cofferdam lines shown on the plans. Vertical pay limits is from the bottom of excavation to a maximum of one foot above the retained grade/streambed. | Mike Coleman | 5 | 2021-06-01 14:09 | 2021-06-04 05:38
20210608 | 20210608013 | 13 | Finish for Steel Plates for Culvert Joints | Is there are requirement for finish on the steel plates used for the culvert joint repairs or are they to be bare steel? | There are no finish requirements for the finish on the steel plates. They shall be bare steel. | Mike Coleman | 6 | 2021-06-02 15:11 | 2021-06-04 05:40
20210608 | 20210608013 | 13 | Temporary markings | Good afternoon. In looking at the temporary markings, the temporary paint item is self-explanatory, thank you. I am wondering what the plan is for temporary markings on the surface after paving but before the rumbles? There is a same day epoxy item that, presumably, will be installed after the center line rumble strips. On similar projects, there would be a temporary epoxy item applied to the surface prior to rumbles. Will this be addressed with an addendum or clarification? Thank you. | An emergency addendum will be issued to clarify. | Mike Coleman | 7 | 2021-06-02 15:51 | 2021-06-04 09:18
20210608 | 20210608013 | 13 | Bearing Repair Details | Please provide plan details of what is required for bearing repairs. Per existing bridge drawings there appears to be two anchor bolts in each abutment bearing plate centered on the short axis. Are the existing anchor bolts to be cut off and ground flush? Where are the new anchor bolts supposed to go? How many are required? What size shims are required? What material should shims be made from? | Existing anchor bolts are to be cut off and ground flush. New anchor bolts should be centered on the short axis with a 1 7/8â€ edge distance to the plate edge. Two bolts required per bearing. Shim size should be same as bearing size (15â€x12â€). Shim height varies from zero to ï¿½â€ and to be determined after cleaning the bearings. Shim material is ASTM A709 Grade 36. Field weld tip of girder flange to top plate of the bearing with ï¿½â€ fillet weld. Provide a 4 ï¿½â€ x 2 ï¿½â€ x 13/16â€ plate washer above bearing top plate at each anchor bolt. An emergency addendum will be issued to clarify. | Mike Coleman | 8 | 2021-06-02 15:52 | 2021-06-04 09:15
20210608 | 20210608013 | 13 | Interim Completion Date | Is any of the work at B-22-616, B-22-617, or C-22-1629/1630/1631 subject to the 8-30-21 interim completion date? | As per the special provisions, these structures are not subject to the interim completion date. | Mike Coleman | 9 | 2021-06-02 16:25 | 2021-06-04 05:41
20210608 | 20210608014 | 14 | Design Files | Can the Department provide the meta-data files for this project? |  |  | 1 | 2021-05-18 08:58
20210608 | 20210608014 | 14 | Asphalt mix question | Plan sheet 18 shows shoulder paving on Elmhurst highlighted as "B",which per sheet 15 is full depth 3MT. Is that correct? If not, and it should actually be highlighted "F", would the paving of the shoulder on I94 be "B" and not "F"? | this will be adjusted in an upcoming addendum. | Mike Coleman | 2 | 2021-05-24 12:53 | 2021-05-27 13:40
20210608 | 20210608014 | 14 | B-67-369 Excavation for Structure | Should there be a bid item for structure excavation for structure B-67-369? | The pay item will be added to the contract by addendum. | Mike Coleman | 3 | 2021-05-25 12:32 | 2021-05-26 11:07
20210608 | 20210608014 | 14 | B-67-369 Preboring Quantity/Clarification | Sheet 188 for B-67-369 calls for piling to be pre-bored to elevation 882.00. Bottom of abutment is located at 916.16. 916.16-882.00 = 34.16 LF of preboring for each pile, and 10 piles total. Why is plan quantity for this only 160 LF and not closer to 350 LF? |  |  | 4 | 2021-06-03 09:03
20210608 | 20210608015 | 15 | 72 Hour milling rule | Base on scope of work, which includes milling, widen shoulder, pave shoulder, and mainline, and as this a PWL job with a test strip, can the 72 hour language in the traffic section (page 2 of the specials) be changed to 96 hours and add the language that states â€˜unless due to weatherâ€™. | The 72-hr restriction for the milled surface will not be changed, as weâ€™ve experienced good success with this specification on similar projects. However, the intent is that the 72-hr rule applies unless due to weather. | Mike Coleman | 1 | 2021-05-27 15:51 | 2021-06-01 05:35
20210608 | 20210608017 | 17 | Design Schedule | Can the design schedule be provided? Thanks | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608017/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-05-25 13:10 | 2021-05-26 12:21
20210608 | 20210608017 | 17 | 643.1205.S Basic Queue Warning System | Hello, regarding the quantity of Flashing Beacon Signs in each direction of the Basic Queue Warning System, the Special Provisions for this item state that three FBS are needed in each direction. However, the Misc Qty tables show six FBS in each direction. The SDD notes on page 152 of the plans state to place FBS on both sides of the road if there are more than two lanes or if specified in the plans. Since this section of roadway is only two lanes, please clarify the quantity of FBS required for each direction as either three FBS placed on one side, or six FBS placed in three locations on both sides. Thanks | We had a discussion with Cara Abts, NC Region Traffic, and she verified that the quantities in the Misc Quan tables are correct. Cara is concerned that during various times, traffic backups could be substantial, and requested the following: Install Flashing Beacon Signs (FBS) in each direction, 6 in succession, all on the same side, prior to the transition from 2 lanes to one lane. For the 3 FBSâ€™s closest to the transition, use the spacing as indicated in the SDD 15D12-d (500â€™, 5,280â€™, 5,280â€™). For the additional 3 FBSâ€™s, space at 5,280â€™. | Mike Coleman | 2 | 2021-05-25 13:36 | 2021-05-27 07:06
20210608 | 20210608017 | 17 | 643.0500 / 643.0600 Flexible Tubular Markers & Bases | Hello, reviewing the Misc. Qty tables for Traffic Control, it appears that the quantity for Flexible Tubular Markers & Bases is doubled in some of the stages. In Stage 2A, there are 963 flex posts installed, and then again in Stage 2B another 963 posts are counted in the same spot. The posts installed in Stage 2A should remain through 2B, correct? The same scenario is presented in the quantities for Stages 4A/4B. Please review, thanks. | When considering construction timeframe constraints, along with anticipated construction production rates, we anticipate Stages 2A and 2B would not be constructed sequentially. Instead, these 2 stages would be separated by construction inactivity during late fall, winter, and early spring. Therefore, in Stage 2A during the fall of 2021, Flexible Tubular Markers & Bases would need to be installed, then removed prior to winter shutdown. They would then also need to be re-installed in the spring of 2022 in Stage 2B, then removed after completion of that stage. The same would hold true for Stages 4A and 4B, but these two stages are separated by mainline construction inactivity during the summer of 2022. | Mike Coleman | 3 | 2021-05-25 14:19 | 2021-05-27 07:09
20210608 | 20210608017 | 17 | 646.9000, 646.9100, 646.9200 Marking Removal Line | Hello, reviewing the Misc. Qty tables for Removing Pavement Markings, it appears that the quantities are doubled in some of the stages. In Stage 2A and 2B, the same amount of Pavement Marking removal is listed for each stage; but since the pavement markings are already removed in Stage 2A they shouldn't need to be removed again in Stage 2B, correct? The same scenario is presented in the quantities for Stages 4A/4B. Please review, thanks. | When considering construction timeframe constraints, along with anticipated construction production rates, we anticipate Stages 2A and 2B would not be constructed sequentially. Instead, these 2 stages would be separated by construction inactivity during late fall, winter, and early spring. Therefore, in Stage 2A during the fall of 2021, existing pavement markings that conflict with traffic control would need to be removed, then temporary markings installed for traffic control, then permanent markings installed on new roadway for stage 2A prior to winter shutdown. The same pavement marking removal would then also take place in the spring of 2022 in Stage 2B, then temporary markings installed for traffic control, then permanent pavement markings installed after completion of that stage. The same would hold true for Stages 4A and 4B, but these two stages are separated by mainline construction inactivity during the summer of 2022. | Mike Coleman | 4 | 2021-05-25 14:31 | 2021-05-27 07:09
20210608 | 20210608017 | 17 | 649.0105 Temporary Marking Line Paint | Hello, reviewing the Misc. Qty tables for Temporary Pavement Markings, it appears that the quantities are doubled in some of the stages. In Stage 2A and 2B, the same amount of Temporary Paint is listed for each stage; but since the pavement markings are already applied in Stage 2A they shouldn't need to be applied again in Stage 2B, correct? The same scenario is presented in the quantities for Stages 4A/4B. Please review, thanks. | When considering construction timeframe constraints, along with anticipated construction production rates, we anticipate Stages 2A and 2B would not be constructed sequentially. Instead, these 2 stages would be separated by construction inactivity during late fall, winter, and early spring. Therefore, in Stage 2A during the fall of 2021, existing pavement markings that conflict with traffic control would need to be removed, then temporary markings installed for traffic control, then permanent markings installed on new roadway for stage 2A prior to winter shutdown. The same pavement marking removal would then also take place in the spring of 2022 in Stage 2B, then temporary markings installed for traffic control, then permanent pavement markings installed after completion of that stage. The same would hold true for Stages 4A and 4B, but these two stages are separated by mainline construction inactivity during the summer of 2022. | Mike Coleman | 5 | 2021-05-25 14:34 | 2021-05-27 07:11
20210608 | 20210608017 | 17 | Temp Rumble Strips | Is there a manufacturer on the approved products list that supplies the 4" wide rumble strips. Do the rumble strips need to be set for every lane closure, including the weekly ones that will be pulled down for the weekend? Being the rumble strips need to be rolled down, the lane closure will need to start before them to be able to install in each lane by having to do one lane at a time and flip. Then tear that lane closure down to the start of the official lane closure, correct? | Regarding the manufacturer and specific product information, you may contact the Department representative Erin Schwark at 414-220-6803, or at erin.schwark@dot.wi.gov for product details. This information will be prepared in an Addendum document and distributed. If possible, we will provide the specific manufacturer and product information in the Addendum. Regarding the second part of the question, the rumble strips will be placed according to the Staging Plans. The plans show that temporary orange rumble strips are needed for the SB direction for Stages 2A and Stages 2B and for the NB direction for Stages 4A and 4B. They are not needed for the other stages. A temporary lane closure following SDDs will be needed to install the rumble strips, one lane at a time. The temporary lane closure would then be removed up to the start of the planned lane closure. | Mike Coleman | 6 | 2021-05-26 19:28 | 2021-05-28 07:36
20210608 | 20210608017 | 17 | Crossover paving | For the asphalt in the staging crossovers, on the plan they are calling them out for PWL Air Void. Can this be looked at to be changed to QMP testing as it will be the first paving on the project with not many tons to do a test strip and the asphalt may come from a different plant than the remainder of the 4MT | An addendum will be issued to correct this. | Mike Coleman | 7 | 2021-05-28 15:51 | 2021-06-03 06:45
20210608 | 20210608017 | 17 | 305.0125 Base Aggregate / CY Conversion Factor to Tonnage | What is the conversion factor for the Base Aggregate per Cubic Yard, Item 305.0125, that should be used for this project to convert the material to Tonnage? | Calculations for the quantities in the Miscellaneous Quantities tables and the estimate use 2.1 tons/cy for Item 305.0125. | Mike Coleman | 8 | 2021-06-05 09:44 | 2021-06-07 08:16
20210608 | 20210608020 | 20 | Project Schedule | Could the schedule developed during design be provided? | An addendum will be issued to increase the contract time for completion to a 50 working day contract. An updated time chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210608020/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. Deanna, please create a link in the NC Region Preliminary Plans Page for proposal #20. | Mike Coleman | 1 | 2021-05-12 11:14 | 2021-05-26 06:14
20210608 | 20210608020 | 20 | Project Timeframe | The working days on this project seem low compared to others of similar sized projects. With the size of project would the Department consider 50 working days? | Agree. The number of allowable working days will be increased to 50 days via addendum. | Mike Coleman | 2 | 2021-05-21 15:16 | 2021-05-26 06:16
20210608 | 20210608020 | 20 | Typical Section | New typical sections show a 4% shoulder on the outside 3â€™. Could this be milled and paved as a 2% shoulder? | The existing 3â€™ paved shoulders vary from a 2.5% cross slope to 4%. These can be milled and paved with mainline at 2% except in the three locations with existing beam guard (STA 144+00, 215+00, 225+00). This change will be included in addendum #1. | Mike Coleman | 3 | 2021-05-21 15:16 | 2021-05-27 07:07
20210608 | 20210608020 | 20 | Asphaltic Surface Patching | Is the quantity for asphaltic surface patching for the culvert patches? If not how are those paid and what is the asphaltic surface patching item for? | There is a construction detail shown on sheet 12 for the pavement at the culvert replacements. It shows 5â€ HMA pavement 4 LT 58-28 S at the culvert replacement locations. Asphaltic surface patching is to address areas where there may be isolated areas of pavement distress, that may develop after milling. | Mike Coleman | 4 | 2021-05-24 10:47 | 2021-05-26 06:25
20210608 | 20210608020 | 20 | Culvert Patches | The patching for the culverts is currently included under the 4LT58-28S pay item. Could this asphalt quantity be paid for under the Asphaltic Surface pay item? | Yes, if the culverts are constructed ahead of the final paving operation then both the lower and upper layers could be paid for as asphaltic surface. | Mike Coleman | 5 | 2021-05-24 11:12 | 2021-05-26 06:26
20210608 | 20210608020 | 20 | Asphaltic Surface Patching | The Asphaltic Surface Patching item includes 500 tons between stations 161+00 and 678+10. What does this 500 tons represent? | Asphaltic surface patching is to address areas where there may be isolated areas of pavement distress that may develop after milling. The pavement condition was reviewed during a field visit and determined the pavement from STA 152+00 (Riske Road) to STA 678+10 (end of the project) was in the worst condition with rutting and deterioration. Approximately 5% of the pavement will need to be repaired within this section of roadway which is how the asphaltic surface patching quantity was determined. | Mike Coleman | 6 | 2021-05-24 11:17 | 2021-05-27 07:26
20210608 | 20210608020 | 20 | Culvert Patches | The plans call for the culverts to be installed and patched prior to Removing Asphaltic Surface Milling. Will the department adjust the Asphaltic Surface quantity to reflect the tons of asphalt required to patch these culverts? | Plan quantity for asphaltic surface will not be adjusted for culvert replacement areas. | Mike Coleman | 7 | 2021-05-27 10:54 | 2021-06-03 07:18
20210608 | 20210608020 | 20 | Milling Item | Will the department consider adding an item for Distressed Milling to cover the removal of distressed areas that may develop after the initial milling is completed? | No. Additional milling required in these locations will be paid as 204.0120, Removing Asphaltic Surface Milling. | Mike Coleman | 8 | 2021-05-27 10:58 | 2021-06-02 07:22
20210608 | 20210608021 | 21 | Typical Finished Sections | on the typical finished sections it appears to have the 11' lane at 2% normal crown and the 1' paved shoulder. Is this correct or is the entire 12' of HMA suppose to be at 2% | All pavement (both the travel lanes and the 1' paved shoulder) should be placed at 2% or follow super elevation transitions. The 4% portion of the shoulder is for the base aggregate portion only. | Mike Coleman | 1 | 2021-05-26 14:03 | 2021-05-27 07:37
20210608 | 20210608021 | 21 | PWL Density | THis project has many different sections where either the NB or SB lane is going in and out of thickness from 2" to 3". This should be re-evaluated to QMP density, as we will need 2 test strips, 2 pay sheets that will be hard to keep straight, and 2 correction factors changing throughout the day | PWL requirements are being removed via addendum. | Mike Coleman | 2 | 2021-05-26 14:16 | 2021-06-01 10:42
20210608 | 20210608021 | 21 | typical section | sta 232+63 - 377+45 LT show pavement with a 11' lane and a 1' paved shoulder 2'' thick, they also show in that station range on the LT side a 12' lane 3'' thick without a paved shoulder. Which one is it? | As part of this project, 24 feet of pavement will be placed (12-ft RT and LT of centerline) in the station range noted below. This will be painted as an 11-foot lane with a 1-foot paved shoulder. | Mike Coleman | 3 | 2021-06-01 13:22 | 2021-06-03 08:12
20210608 | 20210608021 | 21 | Superelevation | The Super tables on sheet 10 do not match existing crosslopes, in some areas the super tables are 4.5% different than existing which is roughly 6", is the intention to build the crosslope to match tables or are we strictly milling and paving depth? | The intent of this project is to match existing superelevations. | Mike Coleman | 4 | 2021-06-03 13:35 | 2021-06-04 05:37
20210608 | 20210608022 | 22 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch & Select Crushed? | We used the following conversion factors for the items requested: Select Crushed used a factor of 1.9 tons/CY Base Aggregate Dense ï¿½-Inch used a factor of 2.2 tons/CY Base Aggregate Dense 1 ï¿½-Inch used a factor of 2.1 tons/CY | Mike Coleman | 1 | 2021-06-01 15:31 | 2021-06-03 07:32
20210608 | 20210608022 | 22 | Minimum Waterway opening required for temporary structure | What is minimum waterway opening requirement for the temporary structure? | Information for the minimum waterway opening can be found on sheet 146 or 162, the General Plans for B-55-262/263. The minimum opening should accommodate the criteria listed under the 5 Year Frequency on the right side of the sheet. | Mike Coleman | 2 | 2021-06-01 15:34 | 2021-06-03 08:11
20210608 | 20210608023 | 23 | Hot Mix Types | Can the 5 MT mix be used in lieu of SMA for the surface course of all ancillary paving. The HMA mixture acceptance table has the surface for sideroads, Beam Guard widenings, and Bypass and turn lanes being surfaced with 4SMA. We feel that SMA is not workable enough for doing intersections and tapers. It is difficult to trim with hand tools and may need to be sawcut after placement. | After discussion with Region PDS and Pavementsâ€¦â€¦.. â€¢ WisDOT will accommodate this request. We will be issuing an addendum to address the quantity and plan changes. | Mike Coleman | 1 | 2021-06-02 06:30 | 2021-06-03 08:14
20210608 | 20210608023 | 23 | Addenda | There are 2 addenda showing up on the DOT website however Bid express only shows 1? |  |  | 2 | 2021-06-07 14:22
20210608 | 20210608024 | 24 | QMP Density | QMP HMA Pavement Nuclear Density is not included in the special provisions. If the department wants the contractor to complete the density testing this should be added. Thank you. | An Addendum will be issued to add QMP Nuclear Density and Incentive Density into the contract. | Mike Coleman | 1 | 2021-05-22 13:14 | 2021-05-24 11:55