## qandasearchletting_results
Date: | 2022-07-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20220712 | 20220712001 | 1 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | USH 12 in this location is a divided US Highway and Class III-A and Class III-B pipe is not allowed on Interstate Highways or Divided US Highway unless for temporary use or at maintenance crossovers in the median. In addition the City of Madison is contributing over 50% of the cost of storm sewer and has elected for the use of concrete pipe. Roadways under the jurisdiction of Dane County will be evaluated for the use of Class III-A or Class III-B pipe and an addenda will be issued as appropriate. Only pipes changed by addenda can be bid with the corresponding bid items for SSP Class IIIA and/or IIIB pipe. | Mike Coleman | 1 | 2022-06-10 10:40 | 2022-06-16 12:23
20220712 | 20220712001 | 1 | Soil Borings | Are soil borings available for this project? | The soil borings can be found at the following location: https://wisdot.box.com/s/ggsv7esg7hj1z8tvimqgm6nwfarsc8ix or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 2 | 2022-06-13 14:43 | 2022-06-15 13:04
20220712 | 20220712001 | 1 | MAAHIC WAY SURCHARGE | From station 454+50 to 459+50 it is shown that the embankment (fill) will be built using granular backfill grade 2 material. Was the quantity of fill in the station to station listing deducted for this area so the fill is not doubled up with grade 2 quantity? Is the 6,900 CY of grade 2 listed the miscellaneous quantities (pg 495) an expanded number? If so at what factor? | Yes, the volume of fill material was subtracted out from the station range (454+50 â€“ 459+50). The quantity listed in the miscellaneous quantities is not expanded but the in-place volume. This item is measured by the department in the final position. | Mike Coleman | 3 | 2022-06-14 11:10 | 2022-06-16 06:05
20220712 | 20220712001 | 1 | EBS BACKFILL | What is the EBS excavation to be backfilled with? It states different materials that EBS can be backfilled with in different parts of the plan. Please clarify what will be allowed. | The EBS within the surcharge earth embankment area on Maahic Way will be replaced with select crushed material according to the construction detail. The EBS at the retaining walls will be replaced with backfill granular grade 2 according to the construction detail. The EBS at the remaining roadway areas along Maahic Way, Millpond Road, Ramp A, and Ramp C will be replaced with suitable fill material per the construction detail. | Mike Coleman | 4 | 2022-06-14 11:12 | 2022-06-16 06:06
20220712 | 20220712001 | 1 | POND LINER CLAY | Is the clay liner quantity an expanded number? Will the clay liner be paid for / measured in its final position? | The pond clay liner quantity is the in-place volume. The pond clay liner will be paid for in its final position. | Mike Coleman | 5 | 2022-06-14 11:13 | 2022-06-16 06:06
20220712 | 20220712001 | 1 | MILLPOND INFIELD OPTIONAL WASTE SITE | Will DOT consider letting contractors raise the height from what is shown in the cross sections max. elevation? There should be no concerns for visual barriers. DOT should allow this to have the most competitive bid and have the biggest cost savings for the tax payers. | An addendum will be issued to adjust the elevation slightly, however, the intent is to maintain the maximum elevation shown in the contract documents. | Mike Coleman | 6 | 2022-06-14 11:24 | 2022-06-15 12:30
20220712 | 20220712001 | 1 | OPTIONAL WASTE SITE | Will EBS and marsh material be allowed to be placed in this waste area? The special provision states to follow standard spec 207 which would allow these materials to be placed outside the roadway foundation. We are assuming this is not a roadway foundation and would be allowed. I this accurate? | Correct, the optional waste site is not a roadway foundation and therefore, materials listed in standard spec 207 can be placed. | Mike Coleman | 7 | 2022-06-15 08:49 | 2022-06-21 06:39
20220712 | 20220712001 | 1 | SPECIAL PROVISION # 33 FUTURE FREE FLOW BYPASS LANE | Where exactly is this lane potentially being constructed? It seems to be described to be from the roadways 1:1â€™s to the slope intercept. Could this be depicted somehow on a plan view? | The lane may be constructed at a future date within the station range provided in the SPV. There is no reason to show this on the plans at this time. Simply follow the SPV as written. | Mike Coleman | 8 | 2022-06-15 08:50 | 2022-06-21 06:40
20220712 | 20220712001 | 1 | S.P. # 32 | Per special provision # 32 please make all groundwater monitoring data, geotechnical reports and any soil testing reports available for review. The WisDOT soils contact was contacted and he stated all documents should of already been available. | The soil borings can be found at the following location: https://wisdot.box.com/s/ggsv7esg7hj1z8tvimqgm6nwfarsc8ix or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 9 | 2022-06-15 11:42 | 2022-06-15 13:11
20220712 | 20220712001 | 1 | SP # 49 GENERAL PROVISIONS FOR CITY OF MADISON STORM SEWER | In paragraph 6 it states all structures to be only precast or cast in place concrete masonry options. Then in paragraph 8 it states bid all structures as field poured and construct all structures as field poured unless the contractor receives approval of the City of Madison designer. Please clarify what will and will not be allowed as this is contradicting. From what is stated in this special provision the City of Madison will not approve precast structures until after ULOâ€™s have been completed that could affect the structures. That would mean that the City of Madison will not approve precast structures until after the award of the contract, correct? Secondly, I am assuming that item numbers 736, 738, 740, 742 are all the cast in place structure items that correlate with the city of Madisonâ€™s above spec and would be the structures that would need to be bid as cast in place? All the other regular structure items (item numbers 374, 376, 378, 380, 382, 384) would be able to be bid as â€œnormalâ€ DOT storm sewer structure item and could be precast structures? Lastly, are the pond outlet structures (item numbers 748, 750, 752 758) able to be precast or must they be cast in place also? | Language in Special Provisions Article 49, paragraph 6 will be revised in Addendum 01 to read â€œConstruct catch basins, manholes and inlets using the cast in place concrete masonry option. All structures shall be reinforced concrete. Concrete brick and block options are prohibited.â€ Article 49, General Provisions for City of Madison Storm Sewer states that all the storm sewer provisions apply to all storm sewer work within Millpond Road and Maahic Way. This includes Item numbers 736, 738, 740, and 742 which are bid as field poured. All other standard WisDOT storm sewer structures not located within Millpond Road and Maahic Way would follow the current WisDOT Standard Specifications. Outlet control structures for Ponds A and B are to follow the General Provisions for City of Madison Storm Sewer and be bid as cast-in-place. The SPVâ€™s for Outlet Control Structure Pond A and Pond B will be updated in Addendum 01 to reflect this. Follow SPVâ€™s Outlet Control Structure Pond C and Pond D for the outlet structures in ponds C and D. | Mike Coleman | 10 | 2022-06-17 08:34 | 2022-06-22 11:55
20220712 | 20220712001 | 1 | Dewatering Items for Ponds / Project | What is DOTâ€™s expectations for final disposal of treated water for the ponds as well as other dewatering operations. Are we allowed to discharge treated water off the project onto adjacent lands? Specifically, Pond A has a lot of water to the south of the existing / proposed pond. This is where the water ultimately ends up. Can contractors discharge treated water into the existing ditch directly adjacent and south of the proposed pond. Or is there another thought / process DOT is envisioning for dewatering the ponds. | As always, the contractorâ€™s dewatering operations will be approved through the DOT and DNR ECIP approval process. | Mike Coleman | 11 | 2022-06-20 11:40 | 2022-06-21 06:41
20220712 | 20220712001 | 1 | Field Office | Is the field office location to be a 3 mile radius from IH 39 and USH 12 interchange or is it 3 miles by roads? | The field office location is to be within a 3-mile radius. | Mike Coleman | 12 | 2022-06-20 14:01 | 2022-06-22 08:07
20220712 | 20220712001 | 1 | Sewer & Water Materials | Given the current market supply and long lead times for sewer and watermain materials as specified, would the department consider alternate materials? If so, could the department provide specifications of alternate materials? | No, the department is not willing to consider alternate materials. | Fred Schunke | 13 | 2022-06-24 08:54 | 2022-06-30 12:14
20220712 | 20220712001 | 1 | Orifice Plate Restrictor 6" | Specials state install steel weir plate restrictor, plans state plug hole with PVC plug. What does DOT want an orifice plate restrictor or plug? Advise with detail showing what is wanted. | On the plan sheets 41 and 45 showing the construction grading details for Pond D, it shows an orifice plate on the west 12-inch RCP pipe and PVC plug on the east outlet control structure. Both of these items are needed. Article 134, will be revised with Addendum 02 to include PVC plugs in addition to PVC pipe and fittings. | Fred Schunke | 14 | 2022-06-24 10:44 | 2022-06-29 14:41
20220712 | 20220712001 | 1 | Earthwork Data | Can the Earthwork Data as presented in the plans be uploaded into an Excel file? | The earthwork data in 30800140-EWK-US-12&18.xlsx and 30800140-EWK-CTH-AB-All.xlsx can be found at the following location: https://wisdot.box.com/s/ggsv7esg7hj1z8tvimqgm6nwfarsc8ix or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Fred Schunke | 15 | 2022-06-27 10:41 | 2022-06-28 11:28
20220712 | 20220712001 | 1 | Special #34 - Marsh Excavation - Around a High Pressure Gas Main | Can a special line item be created to handle this work by the LF of Gas Line excavated and backfilled within this Marsh excavation section vs being incidental to the Marsh Excavation Item. If the Marsh Ex bid item does up or down, this effects the blended unit price causing the DOT or contractor harm or good depending what way the quantity goes. Plus this work will over inflate the average unit prices of Marsh Excavation. This work is non-traditional work on a project and it should not be buried within another item of work. | A separate bid item for excavation near high-pressure gas main will be created and provided in addendum 02. | Fred Schunke | 16 | 2022-06-27 12:44 | 2022-06-29 09:07
20220712 | 20220712001 | 1 | Availability of Pipe Materials | We have been informed that the next production date for hydrants and valves is 11/18/23. How are we to bid this project given the unavailability of materials this fall and how will this impact the overall schedule as far as timing and liquidated damages? | Bid the project as advertised. | Fred Schunke | 17 | 2022-06-27 17:24 | 2022-07-01 09:12
20220712 | 20220712001 | 1 | Phasing of project | The special provision for Stage 2A is approximately 30 days with a significant quantity of sewer and water to install. It looks like some of this work could continue into Phase 2B, what is the intent of this condensed schedule given the layout of the utilities and staging of work? | The estimated start and completion dates listed for each stage in Article 3 â€“ Prosecution and Progress â€“ Stage Construction, will be removed from the specials. These are dates that were considered when estimating the project schedule and are not typically provided. Itâ€™s up to the contractor to come up with their own schedule, while still meeting any required completion dates as listed in the contract documents. | Fred Schunke | 18 | 2022-06-27 17:29 | 2022-06-29 14:40
20220712 | 20220712001 | 1 | Article 3. Prosecution and Progress. Winter Shutdown. Page 10 of 139 | Should the first sentence say "...the completion of Stage 1 in the Fall of 2022...", rather than "Stage 2"? Stage 2 does not begin until Mid-March 2023. | Yes, the first sentence in Article 3 â€“ Prosecution and Progress â€“ Stage Construction â€“ Winter Shutdown, should say â€œâ€¦the completion of Stage 1 in the Fall of 2022.â€ This will be corrected with addendum 02. | Fred Schunke | 19 | 2022-06-28 08:17 | 2022-06-29 14:40
20220712 | 20220712001 | 1 | B-13-893 pier column detail | The plan shows the column footing dowels for the pier P1004's, as a full length bar extending all the way into the pier cap. Can this bar be fabricated in 2 pieces and lapped instead with a shorter protrusion from the footings? This is more typical bar detail on these columns and much easier to construct. | No, the column footing dowels for the pier P1004â€™s cannot be fabricated in 2 pieces and lapped. BOS typically omits the vertical footing-to-column reinforcement lap and extends the reinforcement continuously through the column into the cap if the lap length exceeds half of the column height. The bar lap required for the coated #10 vertical column reinforcement in the B-13-893 pier columns would be 8â€™-8â€ minimum. The columns are 15â€™-6â€ tall so the laps were eliminated to reduce congestion in the column reinforcement, and because the laps would not result in a significant reduction in the required protrusion of column reinforcement from the footings. | Fred Schunke | 20 | 2022-06-29 09:20 | 2022-06-30 12:19
20220712 | 20220712001 | 1 | Field Office | We have had a commercial real estate broker do a search of all available office space that would meet the requirements. There is a couple available that meet the requirements besides the 20 ft x 20 ft meeting room. The closest found has a 16ft x 21ft meeting room. Since the Field Facilities (#59) specs are unattainable will DOT be ok with the smaller meeting room? Please advise. | Bid the project as advertised. | Mike Coleman | 21 | 2022-06-29 11:25 | 2022-07-05 13:41
20220712 | 20220712001 | 1 | SPV 33 - Future Free Flow Bypass Lane | Based on the description in SPV 33 for the Future Free Flow Bypass lane it appears a lane will be added through the optional waste site along an unknown alignment sometime in the future. SPV 33 also states suitable embankment material must be placed in this area. SPV 35 - Optional Waste Site refers to spec 207 Embankment which says unstable embankment materials can be used outside the roadway foundation. These are conflicting specifications. Without knowing where the Future Free Flow Bypass Lane is going we can not determine where suitable embankment materials are to be placed and where unstable materials are to be placed in the optional waste area. Please advise if we can place unstable embankment materials in the optional waste site and where unstable materials can go. | Unstable embankment materials can be placed within a portion of the optional waste site per standard spec 207. We will define the limits of where the unstable materials can be placed within the site via an addendum. | Fred Schunke | 22 | 2022-07-01 07:16 | 2022-07-01 13:07
20220712 | 20220712001 | 1 | Drainage Tables in xls Format | Can the drainage tables for storm sewer be provided in Microsoft excel format? | The drainage tables can be found at the following location: https://wisdot.box.com/s/ggsv7esg7hj1z8tvimqgm6nwfarsc8ixor can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 23 | 2022-07-05 10:40 | 2022-07-06 06:35
20220712 | 20220712001 | 1 | Design Conversion Factors (tons/cy) | What are the design conversion factors used (tons/cy) for these item of work: Base Aggregate Dense 3/4", Base Aggregate Dense 1-1/4", Base Aggregate Dense 3-Inch and Select Crushed Material? | Design conversion factors are as follows (Tons/CY): Base Aggregate Dense 3/4" â€“ 2.1 Base Aggregate Dense 1-1/4" â€“ 2.0 Base Aggregate Dense 3-Inch â€“ 2.2 Select Crushed Material â€“ 1.9 | Mike Coleman | 24 | 2022-07-05 13:02 | 2022-07-06 06:36
20220712 | 20220712001 | 1 | CIP Structures | Please provide detail drawings of the CIP structures required by the City of Madison specifications and included in the plans and proposal. Section 49 changes to paragraph 6 does not allow for pre-cast structures, paragraph 8 allows pre-cast structures based on ULO data and shop drawings approved by City of Madison engineer. These two paragraphs are now in conflict. The original language paragraph 6 allowed pre-cast structures as long as you met the requirements of paragraph 8. Now this pre-cast option doesnâ€™t exist or is otherwise a gray area. | Bid the project as advertised. Paragraph 8 of Article 49 lays out the requirements for precast structures. | Mike Coleman | 25 | 2022-07-05 18:20 | 2022-07-06 08:49
20220712 | 20220712001 | 1 | Casing Pipe 24-Inch, Item SPV.0090.53 | Special Provision item #129.A indicates the 24 inch casing pipe to be Class V RCP and 129.C.2 indicates the casing pipe is to be install by traditional open cut methods. However, the City of Madison Standard Specification section 704.5 allows steel casing pipe installed by bore and jack methods. Is it safe to assume that we can bid the project per City of Madison specifications? | An addenda will be issued to allow steel casing pipe installation by bore and jack methods | Mike Coleman | 26 | 2022-07-06 12:20 | 2022-07-07 14:57
20220712 | 20220712001 | 1 | Geotextile Type SR | The Geotextile Type SR has a conflicting specification. The tensile strength indicates a high strength woven. However, all of the other parts of the specification is an 8 ounce nonwoven geotextile. I'm curious if the Tensile required test ASTM D4595 was a typo. If not it should be noted that the hydraulic properties will need to be adjusted for a high strength woven geotextile, there are no products made that can meet those as they are written for a high strength woven. Any clarification is appreciated. Thank You | The geotextile type R was revised in an addendum that was issued yesterday. | Mike Coleman | 27 | 2022-07-07 16:47 | 2022-07-08 09:11
20220712 | 20220712001 | 1 | Federal Wage Rate Posted - Operators | The Federal Wage Rate posted for the month of July Lettings appear to have Area 1 Operator wage rates as opposed to Highway Heavy Rates, I assume out of error. Please advise if this is correct. |  |  | 28 | 2022-07-08 12:40