## qandasearchletting_results
Date: | 2023-04-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230411 | 20230411002 | 2 | Common Excavation | Please provide the earthwork data station to station sheets. I believe the common excavation quantity is incorrect given the information provided in the earthwork summary. I believe the common excavation quantity should be 34670 CY. If true please revise bid quantity. | The common excavation quantity is incorrect. The correct quantity should be 34,670 CY. An updated earthwork summary table and earthwork data sheets will be updated/added via an addendum to reflect the updated quantity. | Mike Coleman | 1 | 2023-03-17 10:04 | 2023-03-31 07:46
20230411 | 20230411003 | 3 | SPV.0060.36 | Specifications for the Aluminum and Glass Curtain Walls indicate Kawneer 1620 UT or equal but drawings indicate 1-hour rated fire-rated system throughout. Please confirm if rated system is required and if so provide BOD specifications. | Aluminum and Glass Curtain Walls are not required to be fire-rated. This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2023-03-20 15:26 | 2023-03-27 07:56
20230411 | 20230411003 | 3 | Elevator Spec Questions | -On page 64 under Product Data, bullet point 7, it states that â€œall proprietary equipment shall be clearly identifiedâ€¦â€, but under section B.3, line item 2, it states that â€œElevator Equipment shall be third part, non-proprietary in natureâ€. Which takes priority? -Under section B.3.2 (page 70) the spec states that Toe Guards are to be 16-gauge steel. However, in section B.3.10 (page 73) under the Platform section, bullet point 4, it states the toe guard is to be 14-gauge stainless steel. Which takes priority? -On page 74 under Door Operator Equipment, the spec calls for a GAL MOVFR-HSL door operator. In discussions with GAL they say there is no such door operator with that model name that they manufacture. Can you ask the proper individual to clarify exactly what GAL model they are seeking? -On page 77, are they certain they want Simplex selective collective operation and not duplex? | 1. Non-proprietary equipment shall be provided. This will be addressed in an upcoming addendum. 2. 16 gauge is acceptable. This will be addressed in an upcoming addendum. 3. The waterproof GAL MOVFR model is required; model MOVFRW II or approved equal. This will be addressed in an upcoming addendum. 4. Provide duplex operation but with hall fixtures remaining at each elevator landing. Hall lantern shall illuminate/chime prior to the car arriving at the landing. This will be addressed in an upcoming addendum. | Mike Coleman | 2 | 2023-03-22 11:48 | 2023-03-27 07:58
20230411 | 20230411003 | 3 | Elevator Spec Questions Part 2 | -Under section B.3.15 (page 78), is there a specific reason they want a PLC-based controller? PLC based controllers are not as common these days, and are easily 4-5x the cost and currently have a 1 year leadtime for manufacture. -On page 81 under Traveling Cables, the spec calls for hoistway junction boxes under bullet points 7, 8, and 9. Then, bullet point 12 negates that and states all wiring will be direct with no hoistway junction box. Which takes priority? Also, bullet point 5 calls for four (4) Cat 5 twisted shielded pairs for security and telephone systems. Can you clarify if they are simply asking for four (4) twisted shielded pair? Cat 5 wiring is not available in traveling cables in the US. | 1. Microprocessor-based controllers are acceptable provided all other contract requirements are met, including information on spare circuit boards (see A.10 bullet 3, among others). This will be addressed in an upcoming addendum. 2. Provide hoistway junction boxes. Bullet point 12 does not apply. Twisted, shielded pairs are sufficient. This will be addressed in an upcoming addendum. | Mike Coleman | 3 | 2023-03-22 11:49 | 2023-03-29 11:35
20230411 | 20230411003 | 3 | curtainwall elevations | curtainwall elevations notes on sheets 130, 131 and 132 stating â€œ1-hour fire-resistance-rated curtainwall assemblyâ€ as there is no specification for any rated curtainwall system and all CW details are for standard non-rated curtainwall assemblies. Can you have the architect clarify or provide an approved product and specification if required? | Aluminum and Glass Curtain Walls are not required to be fire-rated. This will be addressed in an upcoming addendum. | Mike Coleman | 4 | 2023-03-23 13:35 | 2023-03-27 07:58
20230411 | 20230411003 | 3 | Flagging Reimbursement | Railroad Flagging reimbursement clarification : The bid amount of $285,660 for item 801.0117 by specification shall be reimbursed at a rate of 50% of expenditure. I.E. Contract spends $571,320 in flagging they would get $285,660 back from the reimbursements. If the total for flagging exceeds $571,320 will the reimbursement about increase proportionally or is that a maximum. | Railroad Flagging is reimbursed at 50% of the actual invoiced cost under item 801.0117, regardless of whether that ends up above or below the estimated bid quantity. | Mike Coleman | 5 | 2023-03-23 13:36 | 2023-03-27 07:59
20230411 | 20230411003 | 3 | Rough Carpentry | SPV 0060.27 Rough Carpentry, A.5 Preconstruction testing calls for contractor engage a testing agency for mockup testing, C.2.9 Field quality control B. calls for owner to engage testing agency for air leakage. In SPV.0060.29 Other architectural work A.3.8 call for owner to engage a testing agency for mockup testing and in C.2.4 calls for owner to engage testing agency. Please confirm owner will engage the testing agency for all air barrier, leakage, smoke and water tightness testing and section A.5. in rough carpentry is false. | All testing required in SPV 0060.27 and SPV 0060.29 shall be arranged and engaged by Contractor. This will be addressed in an upcoming addendum. | Mike Coleman | 6 | 2023-03-23 13:36 | 2023-03-29 08:30
20230411 | 20230411003 | 3 | Airport Low Voltage | 1) All cameras that are connected with fiber will need to be powered and we canâ€™t send power over the fiber. The drawings donâ€™t call for any power for these. Are we to provide power to all cameras? If so please provide details. 2) Am I to include fiber SFP modules, media converters and midspans for the cameras? 3) If we are to integrate the cameras into the owners existing system, I need to know what VMS they are using, and how many frames per second they require for recording. Can you provide this information? What compression do they use? How many days do they need stored before overwrite? Record on motion or 24/7? 4) Are spare copper and fiber cables to be terminated or left dark and untested? | 1. Agreed. The cameras fed by fiber will require power in order to function. The data will be fed by fiber, which will be converted into copper (to be read by the camera). Power shall be provided to the media converter and to the camera. Alternatively, the media converter may have an POE (Power Over Ethernet) power output, which would eliminate the need for a second power feed to the cameras. The remaining cameras located less than 300 ft (approx. 100 meters) may be powered by POE, eliminating the need for a power source. A suggested switch in the spec (Section B.4.9.B.1 â€“ â€œCisco Catalyst 9300 or approved equalâ€) is a POE switch. 2. For only cameras exceeding 300 ft in conduit run, SFP modules and media converters shall be included. Midspan may be used, but not required for this design. 3. The existing VMS system is Cognyte. Provide 24/7 recording, frame recording up to 30 frames per second, MJPEG compression type, and a minimum of 30 days of storage. 4. The spares are left dark, but tested. This is to minimize the â€œdowntimeâ€ of the equipment. | Mike Coleman | 7 | 2023-03-24 10:42 | 2023-04-04 06:37
20230411 | 20230411003 | 3 | Flagging | Should it be assumed that all exterior work taking place on the bridge after set in place will require flagging? | Flagging requirements are established by the railroad and captured in Article 9, Railroad Insurance and Coordination â€“ Soo Line Railroad Company (CP), of the special provisions. Brian Osborne (contact information in proposal) with CPRR may be able to clarify work operations that will/will not require flagging. | Mike Coleman | 8 | 2023-03-27 08:05 | 2023-03-27 08:06
20230411 | 20230411003 | 3 | Elevator Specs | Will there be updates to the elevator specifications issued via addendum? | Any updates to elevator specifications would be issued via addendum. | Mike Coleman | 9 | 2023-03-27 08:07 | 2023-03-27 08:07
20230411 | 20230411003 | 3 | RR Shoring | 2400 SF of RR shoring is noted in the bid items. Where is it shown on the drawings? | RR Shoring is represented on sheets 6 and 7 of the plans. | Mike Coleman | 10 | 2023-03-27 08:09 | 2023-03-27 08:10
20230411 | 20230411003 | 3 | Plan Holder List | Is a plan holder list available? | Plan Holder list is available on the departments HCCI website: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2023/20230411.aspx | Mike Coleman | 11 | 2023-03-27 08:11 | 2023-03-27 08:13
20230411 | 20230411003 | 3 | Flagging Costs | Is the particular unit item the â€œrestâ€ of the railroad flagging cost should be allocated, or just sprinkled among the rest of the bid items? | Flagging costs are reimbursed consistent with Article 9, Railroad Insurance and Coordination â€“ Soo Line Railroad Company (CP), of the special provisions. Extent of flagging necessary is based on means and methods and requirements of the railroad. It is up to the contractor to determine and allocate flagging costs. | Mike Coleman | 12 | 2023-03-27 08:15 | 2023-03-27 08:15
20230411 | 20230411003 | 3 | Prequalifications | Will subcontractors need to be prequalified? | No, subcontractors do not need to be prequalified. | Mike Coleman | 13 | 2023-03-27 08:17 | 2023-03-27 08:17
20230411 | 20230411003 | 3 | testing agency clarification | Could the engineer please clarify prior to bid who is paying for the testing agency for building envelope. SPV 0060.23 and air barrier have it called for in field quality as by contractor but in quality control by owner? | This specification will be updated in an upcoming addendum. Quality control will be performed by contractor. | Mike Coleman | 14 | 2023-03-27 08:19 | 2023-03-27 08:20
20230411 | 20230411003 | 3 | Field Observation/testing | Is field observation/testing by the contractors/subcontractors? Concrete testing for example. | Concrete testing requirements are identified in Section 715 QMP Concrete Pavement and Structures of the standard specification. The contractor performs and coordinates all Qc testing. The department coordinates only verification testing. | Mike Coleman | 15 | 2023-03-27 08:21 | 2023-03-27 08:22
20230411 | 20230411003 | 3 | Pre-bid Meeting recording and attendance record | Will this recording of the pre bid meeting and attendance listing be available for reference at a later date? | The Pre-Bid Meeting Recording and attendance record can be found at the following location: https://wisdot.box.com/s/450fhdykczcr35fd42ygw4mpdlhqply4 or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 16 | 2023-03-27 08:23 | 2023-03-27 08:26
20230411 | 20230411003 | 3 | Schindler Elevator | Can Schindler be added to the list of approved manufacturers for the elevators? | No additional manufacturers will be added to this specification. All manufacturers listed or approved equal must meet the non-proprietary requirements of the article for Traction Elevators, Item SPV.0060.06. | Mike Coleman | 17 | 2023-03-27 09:53 | 2023-04-03 11:07
20230411 | 20230411003 | 3 | CCTV question | For the CCTV we are looking for clarification on what the manufacturer of the current headend system (VMS) is? The project documents state that the contractor is responsible for connection to existing camera system but does not specify the make of this system. | The existing VMS system is Cognyte. | Mike Coleman | 18 | 2023-03-27 09:55 | 2023-04-04 06:38
20230411 | 20230411003 | 3 | Drywall Questions | Interior partition types on G-010 say see schedule. Schedule on G-012 shows 3-5/8â€ walls. Should we assume that and full height to deck everywhere except figure 4â€ shaft walls around elevators? And regular batt insulation in interior walls? Make assumptions on interior drywall ceilings heights and light cove details based on elevations on A-301 and A-302? But what about heights of hard lids in Electrical rooms, Janitors closets and other rooms? Exterior soffits like on 1/A-512. Assume that goes all the way around the building and ties into a 3-5/8â€ wall above the 6â€ structural? On 2-A-510 is that a typical exterior wall detail for termination at each floor level with exterior wall hitting I beam then resting on it again on next floor? Is structural framing needed for metal panel ceiling under pedestrian bridge as shown on details 1and 2 on A-522? | 1. Provide 3-5/8â€ interior walls and 4â€ shaft walls. Provide batt insulation in interior walls. 2. The ceiling heights are as follow: Vestibules: 21â€™-3â€ AFF. (east and west towers) Passage: 8â€™-10â€ AFF. Electrical Rooms: 9â€™-0 AFF. (east and west towers) Janitor Closet.: 9â€™-0 AFF. (east and west towers) ATS Room.: 8â€™-9â€ AFF. (east tower) Storage Room.: 9â€™-0 3/8â€ (west tower) 3. The exterior soffit shown on 1/A-512 goes all the way around the building and ties into a 3-5/8â€ metal stud above the 7-3/8â€ wall. 4. Provide steel plates connected to top and bottom of structural beams to provide support for the stud wall construction (typical). Size, thickness, and quantity to be determined by contractor to carry all associated loads. 5. The metal panel ceiling requires a contractor designed support system to comply with performance structural requirements for Exterior Metal Panels specification. This was addressed in an addendum. | Mike Coleman | 19 | 2023-04-03 09:15 | 2023-04-07 09:10
20230411 | 20230411003 | 3 | STH 119 Traffic Closures | Please confirm traffic closures on STH 119 to access the west side of the project can be left in place as needed for construction and will not need to be set up / taken down at the beginning and end of each work day. | STH 119 lane closures can remain in place for consecutive days to construct the West Access Road or during the use of the West Access Road in accordance with Article 5, Traffic. Lane closures are not allowed to take place during the holiday periods in accordance with Article 6, Holiday and Special Event Work Restrictions, unless approved by the engineer. | Mike Coleman | 20 | 2023-04-04 11:01 | 2023-04-06 10:13
20230411 | 20230411003 | 3 | Building Permit | Is an overall building permit from City of Milwaukee required for this project? We didn't see any information on a general building permit listed in the special provisions. | The contractor will be required to secure any required local building permits for the project. | Mike Coleman | 21 | 2023-04-06 12:57 | 2023-04-07 09:11
20230411 | 20230411003 | 3 | SPV.0060.29 - Spray Applied Air and Moisture Barrier | Would a spray applied instead of sheet applied air and moisture barrier be acceptable? |  |  | 22 | 2023-04-10 09:15
20230411 | 20230411004 | 4 | Safety Island | None of the plan sheet call out what is being paid for under the safety island item. Also, what are thickness requirements, no Sdd Either. | An addendum will be prepared to add a construction detail, call out the item on the plan sheets, and update the miscellaneous quantity sheets. | Mike Coleman | 2 | 2023-03-28 10:36 | 2023-04-05 05:59
20230411 | 20230411005 | 5 | Traffic Signal Controllers | Can you please confirm what traffic signal controllers are being used in the existing cabinets for this project? ie. Siemens, Econolite, Etc. | The controllers in the existing cabinets for this project are Econolite Cobalt ASC/3. | Mike Coleman | 1 | 2023-03-23 10:47 | 2023-03-24 07:30
20230411 | 20230411006 | 6 | Base Patching | There are no specifications on the depth of the base patches. This is needed due to the fact that they are bid by the square yard. Also, would the base patching be done prior to, or after the 2" milling. | Base Patching is typically done prior to 2â€ Milling. As for a depth : All work under this item shall be in accordance with the pertinent requirements of Section 390 of the Standard Specifications and as hereinafter modified. This work shall consist of the removal of areas of existing asphalt pavement, concrete pavements overlain with asphalt, including any existing patching, surfacing, or base materials of any type. This shall be done to a depth of six (6) inches below the existing surface at locations as directed by the engineer and as described below. It shall include the construction of an asphalt concrete pavement base course layer to restore the pavement to its present grade prior to the actual surface overlay. Base patching is to be performed prior to commencing the overlay. The Contractor is advised that only the most deteriorated areas will be addressed. Those areas will be determined just prior to the commencement of operations under this Contract. The areas will be delineated in the field with pink paint chevrons at the limits. The Contractor is responsible for locating all utilities within the specified areas to be base patched that may be in conflict with the proposed work as described herein. The Contractor shall be responsible for any and all restoration work to the existing shoulders, foreslopes, and ditches that may be damaged by the work to be performed under this item. The pavements shall be ground or milled to remove the affected areas to a depth of six (6) inches below the adjacent pavement edges. Restoration of the affected areas shall consist of one 6-inch layer of new HMA pavement. The composition of the asphalt mixture used in the restoration to the existing surface shall conform to the item of HMA Pavement 2 MT 58-28S for lower or binder courses as specified below: No. of Gyrations 40 VMA (min.) 12.0 Percent Binder (min.) 4.0 Percent Va 3-5 Percent Crush (min.) 60 1F Percent Elongated <5 Percent Passing Sieve: 25.0mm 100 19.0mm 90-100 12.5mm 90 max. 2.36mm 19-45 0.075mm 1-7 None of the areas that are to be repaired will be allowed to remain unfinished at the end of a workday. The Contractor shall only remove the affected areas to the extent that they can be fully restored during that working day. | Mike Coleman | 1 | 2023-04-04 09:12 | 2023-04-04 12:24
20230411 | 20230411008 | 8 | Design Schedule | Can the Department please provide the preliminary design schedule used for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/uzff7egnbp1hulp96bn6j3jrsaabg3ph or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-03-22 09:10 | 2023-03-23 07:27
20230411 | 20230411008 | 8 | 8' Shoulder | Can the department check the 8' shoulder quantity. When looking at the MQ's it appears the quantities are at full depth and the Typical section shows 3.75" for a total depth | We verify the MQâ€™s with the 3.75â€ for the shoulder and they are correct. | Mike Coleman | 2 | 2023-03-29 07:22 | 2023-03-31 07:47
20230411 | 20230411008 | 8 | Railroad work | Is the contractor to assume that the railroad work will occur during the contract time? Based on this work being performed by others, the contractor will have no contractual authority with the railroad or their contractors to enforce any compliance or coordination with WisDOT contract activities. Per the note in plans on sheet 16, â€œContractor is not responsible for replacing the railroad crossing or any paving between the saw cutsâ€. Will the department remove the language from addendum 1 under Article 3, sub. Traffic, â€œ Under this contract, Contractor is required to reopen USH 8 traffic on a paved surface within 12 hoursâ€¦ Contractor will be responsible for coordinating railroad crossing replacement work by others.â€? | An addendum will be issued to change the note on sheet 16 of the plan to better explaining what work is done by others and what items are covered under this contract. Addendum #1 Prosecution and Progress Traffic section will need to be followed. Railroad work should not be assumed either way and could happen during or outside the contractor schedule, the contractor should coordinate with the railroad and bid accordingly. | Mike Coleman | 3 | 2023-03-30 11:25 | 2023-04-04 11:37
20230411 | 20230411008 | 8 | Contract Time | To allow for adequate phasing to facilitate safe construction operations with traditional sequencing within each stage, time should be allowed to perform HMA paving after the sequential work for pipe installation, then milling, then curb removal & replacement with cure time. Will the Department add 12 days of contract time to allow for improved phasing of work? | After relooking at the time chart and to provide some separation between the cub and milling 10 working days will be added by addendum. | Mike Coleman | 4 | 2023-03-30 11:27 | 2023-04-04 11:34
20230411 | 20230411008 | 8 | Wood Turtle Fencing | It is noted in the special provisions that exclusionary silt fence protection must be installed prior to May 20th. Given the April 11th bid date, bidder is concerned that the Department may not have adequate time to attain a fully executed contract, ECIP approval, and pre-construction conference by this date to allow contractor to install the required fence under this contract. Will the department consider working through existing maintenance contracts to have all required exclusionary fence installed prior to May 20th? | The fence will be installed by others before the dead line and removed/maintained under the contract. An addendum will be coming out to address this. | Mike Coleman | 5 | 2023-03-30 11:28 | 2023-04-04 11:34
20230411 | 20230411008 | 8 | Special Event Work Restrictions | The Hodag Music Festival main event is scheduled for July 6th thru July 9th. Will the Department correct the dates listed in Article 5 for work restrictions related to this event to correlate to the planned dates of the event? | These dates will be changed by addendum to the following. From noon Friday, June 30, 2023 to 6:00 AM Monday, July 10, 2023 for Independence Day/Hodag Music Festival | Mike Coleman | 6 | 2023-03-30 11:29 | 2023-04-03 06:16
20230411 | 20230411008 | 8 | Curb & Gutter Limits at Railroad | Will the curb & gutter replacement shown inside the limits 100-ft from the rail crossing, be performed by others? Can the department please clarify the end station for the curb & gutter at this location? There is a discrepancy between the limits for replacement shown on plan sheet 52, and miscellaneous quantities table on sheet 46. This clarification may warrant RR Flaggers. | The curb and gutter will not be done by others and will be the responsibility of the contractor under this LET contract. An addendum will be sent out to better clarify what items are done by other and what will be the responsibility of the contractor under this contract. | Mike Coleman | 7 | 2023-03-30 12:21 | 2023-04-04 11:36
20230411 | 20230411008 | 8 | Temporary Median Crossover | The misc. qtys. table does not include any quantity for Asphaltic Surface Temporary for the temporary median crossover, shown to be constructed in stage 1. Can the department please provide a detail for the HMA thickness and add the tons to the misc. quantities? | A typical section and quantities will be added by addendum. | Mike Coleman | 8 | 2023-03-31 12:19 | 2023-04-04 11:36
20230411 | 20230411008 | 8 | Milling and Prep Foundation | Is the intent of the plan to mill the existing road to gravel, even if it would be thicker than 6" and then grade the base to a 2% crown. It theoretically should be close, but if material is needed to get to this point, would 1-1/4" Base be added. | The intent is to mill full depth in the lanes that have existing aggregate base under them and follow the Prepare Foundation for Asphaltic Paving (211.0101). Per Dense-Graded Base, 1-1/4â€ or Reclaimed Asphalt will be allowed to restore the roadbed to its required elevation. An estimated quantity of 1-1/4â€ will be added by addendum if the contractor chooses to furnishing and placing required filling from beyond the roadbed limits to restore or adjust to required elevation a foundation constructed under a previous contract per Prepare Foundation for Asphaltic Paving. In the areas that have salvaged Asphaltic Pavement Base Course under the lane an addendum will have the contractor mill only the required 6â€ for the New HMA. If there is remaining HMA surface thicker then than the existing 6â€ HMA pavement the Mill and Relay item will be added to address the areas of thicker existing HMA. This is to not place new 1-1/4â€ base on top of the existing Salvaged Asphaltic Pavement Base Course. The core log can be found at the following location: https://wisdot.box.com/s/uzff7egnbp1hulp96bn6j3jrsaabg3ph or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 9 | 2023-04-03 16:13 | 2023-04-06 06:11
20230411 | 20230411008 | 8 | Mill and Relay | On the addendum item added for Mill and Relay, will the department add the option to pulverize this remaining material in these sections? | An emergency addendum was issued to switch the Mill and Relay item added in addendum #2 to Pulverize and Relay. This will open up the acceptable gradation so that either a mill or pulverizer can be used. | Mike Coleman | 10 | 2023-04-06 13:04 | 2023-04-07 09:12
20230411 | 20230411009 | 9 | Design Schedule | Can the Department please provide the preliminary design schedule used for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/brxefyh5fpj83pgpqyefi4vbpg76i5j7 or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-03-22 09:11 | 2023-03-22 11:01
20230411 | 20230411009 | 9 | Milled Surface | Article 3 of the special provisions states; Do not allow a milled surface open to through traffic to remain in place longer than 48 hours......Would the department consider allowing the milled surface to be driven on for 72 hours if done after Labor Day? | No, the department would not. The 48 hr. restriction is due to the thickness and condition of the existing pavement. | Mike Coleman | 2 | 2023-04-04 14:27 | 2023-04-05 06:47