## qandasearchletting_results
Date: | 2023-07-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230711 | 20230711002 | 2 | Schedule | Can you send out the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/4o1nf1iqpczc0o26apk384wj2yc0i0tp or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-06-07 15:00 | 2023-06-08 09:40
20230711 | 20230711002 | 2 | Main line dowel bar placement at inside and outside concrete shoulders | Will the 10-1/2" main line pavement with a 14'-4" median /shoulder lane need to have a dowel basket in the 4'-0" Concrete Barrier area. I dont see a detail indicating dowel bar placement even though the concrete pavement below the barrier is incidental to the pay item 10'-1/2" pavement. | Correct, no dowel bars are not required within the 4â€™4â€ barrier pad location. Please refer to note 17 on the concrete barrier construction detail on page 28. | Mike Coleman | 2 | 2023-06-08 09:29 | 2023-06-08 11:07
20230711 | 20230711002 | 2 | Excel Sheets | Can you send out the Storm Sewer miscellaneous qty tables and earthwork data sheets as excel files? The earthwork data sheets from the back of the plan by the cross sections. | The requested files can be found at the following location: https://wisdot.box.com/s/4o1nf1iqpczc0o26apk384wj2yc0i0tp or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-06-09 12:20 | 2023-06-19 07:24
20230711 | 20230711002 | 2 | Storm Sewer and Earthwork Tables | Can the Department please provide the storm sewer tables in the miscellaneous quantities and the earthwork tabulations in Excel format? | The requested files can be found at the following location: https://wisdot.box.com/s/4o1nf1iqpczc0o26apk384wj2yc0i0tp or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 4 | 2023-06-12 16:06 | 2023-06-19 07:24
20230711 | 20230711002 | 2 | Drainage Tables in Excel Format | Can the drainage tables for storm sewer pipe and structures be provided in excel format? | The requested files can be found at the following location: https://wisdot.box.com/s/4o1nf1iqpczc0o26apk384wj2yc0i0tp or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 5 | 2023-06-15 10:49 | 2023-06-19 07:24
20230711 | 20230711002 | 2 | Coconut fiber rolls | We can't seem to find the Coconut fiber rolls requirements/specs, could you please point us in the right direction? | See page 181 of the proposal, item 179 â€œCoconut Fiber Rollsâ€, for information regarding the Coconut Fiber Rolls. | Mike Coleman | 6 | 2023-06-19 11:01 | 2023-06-19 12:09
20230711 | 20230711002 | 2 | Coconut Fiber Rolls dimensions and lcoations | We are having a hard time determining the â€œcoconut fiber rollsâ€ dimensions and whether they have to be wrapped with biodegradable or plastic photodegradable netting. | Proposed installation location and associated details for the coconut fiber rolls are shown on plan pages 270 and 272. | Mike Coleman | 7 | 2023-06-21 13:29 | 2023-06-21 13:32
20230711 | 20230711002 | 2 | Steel Diaphragm Web Bolts | Per the details on the steel diaphragm drawings (Sheet 1134 & 1158), the notes state web bolts shall meet ASTM A325 or A449. If A449 bolts are provided, then the requirements of ASTM F3125 Rotational Capacity (ROCAP) Testing would not be applicable as the standard only applies to A325 bolts and there is no ASTM procedure for A449. Is it acceptable to provide A449 bolts without ROCAP testing data? If testing data isn't required for A449 bolts, then are they necessary for A325 bolts when used in steel diaphragms? | Section 506.3.12.3.1 (1)-4 of the Standard Specifications give the requirements for the bolts in question for the prestressed girder diaphragms. | Mike Coleman | 8 | 2023-06-26 11:04 | 2023-06-27 07:32
20230711 | 20230711002 | 2 | Pre-bid Meeting info | Can you post the Pre-bid Meeting presentation and the QA items discussed? | The Pre-bid Meeting and QA can be found at the following location: https://wisdot.box.com/s/4o1nf1iqpczc0o26apk384wj2yc0i0tp or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 9 | 2023-06-29 09:52 | 2023-06-29 09:56
20230711 | 20230711002 | 2 | 643.0910 Traffic Control Covering Signs Type 1 | Is it the intent to install the NB/SB I-43 Detour for the full closures, and then uncover/cover as needed for the closures? And if so, these detour signs will be paid as a Type 1 Cover as shown in the quantity table on page 696? Or should they be paid as a Type 2 Cover? Also, please review the tabulation in this table for the Type 1 Covers. IH 43 NB shows 128 signs at 25 cycles, which should be 3,200 Each, but the shown quantity is 103 Each. Thanks | Yes, that is the intent of the full closure detours. Correct, they should be paid as Traffic Control Covering Signs Type II. Correct, the formula to compute the IH 43 NB detour should have a product of 3,200 EACH. As a result, the total for Traffic Control Covering Signs Type I should be 298 EACH and Traffic Control Covering Signs Type II should be 7,326 EACH. | Mike Coleman | 10 | 2023-06-29 14:10 | 2023-07-05 09:48
20230711 | 20230711002 | 2 | STRUCTURE B-45-116 | WOULD A PRECAST DUAL LINE OF SINGLE CELL 5' X 12" BOX CULVERT BE ACCEPTABLE IN PLACE OF THE POURED IN PLACE TWIN CELL 5' X 12" BOX? | Yes, a precast dual line of single cell 5' x 12" box culvert is acceptable in place of the poured in place twin cell 5' x 12" box. The precast box culvert shop drawings will need to be reviewed by BOS, and the design and details will need to conform to the current WisDOT Bridge Manual and BOS standard details. Since this is a two-cell box culvert, each cell will need to be individually fabricated with a 6â€ clear distance gap between the individual boxes, to be filled with â€œgrade Bâ€ concrete. In addition, CIP aprons should be used given the weir wall specified. | Mike Coleman | 11 | 2023-06-29 15:50 | 2023-07-03 08:09
20230711 | 20230711002 | 2 | Temporary Shoring B-45-116 / Temporary Diversion Channel | Can the temporary shoring quantity/locations for culvert B-45-116 be verified? Related plan sheets 41 & 42 also illustrate temporary shoring that is likely required to retain roadway traffic to be incidental to "temporary diversion channel". There is no temporary diversion channel item. How is the temp. shoring item required to hold up the roadway being paid? | Any temporary shoring required beyond what is shown and quantified in the structure plans for B-45-116 is incidental to item 173. Temporary Water Diversion Bridge B-45-116, Item SPV.0060.4005. Please see page 690 of the plans for the MQ table. | Mike Coleman | 12 | 2023-07-05 13:31 | 2023-07-06 06:05
20230711 | 20230711006 | 6 | B-44-471 and C-44-138 Cofferdams | It is understood the Temporary Diversion details as shown on plan sheet 11 of 278 are for handling the streams. Plan sheets 95 and 96 of 278 indicate the use of cofferdams for both structures. Should there be bid items for these cofferdams? | The Temporary Diversion details as shown on plan sheet 11 of 278 are an illustration of anticipated size and location of diversion channels if the contractor elects to utilize diversion channels during construction of the box culverts. The temporary water diversion items included in the contractor (SPV.0060.01 and SPV.0060.02) give the contractor the option of utilizing a diversion channel or bypass pumping. Proposed cofferdams for the method selected, including material used to construct the cofferdams (sheeting, rock bags with plastic sheeting, or other), shall be detailed in the ECIP submittal. An addendum will be issued to provide clarification that cofferdams are incidental to the Temporary Water Diversion bid items. | Mike Coleman | 1 | 2023-06-20 12:21 | 2023-06-21 06:53
20230711 | 20230711007 | 7 | Project Schedule | Could the design schedule that was developed for this project be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/lq7t0h6c7lnomr45a3wpfe9pmxs463b2 or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-06-13 13:17 | 2023-06-19 08:33
20230711 | 20230711007 | 7 | Contract Length | 25 Working Days appears to be too few working days for this project. With 3 weeks of pipe and grading work required, and 2 weeks of paving beyond the pipes, could the department add 10 working days to the project for the painting, guardrail, restoration and other finishing work? | The region considered your request and we will make an adjustment to contract type and time. We will change the contract to a completion date contract and use November 15, 2023 as the completion date. | Mike Coleman | 2 | 2023-06-21 21:21 | 2023-06-26 10:32
20230711 | 20230711007 | 7 | Asphaltic Surface | The culvert pipe has paving is listed under the 4 LT item and has PWL Air Void testing according to the plans. This work will have to happen prior to the paving of the mainline test strip. With that could this tonnage be separated into a Asphaltic Surface item? | The region has considered this request and will develop an addendum to change the culvert patching to Asphaltic Surface with 4 LT properties. | Mike Coleman | 3 | 2023-06-21 21:27 | 2023-06-26 10:31
20230711 | 20230711008 | 8 | Temp Pipe | Will 60" 12ga 5x1 Galv. be acceptable for temp. pipe? What is the in place pipe? What degree is the elbow shown on Sheet 20? Will the elbow be able to be made into the 24' length of pipe? If in place pipe is concrete, will a concrete to CMP transition be acceptable for the temporary connection? | 1. Temporary culvert pipe material shall conform to Standard Spec 520.2.1(3) 2. Asbuilts show 60-Inch CSCP. 3. The elbows connecting temporary culvert pipe to existing culvert pipe, and to proposed storm sewer, are shown on the plans as 150 degrees. The existing pipe location and elevations shown on the plans should be considered approximate, as noted in the Storm Sewer Plan and MQ tables. 4. This would be acceptable assuming that the connection works in the field; however, it should be noted that the existing pipe was extended on either side with buried elbows that were constructed under two separate projects, and asbuilt information on the location of the elbows is limited. The existing pipe location and elevations shown on the plans should be considered approximate, as noted in the Storm Sewer Plan and MQ tables. 5. This would be acceptable; the contractor will be responsible for any damage to the proposed storm sewer caused by installing or removing the temporary connection, as noted in the Special Provisions. | Mike Coleman | 1 | 2023-06-29 11:21 | 2023-07-10 07:57
20230711 | 20230711008 | 8 | Storm Sewer - Trench Backfill | Will trench backfill according to spec 608.2.2.3 be required for backfilling the storm sewer or could installation be typical to culvert pipes with on-site material being used? | Furnish trench backfill according to Standard Spec 608.2.2.3 | Mike Coleman | 2 | 2023-07-05 14:38 | 2023-07-10 07:54
20230711 | 20230711008 | 8 | Utility Conflict OH Line Sta 99+00 | The OH line at station 99+00 will conflict with the temporary shoring installation/ removal, can the department have this line relocated or de energized while the shoring is being installed/ removed? |  |  | 3 | 2023-07-06 09:29
20230711 | 20230711010 | 10 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/pdp5ere8s7qpi8n7tthnd28qexxj1x7j or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-06-22 08:04 | 2023-06-22 10:00
20230711 | 20230711010 | 10 | Steel Diaphragm Web Bolts | Per the details on the steel diaphragm drawings (Sheet 479, Project 1100-46-71), the notes state web bolts shall meet ASTM A325 or A449. If A449 bolts are provided, then the requirements of ASTM F3125 Rotational Capacity (ROCAP) Testing would not be applicable as the standard only applies to A325 bolts and there is no ASTM procedure for A449. Is it acceptable to provide A449 bolts without ROCAP testing data? If testing data isn't required for A449 bolts, then are they necessary for A325 bolts when used in steel diaphragms? | RoCap testing is not required for diaphragm bolts. Tightening requirements are defined in the notes on Sheet 20 of the bridge plan as ï¿½ turn past snug tight. | Mike Coleman | 2 | 2023-06-26 11:24 | 2023-06-27 07:31
20230711 | 20230711010 | 10 | Earthwork and Storm Sewer Tables | Can the department please provide the earthwork and storm sewer miscellaneous quantities and tabulations in Excel format? | The requested files can be found at the following location: https://wisdot.box.com/s/pdp5ere8s7qpi8n7tthnd28qexxj1x7j or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-06-29 13:27 | 2023-07-03 08:13
20230711 | 20230711010 | 10 | Extended Weekend Full Freeway Closures | On page 15 of 204 in the prosecution and progress, there is a section in regards to extended weekend full freeway closures. In this paragraph, it describes paving the mainline echelon from Friday night to Monday morning. Is this section an option to the contractor, or is the Department requiring weekend echelon paving for all of the mainline in lanes 1 thru 3? | Extended weekend full freeway closures are an option, not required. If this option is used, the mainline paving must be done using echelon paving. | Mike Coleman | 4 | 2023-06-29 16:36 | 2023-07-03 11:24
20230711 | 20230711010 | 10 | Surface Lift HMA Wedging | On page 43 of the plan set there are 2 details of the surface layer paving in the median and on the outside to maintain shoulder drainage. In these details, it shows milling and wedging in stages 2 & 3 and then removing of the wedge in stage 4 with the mainline. Can the Department point us in the right direction for the following questions: 1. How is the initial milling in stage 2 and 3 paid? 2. How is the wedge HMA paid and what mix is supposed to be used? 3. How is the final milling paid to remove the wedged mix that was placed in stages 2&3? | 1. The initial milling in stages 2 and 3 will be paid as Item 204.0120 Removing Asphaltic Surface Milling. The quantity for this is not included in the MQ tables and will be added via addendum. 2. The wedge constructed in stages 2 and 3 will be paid as Item 460.8624 HMA Pavement 4 SMA 58-28 V and should use the 4 SMA 58-28 V mix per the payment item (miscellaneous quantity table on page 390). 3. The final milling to remove the wedge in stage 4 will be paid as Item 204.0120 Removing Asphaltic Surface Milling (miscellaneous quantity table on page 375). | Mike Coleman | 5 | 2023-06-29 16:42 | 2023-07-03 08:15
20230711 | 20230711010 | 10 | Asbestos Inspection Report | Can you post the asbestos inspection report for the structures? | The asbestos inspection report can be found at the following location: https://wisdot.box.com/s/pdp5ere8s7qpi8n7tthnd28qexxj1x7j or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 6 | 2023-07-03 10:34 | 2023-07-03 10:35
20230711 | 20230711010 | 10 | WIDOT Property - North of Structure B-40-200 | Will this old park and ride property be available for a staging area, recycling site, waste area and possible batch plant location as it has been used on past projects? | WisDOT no longer owns the former Park & Ride property north of the freeway. It was purchased by the City of Greenfield in 2021 for future development. | Mike Coleman | 7 | 2023-07-03 15:53 | 2023-07-05 08:34
20230711 | 20230711010 | 10 | WIDOT Property - Center Median from Sta. 232 to 252 | Will this property be available as a staging area, recycle site and possible waste area for excess materials on this project? | The contractor may propose to use the site during construction. Use of the site must be approved by the engineer through the Erosion Control Implementation Plan, Work Zone Ingress and Egress plan, permits, and other contract-required submittals. | Mike Coleman | 8 | 2023-07-03 15:55 | 2023-07-07 07:42
20230711 | 20230711010 | 10 | Interim Completions and Liquidated Damages/02 - Stage 2A/2B Mainline and Ramp Work:July 12, 2024 | This interim completion deadline and unjustified liquidated damages does not seem to have any relationship with future stages of the project or other concurrent projects in which an interim stage would be necessary to be completed. There is significantly more work (working days) to be completed in Stages 2A/2B than are required to complete stages 3 and 4 and the contractor is allowed approximately 2 more weeks to complete stages 2A/2B due to the prescriptive language and interim start/completion dates in 2024. The contractor should be able to control their own schedule and determine when interim stages need to be completed in order to meet the contractual completion deadline of Nov. 1, 2024. If WIDOT want to put a higher penalty on the project completion, that's fine, but the contractor should be able to determine the amount of time required to complete Stages 2A/2B in order to meet this deadline and not be subject to an arbitrary interim completion deadline with associated damages. | The intent of the Stage 2A/2B interim completion date is to limit the duration of the full-time freeway lane closure allowed during that stage, along with completing the stage prior to the Republican National Convention. | Mike Coleman | 9 | 2023-07-03 16:06 | 2023-07-06 10:02
20230711 | 20230711010 | 10 | TRANSITION AND LIGHT BASE CONSTRUCTION | To construct the permanent wall, the asphalt surface will need to be installed. There is a note that states asphalt sawing for light base installation is incidental to the light base. Is the intent to install asphalt prior to the transitions and light bases being installed? If so will the department be paying for the asphalt and common excavation under the contract bid items? |  |  | 10 | 2023-07-06 09:22
20230711 | 20230711010 | 10 | Response to Question 9 | Based on the response to the Interim Completion deadline question and significant Liquidated Damages associated with Stage 2A/2B, it must be the intent of WIDOT that this project must utilize daytime and nightime during the entire Stage 2A/2B operations in order to complete the work required by July 12, 2024. Adding additional crews will not help the schedule as there are multiple operations with multiple subcontractors required to complete all of the work required in the median. In order to efficiently allow enough work room for operations, it must be intended that two shifts per day will be required to complete this portion of the project, 6-7 days/nights per week. |  |  | 11 | 2023-07-06 18:39
20230711 | 20230711010 | 10 | SHES Base Patching Stage 2 West Bound. | Can SHES Base Patching be performed fall of 2023 in Stage 2 Westbound? |  |  | 12 | 2023-07-07 09:04
20230711 | 20230711010 | 10 | Addendum 1 - Nighttime Deck Pour | Addendum 1 added language specifically for deck pours shall not occur over live traffic utilizing freeway closures unless approved by the engineer. As there is nothing specific within the standard specifications (104.6.1, 107.1, 107.8, 108.7.1, 502) or special provisions outlining why this must be done, what are the requirements that will be used to be approved by the engineer? |  |  | 13 | 2023-07-07 11:25
20230711 | 20230711010 | 10 | July 12, 2024 Interim Completion Date. | We are a small subcontractor and are wondering why WisDOT will not either allow Stage 2 work to start earlier in 2024 or allow some of the Stage 2 work to occur this fall like the Stage 2 SHES Base Patching. Can WisDOT please allow Stage 2 work that does not require barrier wall to be installed to occur this fall, weather permitting? It seems that the prime contractors we are speaking with in coordinating our work all would like to start earlier to at least allow SHES Stage to SHES Base Patching to occur earlier. |  |  | 14 | 2023-07-08 10:41
20230711 | 20230711010 | 10 | SHES Base Patching in areas where temporary barrier wall is being placed. | Please clarify that SHES Base Patching can be performed prior to temporary barrier wall being placed in areas where the temporary barrier rests on top of areas to be SHES Base patched. Lane configurations would remain the same, but barrels would be used during the SHES Base Patching and prior to the temporary barrier wall being placed. Work restrictions would be the same as for work behind temporary barrier. a similar question with WisDOT response was submitted for Proposal 12, question 15 of the March 2023 in bid express. |  |  | 15 | 2023-07-09 08:50
20230711 | 20230711010 | 10 | SHES Base Patching Stage Limits. | Can the SHES Base Patching be performed up to Stage Limits or do the SHES Base patches have to match the existing longitudinal joints when there are SHES Base Patches that are in adjacent lanes? |  |  | 16 | 2023-07-09 14:44
20230711 | 20230711010 | 10 | Base Patching Concrete SHES Special | Please confirm the intent of this installation is to install to the depth of the existing asphalt/concrete roadway, as the Prosecution and Progress of the special provisions has this work being completed in Stages 1-3 prior to the Stage 4 mill/overlay. How is the milling of these concrete patches to be paid during the Stage 4 mill/overlay, as the only bid item is for Removing Asphaltic Surface Milling, there is not a bid item for milling concrete? |  |  | 17 | 2023-07-09 20:26
20230711 | 20230711010 | 10 | SHES Base Patching on Ramps and Curb and Gutter on Ramps timing. | Please confirm when SHES Base Patching is to be completed on the ramps. We are being told by a bidder this work must be completed in Stage 3 and not in Stage 1. Please confirm which stage this work must be completed in or if the SHES Base patching can be completed in either Stage. The same for the Curb and Gutter on the ramps. Please note, there is a cement shortage for this fall and being able to perform this work in Stage 3 or in either stages 1 or 3 may help avoid related delays. |  |  | 18 | 2023-07-10 06:20