## qandasearchletting_results
Date: | 2023-09-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20230912 | 20230912004 | 4 | Future Work Orders | Can you provide the quantities and locations of future work orders? | A preliminary listing of anticipated locations and work order dates can be found at the following location. This listing is subject to change. https://wisdot.box.com/s/v2vg9pcfbwmojmg4h5essf4hxw9yc87y or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-08-29 08:14 | 2023-08-29 08:31
20230912 | 20230912004 | 4 | IDIQ - Mobilization | Is the mobilization bid item EA per project or EA per work order? | An addendum was issued to break out Mobilization per site or area. Prequalification has also been waived. | Mike Coleman | 2 | 2023-09-05 12:15 | 2023-09-07 07:03
20230912 | 20230912004 | 4 | Environmentally Sensitive area | Are there any environmentally sensitive areas that may require hand clearing? | On future potential work areas, there is an environmentally sensitive area that may require hand clearing. A plan sheet has been added to the following location: https://wisdot.box.com/s/v2vg9pcfbwmojmg4h5essf4hxw9yc87y or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-09-06 13:07 | 2023-09-06 13:12
20230912 | 20230912004 | 4 | Access - Area 9 | STA 135 - 137 LT has clearing behind guardrail but the guardrail stretches between the bridges. How did the department intend to access this section without guardrail removal? Please advise. |  |  | 4 | 2023-09-06 14:57
20230912 | 20230912005 | 5 | Future Work Orders | Can you provide the quantities and locations of future work orders? | A preliminary listing of anticipated locations and work order dates can be found at the following location. This listing is subject to change. https://wisdot.box.com/s/5zpllmjdm6aq3vu4nl8a3rv8wnvrp1hk or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-08-29 08:15 | 2023-08-29 08:31
20230912 | 20230912006 | 6 | Work Order | Unit prices for the first work order will be determined by the bid prices. Will subsequent work orders allow for different unit pricing? Clearing can vary greatly from one location to the next. | The intent of the IDIQ Tree Clearing contracts is to not negotiate different unit pricing for clearing when adding new work orders. | Mike Coleman | 1 | 2023-08-17 06:44 | 2023-08-18 09:44
20230912 | 20230912006 | 6 | Future Work Orders | Can you provide the quantities and locations of future work orders? | A preliminary listing of anticipated locations and work order dates can be found at the following location. This listing is subject to change. https://wisdot.box.com/s/2cl8r8einn95o9xuahorm5hkjhlj398i or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-08-29 08:16 | 2023-08-29 08:30
20230912 | 20230912007 | 7 | CIR Specifications | Can the special provisions for Item 327.1000.S be updated to the latest revision? Section C.7.3 Surfacing Paragraphs (4) & (5) have been updated/eliminated on other projects. | Revisions will be made in an upcoming addendum. | Mike Coleman | 1 | 2023-08-16 17:45 | 2023-08-17 09:24
20230912 | 20230912007 | 7 | 643.4100 Traffic Control Interim Lane Closure | What is the intent for item 643.4100 Traffic Control Interim Lane Closure? WI-23 only has one lane in each direction of travel, so there isn't a lane to take away via a lane closure. If this is meant for the installation and cure for the HFST, would Temporary Traffic Signals be a more appropriate item to use? Thanks | After discussion with the Region, we will be removing this bid item via addendum. | Mike Coleman | 2 | 2023-08-17 15:41 | 2023-08-24 13:17
20230912 | 20230912007 | 7 | Temporary Pavement Markings | Good morning, can you please clarify where the 148,479 LFT of temporary paint markings are to be installed? It appears, per the notes on plan sheet 13, that the contractor is to place skip markings only (no zones) after pass 1 on the single layer section and after pass 3 on the 2-layer sections It does not stipulate what should be placed on the milled layer on either section or after pass 1 on the 2-layer section. In addition to the quantities appearing to be overblown, has the department thought about the safety and liability aspect of not having no passing zones on what appears to be a fairly busy roadway? Thank you. | It was anticipated that temporary markings would match existing/proposed centerline pavement markings throughout the project. We have updated the MQ Tables for pavement markings to include a remark as to the location of the temporary markings. In single HMA layer locations, temporary paint would be applied to the milled surface. Temporary epoxy would be applied for the LT half of the CL markings on Pass #1 and temporary paint would be applied to the tapered joint surface for the RT half of the CL marking on Pass #1, and temporary epoxy would be applied to the final surface. In areas that the CL markings are skip only, the skip shall be placed to the LT of centerline on Pass #1. In double HMA layer locations, temporary paint would be applied to the milled surface, CIR surface, and Pass #1. Temporary epoxy would be applied for the LT half of the CL markings on Pass #3, temporary paint would be applied to the tapered joint surface for the RT half of the CL marking on Pass #3, and temporary epoxy would be applied to the final surface. In areas that the CL markings are skip only, the skip shall be placed to the LT of centerline on Pass #3. Upon review of quantities, there was a minor adjustment to final quantities of SPV.0090.01 Temporary Marking Line Paint 6-Inch, SPV.0090.02 Temporary Marking Line Epoxy 6-Inch, and SPV.0090.03 Marking Line Epoxy 6-Inch. An addendum will be issued. | Mike Coleman | 3 | 2023-08-21 09:45 | 2023-08-24 13:04
20230912 | 20230912007 | 7 | Curb and Gutter Grading Work. | The new Curb and Gutter is shown as not going back in the same exact location. With this, could the department add to the miscellaneous quantities for removal of the asphalt, sawcutting, base agg, common ex and placement of asphaltic surface for each location? | After discussing this with the Region it was decided to include some additional information in the plans, MQs and quantities. This will be addressed in an upcoming addendum. | Mike Coleman | 4 | 2023-08-28 14:43 | 2023-08-29 12:26
20230912 | 20230912007 | 7 | 96 Hour Milled Surface Paving. | The specials indicate that the milled surface is to be paved within 96 hours. With milling prior to CIR and then the paving process can intersections and the small amount at the east end be excluded from the 96 hour rule as milling these prior to CIR would be necessary? | The intent of the 96 hour limit is for the mill and overlay areas (western 1 mile, intersections, and east end) it is not intended for the 6 miles of CIR. | Mike Coleman | 5 | 2023-08-28 14:44 | 2023-08-29 12:28
20230912 | 20230912007 | 7 | Construction Schedule | Could the Design Construction Schedule developed during design be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/ebthw0szw3mkucntr5y3w8675az6isls or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2023-08-28 14:45 | 2023-08-29 09:47
20230912 | 20230912007 | 7 | Item # 32 - Hauling Excess Shoulder Material | What is the intent of this item? There is no special provision or construction details explaining what this item is. Please advise. | The special provision will be added via addendum. | Mike Coleman | 7 | 2023-09-05 09:54 | 2023-09-05 12:24
20230912 | 20230912007 | 7 | Base Repair for CIR | The item for Base Repair for CIR is approximately 10% of the CIR milling area based on the plan depths. Based on previous jobs this item is not used at all in many of them and when it is the quantity is much less on average. Could the region review this quantity as it seems to quite a bit more that what is seen out in the field? | In our review of this project, it was noted that the roadway was heavily rutted, and the pavement was alligatored and failing in most areas. Because of this, we opted to use 10% for estimating based on the number of areas that could fail once exposed and checked during CIR operations. | Mike Coleman | 8 | 2023-09-05 13:40 | 2023-09-07 07:00
20230912 | 20230912007 | 7 | Tack Cost Quantity | When you back calculate the tons of asphalt to get the square yards of area to be paved it looks like the tack quantity may be incorrect. You have a milled surface to tack, CIR to tack for before the 3MT 58-28 S lower layer, HMA lower lift to tack for surface, and asphalt wedging area to tack. When you do a takeoff to figure out what is needed it looks to be that with the 4 applications areas the plan is around 13,000 GAL short. | An addendum will be issued. | Mike Coleman | 9 | 2023-09-06 14:53 | 2023-09-07 13:21
20230912 | 20230912008 | 8 | Construction Schedule | Could the schedule developed during design be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/sii0l1dcd575qpznfuvgz8g9b1ebesga or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-08-28 14:46 | 2023-08-29 08:36
20230912 | 20230912008 | 8 | Temporary Guardrail Quantity | Is it possible that the temporary guardrail quantity was doubled? It appears that both plansets show the same temporary guardrail on the 74 plansets and the 77 planset from STA 298 - STA 302. Is the intent that these locations will need temporary guardrail twice? | The Temporary Guardrail segments from STA 298-302 should only be counted once each and should only be included on 1 plan set. Given the location of the rail, it should be included under project 6590-02-77. The quantities as shown in AAshtoware should be changed as follows from the current quantity to the actual: 614.100: Current (200 LF); Actual (100 LF) 614.1100: Current (315.2 LF); Actual (157.6 LF) 614.1200: Current (8 EA); Actual (4 EA) An addendum will be issued. | Mike Coleman | 2 | 2023-09-01 11:24 | 2023-09-05 09:46
20230912 | 20230912008 | 8 | Quantites | Could you please verify the Common Excavation quantity and the removing curb quantites. It also seems to have doubled up quantities. | The common excavation and removing curb & gutter quantities were doubled in a couple locations between the two project IDs within the miscellaneous quantities. An emergency addendum will be issued. | Mike Coleman | 3 | 2023-09-07 12:55 | 2023-09-08 06:51
20230912 | 20230912009 | 9 | SP Storm Sewer joint ties | SP23 requires the placement of joint ties on the storm sewer pipe. This is also noted on the misc qty sheet page for storm sewer. Is it really the intent to place joint ties on about 2300' of storm sewer pipe? | After evaluation, it has been determined that the intention is not to tie all storm sewer joints, however various amounts of ties will be required on several runs of pipe near the outfall. The limits of these ties will be communicated via addendum. | Mike Coleman | 1 | 2023-08-15 08:10 | 2023-08-23 14:35
20230912 | 20230912009 | 9 | Erosion Mat II-A | Article 24 of the Specials states to not use rolls of emat less than 6 feet wide in channels. The plan shows the II-A emat being used exclusively in a channel. My supplier states that rolls of II-A are only manufactured in 4 foot wide rolls. Would the Department consider revising Article 24 to allow for 4 foot wide rolls in channels? | After review, it has been determined that Erosion Mat Class II Type C is better suited for this situation. An addendum to remove the Class II Type A and replace with Class II Type C will be forthcoming. The 6-foot width in Article 24 of the special provisions matches that in section 628.3.2(2) and will not be changed. Class II Type C erosion mat options are included on the PAL. | Mike Coleman | 2 | 2023-09-01 12:13 | 2023-09-07 07:04
20230912 | 20230912009 | 9 | Staging | Would the contractor have the ability to rearrange the first 3 stages. For instance, be able to start on Stage 3, as long as storm sewer outfall ditch along the north side of Hwy 80 was constructed first. Then do stages 1 & 2 after. | The Department may consider a revised staging plan after letting. However, there are several considerations that will need to be addressed to ensure that all project commitments have been met. Timely discussion after contract execution will be required to allow for proper review of the contractorâ€™s proposed staging changes. For preparation of the bid, proceed with the project staging as currently proposed. | Mike Coleman | 3 | 2023-09-05 11:16 | 2023-09-07 07:06
20230912 | 20230912009 | 9 | Site Mowing | The SPV requires a non-suction mower and/or hand tools. However, the language surrounding the 1-inch or less initial height and the disposing of material seems to complicate this SPV. 1. What material disposal is anticipated? Is it the mowed grass? With no suction, it reads as though hand raking and bagging is being requested. 2. We're not confident that a non-suction mower can mow the grass to less than 1-inch. Is this a necessary requirement? 3. The east side of the road is mostly wooded or shrubbery. Is mowing anticipated to be needed in these types of areas or just the open lawn-type areas? |  |  | 4 | 2023-09-07 12:50
20230912 | 20230912009 | 9 | Salvage and Reinstall MGS Guardrail System | The payment section states, in part, "providing and installing new posts, blocks and hardware, reinstalling the salvaged rail..." Is this to mean that all of the posts, blocks and hardware in the system need to be replaced, just the wood posts, or just the damaged posts, blocks and hardware? To ask another way, is the intent of the bid item to reuse as much undamaged material in each system as possible or is it mostly to only reuse the rail portion and EAT parts? |  |  | 5 | 2023-09-07 12:58
20230912 | 20230912011 | 11 | Temporary Vehicle Detection STH 47/CTH S, Item SPV.0060.01 | Temporary Vehicle Detection STH 47/CTH S, Item SPV.0060.01, the description in the Special Provisions for this item states "This work also includes maintaining existing detectors". The WI-47 and CTH-S intersection is not a signalized intersection - I can't see anything in the plans about existing loop detectors or any other type of traffic detector at this intersection. Please confirm that there are not any existing detectors that will need to be connected to the Temporary Traffic Signal trailers. Thanks | There are no existing loop detectors at the intersection of STH 47 and CTH S. | Mike Coleman | 1 | 2023-08-10 13:35 | 2023-08-15 10:03
20230912 | 20230912011 | 11 | Distressed Areas After Milling | Miscellaneous Quantities calls out 450 ton of Asphaltic Surface for filling potholes, pop outs or distressed areas after milling. There is not an item for Removing Distressed Asphaltic Surface Milling. Will that item be added or is the intention to wedge those areas with Asphaltic Surface? | Item 211.0101 Prepare Foundation for Asphaltic Paving (project) 01. 6243-05-73 is included and covers removal of material that may adversely affect bond before surfacing. The Asphaltic Surface item will be used to fill voids up to the milled surface created by that removal. | Mike Coleman | 2 | 2023-08-28 14:06 | 2023-08-29 10:34
20230912 | 20230912012 | 12 | Project Schedule | Can the department provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/iv5sapm4wnk2005q5r8r64cyqrtj1kyc or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-08-14 11:12 | 2023-08-14 12:18
20230912 | 20230912012 | 12 | Project Duration | The design schedule does not allow time for staged construction of curb through Commercial Entrances to maintain access to driveways as required per the special provisions, and doesnâ€™t provide the contractor with cure time for the concrete Curb & Gutter prior to HMA Paving. Would the department add 5 working days per stage to both Stage 2 and Stage 3 to allow adequate time for construction? | We agree. An additional 10 working days will be added to the project schedule to account for cure time and staging of driveways for the curb and gutter. An addendum will be issued. | Mike Coleman | 2 | 2023-08-28 16:14 | 2023-08-31 09:39
20230912 | 20230912012 | 12 | Utility Coordination | The design schedule does not show time for work by utilities within the project limits, specifically the WPS gas main from Sta 76+00 to 93+00 and lowering of gas services at two locations. How many days will the utility need to perform their work. Will Working Days be added to accommodate this work by the utility during the project. | According to Utility article of the special provisions the only utility work that will be done during construction is a few water valve adjustments. WPS and all other utilities will complete their relocates prior to construction. The water valve adjustment work will be completed with a vac-truck that should only take a few hours or less at each location. Plan on one day for this operation. The contractor will be able to continue most operations or work around the crew raising water valves so no additional time is added to the contract. | Mike Coleman | 3 | 2023-08-28 16:15 | 2023-08-31 07:48
20230912 | 20230912012 | 12 | Earthwork Table & Cross Sections for Rural Pavement Section | The typical sections show constructing a new â€œsubgradeâ€ surface where the milling depth stops, with a uniform cross slope which extends to the outside shoulder following a consistent same cross-slope beneath the pavement, thus leaving existing base course as the new subgrade surface. Note 1 in the Earthwork Table indicates that "Cut includes existing asphalt and base material", but cut volumes are not calculated beyond Station 101+00. Is the contractor to remove the existing shoulder gravel outside of the pavement milling limits from STA 101+00 to the project limits? Will additional CY of Common Excavation be added for removing this material. | Yes. The intent is for the contractor to remove the existing shoulder gravel outside the pavement milling limits from STA 101+00 to the end of project. We will send out an addendum increasing the Common Excavation to account for removal of this material. | Mike Coleman | 4 | 2023-08-28 16:19 | 2023-09-01 10:41
20230912 | 20230912012 | 12 | Side Road Access & Safety Slope | During the Removing Asphaltic Surface Milling process, when there will be a 9-inch, or 12-inch cut at side roads and private entrances, what material is to be used to ramp existing pavements for access and for safety slopes? | The material used will be determined by the contractors means and methods during construction. The material could vary depending on the location, depth, length and duration the material would be needed. | Mike Coleman | 5 | 2023-08-31 16:39 | 2023-09-01 10:43
20230912 | 20230912012 | 12 | Asphaltic Surface Driveways & Field Entrances Depth | What is the proposed thickness for Asphaltic Surface Driveways & Field Entrances? | The proposed thickness for Asphaltic Surface Driveways & Field Entrances is 4-inches. This will be included in the addendum for the project. | Mike Coleman | 6 | 2023-08-31 16:40 | 2023-09-01 10:42
20230912 | 20230912012 | 12 | Staging Sequence | Will the department remove the language from Article 3 of the Special Provisions, which states: â€œEach stage cannot start until the previous stage has been completedâ€? With this language removed, alternate staging could be proposed by the contractor that would be beneficial to the project; for example, given that Stage 4 is to be constructed in part using flagging, it is feasible that a portion of this work could be safely constructed concurrently with prior stages. | The department and construction management staff will evaluate proposed changes to staging on a case by case basis. | Mike Coleman | 7 | 2023-08-31 17:02 | 2023-09-01 10:43
20230912 | 20230912013 | 13 | Design Project Schedule | Can the design project schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/8whh28p0j339zixrlp5ip2t1xfwz7g84 or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-08-28 12:51 | 2023-08-29 07:13
20230912 | 20230912013 | 13 | Project Start Date | The provided design schedule shows the probable date of beginning as May 6th, 2024 but the special provisions state to start no later than March 1st, 2024? Is this a typo in the special provisions? | There was a typo in Prosecution and Progress. There will not be a restriction of starting the project prior to March 1st, 2024. An addendum will be issued. | Mike Coleman | 2 | 2023-08-30 07:45 | 2023-08-30 09:58
20230912 | 20230912013 | 13 | water main | The plan calls for a short 30 ft directional drill for the 8" Water main. With the short distance it is generally not cost effective to do this. Would other methods of trenchless work be allowed? Such as rat holing, pipe ramming or push/pull to get the pipe under the box culvert? | Directional Drilling will be the required method for installing the water main under the twin storm sewer culverts. The other methods described would not meet the Village requirements for water main installation in these circumstances. | Mike Coleman | 3 | 2023-09-07 09:51 | 2023-09-11 08:59
20230912 | 20230912014 | 14 | B-18-0051 Plan sheets | It appears there may be incorrect plan sheets for B-18-0051? | It appears that the bookmark for B-18-0051 links to B-18-213. Structure plans for B-18-0051 start on page 746 of the plans. | Mike Coleman | 1 | 2023-08-14 10:11 | 2023-08-21 06:57
20230912 | 20230912014 | 14 | Salvaged / Usable Pavement | Can you please provide your calculations and station to station for the existing pavement (both existing asphalt and concrete) in stage 2 (91,450 CY) and stage 4 (90,015 CY)? | The Earthwork Summary will be updated via addendum. As part of that update the salvaged and unusable pavement calculation will be updated. | Mike Coleman | 2 | 2023-08-14 12:55 | 2023-08-18 07:57
20230912 | 20230912014 | 14 | Item 0698 24" rcp jacked | It appears bid item quantity for 0698 should be 679 instead of 545 ft, per sheet 357. | We agree that the total did not sum up the entire column. This update will be included in an addendum. | Mike Coleman | 3 | 2023-08-14 13:38 | 2023-08-18 07:58
20230912 | 20230912014 | 14 | Removing Concrete Pavement | The calculation of the area for bid item of removing concrete pavement does not make sense. For the areas both EB and WB from 604+36 to 776+25 calculate to an average width of 28 feet, the width of the cement stabilized base. But from 777+00 to 985+80 the average width calculates to between 39 and 40 feet, which is the shoulder-to-shoulder width per the typicals. Not 28 feet. Can you either provide your calculations or possibly re-check to make sure the quantity is not overstated? | On page 9 of the plan there are stars next to the 2â€™ additional width call out measurement of the cement stabilized base. These call outs show that the cement stabilized based is wider from 788â€™EBâ€™+00 to the end of the project. This would be 40â€™ wide for this area. | Mike Coleman | 4 | 2023-08-14 14:30 | 2023-08-18 07:58
20230912 | 20230912014 | 14 | General QMP Concrete Pavement | General QMP Question-Proposal Section 501-3 Page 60, Bridges #1021-03-71, 1021-03-72, 1021-03-73, 1022-09-74, 1022-09-78. Section regarding QMP Concrete Pavement, Cast-in-Place Barrier, and structures reads as follows: â€œreplace standard spec 715.3.1.1: Provide slump, air content, concrete temperature, and strength test results as specified in standard spec 710.5. Provide a battery of QC tests, consisting of results for each specified property, using a single sample randomly located within each sublot. Cast 3 specimens for strength evaluation Replace standard spec 715.3.1.1.1(1) with the following Cast 3 beams for flexural strength acceptance testing at 28 daysâ€ Our question pertains that the aforementioned section of the proposal. The way that our team has interpreted it, this section seems to indicate that in addition to the compressive strength specimens flexural strength specimens will also need to be cast. If so, is this going to be an aspect of this project that will have disincentive associated with it or is it an aspect much like the S.A.M. Meter that will hold no penalty and is purely for research and exploration purposes. | The text below is from Special Provision 72. Concrete Pavement 12-Inch Special, Item SPV.0180.02. This language is only intended to modify the standard specifications for this item (Concrete Pavement 12-Inch Special, Item SPV.0180.02) as described in A Description of the special provision. | Mike Coleman | 5 | 2023-08-28 15:25 | 2023-08-29 08:37
20230912 | 20230912014 | 14 | Stage 2 and 2/5 | Stage2 and 2/5 Can you provide a breakout of what tons are completed in Stage 2 and what tons are completed in Stage 5 as they are not even completed in the same years according to the schedule of operations. For instance, Page 327 towards the bottom shows Stage2/5 with Tons. Which stage does these tons represent and are these tons/areas shown within any plan sheets? | An Addendum will be prepared to break out the HMA placed in stage 2 and stage 5. | Mike Coleman | 6 | 2023-08-28 16:11 | 2023-09-01 10:44
20230912 | 20230912014 | 14 | Stage 4 and Stage 4/5 | Can you provide a breakout of what tons are completed in Stage 4 and what tons are completed in Stage 5. For instance, Page 327 towards the bottom shows Stage4/5 with Tons. Which stage does these tons represent and is this shown within any plan sheets showing this breakout? There also seems to be a quantity bust in all stage 4 or stage 4/5 quantities given based on stationing provided on sheet 327 please confirm. | An Addendum will be prepared to break out the HMA placed in stage 4 and stage 5. A correction to the quantities will also be included in the addendum. | Mike Coleman | 7 | 2023-08-28 16:12 | 2023-09-01 10:44
20230912 | 20230912014 | 14 | Stage 5 Paving | On page 7 of 64 stage Complete EB medium Shoulders â€“ As mentioned above is all the EB medium shoulder tonnage complete in this stage or is some in stage 4. Please break this out. In stage 2/5 is shows all WB so confused as to why verbiage on 7 of 64 states in stage 5 â€œComplete EB Median Shouldersâ€ if we are in WB in Stage 2. | All final work in the median is completed in Stage 5. The HMA items will be clarified in the addendum. | Mike Coleman | 8 | 2023-08-28 16:13 | 2023-09-01 10:45
20230912 | 20230912014 | 14 | *** 6â€ HMA Pavement Areas | On plans sheet 15 it shows within the cross sections a note *** 6â€ Pavement (Areas Carrying Temporary Traffic). Can you please define where these areas specifically are with stationing and if shown or called out within the misc. quantities or shown within the plans please advise where. If not can these areas be broken out so we are clear when bidding/construction where exactly we would switch to specified mix versus the asphaltic surface temporary mix type. | The thicknesses for the shoulders is show in the MQ table in the remarks column. | Mike Coleman | 9 | 2023-08-28 16:15 | 2023-09-01 10:45
20230912 | 20230912014 | 14 | Backfill Granular Grade 1 | Backfill Granular Grade 1 is very difficult to find in this area and is very expensive. Can Grade 2 be used instead? Grade 2 usually is used to fill Marsh Excavations. The Marshes on this project are not very wet. Grade 2 is the best option for the Marsh backfill on this project. Please consider using Grade 2 vs Grade 1. Grade 1 is an expensive product that is not needed for its current use on this project. | Based on the soils report and discussions with the WisDOT soils engineer, Grade 1 is the correct use. No changes to the plan are anticipated. | Mike Coleman | 10 | 2023-08-29 11:59 | 2023-09-01 10:46
20230912 | 20230912014 | 14 | Project Schedule | Could the engineer's proposed project schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/3e3m85d7fp8lptdia3obb9e6xx3udvr8 or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 11 | 2023-08-30 19:56 | 2023-09-01 10:48
20230912 | 20230912014 | 14 | Soil Borings | Can the soil borings be provided. | The soils reports can be found at the following location: https://wisdot.box.com/s/3e3m85d7fp8lptdia3obb9e6xx3udvr8 or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 12 | 2023-09-01 08:32 | 2023-09-06 06:02
20230912 | 20230912014 | 14 | Contractor- Data Package | Can the Contractor Data Package be updated based on Addendum #1. | The files for the contractor data packet for the addition of Stage 5 cross sections can be found at the following location: https://wisdot.box.com/s/070kr3qxiuqqr1n46q1ahoc36wmbk5wn or can be accessed on the HCCI September bid letting page under Supplemental Information. | Mike Coleman | 13 | 2023-09-01 08:33 | 2023-09-05 10:40
20230912 | 20230912014 | 14 | Temporary Bridge Vertical Clearances | The spec states : â€œEnsure Structure has a low superstructure elevation no less than existing adjacent bridge or as shown on the plansâ€. The plan also shows a lower PGL for the temporary bridge than the existing bridges. The existing bridges over Mallard Rd currently have a shallow deck depth for the current span. Given the skews, PGL and vertical height restrictions, has the department evaluated that the parameters implied are practical for a temporary bridge? 1. Can the minimum vertical clearances on Mallard Rd be modified to accommodate a 36" steel girder? if not, 2. Will the department update/ modify the temporary roadway quantities on S2_WB to achieve the required vertical clearances on Mallard Road if using a 36" steel girder? and or, 3. Will the department update the plans/ quantities to accommodate for road work on Mallard Road to achieve the required vertical clearances for a 36" steel girder? | An addendum will be issued to note that changes to the profile for the temporary profile are allowed to meet clearance requirements. | Mike Coleman | 14 | 2023-09-01 12:42 | 2023-09-07 06:37
20230912 | 20230912014 | 14 | Right-of-Way Fence Clearing | Is clearing and grubbing incidental to the right-of-way fence or will the entire project need to be cleared to the r/w to accommodate fence removal and installation? | Clearing and grubbing required for placement of fence is incidental to construction per standard specifications 616. | Mike Coleman | 15 | 2023-09-05 12:11 | 2023-09-06 05:47
20230912 | 20230912014 | 14 | Backfill Granular Grade 1 | Last month's WisDOT August Letting Proposal #5 CTH M specified Select Borrow in Article #33 to be used in Marsh Excavation Areas. CTH M's marsh areas were up to 20' in depth and in standing water. Can this same spec be added to this project instead of Grade 1? This material is more readily available in the area and was acceptable on another WisDOT project with deeper and wetter marshes than this project. 33. Select Borrow, Item 208.1100. Conform to standard spec 208 as modified in this special provision. Material Furnish and use material that consists of granular material meeting the following requirements: No more than 8% P-200 of that portion of the #4 sieve. stp-208-005 (20031103) | An addendum will be issued to allow more flexibility on the material for Select Borrow and Backfill Granular Grade 1 based on the keeping the P-200 lest than 8%. | Mike Coleman | 16 | 2023-09-05 12:32 | 2023-09-06 13:14
20230912 | 20230912014 | 14 | Article 27. Select Borrow, Item 208.1100 | Why is the Select Borrow item specified to be Grade #1? Looks like Select Borrow is only for EBS backfill, which Grade #2 is more than acceptable for EBS Backfill. Can Select Borrow be changed to Grade #2 for EBS? Also why is the quantity of Select Borrow 29,413 CY and the EBS quantity is only 2,170 CY? | An addendum will be issued to allow more flexibility on the material for Select Borrow and Backfill Granular Grade 1 based on the keeping the P-200 lest than 8%. The summary for the total quantity on the earthwork summary table will be updated and included in the addendum. | Mike Coleman | 17 | 2023-09-05 14:43 | 2023-09-06 13:14
20230912 | 20230912014 | 14 | Item No. 0422 | Do you have anchors requirements or can we use 12â€ fabric pins for the Erosion Mat Class 3 type D? | The requirement for anchoring erosion mat is listed in Standard Spec 628 Erosion Control. | Mike Coleman | 18 | 2023-09-05 16:41 | 2023-09-07 06:50
20230912 | 20230912014 | 14 | 643.1205.S Basic Traffic Queue Warning System | 1. Misc Qty shows a total of (4) systems during stages 1B, 3, and 5. If a system is placed on EB and WB I-94, where are the other two systems placed? 2. Misc Qty shows (0) days for Stage 2 - please confirm that no Queue System will be needed for the entire 2025 construction season. Thanks | In stage 1A two systems are placed on IH 94 EB (each side of roadway). In stage 1B, 3, and 5 two systems are placed on IH 94 EB (both sides of roadway) and IH 94 WB (both sides of roadway). If lane closures are used in Stage 2 based on the contractors means and methods, then the Basic Traffic Queue Warning System could be needed. | Mike Coleman | 19 | 2023-09-06 09:43 | 2023-09-07 06:54
20230912 | 20230912014 | 14 | Culvert Pipe Transition Detail | There is a culvert pipe transition detail on sheet 20 that does not specify which culverts get 10:1 transition cuts. Which culverts get the 10:1 transitions? The notes for the detail indicate that transition cuts are paid as excavation common. There is no transition cut indicated in the miscellaneous quantities earthwork summary table. Will there be any transition cuts? | All permanent pipes that are not placed by Bore and Jack process will require the culvert pipe transition. The excavation will be paid for as common excavation as noted in the detail. | Mike Coleman | 20 | 2023-09-06 16:40 | 2023-09-08 10:39
20230912 | 20230912014 | 14 | RE: Basic Traffic Queue Warning System, Item 643.1205.S. | Per the special provisions of this project, 41. D. Measurement: "The department will measure Basic Traffic Queue Warning System by the day, acceptably completed, measured as each complete system per roadway." Past projects have defined a "roadway" as a single direction of travel, IE (1) paid day for Eastbound and (1) paid day for Westbound. The response to the prior question asked regarding this item stated that there will be (2) systems per "roadway", measured as (1) on the median side and (1) on the outside lanes of travel. Please confirm that the Contractor will be paid for (2) days per roadway when the EB systems are in place and (2) days per roadway when the WB systems are in place. Thanks | The payment will be based on the special provisions and measured as each roadway. Eastbound lanes will be considered one roadway and Westbound lanes will be considered one roadway under this special provision. The Basic Queue Warning System standard detail is set up to have the FBS signs on the right side of the roadway regardless of the lane closure in use. It is anticipated that the engineer will direct the installation on the right side (outside shoulder) of the roadway only and the FBS signs on the left side (median shoulder) will not be required to be installed. This will be in accordance with the SDD. It is also anticipated that the engineer will direct the installation of the Basic Queue Warning System during Stage 2 and Stage 4 when traffic is on the temporary roadway in case the contractor needs to set lane closures during that stage for access, working room, or switching of traffic stages. These updates will not impact to total estimated quantity. | Mike Coleman | 21 | 2023-09-07 09:01 | 2023-09-08 10:39
20230912 | 20230912014 | 14 | Traffic Control clarification | Special Provisions, 5. Traffic, General has a bullet point that states: "The traffic control contractor must review the project once every day as per the standard spec 643.3.1(5)." However, when reviewing the Standard Spec 643.3.1(5), it does not state that a Traffic Control review must be done daily. Standard Spec states that it must be done immediately after each setup or as necessary. "Review signs, traffic control devices, and temporary pavement marking for location, position, visibility, and appropriateness for job conditions immediately after each setup. Do additional reviews as necessary to provide a safe work zone..." Can this language be removed from the Special Provisions? Or, if it is the intent for the Contractor to review the job daily, can an item be added for Daily Maintenance & Surveillance? Thanks | The contractor will be required to do a daily review of the project per Special Provision 5. Traffic. This was included to provide the contractor with additional guidance as to the amount of additional reviews expected for this project. A new item will not be added to the project. | Mike Coleman | 22 | 2023-09-07 11:41 | 2023-09-08 08:50
20230912 | 20230912014 | 14 | Addendum #3, Select Borrow | In Addendum #3 the Select Borrow specification was changed. It appears that the department is now asking for a flowable fill for Select Borrow per the verbiage change in Materials. Is this really what is intended as it will be an incredibly costly item per this change. | An error was made when the addendum was created. An emergency addendum will be issued to change the article to the following: Furnish and use material that consists of granular material meeting the following requirements: No more than 8% P-200 of that portion of the #4 sieve. ASP-5 is also being revised with the addendum. | Mike Coleman | 23 | 2023-09-07 15:51 | 2023-09-08 10:37
20230912 | 20230912015 | 15 | Prepare Foundation for Asphaltic Shoulders | Is it the intent of the prepare foundation for asphaltic shoulders item to remove the 2â€™ x 4â€ of existing shoulder material from the project? Or can the material be incorporated into the new CABC shoulder after CIR and paving is complete? | The intent of the Item Preparation of Foundation for Asphaltic Shoulders is to remove 2 feet of existing shoulder and the existing material may be used to build the new shoulder as long as it meets the requirement of 211.3.6 in Standard Specification. An addenda is being prepared to clarify plan, items and quantities. | Mike Coleman | 1 | 2023-08-17 08:58 | 2023-08-31 05:44
20230912 | 20230912017 | 17 | Box Culverts | Will precast box culverts be an approved alternate to the cast-in-place box culverts included in the plans? | Precast box culverts will be an acceptable alternate for structures C-4-70, C-4-71, C-4-72. The contractor will need to submit shop drawings to BOS for final acceptance. | Mike Coleman | 1 | 2023-08-28 15:57 | 2023-08-30 06:01
20230912 | 20230912017 | 17 | Project Schedule | Could the engineer's proposed project schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/zidcc44q7kzu4rmpg80zhscyn9z4bbwc or can be accessed on the HCCI September bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-08-30 19:57 | 2023-08-31 11:57
20230912 | 20230912018 | 18 | Contract Time | Is it possible to get more working days added to this contract? With the number of culverts, 10:1 transitions, and basically dedicating every Friday for asphalt patches, it seems that 55 working days would be more realistic without adding extraordinary forces to complete the project. | Working days are being revised via addendum. | Mike Coleman | 1 | 2023-08-17 06:32 | 2023-08-23 14:29
20230912 | 20230912018 | 18 | New Culvert at Station 315+96 in 2023 | It appears that a new metal culvert pipe is on site for installation at Station 315+96. Sawcuts for the pavement removal are also marked? Is this pipe being installed by others in 2023? |  |  | 2 | 2023-09-10 20:50
20230912 | 20230912019 | 19 | Special Culvert Grouting | The miscellaneous quantities show 5 CY of Special Culvert Grouting required at STA 401+23 - 401+56. Is that listed under the wrong station? Should it be for STA 368+21 - 368+23? | The 5 CY of Special Culvert Grouting should be at station 368+21 â€“ 368+23 and not 401+23 â€“ 401+56. An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-08-30 05:30 | 2023-08-30 07:32
20230912 | 20230912019 | 19 | Bevel Reinforcing Detail | The construction detail on sheet 6 shows the side view and states "CUT OFF EXISTING PIPE PLUMB WITH TOP OF INLET OPENING". Is that supposed to be part of this plan? If so please explain. The existing pipe appears to connect directly into precast apron endwalls. | The detail was provided by CO and updated to fit our project. The original detail was for a pour in place endwall. This project is using a pre-cast endwall. Therefore, the note does not apply to this situation. An addendum will be issued. | Mike Coleman | 2 | 2023-08-30 05:40 | 2023-08-30 07:45
20230912 | 20230912019 | 19 | Bypass Pumping | What is the requirement for pumping water for each pipe if any? Being the highway is staying open to traffic 24/7. | Drainage maintenance requirements are described in Article 13 Culvert Pipe Liner, 72-Inch, Item SPV.0090.01 C.3 and Article 14 UV GRP CIPP 72-Inch, Item SPV.0090.03 C.1. | Mike Coleman | 3 | 2023-09-08 11:43 | 2023-09-11 09:01
20230912 | 20230912019 | 19 | Permits | Will the contractor be required to obtain any permits or will the state hold all of them? If contractor required, what permits will be required? | Permitting under Section 404 of the Clean Water Act is described under Article 7 Information to Bidders, U.S. Army Corps of Engineers Section 404 Permit. Temporary and permanent erosion control and storm water management is under Trans 401 of the Wisconsin administrative code and the Standard Specifications Section 107.20 Erosion Control. Permitting required for the contractors operations is discussed in the Standard Specifications Section 107.3 Permits and Licensing | Mike Coleman | 4 | 2023-09-08 11:45 | 2023-09-11 09:29