## qandasearchletting_results
Date:
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20231212 | 20231212001 | 1 | Special Provision 18 (Various Grooved MMA Markings) | Regarding the Swarco Megalux-Beads 30/50 Type 3131 or equivalent: What are the retro reflectivity requirements for the beads? Additionally, it is believed that the Swarco 3131 bead is an 18/20 bead and not a 30/50 bead. The closest similar size to a 30/50 bead is a Type I or Type 2 while an 18/20 bead is larger. Which is the correct type of bead, 30/50 or 18/20? | Please use either a 3131 or 18-50 bead also referred to as the â€œUtah Blend T-13â€. 275 will be used for a minimum retro reflectivity requirements for this | Mike Coleman | 1 | 2023-12-05 13:50 | 2023-12-08 10:44
20231212 | 20231212002 | 2 | Temporary Shoring | A previous question was asked regarding temporary shoring at the pier and the department indicated that no shoring is required along the piers. In review of the plans and staging it appears that shoring will be required for pier construction to maintain the adjacent abutments and fills for both stages. How will this shoring that is required to maintain traffic and the integrity of the structure its traveling on be paid for? There should be quantity for the piers accounted for under the existing temporary shoring item. | The temporary shoring at each abutment location is a representative area that may require shoring. The temporary shoring quantity for each abutment includes the slopes in order to maintain the slope backfill. Shoring for the piers is not anticipated. | Mike Coleman | 5 | 2023-12-06 11:34 | 2023-12-07 15:51
20231212 | 20231212002 | 2 | Geotech Report for B-28-184 and 185 | Looking for the Department to provide the Geotech Reports for Structures B-28-184 and 185 | The geotech reports can be found at the following location: https://wisdot.box.com/s/ocw89is19f1ud3m1c9nakiqlbw70x52u or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 3 | 2023-11-29 16:26 | 2023-12-04 13:41
20231212 | 20231212002 | 2 | Temporary Shoring | Temporary shoring is shown at the piers for structures B-28-184 and B-28-185. What is the purpose and how is it paid? That temporary shoring is not represented in the quantities. | The temporary shoring is not required along the piers. Plan sheets will be updated and quantities reviewed. | Mike Coleman | 1 | 2023-11-28 15:46 | 2023-12-04 13:37
20231212 | 20231212002 | 2 | bearing details sheet B-28-184 & B-28-185 | The drawing for structure B-28-184 on sheet 185 refers to a beveled anchor plate see the Bearing Details sheet; however, that is not included in the plan. Same note for structure B-28-185 on sheet 222. Please confirm if there is a anchor plate required, and if so, provide the bearing Details Sheet(s). | Plan sheet 185 (bridge sheet 22) of B-28-184 and plan sheet 222 (bridge sheet 22) of B-28-185 shows a beveled anchor plate at the bottom of the girder as well as a ï¿½â€ filler on pallet note in the Side View & Typical Section In Span detail. This plate and filler are not required. The note referring to steel anchor plate and Bearing Details sheet is not required as well as there is no bearing details sheet for these bridge plans. | Mike Coleman | 4 | 2023-12-04 15:14 | 2023-12-07 15:50
20231212 | 20231212002 | 2 | Removing Masonry | The Miscellaneous Quantities show that item 204.0185 is a SY item (page #47), but the bid item is paid by the CY. Are the Department's calculations for this item by the SY or the CY? | The Miscellaneous Quantity schedule shows SY but it should have been labeled as CY per the bid item measurement. The calculations were reviewed and they are in CY as they should be. | Mike Coleman | 2 | 2023-11-29 07:34 | 2023-12-04 13:37
20231212 | 20231212003 | 3 | Railroad Work Limits | Can the department provide the limits of the Railroad work limits? | Railroad-related work at crossing 387053U (near Station 35+56; approximately 200 feet north of Maple Street in Minnesota Junction) and crossing 387632D (near Station 239+08; approximately 200 feet south of Clay Street in Burnett) will be performed by WSOR within the existing railroad right of way. Milling and paving quantities are based on begin/end limits adjacent to the new railroad crossing surface (typically 5 feet from the centerline of the track). | Mike Coleman | 1 | 2023-11-30 16:16 | 2023-12-05 10:49
20231212 | 20231212003 | 3 | Schedule | Will the Department provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/n9oier9205le4seutjpm7ibynk8va0ai or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-11-30 16:17 | 2023-12-04 08:03
20231212 | 20231212004 | 4 | Asphaltic Surface Driveways | It appears there are driveways on the project. Can the Department please add an item for asphaltic surface driveways on this project? This will help avoid unnecessary testing requirements on driveways as well as avoid average weighting driveways with mainline paving. | The intention is to use bid item Asphaltic Surface for driveway work. Please note the project has many driveway callouts, many of which are asphalt, the intention is to just replace the asphalt shoulder â€œbump-outsâ€ in the rural mill and overlay section as shown in the construction details on sheet 7 of the plans. These â€œbump-outsâ€ are 2-ft in width and are expected to be placed in conjunction with mainline paving; therefore would use the Bid Item HMA Pavement 4 LT 58-28 S. There is one driveway in the reconstruct section (STA. 157+79, RT) which is existing base aggregate dense. This should be replaced as an asphalt driveway to the proposed R/W line. Construction of this driveway, along with the other field entrances in the reconstruct section, are detailed in Standard Detail Drawing 08D21-01 â€“ Driveways Without Curb & Gutter. Per the SDD, the top surface should be 2â€ to 3â€ Asphaltic Surface / HMA. The intention is to use the bid item Asphaltic Surface for this work. | Mike Coleman | 1 | 2023-11-21 09:25 | 2023-11-27 12:07
20231212 | 20231212004 | 4 | Culvert backfill | what items are being paid to accomplish the additional 10:1 cross drain installation detail on sheet 10 | There are two cross culvert installations on the project for which the detail on sheet 10 applies. The first location, at Sta. 161+86, is located within the curve realignment reconstruction section. Pay items at this location will only include the Culvert Pipe Reinforced Concrete Horizontal Elliptical Class HE-IV 19X30-Inch bid item and associated endwalls, as backfill is included in the cost of the pipe bid item and subbase, base, and HMA 4 LT 58-28 S are all included in the typical reconstruction section. The second location, at Sta. 372+73, is a twin set of culvert pipes. This location falls within the general mill and overlay section of the project. Pay items at this location include: the Culvert Pipe Reinforced Concrete Horizontal Elliptical Class HE-III 29X45-Inch bid item and associated endwalls, Base Aggregate Dense 1 ï¿½-Inch (10-inches thick), and Asphaltic Surface (4-inches thick). Excavation and backfill is included in the cost of the pipe bid item. | Mike Coleman | 2 | 2023-12-05 12:13 | 2023-12-07 04:55
20231212 | 20231212005 | 5 | Railroad Insurance | In Article 6 of the Specials, A.1 states to include specific information. The last line wants us to describe what work is taking place within 50 feet of the RR ROW. It states that a 'Curve Roadway' sign is being placed 150 feet from the track. Why is RR Insurance necessary for this project if we're 150 feet away from the track? | Please note that if any contractorâ€™s equipment or work will be within 50 feet of the railroad. Railroad insurance will be required. If you will not be within 50 feet, RR insurance will not be needed. An addendum will be issued to remove the article. | Mike Coleman | 1 | 2023-11-16 14:41 | 2023-11-21 08:42
20231212 | 20231212006 | 6 | Traffic Control | How does the DOT plan to handle traffic control for the work on structure B-62-63? Due to the planned repairs, the edge of the bridge deck will have reduced capacity once repairs have been started, and several of the guardrail posts are removed for the repairs. This could likely cause safety concerns if there was to be an impact with the in-place bridge railing. |  |  | 2 | 2023-12-07 06:35
20231212 | 20231212006 | 6 | Spec 104.6.1.2.4 (2) Changes | What is the intent of the changes to this specification with regards to protecting slopes exposed by removing protective measures? If guardrail needs to be installed by noon on Fridays, which will be before milling and paving has been completed on the project, will WisDOT be providing grades for the top of rail? Will we be allowed to adjust new guardrail according to Spec 614.3.5? | Standard Specification 104.6.1.2.4 (2) specifically mentions roads â€œopen to all trafficâ€. The intent for the project, according to the Traffic special provision article, is to close the highway to through traffic for completion of milling, concrete curb and gutter, paving and guardrail. An interim completion date is noted in the Prosecution and Progress special provision assigning and expectation when that work should be completed, as well as consequences for failure to complete certain project work by that date. The Department presumes the contractor will provide a schedule so all work for milling, concrete curb and gutter, paving and guardrail be completed by the interim completion date. As such, the guardrail work is expected to be completed before the roadway is opened to â€œall trafficâ€ and Standard Specification 104.6.1.2.4 (2) would apply. The Department will not be providing grades for top of rail. Installation of guardrail elements to appropriate height is an essential part of construction quality for the individual guardrail items. While SDD 114B44 does specifically mention that allowing for a wood block to be adjusted up to 3â€ above the top of post in posts 3 through 9 of Midwest Guardrail Terminal EAT (see CMM 626.1.5 for more discussion on this specific issue), no consideration for adjustment in new installation is provided in the case of other beam guard items and it is expected that wood posts will be flush with the top of blocking when complete. | Mike Coleman | 1 | 2023-12-04 10:30 | 2023-12-05 10:54
20231212 | 20231212007 | 7 | Cross Drain Installation Detail | On page 16 of the plan is show the detail for cross drain culvert pipe installation and it states all pipe excavation and granular backfill grade 2 is incidental to proposed culvert pipes. The 10:1's or "transition cut" should be paid for as excavation common and the transition cut backfill, granular backfill grade 2 in this case, should be a pay item (209.2100) as this is WIDOT industry standard for cross drain culvert pipe installation that are required to have a transition cut (10:1's). Please consider. | The design team agrees that there is an updated construction detail that better identifies the separate pay items associated with standard pipe excavation versus the extra common excavation and granular backfill grade 2 associated with the 10:1 transition cuts. The updated detail and adjustments to the miscellaneous quantities will be included in an upcoming addendum. | Mike Coleman | 1 | 2023-11-09 14:36 | 2023-11-20 07:39
20231212 | 20231212007 | 7 | EBS Backfill | What is allowed for EBS backfill? EBS Fill Detail (page 14 of plan) states engineer approved material from project excavation, while Earthwork Summary, NOTE 11 (page 180 of plan) states another. Please clarify. | The note in the Earthwork Summary will be adjusted to indicate that engineer approved material from project excavation will be allowed for EBS backfill. This change will be reflected in an upcoming addendum. | Mike Coleman | 3 | 2023-11-21 13:42 | 2023-11-29 06:27
20231212 | 20231212007 | 7 | Clearing & Grubbing Traffic Control | What is required for Traffic Control for Clearing and Grubbing operations? Given that these work operations will occur prior to April 1, 2024 there is a good chance that grading, base, etc. operations will not be occurring at that time. Can the road be shut down to traffic this winter for Clearing and Grubbing work and then opened again until all other work starts this spring? | Full closure of STH 19 and posting of the associated detour route will not be permitted until work on the existing pavement begins. If the contractor believes tree removal operations may necessitate additional width prior to the roadway detour being posted, the contractor may elect to implement daily single lane closures and flagging operations in coordination with the Engineer and as detailed in Section 104.6.1.2.2 of the Standard Specifications. It's also possible that roadway work operations could begin in March subject to weather conditions and the prime contractor's schedule, allowing for some tree removal work under closed and detoured roadway conditions prior to April 1. | Mike Coleman | 2 | 2023-11-17 13:50 | 2023-11-22 11:27
20231212 | 20231212007 | 7 | SPV 0165 Special 01 Stamping Concrete | Where is the work to be performed? The Special Provisions say "as shown in plans". A search of the plans shows this item only in the estimate of quantities. No Breakdown with locations or details. | See the structure plans for C-13-3098 on pages 433 â€“ 438 of the published plans. The concrete stamping details for the slope collars that will receive the treatment are specifically detailed on page 437. | Mike Coleman | 4 | 2023-12-06 12:17 | 2023-12-06 13:28
20231212 | 20231212007 | 7 | Earthwork Waste | Will the Department allow the use of loaded off road trucks on the resurfacing areas of the project? | No, written permission per Standard Specification 108.7.2 will not be granted. | Mike Coleman | 5 | 2023-12-11 09:23 | 2023-12-11 12:30
20231212 | 20231212008 | 8 | Soils Report | Can the Department provide the Geotechnical Report for this project? | The soils report can be found at the following location: https://wisdot.box.com/s/hzaybfqm9178jjykp5jweg46tj1pvzuj or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-29 10:40 | 2023-11-30 06:17
20231212 | 20231212009 | 9 | Addendum | BidX is showing you issued an addendum but it's not showing up on the Letting Information website. | It will be posted by 5:00 pm | Mike Coleman | 16 | 2023-12-07 15:37 | 2023-12-07 16:04
20231212 | 20231212009 | 9 | Pre-Approvals for Lighting | Can you confirm if there an opportunity to submit equivalent LED fixtures for review and pre-approval? Or will proposed fixtures be evaluated and approved after bid opening? | No. The City is trying to limit the number of fixtures they have to maintain. The specials called out a specific make and model because the city determined that is what they want to stock moving forward. | Mike Coleman | 1 | 2023-11-13 11:42 | 2023-11-22 06:09
20231212 | 20231212009 | 9 | Moving Structural Steel Sign Supports | Can you provide the size and number of structural bolts that are required for the Truss to Column connection? | Any information regarding the existing Sign Structure for S-13-111 and S-13-112 can be obtained from WisDOT Bureau of Structures Highway Structures Information System (HSI) database. The existing plans for S-13-111 and S-13-112 show eight (8) 3/4" diameter x 2-1/4" long H.S. bolts at each chord connection point for a total of 32 bolts per sign structure. The two plates being connected are each 1/2" thick. The contractor shall provide bolts long enough to entail the use of DTI washers which were not used on the existing structures. | Mike Coleman | 13 | 2023-11-29 13:10 | 2023-12-06 12:55
20231212 | 20231212009 | 9 | Railing Anchor Bolt Embedment Length | For both the tubular screening railing and the combination railing, the alternative adhesive anchor embedment length is listed at the typical 7-inches which is normal for a 9" anchor bolt length on a typical railing. Whereas this project has a non-typical 13 1/2" anchor bolt length. Is this embedment length incorrect? | The plan will be revised to show the corrected alternate adhesive anchor embedment length. | Mike Coleman | 6 | 2023-11-21 10:34 | 2023-11-29 12:07
20231212 | 20231212009 | 9 | Railing Anchor Bolt | Is an ASTM A193 Type 316 anchor bolt an acceptable substitute to the ASTM F593 Type 316 listed in 513.2.1(4)? This would apply to both the Tubular Screening Railing and the Combination Railing. | No, materials should be provided per specifications and plan. | Mike Coleman | 5 | 2023-11-21 10:21 | 2023-11-29 11:38
20231212 | 20231212009 | 9 | Floor Drain | Is it acceptable to substitute a Type H floor drain for the shown Type GC? A few issues, a Type GC floor drain doesn't meet ADA requirements (1/2" sphere requirement & 1/4" height differential requirement), while the standard Type H drain also doesn't meet this requirement, a construction detail could be provided to require a fabricated ADA grate. Additionally, Type GC castings can have extended lead times that can affect construction schedules. | Yes this is an acceptable substitute, plan sheets will be revised to show an ADA compliant grate for the Type GC drain. | Mike Coleman | 3 | 2023-11-21 10:16 | 2023-11-29 12:06
20231212 | 20231212009 | 9 | Concrete Masonry Bridges - Quantity | Note on plan states that the concrete deck on the prefabricated bridges is included in the Prefabricated bridge pay item. The special provisions measurement & payment section for the prefabricated bridge does not mention payment for the concrete deck. Please confirm where the concrete deck is paid. Also confirm the Concrete Masonry Bridges quantity. | The concrete deck on the truss is paid as part of the truss bis item. The special provisions has been revised via addendum to reflect this. Concrete Masonry items have been confirmed. | Mike Coleman | 14 | 2023-11-30 09:50 | 2023-12-04 13:49
20231212 | 20231212009 | 9 | Temporary Precast Barrier | Please confirm the Department will pay for delivery of the temporary barrier when it is relocated from Stage 1 to Stage 2 as indicated in the Miscellaneous Quantities table. | Yes, the payment for delivery of the temporary barrier should be paid according to the miscellaneous quantities as shown. | Mike Coleman | 2 | 2023-11-21 10:07 | 2023-11-29 11:36
20231212 | 20231212009 | 9 | City of Madison Standard Specification | Please update special provision #08 to include a written description detailing which version of the City of Madison Standard Specification is being referenced in the hyperlink. The current link is for 2023 but may change as construction progresses. | It will be the 2023 City of Madison Standard Specs, it wonâ€™t change through construction. | Mike Coleman | 9 | 2023-11-28 08:58 | 2023-11-29 12:05
20231212 | 20231212009 | 9 | Sign Structure Anchor Rod | Please verify the dimensions of the relocated sign structure's anchor bolts. The bid plan dimensions on plan sheet 225 & 229 do not match Standard Spec 531.2.2(2). | The plan shall be revised to show corrected thread dimension for anchor bolts. | Mike Coleman | 8 | 2023-11-28 07:40 | 2023-11-29 12:09
20231212 | 20231212009 | 9 | Buy America Provision | Should the Buy America Provision be updated to include the changes made to CMM 228.5 in November 2023? | A Buy American addendum was issued. | Mike Coleman | 11 | 2023-11-28 12:46 | 2023-12-07 15:41
20231212 | 20231212009 | 9 | Floor Drain Quantity | Should the quantity of floor drains be two or are the pair paid as one because they're connected by the downspouts? | The plan floor drain quantity shall be revised to be 2. | Mike Coleman | 7 | 2023-11-21 10:41 | 2023-11-29 12:08
20231212 | 20231212009 | 9 | Project Prosecution and Progress | The project bids on December 12th and requires a 90 day notice to the FAA/MSN Airport prior to beginning any onsite work, but clearing must be completed prior to March 31st. With the week+ time likely required for the Department to award the project and time required to complete clearing, please advise how this schedule is to be met. |  |  | 15 | 2023-12-05 09:10
20231212 | 20231212009 | 9 | Railing Member Details | The railing tubular screening is a modified standard detail. There is a carry over of using a 1/2" x 2 1/2" end spindle at the cantilever railing locations (Reference Plan Sheet 215). With the modified design using a 3" tubular rail a 2 1/2" end spindle would not be suitable. Please clarify the end spindle detail. Additionally, on Plan Sheet 215 there is a detail called "TYP AT MID-RAIL DETAIL". I would assume this is a reference to the top rail as it calls for a 2 1/2" x 2 1/2" square plate and this top rail is terminating at a stand alone post. It is unclear what is being detailed or where the detail is being applied. | The railing detail "TYP AT OVERHANG DETAIL AT TOP AND BOTTOM RAILS" will be revised to reflect the correct tubing and end spindle. The "TYP AT MID-RAIL DETAIL" will be removed as it is not used. These changes will be accomplished via addendum. | Mike Coleman | 12 | 2023-11-28 14:34 | 2023-12-04 13:51
20231212 | 20231212009 | 9 | Adjusting Sanitary Manhole Cover | The Special Provision #29 states the adjustment range will be between 3 inches and 9 inches. The manhole at STA 101+34 will exceed this tolerance. Additionally, the special provision states that payment is full compensation for "replacing". What replacement activity is to be included in the bid? | The field surveyed manhole will need to be adjusted approximately 6 inches to be brought to finished grade. The special provision will be revised and the reference to replacing removed. | Mike Coleman | 10 | 2023-11-28 09:43 | 2023-12-04 13:47
20231212 | 20231212009 | 9 | Asphalt Mix Design | What mix is to be supplied under the Asphaltic Surface bid item? | The mix for the bid item Asphaltic Surface should follow the Standard Specification 465.2. | Mike Coleman | 17 | 2023-12-08 10:22 | 2023-12-11 11:30
20231212 | 20231212009 | 9 | Railing Base Plate Material | Would it be acceptable to substitute ASTM A572 Grade 36 plate for the specified ASTM A709 Grade 36 plate for both the Tubular Screening and Combination Railing base plates? | An acceptable substitute would be ASTM A572 Grade 50 or 55. | Mike Coleman | 4 | 2023-11-21 10:18 | 2023-11-29 11:37
20231212 | 20231212012 | 12 | Request for Contract Time Extension | 75WD's for a project of this magnitude and complexity seems extremely aggressive. Would the department consider a request for additional working days be added to the contract? | The working days were based on published production rates and past project. The corridor is a major route into and out of West Salem and from the northern La Crosse area Communities. The department is comfortable with the working days currently proposed. | Mike Coleman | 7 | 2023-12-06 13:48 | 2023-12-07 15:47
20231212 | 20231212012 | 12 | Geotech Report - request | Can the Department provide the geotech report. | The soils report can be found at the following location: https://wisdot.box.com/s/re77bx1wp2yvgxvhpb9oel87nn3avetp or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-29 14:29 | 2023-11-30 10:36
20231212 | 20231212012 | 12 | Seal Concrete | Can the dimensions of each seal be given for the project? | The seal dimensions shall be a minimum of 3 feet greater than the pier footing dimensions. | Mike Coleman | 2 | 2023-11-30 10:55 | 2023-12-04 06:45
20231212 | 20231212012 | 12 | Cofferdams | Cofferdam seals are designed for a water elevation of 675.00 . The Q2 elevation on the project is 681.54. How will contract time and other contractor expenses be handled if work canâ€™t proceed due to water elevations above 675.00? | We felt this was an adequate water surface elevation to design the concrete seal based on discussions with the county and WisDOT. The observed water elevation was taken on 4/23/21. If a contractor feels this seal and cofferdam shall be resized according to their feel for the water elevation, then the bid should reflect this. We state what the water elevation the seal was designed for to assist the contractor in understanding our interpretation. | Mike Coleman | 5 | 2023-12-05 13:25 | 2023-12-11 06:42
20231212 | 20231212012 | 12 | Contract Time | Current contract time is very aggressive. Considering the amount of work, was there any consideration given to allowing more than 75 wd? Can the project schedule be provided? | The working days were based on published production rates and past project. The corridor is a major route into and out of West Salem and from the northern La Crosse area Communities. The department is comfortable with the working days currently proposed. | Mike Coleman | 6 | 2023-12-05 13:26 | 2023-12-07 15:47
20231212 | 20231212012 | 12 | Superstructure Concrete Quantity | Please double check concrete quantity for bridge superstructure. | The superstructure quantity was incorrect in the table of Estimated Quantities. The revised superstructure concrete quantity should have been 584 CY instead of 413.2 CY. | Mike Coleman | 3 | 2023-12-05 10:17 | 2023-12-07 04:46
20231212 | 20231212012 | 12 | 503.0172 EOQ | The EOQ lists item 503.0172 prestressed girder as 972 LF; however, the beam quantities only add up to 954 LF. Please confirm which quantity is correct and provide additional details, if necessary. | Sheet 2 of the bridge plan, in the Estimate of Quantities table has bid item 503.0172 incorrect. The correct quantity should be 954 linear feet. All other details in the plan set are correct in depicting the girder length. | Mike Coleman | 4 | 2023-12-05 11:01 | 2023-12-07 04:48
20231212 | 20231212013 | 13 | B-32-181 Work | Can the work on B-32-181 be done at the same time as the 15 working day closure or does it have to be done separately under flagging? | The work on B-32-181 may be done at the same time as the 15 working day closure. If done during the road closure, this work must also comply with the road closure and traffic control conditions in the â€œInterim Completion and Liquidated Damages â€“ STH 108 Culverts and Slope Stabilization: 15 Work Daysâ€ section of the Prosecution and Progress special provision. | Mike Coleman | 7 | 2023-12-06 11:35 | 2023-12-06 13:29
20231212 | 20231212013 | 13 | Pavement Marking | Good Morning, The current bid item for the permanent marking is surface applied Marking Line Epoxy 6-Inch. Should this project have Marking Line Grooved Wet Reflective Epoxy 6-Inch for the permanent marking? | The item should be Marking Line Grooved Wet Reflective Epoxy 6-Inch. An addendum will be issued for the change. | Mike Coleman | 1 | 2023-11-30 10:33 | 2023-11-30 11:37
20231212 | 20231212013 | 13 | Barrier System Grading Shaping Finishing | If page 58 bottom table is the summary of incidental items and quantities, then what is the right side table at the top of page 59? | The right side of the table â€œGuardrail Summaryâ€ on page 59 are preliminary estimates and are in error. An addendum has been submitted to clarify. | Mike Coleman | 6 | 2023-12-06 10:45 | 2023-12-06 13:12
20231212 | 20231212013 | 13 | Cross Culverts | Is the common Excavation and backfill soils for the cross culverts incidental to the pipe item itself? | Excavation and backfill for cross culverts is included in the unit price per LF according to Standard Specification 520.5.2. | Mike Coleman | 3 | 2023-12-01 16:07 | 2023-12-04 07:40
20231212 | 20231212013 | 13 | Barrier System Grading Shaping Finishing | Is there a table for bidding purposes only that includes the quantities of all the incidental items included in this item? (Common Ex, Borrow, Salvage topsoil, restoration) | Earthwork for Barrier System Grading, Shaping Finishing is summarized in the Earthwork Summary table on page 58. Topsoil, seeding and fertilizer were not included in the plans and will be estimated in an addendum. | Mike Coleman | 4 | 2023-12-01 16:09 | 2023-12-04 07:59
20231212 | 20231212013 | 13 | Station 37+50 | Should the pipe for this station be Corrugated Steel? Sheet 12 shows it as steel. Sheet 58 shows concrete and the table on sheet 53 shows 50' of concrete for item 78. | The culvert pipe at STA 34+50 will be changed to Culvert Pipe Class III-B 24-Inch. An addendum will be issued to update the plan sheet and quantities. | Mike Coleman | 2 | 2023-11-30 13:32 | 2023-12-04 05:32
20231212 | 20231212015 | 15 | Traffic Control | Are the traffic control closures shown on sheets 8 - 36 expected to be longterm closures such that they can always be left up? If the closures are longterm, can the contractor work within those closures during the daytime with equipment and materials? | All freeway and local road lane and shoulder closures need to adhere to language included under the â€˜Freeway and Ramp Closure Restrictionsâ€™ and â€˜Local Road Closure Restrictionsâ€™ sections within the Prosecution and Progress article of the project specifications. | Mike Coleman | 9 | 2023-12-04 11:52 | 2023-12-05 06:25
20231212 | 20231212015 | 15 | Roadside Clearing | Can station ranges for roadside clearing be provided? | The number of stations for Roadside Clearing at individual walls are estimated amounts and not based on specific station ranges. Tree growth and/or falling branches that are impacting noise walls are changing over time. The contractor should bid the item based on current conditions at each wall. | Mike Coleman | 6 | 2023-11-29 09:52 | 2023-11-30 06:26
20231212 | 20231212015 | 15 | Noise Wall Shop Drawings | Can the Department please provide the shop drawings for the various noise walls? The DOT's structure website does not appear to have records of all the shop drawings (notably the N-40-17 wall). These will be needed for the post/panel replacement as well as the post foundation removal/replacement. | All available as builts and shop drawings are available. However, the information is incomplete. For example, the Department is not able to locate shop drawings for N-40-17, as well as other noise walls. The as-builts and shop drawings available can be found at the following location: https://wisdot.box.com/s/o4a2m5lpk6ugwufs2ft443deq8937w96or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 5 | 2023-11-27 16:52 | 2023-11-29 12:17
20231212 | 20231212015 | 15 | Schedule | Could the Department please provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/o4a2m5lpk6ugwufs2ft443deq8937w96 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-11-20 10:46 | 2023-11-21 08:37
20231212 | 20231212015 | 15 | Top Panel Support Repair Detail - Concrete Post | Please provide the detail for the top panel support repair detail for the concrete posts. Right now, the plans only show the detail for the h-pile post support repair (i.e. Structure N-40-17 page 97, sheet 2 of 2) | The top panel support repair detail was inadvertently included on the N-40-17 plans. An addendum will be issued to remove the detail and correct the quantities. | Mike Coleman | 2 | 2023-11-21 12:24 | 2023-11-28 06:32
20231212 | 20231212015 | 15 | N-40-17 Post Foundation | Since the Department does not have the shop drawings for the N-40-17 wall, please provide the existing post foundation depths and widths for item SPV.0060.03. | Since the Department canâ€™t locate shop drawings for N-40-17, the existing post foundation depths and widths are not known. The contractor is expected to design replacement posts based on the â€˜Noise Barrier Loading Diagramâ€™ detail that is being added via addendum and the required 35 PSF loading â€“ see question #3. These design requirements may be different from what was used for the original wall design, resulting in replacement posts having a different depth and width than the original posts. | Mike Coleman | 8 | 2023-11-29 13:06 | 2023-11-30 10:33
20231212 | 20231212015 | 15 | Noise Barrier Support Post Replacement | SPV 18 for the noise barrier support post replacement requires the contractor to "design" the new replacement post. Please advise what loads we are designing for as the plans and specs currently do not have any required design loads. | The replacement posts for N-40-17 are part of the ground mounted portion of the noise barrier. Those posts should be designed for 35 PSF. A â€˜Noise Barrier Loading Diagramâ€™ detail will be added to the plan as part of an addendum. | Mike Coleman | 3 | 2023-11-27 14:21 | 2023-11-29 06:24
20231212 | 20231212015 | 15 | Replacement Noise Barrier Panels Color | SPV 22 requires the "colors and surface textures must closely match those of the individual panel being replaced". Most of these walls are pretty old and colors on the panels have faded over time from what was originally installed per the as-built shop drawings. Please advise how the panel supplier is supposed to match the colors of the new panels to the existing panels onsite that have no federal color associated with them due to weathering over years. | The contractor will need to work with the construction engineer to develop acceptable color matches for the various posts and panels being replaced, as well as where concrete surface repair is required. Perfect color matches are not expected, and the contractor is not expected to provide matches at every single repair/replacement location of a noise wall. Best fits for colors at each wall will be acceptable and will be based on working with the construction engineer. | Mike Coleman | 4 | 2023-11-27 14:30 | 2023-11-29 06:35
20231212 | 20231212015 | 15 | Protective Coating Clear - Both Sides of Posts? | The protective clear coating notes for the N-40-0008 call for "Protective coating clear to be applied to all posts roadside faces". The N-40-0017 wall calls for "Protective Coating Clear to be applied to all concrete posts 14-191". Assuming that there is a typo and post 191 is supposed to be 119 (Per the drawing, there are only 119 posts at the 17 wall), does the State want both sides of the concrete posts to have the protective coating clear applied? If so, will there be additional roadside clearing added at the backside of 17 wall as there is currently no clearing planned at the 17 wall. | The N-40-17 the protective clear coating only needs to be applied to the roadside faces of the concrete posts. The note will be updated, including the number of posts, as part of an addendum. | Mike Coleman | 7 | 2023-11-29 11:52 | 2023-11-30 06:27
20231212 | 20231212015 | 15 | Protective Coating Clear | The spec is vague on product requirements for the Protective Coating Clear (502.6500) bid item, is there a list of products or an approved list of products that must be used for this bid item. | There is not an approved products list. The material selected by the contractor needs to meet the spec requirements as defined in 502.2.13. | Mike Coleman | 10 | 2023-12-04 12:56 | 2023-12-06 12:54
20231212 | 20231212016 | 16 | Deck Chipping/Full Depth Repairs/Temporary Supports | (1) Is deck chipping allowed on these bridges in the areas above live Capitol Drive traffic? (2) If full depth repairs on the overlay bridges are present over both lanes of Capitol Drive traffic is the intention to do the repairs over the 'live' lanes with full closures at night or would these repairs have to be done in two different stages and the temporary span supports moved? If done in stages and the temporary supports are moved, would the pay quantity overrun accordingly? | 1) The contractor is responsible for protecting facilities below their operations per standard specifications 107.8, 104.6, and 203. If the contractor chooses to chip the deck over live traffic, it is recommended to perform removing loose concrete operations below slab prior to chipping. 2) The full depth repairs over the inside lanes of Capitol Dr will require full nighttime closures when in the Capitol Dr outside lane closure configuration for stages 1B, 1C, and 2. All full depth repairs must reach 3,500 psi strength prior to removing temporary supports. The note on page 87 of the plan stating full depth repair as a construction operation when in the inside lane closure configuration is incorrect. All full depth repair should occur with all temporary supports in place as shown on page 74 of the plan. The plan quantity is correct. | Mike Coleman | 2 | 2023-12-06 16:33 | 2023-12-08 06:41
20231212 | 20231212016 | 16 | Vertical Clearance | It has been allowed on past projects to reduce the vertical clearance for structures temporarily with proper signage and warning. Is it anticipated that a temporary reduced vertical clearance of the Capitol Dr frontage roads would be allowed for bridge painting? For reference, WisDOT project 1228-22-72 allowed a temporary 14' clearance for a non-OSOW route. | A temporary vertical clearance reduction to 14â€™ over the Capitol Dr frontage roads is allowed with proper signing and advance warning. | Mike Coleman | 1 | 2023-12-06 16:11 | 2023-12-07 15:55
20231212 | 20231212017 | 17 | Asphaltic Surface - 1 or 2 lifts? | For the 5" cycle track paved under the Asphaltic Surface item, will the contractor be allowed to pave this in a single lift? Or will two lifts be required? |  |  | 1 | 2023-12-01 12:34
20231212 | 20231212018 | 18 | Can the soils report please be provided? | Can the soils report please be provided? | The soils report can be found at the following location: https://wisdot.box.com/s/iqtxbrwayqe595w1ccl9hukw8l30lyg7 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-19 10:28 | 2023-11-21 07:41
20231212 | 20231212018 | 18 | Schedule | Could the Department please provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/iqtxbrwayqe595w1ccl9hukw8l30lyg7 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-11-20 10:47 | 2023-11-21 09:14
20231212 | 20231212018 | 18 | Turbidity Barrier Concerns | FDM 10-10-45 states that turbidity barriers are not recommended where currents exceed 5 ft/second. Plan hydraulic data states 2 year velocity of 6.22 FPS and 100 year of 7.96 FPS. Furthermore, if this work is done in early spring the velocities are typically much higher. Will the Department compensate the contractor for BMPs and/or diverters needed above and beyond turbidity barrier? | The Turbidity barrier is an acceptable option to the DNR in this sensitive yet fast flowing water, to allow for installation and work access. Rock bags are included to hold the barrier in place and for diversion. Due to shallow bedrock alternatives like sheet pile cannot be employed. The barrier could be altered by the contractor with DNR coordination, and the current bid price should include the necessary alterations to the barrier to meet DNR requirements for instream restrictions. Repairs will be paid for by the Department. | Mike Coleman | 5 | 2023-12-05 13:45 | 2023-12-08 06:35
20231212 | 20231212018 | 18 | ESTIMATED QUANTITIES | For the proposal line number 0472 for Traffic Signal Face 3S 12-Inch the estimated quantity is showing 15, but that number matches the intersection of STH 38 & Rapids Dr. It does not seem to account for the quantity of 1 on the other intersection of STH 38 & Old Mill Rd. So should the total quantity be 16? | The estimated quantity of 15 Total for Line 0472 (Traffic Signal Face 3S 12-Inch) is correct. The Construction Notes on the Traffic Signal Removal Plan for STH 38 & Old Mill Rd (Sheet #76) state that the signal pole and signal head #16 will be salvaged and reinstalled on a new concrete base. Therefore, the 658.0173 item (Traffic Signal Face 3S 12-Inch) isnâ€™t needed at STH 38 & Old Mill Rd since weâ€™ll be reusing the existing signal face. | Mike Coleman | 4 | 2023-11-29 15:26 | 2023-12-04 13:52
20231212 | 20231212018 | 18 | B-51-157 - Pre-Stage 1 Full Depth Deck Repair Locations | Please provide the approximate locations of the full depth deck repairs that are called out to be performed pre-stage 1. |  |  | 3 | 2023-11-20 11:42
20231212 | 20231212018 | 18 | Lighting Install Print & Conduit Removal | There is no lighting plan, only a lighting removal. Are we reinstalling? In the lighting removal plan the prints call for the removal of all 2" PVC, but there is no line item for this. We would normally abandon in place, is this acceptable? |  |  | 7 | 2023-12-07 09:45
20231212 | 20231212018 | 18 | Excavation Rock - Blasting | Will blasting be allowed to aid in the removal of bed rock for subgrade, ditching, and/or storm sewer work? |  |  | 6 | 2023-12-06 15:18
20231212 | 20231212019 | 19 | 48" depth | is there depth information on the 48" storm sewer replacement in Silvernail | The approximate depth to invert is 5.9 feet. | Mike Coleman | 2 | 2023-12-05 13:37 | 2023-12-06 08:01
20231212 | 20231212019 | 19 | Common Excavation Qty and Earthwork Table | Per the project plan set on Page 132, Earth work summary table. There are associated notes 8,9,10 on the page regarding the excavation for Sidewalk, Curb & Gutter and Base patching. That all excavation for these items is not included in the table and â€œShouldâ€ be considered additional waste, incidental to the item. However, per the standard specifications for Base patching, Curb & Gutter and Concrete sidewalk, the specification is written that department will pay for excavation either under other contract bid items; or if covered by a bid item in the contract, as specified in the specifications; or if the contract has an excavation bid item, the department will pay separately for excavation. Please see include specifications below. No mention of the Base patching, Curb & Gutter, or Concrete sidewalk Excavation is included in the special provisions for the project. Will the department be issuing an addendum to revise the Common excavation quantity and revised earth worktable? 390.5 (6) (6) If the engineer orders the contractor to excavate yielding or unstable subgrade materials and backfill with suitable materials, the department will pay for that work either under other contract bid items, or as extra work. 601.4 (4) (4) The department will measure excavation required for and performed during this work, if covered by a bid item in the contract, as specified in the specifications. However, if the contract does not provide a bid item for excavation, it is incidental to the work. 602.5.2 Payment for the Concrete Sidewalk, Loading Zone, and Steps bid items is full compensation for providing concrete and reinforcement; for granular subbase or aggregate base; for excavation and backfill; and for restoring the site. Payment also includes providing tie bars and dowel bars in unhardened concrete. For tie bars and dowel bars provided in concrete not placed under the contract, the department will pay separately under the Drilled Tie Bars and Drilled Dowel Bars bid items as specified in 416.5. If the contract has an excavation bid item, the department will pay separately for excavation. | â€¢ Base patching o From ASP-6, 390.5 (2): Payment for Removing Pavement for Base Patching is full compensation for removing old pavement; for preparing the foundation and bringing up to grade. If the engineer orders the contractor to excavate yielding or unstable subgrade materials and backfill with suitable materials, the department will pay for that work with contract bid items or as agreed upon using 109.4 o Pavement removal is paid under item 390.0100 o EBS was done when the roadway was reconstructed. No EBS is anticipated for this work, so no change is proposed to the quantity for excavation common. â€¢ Concrete curb & gutter: o 601.4 (4): The department will measure excavation required for and performed during this work, if covered by a bid item in the contract, as specified in the specifications. However, if the contract does not provide a bid item for excavation, it is incidental to the work. o Since curb is being replaced in its existing location, and removal is paid under item 204.0150, for simplicity we propose to modify 601.4 (4) to: Excavation required and performed during this work is incidental to the work. â€¢ Concrete sidewalk: o 602.5.2 (1): Payment for the Concrete Sidewalk, Driveways, Loading Zone, and Steps bid items is full compensation for foundation excavation, preparation, and backfill if there is no adjacent roadway excavation taking place; for granular subbase or aggregate base if there is no adjacent roadway subbase or aggregate base being placed; providing concrete and reinforcement, and for restoring the site. Payment also includes providing tie bars and dowel bars in unhardened concrete. The department will pay separately for tie bars and dowel bars used to connect the work to concrete not placed under the contract under the Drilled Tie Bars and Drilled Dowel Bars bid items as specified in 416.5. The department will pay separately for coloring concrete as required. o Since there is no roadway excavation adjacent to proposed concrete sidewalk, we read this to say that foundation excavation is incidental to this work. o To follow this specification with respect to base aggregate, we propose to modify the MQ table for â€œAggregateâ€ by combining the â€œCurb & Gutter,â€ â€œSidewalk,â€ and â€œDrivewaysâ€ lines into a single â€œUndistributedâ€ line, with the intent that this quantity is used to supplement existing base aggregate where needed throughout the project (curb, driveways, base patching, etc.). We would also add a note below this table: â€œConcrete sidewalk 5-inch shall be constructed over 4 inches of Base Aggregate Dense 1 ï¿½-Inch. Payment for aggregate base beneath sidewalk is incidental to the bid item Concrete Sidewalk 5-Inchâ€ | Mike Coleman | 1 | 2023-12-04 13:25 | 2023-12-05 10:47
20231212 | 20231212020 | 20 | Topsoil / Concrete Sidewalk | It appears that there isn't a quantity for topsoiling behind the curb and gutter that is to be removed and replaced. How is this topsoiling going to be handled? It also appears on the north end of the project where the median curb and gutter is to be removed and replaced there is no quantity for median concrete sidewalk removal. Is it planned to remove and replace the curb and gutter while leaving the median sidewalk in? | Topsoil was not included as a bid item behind the concrete curb and gutter. Existing soil is adequate at replacement locations and site restoration is included as part of the concrete curb and gutter bid item. Spot replacement of concrete curb and gutter adjacent to sidewalk is intended to be completed while leaving the median sidewalk in place. | Mike Coleman | 7 | 2023-12-07 09:09 | 2023-12-11 06:47
20231212 | 20231212020 | 20 | AC Grade | On page 19 of the Specials the AC Grade for the SMA calls out 58-28 H. In the Miscellaneous quantities on page 111 of the plans as well while bid item # 50 in the Proposal Schedule of items, page 2 of 9, calls out 58-28 V. Would the department please clarify which grade of Ac should be bid. | The Special Provision bid item is incorrect. SMA 58-28 V, as indicated in the miscellaneous quantities and proposal is the correct bid item An addendum will be submitted to update the special provisions. | Mike Coleman | 2 | 2023-11-27 10:45 | 2023-11-28 06:31
20231212 | 20231212020 | 20 | Stage 3A Off Peak | On page 7 of the Specials, specifically Stage 3A -Off Peak, it is stated the Left Turn Lane closure may be permitted for only one night. This intersection includes installation of the Sloped Nose Median as well as Removing Asphaltic Surface and installation of lower layer of HMA. The contractor will require 4 nights to perform this work. | The intent of the single night I-41 left turn lane closures used in conjunction with the CTH T restriction to right-in/right-out movements only is for milling and paving of the intersection. Closures of the I-41 left turn lanes is allowed during off-peak periods for consecutive nights to complete construction of the Concrete Median Sloped Nose provided the intersection remains open to cross-traffic. The continuous closure of the I-41 left thru-lane allows for protection of the Concrete Median Sloped Nose work with traffic control devices during daytime periods while the left turn lanes are open to traffic. | Mike Coleman | 4 | 2023-12-04 11:05 | 2023-12-05 06:23
20231212 | 20231212020 | 20 | Removing Asphaltic Surface Quantity | Per sheet 10 of the plans, it calls for the median to be paved with 2" of Asphaltic Surface, the mix quantity is accounted for in the miscellaneous quantities on sheet 112. The removal of the asphaltic surface in this area does not appear to be accounted for. Will that be added? | Added a quantity for removal of asphaltic material in this area. An addendum will be submitted to update the plans and quantities. | Mike Coleman | 5 | 2023-12-06 07:43 | 2023-12-06 12:50
20231212 | 20231212020 | 20 | Curb Patching | There is 5,092 LF on new curb being installed that will require patching. Will Asphaltic Surface be used for this and if so can that quantity be added to the Asphaltic Surface Items listed on Sheets 11 & 112. | Added a Construction Detail and updated the Miscellaneous Quantities to address patching at new curb installation. An addendum has been submitted to update the plans and quantities. | Mike Coleman | 3 | 2023-11-30 15:18 | 2023-12-05 06:23
20231212 | 20231212020 | 20 | Mix Type for Intersections & Turn Lanes | Would the department consider changing the mix type of the upper layer for the turn lanes and intersection from SMA to 4HT? In past projects (I-43, I-41, STH 172) the ramps have not been paved with SMA but with a 4 HT. | The department will allow HT mix to be used in the turn lanes and intersections for this project. | Mike Coleman | 6 | 2023-12-06 08:46 | 2023-12-06 13:05
20231212 | 20231212020 | 20 | Construction Schedule | Would the Department provide their construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/hr131q4geyg7qh7g7cr6qtuhves51z0o or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-11-27 10:38 | 2023-11-28 06:29
20231212 | 20231212021 | 21 | Department Construction Schedule | Can the department provide the construction schedule used in design? | The design schedule can be found at the following location: https://wisdot.box.com/s/fmrdxtc061jsk4pamn3f16oq5h3irf43 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2023-11-27 11:32 | 2023-11-28 06:22
20231212 | 20231212021 | 21 | Sand Barrel Arrays | For the Sand Barrel Arrays (Line 0118), do you have a drawing of the Overhead Sign Support that these will be protecting? Looking for the dimensions of the base (width, etc....). | We do not have the drawings readily available showing the Overhead Sign Support for each of the sand barrel array locations. We did take some field measurements of the support bases. The bases were approximately 2.75 feet wide by approximately 7.25 feet long. The heights ranged from 1.7 to 2.5 feet high. | Mike Coleman | 1 | 2023-11-13 16:29 | 2023-11-16 12:59
20231212 | 20231212021 | 21 | Sand Barrel Arrays | It appears the existing base, which is to be paved over, is not long enough for the new sand barrel array arrangement by length. Will a concrete base extension be required or will an extension of just an asphalt base be sufficient to accomplish the extension? |  |  | 11 | 2023-12-11 09:35
20231212 | 20231212021 | 21 | Inlet extension rings | Notes in the misc quantities say that we are suppossed to replace the top wo rings at the same locations as these proposed extension rings. There also appears to be no curb replacement at these locations which I would expect, is this plan note in error? Are we really supposed to replace the top two rings without removing and replacing some c&g? Isn't the intent of the extension rings to make the raising of the grate rim elevation simpler by just removing the grate, dropping in the extension ring and reseting the grate prior to the asphalt overlay? Please advise. | The remarks portion of the misc. quantities will be revised to only have the note â€œEXISTING CASTING SIMILAR TO TYPE A, REPLACE TOP TWO RINGSâ€ note for the locations where we are adjusting inlet covers and not where we have the inlet extension rings only. The intent is that the extension rings make it simpler by dropping in the extension ring and resetting the grate prior to the asphalt overlay. We do have locations where we are adjusting inlet covers by replacing the top two rings and using the extension rings, but at these locations we are also replacing curb and gutter. Those quantities are accounted for. An addendum will be issued with the applicable above revisions. | Mike Coleman | 10 | 2023-12-05 16:14 | 2023-12-07 15:49
20231212 | 20231212021 | 21 | Base Patching | On Page 22 the Base Patching Concrete Detail ** states the patch could be as small as 2' x 6' is it the DOT's intention to actually stop the base patch in the middle of a 12' panel or possibly just to fix a portion of the panel? If this is true, the miscellaneous quantities are inflated. Could this be clarified? | An addendum will be issued that will revise the construction detail and quantities to address this and provide clarification. | Mike Coleman | 3 | 2023-11-30 12:57 | 2023-12-04 06:48
20231212 | 20231212021 | 21 | Saturday work | Permitted lane closures seem to not address Saturday work. The contractor can close the lanes on the highway Friday night at 6PM but must have open before midnight. Is this the intent? Please clarify. | An addendum will be issued to address permitted lane closures for Saturday work and provide clarification. | Mike Coleman | 8 | 2023-12-05 09:09 | 2023-12-07 15:43
20231212 | 20231212021 | 21 | Inlet adjusts | The notes in the misc. quantities says that we are supposed to replace the top two rings, per DOT specifications shouldn't these be called classified and paid as reconstructs? | The locations identified for Adjusting Inlet Covers do not require removal of masonry beyond the grade adjustment devices (top two rings) specified in the plan. The item should be bid accordingly and will not be changed to reconstructs. | Mike Coleman | 9 | 2023-12-05 16:08 | 2023-12-07 15:43
20231212 | 20231212021 | 21 | University Ave / Nicolet Dr. / Bay Settlement Rd | There are no time restrictions listed in the Traffic Section "construct under single lane closures". Can these local streets be closed at any time of day? | University Avenue / Nicolet Drive / Bay Settlement Road can have single lane closures at any time of the day. | Mike Coleman | 6 | 2023-12-05 08:53 | 2023-12-06 13:02
20231212 | 20231212021 | 21 | Detour for Bay Settlement Ramps | This section states the 4 ramps at Bay Settlement can be closed for a maximum of 7 calendar days. The detour route for all 4 ramps is the same. Can they all be closed at the same time? | The 4 ramps at Bay Settlement Road can be closed at the same time if the closures do not violate the two consecutive ramps being closed simultaneously portion of the special provisions. | Mike Coleman | 7 | 2023-12-05 08:57 | 2023-12-07 15:41
20231212 | 20231212021 | 21 | University Ave/ Nicolet Dr Surface HMA Type | Would the department consider changing the HMA surface mix on University Ave/ Nicolet Dr. from a 4 SMA to a 4 MT or HT? The short lengths, intersections, and typical requirement to taper the HMA at the curb and gutter present constructability issues with SMA due to the use of a transfer machine and the limited workability of the SMA mix. | We reviewed the pavement needs for University Ave/ Nicolet Dr and determined that interlayer/SMA is needed, however we are including revisions in the next addendum that will address some of the constructability concerns in those areas. | Mike Coleman | 4 | 2023-12-01 10:11 | 2023-12-06 12:59
20231212 | 20231212021 | 21 | Nicolet Dr./ University Ave/ Bay Settlement (Service Ramps) HMA Type | Would the department consider changing the mix type on these ramps from Interlayer/SMA/4 LT to entirely 4HT or entirely Interlayer/SMA? In past projects (I-43, I-41, STH 172) the ramps have not been paved with SMA but with a 4 HT. This would allow the ramps to be paved in echelon eliminating all longitudinal cold joints. | We reviewed the pavement needs for the service ramps and determined that interlayer/SMA is needed, however we are adding a note to be included in the next addendum that will allow for an optional change to the shoulder to allow paving in echelon if desired. | Mike Coleman | 5 | 2023-12-01 10:19 | 2023-12-06 13:01
20231212 | 20231212022 | 22 | Soil Borings | Can the Department please provide the soil boring for this project? | The soil boring information can be found at the following location: https://wisdot.box.com/s/2gplssx9ddcvnpzgpn2f3crhfuqn0153 can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2023-11-28 14:12 | 2023-11-29 12:20
20231212 | 20231212022 | 22 | Department Construction Schedule | Can the department provide the construction schedule used in design? | The design schedule can be found at the following location: https://wisdot.box.com/s/2gplssx9ddcvnpzgpn2f3crhfuqn0153 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2023-11-27 11:28 | 2023-11-28 06:02
20231212 | 20231212022 | 22 | Rock Excavation | For the rock excavation 122+00 - 131+50 area, is it the intention to be removed mechanically as there is no access to get a drill in halfway up the hill without a bench. Can the back slope of the rock be closer to vertical or does it need to be at 0.5:1? Can more rock be removed to make blasting feasible, as designed to thin in areas for blasting. | The Department does not dictate means and methods to perform Excavation rock to the limits indicted in the plan are not specified. Variance to the back slope limits maybe dependent on the suitability of the rock present. | Mike Coleman | 5 | 2023-12-06 14:36 | 2023-12-07 15:52
20231212 | 20231212022 | 22 | Waste | Will waste be permitted to be permanently placed in the DOT right of way from approximately Sta 210 - 222 RT? | The department has investigated some of area mentioned in question and the contractor should be aware of culturally significant site on approximately eastern 1/3 of property mentioned in question, this area cannot be used as a waste site. In the western 2/3 of site -Any waste site proposed needs to follow the approval procedures for disposal sites in standard specification 107. The DOT cannot approve any proposal until the environmental impacts are known and agency coordination completed. | Mike Coleman | 3 | 2023-12-01 15:57 | 2023-12-06 07:59
20231212 | 20231212023 | 23 | preliminary schedule | Contractor is requesting a copy of the DOT's preliminary construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/xvg0wp41j4vw466lc5p694p24ddhm2yu or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-11-27 09:50 | 2023-11-28 06:27
20231212 | 20231212023 | 23 | traffic control | Contractor is requesting a minimum lane closure of 2 miles. Per the specials, the job is not constructible. With traffic not allowed on a milled surface the milling and paving train will require 2 miles. Train consists of multiple mills, multiple trucks for mills and clean up behind the mills, followed by tack truck and cure for tack. Behind the tack truck and cure, there are multiple trucks, transfer machine, paver, breakdown roller, mid roller, cold roller followed by density tech as well as QV. In addition a safety buffer for flaggers must be included on each end of the work zone. On warm days, the paving train alone, (not including the mill) will be out past a mile. The more this train is tightened the more unsafe it becomes for our people and the traveling public. | The Department is re-evaluating traffic volumes and lane capacities in this stretch of STH 42 and plans to increase the maximum allowable lane closure length as part of an upcoming addendum. | Mike Coleman | 1 | 2023-11-27 08:11 | 2023-11-29 06:30
20231212 | 20231212023 | 23 | State owned property available for contractors use | Does the Department have any state owned land that a contractor could utilize for this project (approximately 2 to 3 acres)? Specifically for staging, material storage, asphalt milling storage, temporary asphalt plant, etc.? If so, can you please provide the location and/or locations? | The Department has not confirmed the availability nor gotten environmental approvals to use any such state-owned land for such purposes. Contractors can research potentially available land for use by viewing Land Records on Door Countyâ€™s public website. If a specific piece of state-owned land of interest is identified by a contractor, they should make the Department aware of the location of the specific parcel before pursuing it. It is the responsibility of the contractor to acquire any necessary environmental approvals and/or permits to use such state-owned lands. The Department cannot guarantee any such state-owned lands will ultimately be approved for a contractorâ€™s use for this project. | Mike Coleman | 5 | 2023-11-27 15:24 | 2023-12-04 05:59
20231212 | 20231212023 | 23 | culvert patching | Page 3 of the special provisions states, " At the end of each day, open trench culvert pipe replacement adjacent to live traffic must be brought up to the existing paved surface elevation according to the construction details in the plan." Does this include the asphaltic surface for that patch? | Yes. The asphaltic surface is part of the New Culvert Pipes With Transition Detail and is part of the required work to be completed by the end of each day. | Mike Coleman | 4 | 2023-11-27 10:50 | 2023-11-29 06:33
20231212 | 20231212023 | 23 | Paved section | Specials on page 2 state: At any roadway locations, the lower lift must be paved across the entire roadway section at the end of each day. The job is not constructible with this language. Contractor cannot allow traffic on a milled surface and can not be in both lanes the same day. In addition, plan sheets 25 through 27 indicate a vertical edge of 2â€ or less allowable. After the mill and fill operation the vertical height between the 2 lanes will be less than 2â€. | As part of an upcoming addendum, this requirement will be removed from the contract. In addition, to help facilitate this change to the paving process, language will be added via the addendum to eliminate the standard spec requirement for notched wedge longitudinal joints. | Mike Coleman | 2 | 2023-11-27 08:15 | 2023-11-29 06:31
20231212 | 20231212024 | 24 | Concrete Items | Concrete Items are not on the proposal or in misc. quantities on plan. Driveway curb on plan sheet #52 and concrete driveway @ sta 159+75 lt | Notes on the plan sheets will be revised to address these issues as part of an upcoming addendum. | Mike Coleman | 6 | 2023-11-30 14:12 | 2023-12-04 13:54
20231212 | 20231212024 | 24 | preliminary schedule | Contractor is requesting a copy of the DOT's preliminary construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/21hsg760iumbiey207igm0ejymf0bfv3 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-11-27 09:51 | 2023-11-28 07:05
20231212 | 20231212024 | 24 | Traffic control | Contractor is requesting a minimum lane closure of 2 miles. Per the specials, the job is not constructible. With traffic not allowed on a milled surface the milling and paving train will require 2 miles. Train consists of multiple mills, multiple trucks for mills and clean up behind the mills, followed by tack truck and cure for tack. Behind the tack truck and cure, there are multiple trucks, transfer machine, paver, breakdown roller, mid roller, cold roller followed by density tech as well as QV. In addition a safety buffer for flaggers must be included on each end of the work zone. On warm days, the paving train alone, (not including the mill) will be out past a mile. The more this train is tightened the more unsafe it becomes for our people and the traveling public. | The Department is re-evaluating traffic volumes and lane capacities in this stretch of STH 42 and plans to increase the maximum allowable lane closure length as part of an upcoming addendum. | Mike Coleman | 1 | 2023-11-27 08:10 | 2023-11-29 06:29
20231212 | 20231212024 | 24 | State owned land for staging | Does the Department have any state owned land that a contractor could utilize for this project (approximately 2 to 3 acres)? Specifically for staging, material storage, asphalt milling storage, temporary asphalt plant, etc.? If so, can you please provide the location and/or locations? | The Department has not confirmed the availability nor gotten environmental approvals to use any such state-owned land for such purposes. Contractors can research potentially available land for use by viewing Land Records on Door Countyâ€™s public website. If a specific piece of state-owned land of interest is identified by a contractor, they should make the Department aware of the location of the specific parcel before pursuing it. It is the responsibility of the contractor to acquire any necessary environmental approvals and/or permits to use such state-owned lands. The Department cannot guarantee any such state-owned lands will ultimately be approved for a contractorâ€™s use for this project. | Mike Coleman | 4 | 2023-11-27 15:26 | 2023-12-04 06:42
20231212 | 20231212024 | 24 | traffic | Specials on page 2 state. â€œWhere the existing asphalt has been milled, pave HMA, place shoulder aggregate, appropriately sign, and install permanent pavement markings prior to opening for STH 42 peak hours defined in the traffic articleâ€. The job is not constructible with this language if the contactor has to pave the job after May 30th. The work by others indicates this may be the case as well as contractor schedule. Please remove shoulder aggregate and the install of permanent pavement markings. This is a 2â€ off and 2â€ on job and existing shoulder gravel is available to the address the spec language for a drop off of greater than 2â€. Grooved wet reflective has a minimum 48 hour cure period after paving. Temp paint will be applied were need for the grooved wet reflective. | This concern will be addressed with revised contract language as part of an upcoming addendum. | Mike Coleman | 2 | 2023-11-27 08:21 | 2023-11-29 06:32
20231212 | 20231212024 | 24 | CURB AND GUTTER | The are quantities for curb removal and curb staking shown in the miscellaneous quantities and there is curb shown on the plan. Should there be a corresponding curb item in those areas? | The intent is to saw and remove just the curb head at specific locations. There is no new curb and gutter item/quantity proposed with this project. The items and the curb removal detail will be revised as part of an upcoming addendum to address this issue. | Mike Coleman | 5 | 2023-11-30 14:01 | 2023-12-04 07:07
20231212 | 20231212025 | 25 | Geotech Report | Can the department provide the geotech report for Structures R-68-13 and 14? | The Geotech report can be found at the following location: https://wisdot.box.com/s/5p0sz37jqusnzlhlbqzt8h79k696f9hp or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-29 15:06 | 2023-11-30 10:31
20231212 | 20231212025 | 25 | Schedule | Could the department provide the schedule developed during the design phase? | The design schedule can be found at the following location: https://wisdot.box.com/s/5p0sz37jqusnzlhlbqzt8h79k696f9hp or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2023-12-01 10:21 | 2023-12-04 13:58
20231212 | 20231212025 | 25 | Extra Depth Shoulder Paving | In areas of 4" shoulder (as indicated on sheet 7), could the bottom 2" of asphalt be specified as Asphaltic Surface, as these need to be done prior to the Test Strip. |  |  | 2 | 2023-12-01 10:20
20231212 | 20231212025 | 25 | Beam Guard | With the amount of work needing to be done behind the beam guard prior to paving that will require the existing rail to be dropped to do the work, will the department add the special provision of salvage and reinstall beam guard or the item of adjusting beam guard. This will make it possible to install new rail or adjust new rail after paving is done to the proper required heights | We anticipate that there is enough information in the plans to determine the correct height of the guardrail. Please bid the project per the plan and special provisions. | Mike Coleman | 4 | 2023-12-06 05:41 | 2023-12-08 06:42
20231212 | 20231212029 | 29 | Gland Replacement | Could we get more information /drawings on the expansion joint gland for B-9-48. Depending on the type may be a special order. | The 2004 as-built plan provides the dimensions that the contractor is looking for on page 5 of the as-built plan. The as-built plan can be found at the following location: https://wisdot.box.com/s/ku4in7aycs27wh7b3zmqoqn6lh0998hf or can be accessed on the HCCI November bid letting page under Supplemental Information. The proposed gland suppliers and other requirements are defined in Article 42 of the proposal. | Mike Coleman | 1 | 2023-11-16 13:17 | 2023-11-17 09:31
20231212 | 20231212029 | 29 | Cleaning Box Culverts | Please clarify the intent of the 2 Cleaning Box Culvert items. Is any cleaning required inside the box itself or is it limited to the aprons and areas outside the box culverts? | Per the special provisions, the intent is to clean at the inlet and outlet (debris, wood, vegetation, sediment) that is impacting flow. If any large wood debris has ended up inside the box cells impacting flow, that would need to be removed. Do not remove sediment inside the box culvert per the special provision. | Mike Coleman | 3 | 2023-12-01 14:01 | 2023-12-04 13:46
20231212 | 20231212029 | 29 | Interim Liquidated Damages | Please clarify the Lane Rental Fee Assessment for Stage 5 and Stage 10 under Article #3 Prosecution and Progress - Paragraph - Interim Liquidated Damages and Article #4 Lane Rental Fee Assessment. It appears if bi-directional traffic is not reopened to two-way two-lane by noon the Friday before Memorial weekend the damages will be $5,000 per hour per direction which is equals $5,000.00 x 2 directions x 24 hours/day = $240,000.00 per day. Is $240,000.00 per day correct? This dollar amount is way higher than other projects in the area. What items of work need to be completed prior to reopening to two-way two-lane traffic? Other projects in the area have allowed gravel shoulders (no asphalt) drums on the gravel shoulders and a painted centerline only. The remaining work will be completed under single lane closures after the holiday. Will this be allowed on this project also? | â€¢ Yes, the lane rental fee assessment is correct. The roadway needs to be open to traffic by the time and date(s) indicated in the special provisions. â€¢ The roadway needs to be completed and open to traffic including shoulder paving. Use of gravel shoulders in high-speed conditions are not anticipated on this project. | Mike Coleman | 4 | 2023-12-07 11:05 | 2023-12-11 06:38
20231212 | 20231212029 | 29 | High Friction Surface Treatment | The above project has a specification that specifically calls for a fully automated system. Will a semi-automated application (one which automatically mixes and proportions the epoxy but spreads it to width with a notched squeegee) be permitted on this project on the drive lanes as well as the tapered areas and shoulders? This was allowed in two projects in the November letting (projects number 21 and 35). | The Region would like the driving lanes on USH 53 and the ramps done with the fully automated placement as shown in the plan. The lengths of placement are significant enough to warrant automated placement. The project would consider shoulders and tapers for an exception to the fully automated placement. | Mike Coleman | 2 | 2023-11-27 09:45 | 2023-11-29 11:35
20231212 | 20231212030 | 30 | Work Restrictions | In Section 3, Prosecution and Progress, the work restrictions state that traffic will be allowed to run on the lower layer of new HMA pavement for a maximum of 10 calendar days before the upper layer of HMA pavement must be in place. Where a lower layer is constructed the plan shows milling 3/4-inch and paving back 1 1-4" increasing the pavement structure. Could the 10 day restriction be eliminated but require the contractor to continue paving operations after completing the lower layer or extend the days to 20 days to reduce mobilizations and costs for the department? | The timing restrictions are in place to reduce the risk of further damaging the existing concrete pavement and joints that will remain. The timing restrictions allowing traffic to run on the milled/ground surface will be extended from 7 to 10 calendar days in order to accommodate construction operations. We will submit an addendum to address the change. | Mike Coleman | 3 | 2023-12-01 18:00 | 2023-12-06 06:19
20231212 | 20231212030 | 30 | existing pavement history | Is there any information available about the existing concrete pavement on this project? i.e. mix design information, build year etc. How much was removed when the pavement was diamond ground? | The as-built plans can be found at the following location: https://wisdot.box.com/s/1ciga7q4ercvv768nlcdwq10i9flamf2 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2023-11-16 16:25 | 2023-11-21 07:48
20231212 | 20231212030 | 30 | Prep Foundation | Section 31, Prepare Foundation for Asphaltic Paving Special 1530-02-70, Item SPV.0060.02, states that removal of all surplus material/fillers and asphalt patching of the cracks should be completed after the surface milling. Due to the time it will take to complete this work and along with the asphalt shoulder widening this will conflict with Section 3, Prosecution and Progress, where the work restriction states that traffic will be allowed to run on the existing milled surface for a maximum of 7 calendar days. Would the DOT consider allowing the preparation work to be completed prior to the surface milling or removing the time restriction traffic is allowed to run on the milled surface? Completing the crack patching prior to milling also helps reduce reflection of the patching areas through the new asphalt pavement surface. | Performing the Prepare Foundation for Asphaltic Paving special provision item prior to milling introduces the risk of debonding occurring during the milling process. The timing restrictions allowing traffic to run on the milled/ground surface will be extended from 7 to 10 calendar days in order to accommodate construction operations. We will submit an addendum to address the change. | Mike Coleman | 4 | 2023-12-01 18:08 | 2023-12-06 06:20
20231212 | 20231212030 | 30 | Project Stationing | The project appears to skip a section of USH 10 between 479+52 and 490+04. Is the intention to leave this section of pavement in place as is? | Yes, this section of USH 10 will be left as is and handled by a separate project in the future. | Mike Coleman | 2 | 2023-12-01 17:45 | 2023-12-05 10:51
20231212 | 20231212030 | 30 | Spec 104.6.1.2.4 (2) Changes | What is the intent of the changes to this specification with regards to protecting slopes exposed by removing protective measures? If guardrail needs to be installed by noon on Fridays, which could be before milling and paving has been completed on the project, will WisDOT be providing grades for the top of rail? Will we be allowed to adjust new guardrail according to Spec 614.3.5? | Standard specification 104.6.1.2.4(2) applies. The contractor shall adhere to the standard specifications and other contract documents and shall plan accordingly. | Mike Coleman | 5 | 2023-12-04 10:32 | 2023-12-06 08:39
20231212 | 20231212031 | 31 | 643.0600, 643.0705 Flexible Tubular Markers | Can the quantities for items 643.0600 and 643.0705 be reviewed for project ID 1530-05-73? In the Misc. Qty. table on page 65, the total number of items was multiplied by the number of days in the stage, resulting in an incorrect total as these items are paid as EACH, not DAYS. Thanks | For project ID: 1530-05-73 the quantities for the following bid items should be revised as shown below: 643.0600, Traffic Control Flexible Tubular Marker Bases, 130 EACH 643.0705, Traffic Control Warning Lights Type A, 452 DAYS (No change to this quantity is required since this bid item is paid for by days.) An addendum will be issued. | Mike Coleman | 1 | 2023-11-28 11:06 | 2023-11-30 06:29
20231212 | 20231212031 | 31 | 643.0920 Covering Signs Type 2 | Please review quantities for item 643.0920 Traffic Control Covering Signs Type II. The Misc Qty table on page 65 shows the quantity as EACH, but then the quantity is multiplied by the number of days in the stage, resulting in an error as the item is paid as EACH, not as DAYS. Thanks. | For project ID: 1530-05-73 the quantities for the following bid items should be revised as shown below: 643.0920, Traffic Control Covering Signs Type II, 7 EACH An addendum will be issued. | Mike Coleman | 2 | 2023-11-28 13:55 | 2023-11-30 06:30
20231212 | 20231212031 | 31 | Spec 104.6.1.2.4 (2) Changes | What is the intent of the changes to this specification with regards to protecting slopes exposed by removing protective measures? If guardrail needs to be installed by noon on Fridays, which will be before milling and paving has been completed on the project, will WisDOT be providing grades for the top of rail? Will we be allowed to adjust new guardrail according to Spec 614.3.5? | The existing slopes are steep and not recoverable if a vehicle leaves the highway. The proposal and plan do not state that the guardrail needs to be installed before milling and paving. WisDOT will not be providing grades for the top of rail. Adjusting new guardrail would be determined by contractor means and methods and would be considered incidental to contract bid items. | Mike Coleman | 3 | 2023-12-04 10:32 | 2023-12-06 08:04
20231212 | 20231212031 | 31 | Temporary Guardrail | Will temporary guardrail be required at certain locations and if so, will that be incidental to the contract? For example, at 88+95 to 106+50, the guardrail will need to be removed to reconstruct the shoulder. According to spec 104.6.1.2.4 (2) that will have to be done in increments and be reinstalled by noon Friday. The guardrail will then have to be removed again to be able to install the curb under the guardrail and then reinstalled. | Temporary guardrail will be incidental to the contract and utilized on an as needed basis depending on contractor means and methods. This section of guardrail is within a climbing lane where traffic will be shifted and located outside of the temporary clear zone requirements of 15 feet minimum for posted speed limits above 55 mph listed in FDM 11-50-35.6.1. Temporary guardrail should not be needed in this location. | Mike Coleman | 4 | 2023-12-04 11:54 | 2023-12-06 08:06
20231212 | 20231212032 | 32 | Modular Block Wall | The existing wall has blocks that are 6" tall and a beveled face. The plan appears to show removing a portion of the existing wall and extending southeast with the proposed wall. There are currently no products on the approved products listing with that same height or face. Please clarify how the existing and proposed walls are to join each other since the block heights will not be the same. | â€¢ There will need to be field fitting by the contractor. The contractor may need to trim the bevel off on the last existing block to field match block course. â€¢ There are at least two APL products with 6-inch blocks to allow course heights to match (non-beveled as noted) and color scheme. â€¢ The contractor is also allowed to submit a non-APL product during bidding for approval per the special provision. â€¢ An addendum will be issued to address the necessary field fitting and disposition of the existing wall section. | Mike Coleman | 1 | 2023-11-30 11:07 | 2023-12-04 06:47
20231212 | 20231212032 | 32 | Modular Block Wall | The manufacturer of the existing retaining wall can provide blocks that are of the same size, type, and color as the existing. However, those blocks are not and will not be on the approved products list prior to the bid letting. Would the Department consider those as an acceptable alternative? | At this time, the Department cannot approve the wall block without proper review and evaluation per the special provisions. The contractor should bid the wall as currently shown in the plans and special provisions and as supplemented in Addendum #1. | Mike Coleman | 2 | 2023-12-04 10:39 | 2023-12-06 06:23
20231212 | 20231212033 | 33 | Common Excavation | The earthwork summary shows most of the common excavation from the transition cuts as being waste. The plan does not appear to address the material required to backfill the transition cuts. Please clarify the intent of the common excavation at the transition cuts. | The material generated from excavating the transition cut is anticipated to be utilized for backfill. | Mike Coleman | 1 | 2023-11-28 13:45 | 2023-11-30 06:31
20231212 | 20231212033 | 33 | B-09-0026 - Shoring | The notes for work to be performed on structure B-9-26 state that if more than 1/3 of the top mat slab reinforcement is exposed, adjacent spans must be shored. If this scenario is encountered, will the shoring be reimbursed by the Department? Due to the uncertainty of repair quantities and extents, there is a large amount of risk with this note. | Multiple means and methods are potentially available. For instance, if necessary, a contractor could utilize shoring or repair in stages to limit the exposed steel among other alternatives. Any associated costs beyond the current bid items included in the contract would be incidental to complete this work. | Mike Coleman | 2 | 2023-12-05 13:57 | 2023-12-08 06:40
20231212 | 20231212034 | 34 | Earthwork Summary | Could the quantities in the summary by verified? It seems the common ex quantity for the transition cut may be getting used to balance the earthwork but that will be needed to backfill the pipe. There will be some excess generated at the pipe replacements but that will include the unusable pavement material. |  |  | 2 | 2023-12-05 15:57
20231212 | 20231212034 | 34 | SMA for County roads and major intersections | Sheet 35 of the plans, asphalt items summary, show 4SMA being utilized on county roads and major intersections, can the 5MT be utilized for surface on these in lieu of the SMA due to the challenging workability of placing SMA in small quantities? |  |  | 1 | 2023-12-04 11:17
20231212 | 20231212035 | 35 | Structure Staking | Structure staking is normally included on structure redeck projects. Will it be added to this project? | The item will be added via addendum. | Mike Coleman | 2 | 2023-11-30 11:04 | 2023-12-04 06:55
20231212 | 20231212035 | 35 | P-17-62 deck bill of bars | There appears to be only enough of the S415 and S416 hat bars for 5 of the girder lines and not all 6. Should the quantity be 24 of the S415's and 420 of the S416's? | The quantity should be 24. An addendum will be issued to correct this. | Mike Coleman | 1 | 2023-11-30 08:52 | 2023-12-04 06:55
20231212 | 20231212035 | 35 | Thrie Beam Attachment | There will not be enough room to attach a thrie beam back-up plate to the guardrail on the bridge. How will this work? | The wing post spacing is not desirable. The location of the back-up plate will be non-typical but will work. | Mike Coleman | 3 | 2023-12-05 14:33 | 2023-12-06 12:52
20231212 | 20231212036 | 36 | Gravity Retaining Walls | It appears the existing retaining wall has a 6" block height. WisDOT approved block typically will have an 8" height for small block walls. Also, given the height of these walls, including the bury depth, using small blocks will require the installation of geogrid making these MSE walls. Is the existing wall MSE and does WisDOT have the ROW to install geogrids? Large block gravity walls would work here but would not meet the note requiring the contractor to match the existing wall. | A block wall system without soil reinforcement is required because right of way is not available. It is unknown if the existing wall has soil reinforcement. Addendum #02 will be issued to allow consideration of block wall systems not approved by WisDOT, and to allow variance in height and with matching the existing wall. | Mike Coleman | 3 | 2023-12-05 13:07 | 2023-12-07 04:54
20231212 | 20231212036 | 36 | Catch Basin Sumps | Standard detail says catch Basins should have a 2' sump. I noticed that the catch basin in these plan don't include a sump is this correct? | The catch basins should include the 2â€™ sump in accordance with the Standard Detail Drawing. The Storm Sewer Schedule in the plans will be updated via addendum. | Mike Coleman | 1 | 2023-11-21 07:56 | 2023-11-27 08:05
20231212 | 20231212036 | 36 | Curb & Gutter Staking | The quantity for curb and gutter staking appears to include the Type A curb and gutter. The Standard Specifications state in Section 650.4 that Construction Staking Curb Gutter and Curb & Gutter will not be measured when adjacent to concrete pavement. Will the department pay for the Type A curb and gutter staking along with the concrete pavement staking? | Addendum #1 has removed the Type A curb and gutter from the staking item quantity. | Mike Coleman | 2 | 2023-11-30 11:50 | 2023-11-30 12:50
20231212 | 20231212038 | 38 | Railing Thrie Beam Attachment | Please confirm only wing 2 of the structure receives the provisions for thrie beam guard rail attachment as shown on sheet 1 of the structure plans. |  |  | 2 | 2023-12-05 14:48
20231212 | 20231212038 | 38 | Structure Removal/ Shoring | Was temporary shoring considered as a bid item for erosion control to allow removal of the existing pipes? Right now nothing is shown. |  |  | 1 | 2023-12-05 13:28