## qandasearchletting_results
Date: | 2024-03-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240312 | 20240312002 | 2 | River Water Levels | Beyond seasonal water level changes, are there any anticipated river water level lowering adjustments planned during construction (i.e. dam maintenance)? | We are not aware of any scheduled Dam Maintenance. With the expedited schedule of this project there was not sufficient time to coordinate and acquire a permit to lower the Rock River. Please move forward with the plan as is and making the connection of the arch under water. | Mike Coleman | 3 | 2024-03-06 15:30 | 2024-03-08 09:51
20240312 | 20240312002 | 2 | Water Levels | In review of the responses to questions 2 & 3, would the contractor be correct to interpret that Special Provision #8 Rock River Seasonal Water Level Changes would not be applicable for any intentional manipulations by other entities to lower water levels that are not identified in the contract documents that may affect the intended contractor means and methods. |  |  | 4 | 2024-03-09 06:17
20240312 | 20240312002 | 2 | Staking | Is there electric staking on this project? | Yes the project should include item 650.8501 Construction Staking Electrical Installations (3050-04-81). The item will be added with an addendum. | Mike Coleman | 1 | 2024-02-26 16:05 | 2024-02-28 06:52
20240312 | 20240312002 | 2 | Arch Rib Cofferdam Conflict | Normal and current river water levels indicate that the base of the arch ribs will be below water. The cofferdams required for the plan concrete seal configurations also conflict with the arches so the cofferdams will need to be removed prior to the arch erection. As a result, the lower end of the arches (bearings & shims), the grouting at the bases of spandrels #1 & #10 as well as the joint sealing at the arch seat will be below water. Can provisions for temporarily lowering of the river levels be provided to adequately complete the work? | Yes, we anticipate the arch connection being underwater. However, with the expedited schedule of this project there was not sufficient time to coordinate and acquire a permit to lower the Rock River. Please move forward with the plan as is and making the connection under water. | Mike Coleman | 2 | 2024-03-04 17:27 | 2024-03-07 15:37
20240312 | 20240312005 | 5 | HMA Q's | 1. There are intersections shown in the plan details starting on page 77 with clear mill limits shown. There are other intersections shown without clear mill limits. At these intersections, is it anticipated that they are milled back according to the applicable butt joint construction detail? 2. Areas at the pipe and RR sections are shown to have HMA placed with the respective 3MT and 4MT items. These will be done prior to mill and overlay operations. Can these areas be changed to Asphaltic Surface with a MT designation and not be included in PWL as a test strip cannot occur ahead of this work? | 1. Correct, the construction details on page 10 of the plan show the side road mill limits depending upon mill and overlay depth. 2. Pavement Thicknesses and Type have been revised and included in Addenda #2. Asphaltic Surface quantity has been revised to include a lower layer at both Culvert Replacement and Railroad Crossings. Layer thicknesses have been adjusted to better match the proposed mill and overlays surrounding these locations. | Mike Coleman | 3 | 2024-03-04 11:10 | 2024-03-06 13:26
20240312 | 20240312005 | 5 | Design Schedule | Could the schedule developed during design be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/my4u5eyd1j9izizl7qxyqgd14fs9dg9r or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-02-14 08:08 | 2024-02-27 07:19
20240312 | 20240312005 | 5 | staking | Is there a sidewalk lump sum staking item for this project or is it included in the curb ramp item? | An addendum will be issued to add the pay item. | Mike Coleman | 2 | 2024-02-26 16:08 | 2024-02-28 07:04
20240312 | 20240312005 | 5 | Removing Concrete sidewalk | Removing sidewalk on the proposal is in SY's and in miscellaneous quantities it is SF, SY seams to be a misprint |  |  | 7 | 2024-03-10 15:35
20240312 | 20240312005 | 5 | Traffic Control | The North Section of the project is predominantly a 4 Lane section. These areas are not shown to have barrels or lane closures in the plans. Could barrels and other devices for lane closures be added as flagging 4 lanes of traffic would provide an unsafe work environment to both the contractor and the traveling public? | Quantities added, via addenda #2, for use of SDD Traffic Control, Lane Closure to complete milling and overlay work on USH 51 from structure B-11-94 to Ontario Street. The special provisions under article 4 already referenced using SDD Traffic Control, Lane Closure (B-11-94 to Ontario Street) for work at this location. SDD Traffic Control, Lane Closure added to plan through addenda #2. | Mike Coleman | 6 | 2024-03-04 11:12 | 2024-03-06 13:27
20240312 | 20240312005 | 5 | Sloped Nose | There is no sloped nose item and there are approximately 270 SF, will an addendum be sent out |  |  | 8 | 2024-03-10 15:59
20240312 | 20240312005 | 5 | Start Date | With the let closing on March 12 and a requirement that a biologist needs a few weeks to clear the site prior to start of work, the start by date of April 15th does not seem attainable. Can a date of May 1st be considered? | Revised language will read â€œThe Notice to Proceed will be issued such that work shall start no later than May 6, 2024, unless otherwise approved by the engineer.â€ An addendum is forthcoming. | Mike Coleman | 5 | 2024-03-04 11:11 | 2024-03-06 13:26
20240312 | 20240312006 | 6 | Temporary Structure | Is base agg dense 1 1/4 inch an acceptable driving surface on the bridge deck? e g have a timber mat deck and a 6-inch base agg overlay. |  |  | 1 | 2024-03-08 09:52
20240312 | 20240312008 | 8 | Base Patching Asphaltic | Are the locations for base patching asphaltic known or are they un-distributed? Will base patching be completed before or after milling? | The quantities for asphaltic base patching are undistributed and locations are to be determined in the field by the engineer. The asphaltic base patching can be completed prior to milling or after milling but prior to the placement of the final HMA surface. | Mike Coleman | 2 | 2024-02-29 14:36 | 2024-03-05 09:32
20240312 | 20240312008 | 8 | HMA Longitudinal Joint Repair | HMA longitudinal joint repair item is shown in the typical sections and on the plan sheets to be completed at 2â€™ wide. However, detail sheet shows the work to be completed at a width of 1.5â€™ to 3â€™. Which width is correct? Also, joint repair item includes removal of loose/spalling concrete. The existing concrete below the asphalt was rubblized under a previous projects. How much concrete will WisDOT require to be removed? Are the as builts available from past projects? | The intent of the HMA Longitudinal Joint Repair item is to remove the existing HMA down to the rubblized concrete pavement at a width of 2 feet. It is anticipated that none of the rubblized concrete would be removed unless the contractors operations removes and/or disturbs the underlying rubblized concrete. The As-Builts can be found at the following location: https://wisdot.box.com/s/gs8p5qzjvw5d8i0woksoto2kohtpyvqg or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-02-29 14:34 | 2024-03-05 09:30
20240312 | 20240312009 | 9 | Boring Logs | Please provide the boring logs. | Per former Pavement Design Engineer, the soil boring was not needed for this improvement project. Therefore, a Level 1 Subsurface Report was provided for the pavement design report for this project. The Level 1 Subsurface Report can be found at the following location: https://wisdot.box.com/s/qto69b9xcukhi4co4odfd74a7iqjns8y or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-03-06 08:15 | 2024-03-06 10:07
20240312 | 20240312009 | 9 | III A pipe material | the items for culvert pipe and stormm sewer pipe are class !!!-A, however the plan is calling out for specific materials at different locations should we plan on using the materials specified in the plan? |  |  | 2 | 2024-03-07 09:28
20240312 | 20240312010 | 10 | TRAFFIC SIGNAL CONTROLLER | Can you please confirm what brand traffic signal controller is being used at the intersections for this project so we can make sure we are quoting compatible parts? (IE. McCain, Econolite, Siemens, Etc.) | All existing equipment is Econolite or Eagle. | Mike Coleman | 1 | 2024-02-20 13:53 | 2024-02-21 07:33
20240312 | 20240312011 | 11 | Design Schedule | Please provide the project design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/jzdcakjxtu0cn34a5euizrdizivrx7d4 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2024-03-07 11:04 | 2024-03-08 09:24
20240312 | 20240312011 | 11 | Dowel Bars | The dowel bar quantity seems to be low. | The dowel bar quantity is incorrect. It will be revised via addendum. | Mike Coleman | 1 | 2024-02-13 16:15 | 2024-02-22 07:14
20240312 | 20240312011 | 11 | Earthwork Data sheets - Information corrupted | The information contained on the Earthwork Data sheets (pgs. 432-436) seem to have been corrupted. Can this information be found elsewhere? If not, can it be reissued in a way that can be read/used? | An addendum will be issued to update the sheets. | Mike Coleman | 3 | 2024-02-22 15:12 | 2024-02-28 07:03
20240312 | 20240312011 | 11 | Quantity Change to Base Patching | The revised quantity seems way more than will be necessary given the existing condition of the roadway. Is there any breakdown of the location of the Base patches or the method used to determine the quantity? |  |  | 7 | 2024-03-09 10:21
20240312 | 20240312011 | 11 | C-40-44 | To complete the intent of work to repair the pipe penetration areas, it appears the Department is outlining to complete this work without impacting traffic above. If required to replace the walls of the culvert without excavation on the exterior of the box culvert, would violate OSHA regulations by having an open excavation over 5â€™. From a constructability standpoint, the wall of the culvert should be excavated and exposed from the outside so the repair can be formed and poured to the lines and limits shown. It would be recommended that items such as removing structure and concrete masonry be utilized in place of concrete surface repair. Additionally the cofferdam item only outlines scope within the culvert. Does the Department intend to review feasibility to access this work safely and allow for it to be constructed in a manner that would provide a quality product? This would require additional traffic control staging and pavement replacement. | OSHA standards discuss requiring a protective system with open trenching 5â€™ or greater. Because these repairs occur on the inside of an existing concrete box culvert around an existing pipe penetration, these repair activities do not meet the requirements of open trench excavating and therefore do not require additional protective system. Work is not required on the outside of culvert box as suggested. Commenting on specific forming of repairs gets into means and methods for the repair work. No additional bid items are required. An addendum will be issued to clarify limiting traffic over pipe penetration areas during demolition and repair activities. | Mike Coleman | 4 | 2024-03-01 15:26 | 2024-03-07 15:39
20240312 | 20240312011 | 11 | Plans and Specs | Where is the Asphaltic Surface Patching with a pay item quantity of 406 TONS to be utilized on the project? It is not shown anywhere on the plans other than the miscellaneous quantities table on sheet 226. | The asphaltic surface patching is to be used on any shoulders that require repairs prior to putting staged traffic on them. We estimated that approximately 20% of the shoulder area would need repairs. | Mike Coleman | 2 | 2024-02-21 10:44 | 2024-02-29 07:25
20240312 | 20240312011 | 11 | Asphaltic Surface | Where is the Asphaltic Surface with a pay item quantity of 1826 TONS located? It is not shown anywhere on the plans other than the miscellaneous quantities table on sheet 229 which it is stated that "7" BASE UNDER ASPHALTIC SURFACE." It is not called out anywhere on the plan details or curb ramp details. | The item for asphaltic surface is called out in the ASPHALT & CONCRETE REMOVAL AT CURB RAMPS construction detail on sheet 8. | Mike Coleman | 5 | 2024-03-04 13:05 | 2024-03-05 07:17
20240312 | 20240312012 | 12 | Soil Borings | Can the Department provide the soil borings for this project? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/7msvjv9s7yocwpvaxehlhf2hlouzeerq or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 7 | 2024-03-06 08:14 | 2024-03-07 08:08
20240312 | 20240312012 | 12 | Design Schedule | Can the design schedule be provided for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/7msvjv9s7yocwpvaxehlhf2hlouzeerq or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2024-03-01 10:14 | 2024-03-05 07:23
20240312 | 20240312012 | 12 | Drainage Tables in Excel Format | Can the drainage tables on sheets 91-94 from the plant set be provided in Excel format? | The storm sewer tables can be found at the following location: https://wisdot.box.com/s/7msvjv9s7yocwpvaxehlhf2hlouzeerq or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 5 | 2024-03-05 09:39 | 2024-03-08 07:34
20240312 | 20240312012 | 12 | Traffic Signal Controller | Can you please confirm what brand traffic signal controller is being used at the intersection for this project so we can make sure we are quoting compatible parts? (IE. McCain, Econolite, Siemens, Etc.) | All signal equipment must meet NEMA TS2 standards as stated in the specifications. No particular brand will be specified. | Mike Coleman | 2 | 2024-02-20 13:55 | 2024-02-22 07:15
20240312 | 20240312012 | 12 | Missing Storm Sewer Information | On Sheet 122 at Station 60+50 Right what size pipe and structure is designed for that location, the plan is missing this information | The pipes (15â€) and structure (2â€™x2.5â€™ inlet) shown will be addressed in an upcoming addendum. | Mike Coleman | 4 | 2024-03-05 08:57 | 2024-03-07 07:46
20240312 | 20240312012 | 12 | Field Office | With the project requiring a special field office facility, how long with the field office be required? The completion date for this project is May 30th 2025. Will the field office be required through this date or can it be vacated by the engineering staff before that date? The reason for asking this question is because rent on a field office is not an insignificant amount of money. | The duration of the field office will be determined by the engineer as stated in Section 642.3 of the 2024 Standard Specifications. The contractor should plan on having the field office available through June 2025. | Mike Coleman | 6 | 2024-03-05 14:42 | 2024-03-08 09:52
20240312 | 20240312012 | 12 | Storm Sewer and Culvert Bid Items | Would the department be opposed to adding additional competition for Class III storm sewer bid items and driveway culvert items with adding either Class IIIA or Class IIIB items? Currently, the storm sewer bid items seem to only be specified outside pavement limits, but the ADT is below FDM guidance limits at less than 20,000 for culverts and no ADT restriction for storm sewer items. | This project is a local program project, and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2024-02-12 12:40 | 2024-02-20 09:11
20240312 | 20240312014 | 14 | staking | Is there an item for electric staking on this project? | Bid item Construction Staking Electrical Installations (01. 2740-02-70) will be added to the contract through Addenda #1. | Mike Coleman | 1 | 2024-02-26 16:09 | 2024-02-28 06:53
20240312 | 20240312017 | 17 | Bird Netting Follow Up Question | Provided the department's response to question one and that no work is planned to take place beyond the B-70-265/266 structure approaches, to what extent will the department require bird deterrent to be installed? The entire 123,597 SF of both structures or just a portion near the structure approaches? | Provide netting to cover the span between the abutment and the first pier on either end of the structure. | Mike Coleman | 2 | 2024-02-21 07:55 | 2024-02-27 09:24
20240312 | 20240312017 | 17 | Bird Netting | Regarding the Department's responses to questions one and two, will the Department issue a conditional notice to proceed to install the bird netting prior to the April 15th migratory bird nesting requirements? With a March 12 letting, and contract award process, there is a very limited timeframe left to install the netting prior to April 15th. Especially for the amount netting required per the Department's response to question two. | Yes, assuming that the contract is awarded and executed, the Department would issue a conditional notice to proceed to allow installation of the bird netting prior to April 15th. | Mike Coleman | 4 | 2024-03-05 08:32 | 2024-03-05 09:28
20240312 | 20240312017 | 17 | Bird Deterrent System | Why are the bird deterrent system items included with this contract? There is no work taking place in areas where birds nest on this project. | Netting will be required due to our proposed work on the structural approach slabs at both ends of structures B-70-265/266 and the presence of birds nesting during previous surveys. | Mike Coleman | 1 | 2024-02-19 12:45 | 2024-02-21 06:49
20240312 | 20240312017 | 17 | Asphaltic Base | Would the department consider changing the Asphaltic Base item (315.0100) to 465.0110 Asphaltic Surface Patching? This would allow the contractor to use a standard 19mm HMA Pavement instead of a 1-inch nominal. | An addenda will be issued to use Asphaltic Surface Patching in place of Asphaltic Base. | Mike Coleman | 3 | 2024-03-01 12:54 | 2024-03-05 07:28
20240312 | 20240312018 | 18 | B-44-333 Concrete Qtys | Concrete masonry bridges and HPC masonry structures qtys do not seem to be correct for B-44-333 as shown on sheet 3 of the structures plan. Please review and provide updated qtys. Also the parapet footing shown on sheet 19 of the structures plan is that to be paid under the Concrete Masonry Bridges item or the HPC Masonry Structures bid item. | The total quantity of concrete (bid items 502.0100 and SPV.0035.01) shown in the plan is correct. However, the plans currently quantify the concrete in the parapets that are located on the abutment wings and parapet footings under the 502.0100 bid item. Since all parapet concrete is typically considered â€œsuperstructureâ€ concrete, these should be quantified under the SPV.0035.01 bid item. We will update the plan quantities and issue an addendum. The parapet footing concrete should be paid for under the 502.0100 bid item. We will add a general note to the plan that better clarifies how cast-in-place concrete is to be paid for and include that in the addendum as well. | Mike Coleman | 1 | 2024-02-16 12:05 | 2024-02-23 07:01
20240312 | 20240312018 | 18 | Borrow from the Excess ROW | It appears there is excess ROW on the North side of IH 41 and on both east and west sides of CTH CC. Is that excess ROW available to remove borrow from? If so can the department give the contractor there requirements of obtaining it for this project? (like area available, max slopes, max depth, etc.) | DOT does not approve borrow sites, especially if we have not cleared it for environmental first. The contractor needs to follow Standard Spec 208 and get all applicable permits and follow other project environmental specs (like tree clearing). All those permits and approvals would determine the size and shape the pit it would create. | Mike Coleman | 3 | 2024-02-27 12:38 | 2024-02-29 07:43
20240312 | 20240312018 | 18 | Work Zone Restrictions | SPV 4 work zone restrictions requires that "material and equipment delivery is only permitted within lane closures". Please advise if work at the center pier will be allowed during daytime hours once the temporary barrier block is installed? Work includes material deliveries (piling, rebar, concrete, etc) and equipment loads in and out of the median. | Material and equipment deliveries are required to be completed within lane closures during allowable hours. Passenger vehicles transporting individuals working on the project are not required to access the work area within a lane closure, so those individuals are able to work in the median with previously delivered materials and equipment. | Mike Coleman | 4 | 2024-03-06 10:11 | 2024-03-07 08:11
20240312 | 20240312018 | 18 | Temp Barrier Block | The delivered qty for item 104 is 4,920LF of temp barrier block but the installed qty for item 106 is 5,520LF. Looking at the traffic control plans the block never gets moved on the project so shouldn't the qtys for item 104 and 106 match each other. | Additional quantity of 603.8125 Concrete Barrier Temporary Precast Installed was included with the project in the event the temporary barrier needed to be moved to accommodate contractor work operations, for example removing the existing barrier along and paving of the outside IH 41 shoulders if those work operations were completed prior to the proposed guardrail being completed in the area. | Mike Coleman | 2 | 2024-02-23 13:04 | 2024-02-28 06:55
20240312 | 20240312020 | 20 | Elliptical Pipe Endwalls | Horizontal Elliptical pipe end wall on sheet SDD 08F10-02 and detail in profile on Sheet 23 do not match and have different sections shown behind them with no description. Is it allowable that these end wall be built by the contractor at our shop. | The profile on sheet 23 is a side profile showing inverts, skews, and stations for each of the two pipes, not an endwall front view. The concrete masonry endwalls must be poured as shown in SDD 08F10-02. | Mike Coleman | 5 | 2024-03-05 11:01 | 2024-03-06 06:30
20240312 | 20240312020 | 20 | Dowel Bars | Is the new concrete pavement to have doweled joints? | The new concrete pavement shall be doweled concrete pavement. An addendum will be issued to add a note to the miscellaneous quantities sheet. | Mike Coleman | 4 | 2024-03-04 08:11 | 2024-03-05 13:29
20240312 | 20240312020 | 20 | Item 68 pipe skew | Is the pipe needing to have cut ends for the skew or is it just being installed at a skew? The plans seem to show the pipe sticking through the concrete headwall. | The skewed double barrel pipe crossing at STA 61+68 shall be constructed in accordance with SDD 08F-10-02. The pipes shall have skewed cut ends to match the concrete headwall. The pipes shall not project through the concrete headwall. One other note. The skew should be 34 ï¿½ RHF not 1 ï¿½ RHF. | Mike Coleman | 1 | 2024-02-28 11:30 | 2024-02-29 12:11
20240312 | 20240312020 | 20 | 305.0120 Base Aggregate Dense 1 1/4-Inch Quantity | The quantity for item 305.0120 Base Aggregate Dense 1 1/4-Inch seems to be extremely low for the project. There is also no base aggregate 1 1/4-Inch listed from Station 53+28 to 61+14 but if you look at the typical section for that portion of the project it shows 12 Inches of base aggregate 1 1/4-Inch. Could the department provide more detail on the quantity for this item? | The quantities for Base Aggregate Dense 3/4 Inch and 1-1/4 Inch have been reviewed and will be updated via addendum. | Mike Coleman | 3 | 2024-03-03 13:47 | 2024-03-05 13:28
20240312 | 20240312020 | 20 | Soil Borings | Will soil borings be made available for this letting? Rock is identified in the sanitary sewer SPV items. | The soils report can be found at the following location: https://wisdot.box.com/s/doiofmymonwxypoaled9eh9w2hdehi7m or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-03-01 08:47 | 2024-03-04 12:03
20240312 | 20240312021 | 21 | 3MT Mixture Acceptance Table | Based on the quantity of 3MT 58-28S on project #1175-19-72, can the department change the mixture acceptance table on sheet 34 to show the mixture acceptance for the 3MT as QMP? This does not meet the statistical requirements for PWL. | There will be an addendum sent to change the table. | Mike Coleman | 2 | 2024-03-01 12:24 | 2024-03-04 13:37
20240312 | 20240312021 | 21 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/910hl0tmxjzfmzpftip7fs7t41wh290s or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-02-20 15:08 | 2024-02-22 07:12
20240312 | 20240312021 | 21 | Culvert | What are the accepted materials for line 0072, 0074, and 0076? | 0072 - 520.1024 Apron Endwalls for Culvert Pipe 24-Inch â€“ Per Standard Specifications 520.2.3 Apron Endwalls for Culvert Pipe the contractor selects the correct endwall type based on the type of pipe selected. 0074 - 520.3424 Culvert Pipe Class III-A Non-metal 24- Inch â€“ Per FDM 13-1-15.2 and Table 15.2 Culvert Material Selection Criteria has a max fill depth of 11 ft. 0076 - 520.3624 Culvert Pipe Class III-B Non-metal 24- Inch - Per FDM 13-1-15.2 and Table 15.2 Culvert Material Selection Criteria has a max fill depth of 15 ft. | Mike Coleman | 4 | 2024-03-04 13:59 | 2024-03-05 09:34
20240312 | 20240312021 | 21 | Shuttle Service | Will the department allow a temporary pedestrian crossing to be build at the crossing near STA 287+40 while it is being rebuilt instead of providing the shuttle service talked about in the special provisions. If not, Where would be the planned pick up and drop locations be for the service, as it would be a complete hazard on the shoulder of Hwy 51. would the service need to be a 24 hours service or what would be the required hours of service as people do bike in the dark. | The intent of the of the shuttle service is for the contractor to choose the best means and methods to maintain connectivity of the trail by shuttling pedestrians and/or hard surface ADA accommodation during the time the crossing is being rebuilt. The shuttle service item will cover the means and methods the contractor choose. If the shuttle is use the expectation would be the pedestrian would be pick up and dropped off at the closest side road crossing where they can re-access the trail. | Mike Coleman | 5 | 2024-03-06 16:09 | 2024-03-07 15:35
20240312 | 20240312021 | 21 | Milled Surface | Would the department consider allowing traffic to run on a milled surface for 96 hours if the milling and paving work occurs after Labor Day? | The department looked at the traffic counts and there is no real change in ADDT between spring, summer, and fall. What is in the current proposal will need to be followed and will NOT be changed to 96 hr. | Mike Coleman | 3 | 2024-03-01 12:24 | 2024-03-04 12:05
20240312 | 20240312022 | 22 | Storm sewer inlets / inlet covers | Type S inlet covers do not fit properly on Inlets 2'x3'. Will the inlet castings or inlets be revised to match up? | Structures 1A and 2C require Type S covers and the incorrect inlet type was included for these structures. A different inlet type will be added to the miscellaneous quantities chart in an addenda. | Mike Coleman | 1 | 2024-02-26 13:35 | 2024-02-29 07:30
20240312 | 20240312023 | 23 | Utility Conflict | The Specials state that the FO line in the NW corner of WI-13/CR-J is in conflict and is an issue to work out in the field. There is not 'adjustment' allowed that I'm aware of in the MGS Short Radius section of MGS guardrail. More complicated than that, there is no mention of the existing electrical utility that is present throughout this entire radius of the guardrail at this intersection and presumably in conflict from around STA 113 up to the bridge near STA 115. What details are the Specials referring to when it states, "Adjust barrier as allowed per standard details drawings and/or standard specifications to avoid all underground utilities as required by statute and according to MATC requirements" that allows the contractor to avoid all utilities in this area? | RE: MATC Fiber Optic The fiber optic line is encased in a 1.25â€ orange conduit buried ~3â€™ or more below grade. SDD14B53 (Short Radius MGS - Details) depicts CRT posts in radius are spaced 6â€™ 3â€ TYP and since it states typical design assumes this allows for some flexibility in the spacing to avoid utilities. SDD14B53 (Short Radius MGS - General Notes) also states to refer to SDD14B42 (MGS Guardrail) for installation information. SDD14B42-07-C includes a diagram for post installation when an underground obstruction/utility conflict occurs, and design assumes this can be used if the deviation is too much from typical 6â€™ 3â€ spacing to avoid the UG fiber. RE: Village of Friendship UG Electric The noted electrical line is the conduit connecting the existing OH lighting system. The existing conduit is 1 1/2" in diameter. Adjustment for the crossing for the Short Radius MGS would be expected to be handled similar to the fiber optic above. Beyond the radius, the conduit is located 2-3 feet behind the curb and gutter (behind the existing guardrail posts, and no conflict is anticipated. The new beam guard posts are planned to be installed at a similar offset to where they currently exist. Utilize SDD14B42-07-C for underground obstruction /utility conflict if a conflict exists. | Mike Coleman | 2 | 2024-02-27 08:21 | 2024-03-05 07:26
20240312 | 20240312023 | 23 | SPV.0060.03 | Would you allow reinforcing steel to not be epoxy coated. This is outside the standard. | The inclusion of epoxy coated reinforcing steel was copied from another specification in error. An addenda will be issued remove this language. | Mike Coleman | 1 | 2024-02-27 07:49 | 2024-03-05 07:17
20240312 | 20240312024 | 24 | Project Design Schedule | Can the department provide the design construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/l42k9bwtsxt09axln4iw1m3h1h2121og or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-02-29 12:10 | 2024-02-29 14:33
20240312 | 20240312024 | 24 | Schudule | Looking at the schedule it looks like the base patching is to be done when the Apple Tree Lane work is happening. Can the Detour be set up at the same time as the Apple Tree Lane closure? Otherwise the schedule doesn't seem to account time for the detour. Please clarify. The schedule also doesn't seem to account for all of the misc items. Is there enough time to build this job? |  |  | 3 | 2024-03-05 20:35
20240312 | 20240312024 | 24 | Detour Duration | There does not seem to be enough days to complete all the base patching, asphalt milling, paving of the entire road-a-bout/legs, and pavement marking that is called out in the special provision for the 4 calendar day detour. Would the department consider adding two days to this detour. | An additional two days will be added to the detour. Additionally, the detour will be changed from consecutive Calendar Days to consecutive Working Days to allow for additional flexibility in case of an unplanned weather event occurs. | Mike Coleman | 2 | 2024-03-05 12:59 | 2024-03-08 12:15
20240312 | 20240312026 | 26 | Addition Cross Section | 1) Sheet 105 of the plans calls out the work for Stage 2B as milling 2â€ of existing asphalt, from STA 331+07 - STA 384+46 can the Department provide a detail for the cross section for this work? | The purpose of the milling is to reduce the vertical difference between the existing pavement and the proposed pavement during the staged construction. The traffic control typical section shown on Page 105 provides a general representation of the milling work and an additional detail will not be provided. Please bid the project per the plan and special provisions. | Mike Coleman | 2 | 2024-03-04 10:48 | 2024-03-06 07:46
20240312 | 20240312026 | 26 | 2" Milling Area | 2) Sheet 105 of the plans calls out the work for Stage 2B as milling 2â€ of existing asphalt, from STA 331+07 - STA 384+46 will this quantity be added to the Removing Asphaltic Surface Milling item? | The removal of the asphalt by milling from Station 331+07 to Station 384+46 will not be paid separately with the item Removing Asphaltic Surface Milling. The removal of the asphalt is being paid for by Removal Asphaltic Surface and Excavation Common. The contractor may choose to remove the existing asphalt a different way other than milling based on their own means and methods. Please bid the project per the plan and special provisions. | Mike Coleman | 3 | 2024-03-04 10:49 | 2024-03-06 07:47
20240312 | 20240312026 | 26 | Temporary 12:1 Max HMA Slope | 3) On sheet 106 of the plans, the Typical for Stage 2C from STA 331+07 - STA 384+46 shows a Temporary 12:1 Max HMA Slope. Should this quantity be added to the Asphaltic Surface Temporary item? | We will be issuing an addendum to adjust the Asphaltic Surface Temporary quantity. | Mike Coleman | 4 | 2024-03-04 10:50 | 2024-03-07 15:38
20240312 | 20240312026 | 26 | Storm sewer connections | For a few storm sewer connections, the work may involve excavation into the shifted traffic lanes. This will be done during daylight working hours with flagging operations. Is it acceptable to patch the connection point with base course for the interim and then patch in asphalt by the end of the day Friday? This is the guidance given for the cross culvert pipe on this same project. | The patches for the storm sewer connections can be completed in a similar fashion to the culvert pipe replacement where traffic can temporarily ride on an aggregate surface and it can be patched in with asphalt by the end of the work week per the special provisions regarding culvert replacements. | Mike Coleman | 5 | 2024-03-05 11:18 | 2024-03-06 07:48
20240312 | 20240312026 | 26 | Storm Sewer Connections - Patching | For the storm sewer connections involving excavation into the shifted traffic lanes from STA 331+07 - STA 384+46, it does not appear that this HMA has been included in the Asphaltic Surface Temporary quantity. Can this be added to the bid item? | We will be issuing an addendum to adjust the Asphaltic Surface Temporary quantity. | Mike Coleman | 6 | 2024-03-05 16:29 | 2024-03-07 15:39
20240312 | 20240312026 | 26 | Base Aggregate Dense under the sidewalk | Nowhere in a plan does it show placing base aggregate under the new sidewalk. Is this what department expects to be done? |  |  | 7 | 2024-03-08 13:42
20240312 | 20240312026 | 26 | Slip forming curb | STA 385 to 401 it appears that new curb goes in the same spot, but existing sidewalk stays. Would WisDOT allow removing 2 feet of existing sidewalk to allow slipform for new curb and gutter? |  |  | 8 | 2024-03-08 14:13
20240312 | 20240312026 | 26 | Construction Schedule | Would the Department provide their construction schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/atusjux2fhovr82u61q8lilbto63p4m0 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-02-26 09:15 | 2024-02-28 08:52
20240312 | 20240312027 | 27 | Asphalt Removal | In stage 3 stations 103 to 105 need to have asphalt removed that is not part of common excavation. Will you be adding the item of Removing Asphalt to cover this work? | Yes. The Removing Asphalt bid item will be added to cover the areas in stage 3 that arenâ€™t part of Common Excavation. An addendum will be issued. | Mike Coleman | 1 | 2024-02-28 13:52 | 2024-03-05 13:30
20240312 | 20240312036 | 36 | Construction Staking | Some recent signing projects in the Northwest region have included Construction Staking Resurfacing Reference to aid with the location of sign placement. Should that be added to this project? | This is covered under standard spec 105.6.2 Contractor Staking. The Construction Staking Resurfacing Reference item will not be added for this project. | Mike Coleman | 1 | 2024-02-27 12:09 | 2024-02-28 09:14