## qandasearchletting_results
Date: | 2024-06-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240611 | 20240611001 | 1 | Help with testing special characters | I want to know about a 1&#39; pipe, a 2&quot; pipe &amp; what the % of the job is (let on January) &amp; when it&#39;s not; what happens&#58; |  |  | 2 | 2024-06-04 12:37
20240611 | 20240611001 | 1 | Blandings Turtle Fence | Was this installed by Others or will the terminal pad grading need to be performed after 10/15? | The fencing with this project was installed by others prior to May 20th. | Mike Coleman | 1 | 2024-05-20 07:50 | 2024-05-21 06:16
20240611 | 20240611002 | 2 | Trees | Are all the evergreens for this project B&amp;B or is container acceptable as well? Please advise. | All evergreen trees for the project shall be B&B as noted on the Site Restoration Plan sheets (pages 108-109). | Mike Coleman | 4 | 2024-06-03 14:04 | 2024-06-05 05:22
20240611 | 20240611002 | 2 | Asbestos Report | Can the asbestos report be posted? | The asbestos report can be found at the following location: https://wisdot.box.com/s/ygb84szppi3qi0doefua1fxj9q6njsbu or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-05-29 12:16 | 2024-05-29 12:25
20240611 | 20240611002 | 2 | Type 10 Base | I don&#39;t see the location of the Type 10 base in any of the electrical plans. Can you provide the plan sheets that show this base and the structure it is for? | The Type 10 base is shown on the Continuous Count Station Detail plan sheet (page 26). | Mike Coleman | 6 | 2024-06-05 09:01 | 2024-06-06 06:28
20240611 | 20240611002 | 2 | Casings for Footings | If using a CMP for casing, can that remain in place permanently? | If a CMP is used for casing when constructing High Mast Lighting foundations, there would be no structural design concerns with leaving it in place, so long as conduit installation is considered and planned for. | Mike Coleman | 1 | 2024-05-28 15:41 | 2024-05-30 09:42
20240611 | 20240611002 | 2 | Right of Way | Will the Department approve a borrow pit within a portion of the approximately 20 acres of right of way located West of the proposed Rest Area that is not designated as a wet land? | Based on a WisDOT regional review, a borrow pit in this area would not be approved. | Mike Coleman | 5 | 2024-06-03 14:37 | 2024-06-06 06:37
20240611 | 20240611002 | 2 | Right of Way | Will the Department approve a borrow pit within the approximately 20 acres of right of way located West of the proposed Rest Area? | Wetland delineation information obtained for the project showed some large areas of wetland to the west of the proposed rest area, so further coordination with WisDOT and WDNR would be required prior to approval. | Mike Coleman | 3 | 2024-05-31 07:26 | 2024-06-03 06:19
20240611 | 20240611003 | 3 | Removing and Paving Operations | So looing at the boring in the plan sheets would say that most of the project we will be down to base aggregate after milling. How does DOT intent on holding a 7 days requirement between milling and paving with the EBS areas on the project? 4,900 CY roughly 10 days, 14,000 tons of base between 1 1/4&quot; and 3&quot; figure roughly 1000 - 1500 tons per day = 11-15 days. doesn&#39;t seem like there will be enough time to get the grading work done before the pavement has to be installed. | An addendum will be issued to remove the 7 day requirement. | Mike Coleman | 3 | 2024-05-30 18:51 | 2024-06-06 12:46
20240611 | 20240611003 | 3 | Interim Completion Date and Contract Completion Date | What is the significance of the September 30th Interim Completion date for all HMA work to be completed? Then the Contract Completion is October 31st seems like that is contradicting? | The significance of the Interim Completion date of September 30th is to avoid cold weather paving with this project. The intention is for paving to be completed before October and during the month of October other work, like the base aggregate shoulders and guardrail, and finishing items can be completed. | Mike Coleman | 1 | 2024-05-30 18:15 | 2024-06-04 07:51
20240611 | 20240611003 | 3 | Design Schedule | Would DOT be willing to share the project design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/kol6s7hw2rt1vyywjucjcmuiujoi1bhk or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-05-30 18:38 | 2024-06-04 07:49
20240611 | 20240611004 | 4 | Plan Holders List | I am looking to quote aggregates for this letting. how do i get a plan holders list? | The plan holders list can be found at the following location: https://wisconsindot.gov/hccidocs/bid-let/2024/20240611/planholders.pdf and/or you can submit a quote in Bid Express utilizing the Small Business Network. | Mike Coleman | 1 | 2024-05-15 08:06 | 2024-05-15 08:48
20240611 | 20240611005 | 5 | Clearing & Grubbing | I see the clearing line item but there is no grubbing called for. Could you please confirm that grubbing will not be needed on this? | There is no grubbing that will be done with this project. The grubbing will be done on a future project. | Mike Coleman | 1 | 2024-05-29 16:52 | 2024-05-31 09:25
20240611 | 20240611006 | 6 | Bar Steel Reinforcement HS Coated Structures | Calculated coated bar steel quantity from the bill of bars is 5,286 lbs less than the estimated plan quantity of 19,320 lbs. Is the bill of bars correct? | The bill of bars is correct, but the calculated weight was not. An addendum will be issued for the revised quantity. | Mike Coleman | 2 | 2024-06-03 19:36 | 2024-06-06 06:39
20240611 | 20240611006 | 6 | Temporary Structure | Is a gravel surface acceptable for the driving surface on the temporary structure? | A gravel driving surface on the temporary bridge is not acceptable unless the gravel can be detained within the structure such that no gravel would spill into the creek. | Mike Coleman | 1 | 2024-06-03 19:35 | 2024-06-06 06:38
20240611 | 20240611006 | 6 | Bar Steel Reinforcement HS Coated - Weight | The weight on page 11 of 19,320 lbs., which is approximately 5,286 lbs. more than the weight of the Bill of Bars. Can this be reviewed? | Bill of bars is correct, but the calculated weight was not modified accordingly. An Addendum will be issued with the correct quantity for Bar Steel Reinforcement HS Coated. | Mike Coleman | 3 | 2024-06-04 07:28 | 2024-06-06 06:40
20240611 | 20240611006 | 6 | Temp Structure | Why is a min 50&#39; clear span necessary when a couple of 4&#39; diameter CMP&#39;s would give the minimum clear opening required? If CMP was not allowed the temporary could be built on the skew shortening the clear span considerably. | The 50â€™ clear span is required to minimize disturbance to creek. Alternative crossing methods can be explored with DNR at the time of construction. We acknowledge the angle of temporary bridge relative to the creek results in a longer structure; however, proposed location minimizes land required, tree loss, and allows the temporary road to closer follow the natural slope, reducing the disturbance necessary to construct it. | Mike Coleman | 4 | 2024-06-06 08:44 | 2024-06-06 13:51
20240611 | 20240611007 | 7 | Quantities | After an initial review of the plan quantities shown it appears that Ramp C &amp; D quantities shown in the station to station summary (plan page 338) do not match the cross sections. This would include the cut, fill and drainage blanket quantities. The area (SF) shown in the table are not matching the cross sections. Please confirm that the quantities for Ramps C &amp; D are correct and all other areas of the project for this matter. | Minor discrepancies were found between the earthwork data and the design surface models. This has been corrected and revised in the posted earthwork Excel summary. The plan sheets will be updated via addendum. | Mike Coleman | 4 | 2024-05-20 14:55 | 2024-05-28 07:00
20240611 | 20240611007 | 7 | Barrier Block & Crash Cushion Emergency Mob Items | All projects so far on this corridor have had the emergency response to barrier block and crash cushion SPV items but this job does not. Please advise if this job will be adding these items or how work will be paid for if block or crash cushions are damaged or misplaced by the traveling public. | The SPV items for emergency response to traffic involving concrete barrier and crash cushions will not be added to this project. Maintenance of these items will be incidental to current bid items SPV.0060.04 (Crash Cushions Temporary Left in Place) and SPV.0090.01 (Concrete Barrier Temporary Precast Left in Place). The temporary concrete barrier will be placed 8 feet from the existing edgeline and pinned so there is a much lower risk of impact and need for emergency repair. | Mike Coleman | 16 | 2024-06-05 11:23 | 2024-06-06 13:38
20240611 | 20240611007 | 7 | Soil Boring Reports | Are soil boring reports available for this project? | The soils reports can be found at the following location: https://wisdot.box.com/s/uoybsj3bim8a0kkooh0khiovm9er9f3q or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-05-14 14:28 | 2024-05-23 12:40
20240611 | 20240611007 | 7 | WIDOT Response to Question 14 | Based on the response to this question, it seems the intent is to install this storm sewer after drainage blanket/wicks/surcharge/surcharge period has occurred. What about other storm sewer/culvert pipes on the project that occur in areas of surcharge? It is most likely that the surcharge duration for Area C and D will extend beyond the contract completion. Is it the intent to have the contractor return after contract completion to install these pipes? There are culvert pipes planned to drain the I-41 NB/SB ditches at the locations of the new abutments. What is planned for temporary drainage if these culverts are not installed prior to the embankment/surcharge construction? There is nothing in the special provisions that require the storm sewer/culvert pipes on the project to be installed after drainage blanket/wicks/surcharge periods have occurred. | Only the permanent storm sewer located in Area A would need to wait for embankment settlement. Other temporary culverts/drainage structures located within areas B, C, D, and E can be installed with the embankment and do not need to wait for settlement to occur. All of this work can be completed during the contract time. | Mike Coleman | 18 | 2024-06-07 10:59 | 2024-06-10 11:53
20240611 | 20240611007 | 7 | Settlement Gauges | How long after completion of embankment does the settlement gauges have to be monitored? Can a table be provided? All it currently states is &acirc;&#128;&#156;the termination of monitoring as agreed to with engineer&acirc;&#128;&#157;. This is too variable. Please provide the embankment settlement period schedule. | Settlement gauges need to be monitored for 4 months after embankment placement is complete or the contract completion date, whichever occurs first. Data collection required beyond this point will be the responsibility of the Department. The Southbridge Settlement Schedule can be found at the following location: https://wisdot.box.com/s/uoybsj3bim8a0kkooh0khiovm9er9f3q or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 7 | 2024-05-20 15:38 | 2024-05-28 07:05
20240611 | 20240611007 | 7 | Construction Access | In Article 4.1 of the special provisions, Construction Access, it states &acirc;&#128;&#156;During the period when lane closures are not allowed on IH41, access into the work zones from IH41 must be made with a deceleration lane&acirc;&#128;&brvbar;.&acirc;&#128;&#157;. Two paragraphs down it states &acirc;&#128;&#156;Access to and from IH 41 for embankment placement or other grading activities will be prohibited. Contractor shall utilize existing frontage roads (Mid Valley Drive, French Road) to access the project site.&acirc;&#128;&#157; Will ingress and egress access points be allowed for access to the work zone from IH41 or will the frontage roads be the only allowed access points? | Access will not be allowed from I-41 to the project site for hauling activities (ie. embankment, aggregate, paving). Ingress and egress access to the work zone will be limited to the frontage roads. Limited access will be allowed during night-time lane closures of I-41 for crash cushion and temporary barrier wall installation. | Mike Coleman | 12 | 2024-05-30 15:01 | 2024-06-05 05:21
20240611 | 20240611007 | 7 | Drainage Blanket | Is the drainage blanket item going to require the QMP subgrade spec? | No. The QMP subgrade spec applies to subgrade materials above the drainage blanket. | Mike Coleman | 6 | 2024-05-20 15:37 | 2024-05-22 08:03
20240611 | 20240611007 | 7 | Field Facilities | Per 1.7 Field Facilities of the Special Provisions, the department will provide primary field facilities but bid item 246 Field Office Type B is included. Please clarify SP 1.7 or remove the bid item. | The I-41 Field Office (3600 Commerce Ct) will be the primary facility and is the location where all meetings will be held (precon, weekly, prepour, etc). The bid item of Field Office Type B (642.5001) is included in the contract for inspection staff due to the longer distance from the primary facility to the project site. | Mike Coleman | 9 | 2024-05-29 09:35 | 2024-05-31 09:18
20240611 | 20240611007 | 7 | Wick Drains | Per plan page 37 and Article 9.11 of the Special Provisions, payment for Prebored Prefabricated Vertical Drains is full compensation for the cost of furnishing the prefabricated vertical drain material. Typically, the Department has paid for all wick drains installed under the Prefabricated Vertical Drains item even through where preboring has been performed. How does the Department intend to measure and distinguish the quantities paid under Prebored and Prefabricated in the field with this measurement system? The Department has simply counted the rolls of material used in the past and paid for all installed quantities under the Prefabricated Vertical Drains bid item. | Addendum #1 will modify the payment of these items. When a location requires preboring, the contractor will be paid the full length of the wick drain installation under the Prebore Prefabricated Vertical Drains bid item. The final measurement of these items will be determined based on the contractorâ€™s installation method and agreed to with the project engineer. | Mike Coleman | 11 | 2024-05-29 10:51 | 2024-05-31 09:23
20240611 | 20240611007 | 7 | Embankment & Drainage Blanket QTYs | Please confirm that the quantity for the drainage blanket item has been deducted from the embankment quantity and that the embankment quantity is only the &acirc;&#128;&#156;fill outside&acirc;&#128;&#157; of the drainage blanket? | Correct. The embankment quantity does not include the drainage blanket. This can be verified on the Excel spreadsheet for the earthwork summary. | Mike Coleman | 5 | 2024-05-20 15:36 | 2024-05-28 06:49
20240611 | 20240611007 | 7 | Project Access | Please confirm that this project will always have access to / from the frontage roads. Mid Valley Drive North, Mid Valley Drive South, French Road South &amp; Southbridge Road North for both 2024 and 2025? | The contractor will have access to the west side of I-41 via Mid Valley Drive both north and south of the project. Access to the east side of I-41 will be provided from French Road (south) and Southbridge Road (east). There will be local construction projects in 2024 and 2025 along Lawrence Drive near Southbridge Road that may change traffic patterns but access will be maintained to Innovation Court. | Mike Coleman | 8 | 2024-05-20 15:39 | 2024-05-22 08:03
20240611 | 20240611007 | 7 | Design Schedule | Please provide the design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/uoybsj3bim8a0kkooh0khiovm9er9f3q or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-05-14 14:29 | 2024-05-16 08:09
20240611 | 20240611007 | 7 | Earthwork | Please provide the earthwork data in excel format. | The earthwork data spreadsheets can be found at the following location: https://wisdot.box.com/s/uoybsj3bim8a0kkooh0khiovm9er9f3q or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-05-20 11:56 | 2024-05-28 06:59
20240611 | 20240611007 | 7 | Staging | Should the storm sewer in Area A be installed before wick drains and drainage blanket construction or after the fill placement and settlement period is complete? | Storm sewer should be installed after the drainage blanket, wick drains, and embankment is placed in Area A. Area A has a 5-month settlement period so storm sewer could be installed in early 2025. Note that storm sewer for pond D outfall can be installed in 2024. | Mike Coleman | 14 | 2024-06-04 16:11 | 2024-06-06 08:28
20240611 | 20240611007 | 7 | Removing Billboard Sign (Sta 607+00â€™GVFNâ€™), Item 204.9060.S.01 | Special Provision 8.4 states removing the concrete footing including piles is required. Can the piles be cut 2&#39; below grade and left in place? | Yes. If piles are found, they can be cut and removed to a minimum of 2 feet below final subgrade. | Mike Coleman | 10 | 2024-05-29 09:49 | 2024-05-31 09:20
20240611 | 20240611007 | 7 | Special Provision 9.2 Notice to Contractor - Salvaged Topsoil | This provision states that all existing topsoil (average depth identified as 12&quot;) beneath proposed embankments will be removed incidental to the Salvaged Topsoil required on the project. WIDOT Standard Specifications Section 625.1(2) states that only the topsoil removed from the proposed roadway excavations and embankment required to cover the slopes to the depth specified in the plans in order to generate enough material for the proposed Salvaged Topsoil shall be removed. Any depths required beyond the depth necessary to place the Salvaged Topsoil should not be considered incidental and should be paid for as Excavation Below Subgrade as it is on other projects. Please remove this Special Provision from the project and use Standard Specifications that are used on all other projects in regards to the Salvaged Topsoil bid item. | I agree that the current special provision is written poorly and can be interpreted incorrectly. Our intent is that salvaged topsoil beyond 12â€ in depth would be paid as EBS. The excess topsoil referred to in the spec would be between 6â€ (depth to be placed) and 12â€ (assumed existing depth). We did add an undistributed quantity of EBS to the earthwork table specifically for excess topsoil. 8070 CY was assumed and a comment was added explaining what it is for. | Mike Coleman | 17 | 2024-06-06 22:37 | 2024-06-10 10:31
20240611 | 20240611007 | 7 | Response to Question 17 | WIDOT Standard Specifications for Salvaged Topsoil require only stripping the quantity required to place as Salvaged Topsoil without a specific depth of stripping requirement. Any stripping topsoil beyond the depth required for Salvaged Topsoil is considered Excavation Below Subgrade. The special provisions on this project and the response to Question 17 are requiring stripping existing topsoil at a depth of 12&quot; which will generate more salvaged topsoil than is required for the Salvaged Topsoil bid item, therefore making additional excavation incidental to this bid item. Please remove this special provision and use WIDOT Standard Specifications so that incidental excavation is not included in the Salvaged Topsoil bid item. | Based on soil borings for this area the estimated average depth of existing topsoil is 12â€. Topsoil removal up to 12â€ within embankment areas will be incidental to the salvaged topsoil bid item. Topsoil that is encountered over 12â€ will be paid as EBS. An undistributed quantity of EBS specifically for excess topsoil (8,070 CY) has been included in the contract. | Mike Coleman | 19 | 2024-06-10 10:50 | 2024-06-10 11:54
20240611 | 20240611007 | 7 | Storm Sewer | Will aggregate backfill be required for the full depth of the storm sewer from Structure 5B - 5C or can trench spoils be utilized beyond 1&#39; above the top of the pipe? | All storm sewer including from structure 5B to 5C will need trench backfill material (12â€ above top of pipe to top of subgrade) conforming to standard specs 209.2 or 520.2.5.2 for granular material. | Mike Coleman | 15 | 2024-06-04 16:13 | 2024-06-06 12:39
20240611 | 20240611007 | 7 | Right of Way | Will the Department approve the construction of a storm water pond located within the DOT property bound by Mid Valley Drive South, Ramp C, and Southbridge Road EB to obtain borrow for the project? | This request would need to go through the ECIP process as a select site for borrow. Additional coordination may be needed depending on the scale and impacts of this request | Mike Coleman | 13 | 2024-06-03 13:52 | 2024-06-05 05:23
20240611 | 20240611008 | 8 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/a6qrmekd8xzknnoqhpqaf055axzjoufy or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-05-31 11:08 | 2024-06-03 10:49
20240611 | 20240611008 | 8 | Crash Cushions pad | On the plan set page 22 under Crash Cushions Temporary it has (4&#39;x26&#39;PAD) is this an asphalt pad or concrete? Usually the pads are for permanent Crash Cushions, wondering if it was mistakenly put in there. | Per FDM 11.30 and CMM manual 145.12.1, most models of temp crash cushions should be placed on pavement as well. However, the proposed location of the temp crash cushions for this project were adjusted so they fall on existing pavement avoiding the need for a pad. If the temporary crash cushions are placed as shown in the plans, the (4'x26' PAD) note is obsolete and no additional work would be needed. | Mike Coleman | 2 | 2024-06-03 10:22 | 2024-06-04 07:52
20240611 | 20240611009 | 9 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/q8a6ckn1l8i7oazw5pngut1yj3gpc3t7 or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-05-28 15:34 | 2024-05-29 08:19
20240611 | 20240611009 | 9 | HMA Acceptance Table | Per the HMA Acceptance Table on sheet 42 of the plans, bid item 465.0105 mixture acceptance is to be tested via &acirc;&#128;&#156;QMP as per standard specification 465&acirc;&#128;&#157; however per SS 465 Asphaltic surface is not testable. Can the department please remove this requirement from the HMA Acceptance Table? | Follow SS 465 for material acceptance for 465.0105 Asphaltic Surface. | Mike Coleman | 3 | 2024-06-04 15:27 | 2024-06-05 11:01
20240611 | 20240611009 | 9 | Milling and Paving Width | The contractor has examined the site per standard specification 102.5 and has discovered that the existing roadway varies in width from 24&acirc;&#128;&#153; to 27&acirc;&#128;&#153; which conflicts with the typical existing section shown in the plan set. What is the intention for milling the existing roadway? What is the intended width of new pavement on the roadway in both the standard mainline sections and the areas with guardrail/widened asphalt shoulders? | The intent is to match existing width on typical mainline areas and match the guardrail tapers as laid out in the construction details. The department will issue an addendum to make this clear. | Mike Coleman | 2 | 2024-06-03 07:46 | 2024-06-04 07:52
20240611 | 20240611010 | 10 | Traffic control B-18-34 | Will full closures be allowed on B-18-34 for performing the bridge jacking? | The contractor wonâ€™t have to jack the bridge up much to get the sheeting under the bearings, and it should be do-able during staged construction. The girders that will need to be jacked shouldnâ€™t experience much, if any, live loading during the jacking operation with traffic relegated to the other half of the bridge at a time. | Mike Coleman | 1 | 2024-05-23 11:49 | 2024-05-28 06:51
20240611 | 20240611011 | 11 | B-52-51 Box Culvert | The plans call for removing the sediment from the north barrel of the box. The SPV&#39;s say none of the sediment in the cells of the box culvert shall be disturbed. What needs to be completed? | We will issue an addenda to clarify discrepancy. | Mike Coleman | 1 | 2024-05-23 06:09 | 2024-05-28 07:00
20240611 | 20240611011 | 11 | Grooving for Pavement Marking | The special provisions state the Marking Line Grooved Wet Reflective Epoxy 6&quot; Centerline be applied the same day as paving operations. This can not be done as the spec for grooving requires a waiting period of 48 hours after paving prior to Grooving asphalt. |  |  | 2 | 2024-06-03 08:54
20240611 | 20240611012 | 12 | dowel baskets | Are dowel baskets required in Bike lanes with integral curb and gutters per details on sheet 19. | Dowel baskets are required in all bike lanes with integral curb and gutters and as indicated on the typical sections and SDD 13C13-11. | Mike Coleman | 3 | 2024-05-16 10:19 | 2024-05-20 06:12
20240611 | 20240611012 | 12 | casting types | can the casting types in the MQ&#39;s be verified. it appears the manhole and inlet castings are not accurate | These are City of Milwaukee standard drainage items/structures (not-WisDOTâ€™s). â€¢ Inlets have MS57 grate with MS51 frame. â€¢ Manholes have MS58-A cover with MS21 frame. | Mike Coleman | 7 | 2024-06-06 11:26 | 2024-06-10 09:50
20240611 | 20240611012 | 12 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/26niea7flkp1xvt7ufj1vnnc5ab7ca6u or can be accessed on the HCCI June bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-05-14 07:34 | 2024-05-15 08:57
20240611 | 20240611012 | 12 | Cold weather items | Given the interim completion date, should the contract include cold weather Pavement Marking, HMA, and Concrete items? | The interim completion date of November 1 was set for this project such that all work be completed before cold weather, impacting construction items and activities, begins. The use of cold weather protection items in past projects have been used to continue working between mid-November and end of December. | Mike Coleman | 6 | 2024-06-05 15:09 | 2024-06-06 12:36
20240611 | 20240611012 | 12 | Paving Clearance Intergal Curb | In the special provisions it is called out Zero (0&acirc;&#128;&#157;) Clearance Slip or integral paving machine. This area is called out for the new proposed curb line between E Kenwood Ave and E. Hampshire Ave Sta. 29+50 to 33+00 Approximately. However, per the typical sections in the drawings a one foot (1&acirc;&#128;&#153;) Clearance is shown behind the Concrete Curb Intergal Type J &amp; D. Is it under the designers assumption that the entire Intergal curb be Zero ( 0 ) Clearance as there is no room shown for track line of integral paver? | As indicated in the special provisions, the proposed curb on both sides of the road between E Kenwood Ave & E Hampshire Ave a â€œ0â€ clearance slip or integral paving machine shall be used. No tree root system and soil disturbance is allowed behind the existing curb. The roadway width will be narrowed (from the existing 62â€™ to the proposed 61.5â€™) in this segment which provides 3â€ of clearance on each side of the roadway. Also, the limits of the 6â€ base aggregate shall flash with the back of the proposed curb on both sides between this segment (Kenwood to Hampshire) of the road. | Mike Coleman | 4 | 2024-05-30 11:11 | 2024-05-31 09:26
20240611 | 20240611012 | 12 | Can the Soils Report be provided? | Please provide the soils report. | The Geotech Report can be found at the following location: https://wisdot.box.com/s/26niea7flkp1xvt7ufj1vnnc5ab7ca6u or can be accessed on the HCCI June bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-05-14 07:33 | 2024-05-15 08:53
20240611 | 20240611012 | 12 | Milling depths and 4LT quantity | The asphaltic surface milling detail calls for a 2&quot; depth. However, the 4LT 58-28 S quantity (AP4) going back in the milled areas appears to be overstated. Is the intent to mill 4&quot; and pave in 4&quot; of asphalt? | Intent is to mill 4â€ and pave back 4â€. | Mike Coleman | 8 | 2024-06-06 15:57 | 2024-06-10 12:27
20240611 | 20240611012 | 12 | PAVING CLEARANCE | The typical drawings for Finished typical sections show a one foot clearance behind the back of the Integral curb, for all finished typical sections in the plan set from station 7+84 to station 55+00. Is it the designers assumption that there will no room for track line behind the new Integral curb? Beyond the Zero clearance called out between Sta. 29+50 and Sta. 33+00. |  |  | 5 | 2024-06-03 14:14