## qandasearchletting_results
Date: | 2024-08-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20240813 | 20240813001 | 1 | Item 1 - Individual Site Bid Items | I noticed the addendum removed the mobilization rates per site. Is there a reason for this? Every site has different needs which input to their cost of mobilization. This is especially important as additional areas are added via work orders after award. For the original contract we are able to work out an average STA cost for Clearing based on the plans provided. But without knowing which sites will be added we are not able to do that for future locations. | The site specific mobilization items were removed to maintain consistency with the other regional tree clearing projects throughout the state. Project staff from the 5 WisDOT regions and staff from Central Office discussed the mobilization issue and determined this was the appropriate action to take. | Mike Coleman | 1 | 2024-08-02 17:40 | 2024-08-06 08:30
20240813 | 20240813001 | 1 | Item 1 - Traffic Control | Will traffic control be paid under both the &quot;Site Traffic Control&quot; item and the specific traffic control item used (ex - Work on Shoulder, etc)? Also, there are 29 EA of each of these items but only 7 sites provided. Please advise the intention of this. | The intention is to pay for the traffic control the site item for each site, in addition if any of the specific traffic control situations are required for specific sites, they will be paid using that specific item for the required action. The intention is to have the items available to be used on the initial and future work orders. There are 7 sites in the initial contract. There are 29 total sites that have been identified as possibly being included in the contract, which means 22 additional sites could be added with future work orders. | Mike Coleman | 2 | 2024-08-02 17:42 | 2024-08-06 08:29
20240813 | 20240813001 | 1 | Traffic Control - Follow Up RFI | As a follow up to the previous traffic control question -- to confirm&#58; *Each site will be paid both &quot;Site Traffic Control&quot; and the designated traffic control item | The contractor will be paid the Site Traffic Control Item (SPV.0060.17) for each site acceptably completed. The contractor will also be paid for the individual situations that may be required at each site to complete the work. If work on a shoulder or parking lane is required at a site, then item SPV.0060.03 (Work on Shoulder or Parking Lane) would be paid for at that site. If work on the shoulder of a divided roadway is required at a site, then item SPV.0060.04 (Shoulder Closure on Divided Roadway) would be paid for at that site. If flagging operations are required at a site, then Item SPV.0060.05 (Lane Closure With Flagging Operation) would be paid at that site. | Mike Coleman | 3 | 2024-08-06 13:12 | 2024-08-07 05:36
20240813 | 20240813003 | 3 | City of Fitchburg Standard Spec | Where can we find the City of Fitchburg Standard Specifications? | The City of Fitchburg Standard Specifications can be found here, under the Resources header: https://www.fitchburgwi.gov/141/Public-Works A direct link to the document is here: https://www.fitchburgwi.gov/DocumentCenter/View/26554/2024-Standard-Specifications?bidId= | Mike Coleman | 1 | 2024-07-19 10:33 | 2024-07-25 13:38
20240813 | 20240813003 | 3 | Design Files | Can the Department provide the design Cad files for this project? | This is a local program project. On local program projects, there is no requirement for contractor data packets. | Mike Coleman | 2 | 2024-07-22 12:35 | 2024-07-24 16:06
20240813 | 20240813003 | 3 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The geotechnical report can be found at the following location: https://wisdot.box.com/s/2lnff75h6wxtyfu0uboi23rzllvogzy3 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-07-22 12:40 | 2024-07-25 13:45
20240813 | 20240813003 | 3 | Asphalt Bike Path | According to the plan set, the bike path is to be placed as a 5 LT 58-28 S. Can the Department make this an Asphaltic Surface item to eliminate the need for density testing etc., and designate in the special provisions that contractors must supply a 5 LT? | City of Fitchburg standard specs call out density standards for shared-use paths (section 5.4.01.A) and after checking with City of Fitchburg officials they confirmed that they do not want to eliminate the density testing requirements for the shared-use path pavement. | Mike Coleman | 5 | 2024-07-23 14:33 | 2024-07-26 09:16
20240813 | 20240813003 | 3 | 0348 - FURNISH AND INSTALL APS SYSTEM | Will the Campbell PedSafety WiAPB APS push button be accepted as a compatible substitute for the APS System for this project as it is now on the WisDOT state contract (RFB#510575)? | The approved item was selected to maintain equipment consistency and maintenance for the City of Fitchburg, so an alternative item would not be acceptable as a substitute. | Mike Coleman | 6 | 2024-07-25 15:02 | 2024-07-31 08:44
20240813 | 20240813003 | 3 | Transformer Bases | The transformer bases for this project are 28 months out. How would you advise us to bid this project with that time frame? Wouldn&#39;t get the transformer bases in time. Thank you. |  |  | 7 | 2024-08-12 13:42
20240813 | 20240813004 | 4 | Contract Completion Time / Traffic Control Days | The contract completion time on the specs says 45 days but in the traffic control misc. quantities it has 74 days. What is the reason for the difference? | The contract completion time specified with the project is 45 Working Days. The traffic control quantities are determined/calculated using the number of Calendar Days that encompass the project duration. The 74 Calendar Days used to calculate the traffic control quantities is equivalent to 45 Working Days. Please see the details within the â€œContract Time for Completionâ€ chart for the origin of where both these numbers are determined. | Mike Coleman | 1 | 2024-08-05 12:26 | 2024-08-05 13:04
20240813 | 20240813005 | 5 | Asphalt Qtys | 4 LT 58-28S&#58; According to the SY for milling the qty should be closer to 3,450 ton, not 3,700 ton. Can the Department adjust to the correct qty please? Asphaltic Surface Patching&#58; What is this item for? If this is for filling in the distressed milling, the item should be Asphaltic Surface per the SPV. In addition, the qty does not appear to be correct if distressed is 2&quot;, the qty should be around 180 tons, not 1,100 tons. | The 4 LT 58-28 quantity utilized the higher limit for the conversion to tonnage, which is typical when we finalize the quantity for this item. After review, there is an adjustment that is needed for the distressed milling quantity listed on the Miscellaneous Quantity sheet. The total should be 4690 SY (see below): STA. 300+35 â€“ STA. 332+00 = 2510 SY STA. 332+00 â€“ STA. 360+00 = 2180 SY The distressed milling quantity is based on 15% of the total milling area. The intent of the asphalt patching quantity was to fill in the lower areas of the distressed milling. The 1100 tons matches the area of distressed milling as corrected and explained above. | Mike Coleman | 1 | 2024-08-01 09:51 | 2024-08-06 08:28
20240813 | 20240813005 | 5 | Follow up to Question #1/Addendum #1 | Addendum #1 corrected the quantity of distressed milling from 1,600 SY to 4,690 SY. Per the special provisions, the distressed milling is supposed to be 2&quot; thick. With that said, the associated paving item is the incorrect item per the SPVs and the incorrect quantity. The quantity should be ~525 tons, not 1,100 tons. Please adjust via addendum. | The Distressed Milling Quantity (SY) is undistributed and based upon 15% of the total milling area. An adjustment to this quantity was addressed with addendum #1. The overall depth of asphalt varies throughout the length of the project. The intent of the Asphaltic Surface Patching Item (460.0110) is to fill in the lower areas of the distressed milling and will vary based upon location. The quantity of 1100 tons for Item 460.0110 accounts for the undistributed Distressed Milling Quantity and variation in existing asphalt depth for the project. | Mike Coleman | 2 | 2024-08-08 16:44 | 2024-08-12 09:08
20240813 | 20240813006 | 6 | Guardrail Removal | Should there be an item for guardrail removal? | Bid Item 204.0165 REMOVING GUARDRAIL was not provided in the plan, nor included in the miscellaneous quantities or estimate. An addendum will be prepared to include this item. | Mike Coleman | 1 | 2024-07-12 09:47 | 2024-07-24 15:19
20240813 | 20240813006 | 6 | 2025 Work | Will the road be closed again in 2025 or will that work be completed under traffic? | The plans are set up that the road will again be closed in 2025 for the removal of the temporary pavement and regrading and application of the permanent pavement. | Mike Coleman | 2 | 2024-08-09 06:06 | 2024-08-09 09:12
20240813 | 20240813007 | 7 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/si7qgc3ak1ywx67305famf7lair377wk or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-26 08:14 | 2024-07-29 08:11
20240813 | 20240813008 | 8 | Design Schedule | Could the Department Provide the Design Schedule for this job? | The design schedule can be found at the following location: https://wisdot.box.com/s/05ysp6r4w5q96wsfjqkqbiefzt26bt2o or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-23 14:29 | 2024-07-25 07:50
20240813 | 20240813008 | 8 | Bid Item 0006 | There does not appear to be a C-70-7 structure in the plans. Can details for the work to be performed at this structure be provided? | Structure C-70-7 is the existing box culvert to be replaced by structure B-70-0327. Structure C-70-7 is to be backfilled as noted on the structure sheets once B-70-0327 is complete and operational. | Mike Coleman | 2 | 2024-08-02 13:35 | 2024-08-08 09:26
20240813 | 20240813008 | 8 | Box Culvert Extensions | Why are three of the box culvert extensions not included with the other similar structures? There are three culverts that are paid for separately and all items related to their completion are paid as a single LS item. This differs from the remainder of the culvert extension structures on this plan. | There are two parts to the question: 1. The three culverts shown in series 2 sheets as construction details are less than 20 s.f. in cross section. Accordingly, per their policy, the Bureau of Structures has removed these culverts from the BOS structure inventory. Therefore, these structures are not shown in series 8 structure sheets even though similar work is required. 2. The â€œeachâ€ bid item for the 3 extensions was used to align with the approach used for roadway drainage culvert apron endwalls. The quantities for individual items such as concrete and rebar are provided in the plans for information to inform bid price development. | Mike Coleman | 3 | 2024-08-02 14:11 | 2024-08-08 09:28
20240813 | 20240813008 | 8 | Fish Spawning | Which culvert locations that have specified construction activity carry waterways that ultimately connect to Lake Winnebago? | All the culverts ultimately connect to Lake Winnebago except for the following: C-20-008, C-20-012, and C-20-015. Those three structures can be excluded from the instream restriction dates. | Mike Coleman | 4 | 2024-08-05 10:17 | 2024-08-12 07:42
20240813 | 20240813008 | 8 | Cable Barrier Across County Lines | There is a run of cable barrier that is in both counties. Will the Department allow any of the approved systems for those counties to be installed on that run? | For a cable guard run that occurs in Fond du Lac and Winnebago counties the Department will allow either of the systems on the Approved Products List for FOND DU LAC COUNTY. The majority of that run is within Fond du Lac county, so that accounts for the majority of the risk for a crash that would impact the cable guard. | Mike Coleman | 5 | 2024-08-05 13:10 | 2024-08-08 06:07
20240813 | 20240813008 | 8 | Soil Boring Information | Could the engineer please provide information of soil boring for the cable barrier? | The soil boring information can be found at the following location: https://wisdot.box.com/s/05ysp6r4w5q96wsfjqkqbiefzt26bt2o or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 6 | 2024-08-07 14:08 | 2024-08-08 07:42
20240813 | 20240813008 | 8 | Culvert Extension | The misc quantities call for temporary barrier wall and crash cushions at all culvert extension locations. Per section 6 of the special provisions for the work to be performed in Stage 1 (M) single lanes closures are required during off peak traffic hours. Is the intention to have work associated with the culvert extensions also be performed during off peak traffic hours even with the barrier wall installed since these are also called out for work in Stage 1 (M)? | The temporary barrier is needed to protect the exposed temporary shoring and the work area due to the proximity to the travel lanes. The temporary barrier wall may allow the contractor to work during peak hours as long as all equipment, materials and workers are located on the protected side of the barrier. There will be restrictions on ingress and egress during peak hours. Ingress and egress shall be set up with the proper traffic control devices, buffers, tapers, deceleration, and acceleration lengths as shown on Standard Detail Drawing 15D47. | Mike Coleman | 7 | 2024-08-08 09:24 | 2024-08-08 11:17
20240813 | 20240813009 | 9 | Mobile Storage System Questions. | 2.2b2 of spec&#58; Mobile Storage Shelving fire retardant floor and ramp where required. Is it going to be required in the evidence room 109 109a? 2.2b3 of spec&#58; Lists that floor covering will be done by others. According to the drawings/plans on page 190 evidence room 109, 109a will have a sealed concrete finish. What flooring if any will be used on the floor/ramp of the mobile system? Shelving dimensions for mobile storage shelving. What is the overall height of the system? What are the dimensions of the individual shelves? (height, width, depth) How many shelves per column? | 1. Per Code Plan drawing sheet 1/T102 and corresponding code summary analysis, adjacent floor, wall and ceiling assemblies to Evidence Storage 109A are not fire rated. Ramp construction shall not have a flame spread index greater than Class C tested in accordance with NFPA 286. 2. LVT-01. See 1/A804. 3. Per architectural drawings 7/A500 & 12/A500, individual shelves scale at: 10-0â€ long, 24â€ deep, 7â€™-0â€ tall. | Mike Coleman | 1 | 2024-07-16 15:33 | 2024-07-26 09:26
20240813 | 20240813009 | 9 | Schedule | Does the department have a design schedule for this project they can share with the contractor? | The design schedule can be found at the following location: https://wisdot.box.com/s/fx8ye1hi5hbt5uigvb5k5was2el1n64s or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-07-24 19:32 | 2024-07-25 13:35
20240813 | 20240813009 | 9 | Building Steel Fabricator | Please confirm that building structural steel fabricators do not need to be on any of the DOT&#39;s approved product lists that are related to bridge work. It is our understanding that if the requirements as called out in spec 051200 1.4 are met the fabricator would be acceptable. | Correct, structural steel fabricators for the building do NOT need to be on the approved product list. Follow requirements as listed in specifications. | Mike Coleman | 3 | 2024-07-25 16:28 | 2024-07-29 12:35
20240813 | 20240813009 | 9 | 102226 Operable Partitions | We are putting together our quote for the specified manufacturer (Modernfold) and had a few questions/clarifications on this section. â€¢ There is a wall jamb specified but the plan shows a bulb seal with a plate. Also, the jamb is noted to help stabilize the pass door â€“ there is no pass door shown in the drawings. There would need to be blocking in the wall for either the jamb or bulb seal by others and the plate that is shown isnâ€™t something that we would supply. If you would like a pass door we will supply a jamb. â€¢ The pocket would not be big enough if a pass door is included. The pocket width would change to 4â€™8â€ wide if a pass door is included. Please verify a pass door is required. â€¢ There is a reference to tack boards and marker boards â€“ as shown on drawings. The drawings donâ€™t appear to indicate the locations of these. Also, a tack board canâ€™t be placed on the final closure panel or pass doors. â€¢ The spec is calling for either fabric or carpet but A804 PW-01 shows Vinyl in LenTex Lennon Grass â€œ Prairieâ€. Can you please let me know which is preferred? | 1. No pass door; refer to sheet A-504 for further information. Contractor has the option to omit prefinished metal surround if installation meets manufacturerâ€™s approved installation and required STC rating is maintained. 2. No pass door; refer to sheet A-504 for further information. 3. No tack or marker boards; refer to sheet A-504 for further information. 4. Finishes indicated on the drawings (A-804) supersede specifications. | Mike Coleman | 4 | 2024-07-29 16:56 | 2024-08-01 13:50
20240813 | 20240813009 | 9 | BABA and HVAC Equipment Questions | Which Buy America Act is being used? Is it BABA/IIJA Build America Buy America; or the Buy American Act of 1933 FAR Clauses 52.225-9,-10,-11; or the Federal Highway Administration Buy America Made in USA CFR 635.410? This is not outlined anywhere in the specifications. The pot feeder in the mechanical detail M601 has a note stating &quot;connect to systems as detailed and specified.(CP-3 &amp; CP-4, CP-5 &amp; CP-6&quot; but the pot feeder is not depicted anywhere in the drawings and it is not schedule. So does there need to be a pot feeder for both the Chilled Water and Hot Water System? Is the Camus Valiant an acceptable boiler manufacturer? | 1. The proposal document contains the copy of the Buy America provision to be used for this contract. 2. Yes. Please review specification 23 25 00 HVAC Water Treatment under 2.6 Treatment Equipment and 3.4 Closed Water Systems. 3. Manufacturer is generally acceptable. Contractor shall verify unit submitted meets requirements of plan documents and specifications. Refer to Division 1 and 23 05 00 for equipment substitutions. | Mike Coleman | 5 | 2024-07-31 08:43 | 2024-08-02 09:59
20240813 | 20240813009 | 9 | Wall Elevations | 1. Sheets S103 &amp; S104 do not state the top of wall elevations but refer to section cut 4/S803. Section cut 4/S803 states to refer to plan for top of wall elevations. Can you please confirm the desired top of wall elevations? | Note 5 under Foundation Notes on S102 holds for the entirety of the structure. Top of Foundation Wall Elevation = 99â€™-0â€ UNO | Mike Coleman | 6 | 2024-07-31 10:57 | 2024-08-02 09:57
20240813 | 20240813009 | 9 | Floor Finishes in Rooms 112 & 113 | What is the desired product for Epoxy Paint called out for the floor finish in rooms 112 and 113? | Floor finish in rooms 112 and 113 to be Epoxy Paint as indicated on the room finish schedule. Specification section 09 91 00 will be revised and included in an Addenda. Semi-Gloss, fast cure epoxy: 1. 2 coats. 2. Minimum DFT: 5.0 â€“ 10.0 mils. 3. Minimum VS: 72 percent. 4. Surface Preparation: SSPC-SP 14 to a CSP 1-3. 5. Color as selected by E/A. 6. S-W: Macropoxy 646. | Mike Coleman | 7 | 2024-07-31 14:10 | 2024-08-06 08:24
20240813 | 20240813009 | 9 | SolarEdge inverters | Spec section 48 14 00 references Buy America and states to use&#58; 2.3 INVERTER A. Manufacturer&#58; Solar Edge B. Model&#58; SE10KUS; three phase inverter; (-40C TO 60C) 120/208V - with AC RSD; DC safe-ty switch and AFCI; primary unit; 12 year warranty C. Power Optimizer&#58; S500B 1&#58;1; S series; 500W/80V PVRSS compliant (MC4 input connectors) - 208V/480V 25 year warranty included SolarEdge inverters are manufactured in Israel. Would it be best to bid with the specified equipment, or should we use our best judgment on a Buy American eligible inverter(s)? | The Solar Edge unit specified can be called the basis of design. Currently, we are not able to identify an American manufactured unit that meets the specified voltage and power capacity. If the contractors are aware of a unit that meets the design basis and is American made, they can submit that as part of their bid otherwise the inverter would be covered by FHWAâ€™s General Waiver for Manufactured Products. Buy America for iron & steel may still apply for predominantly steel or iron components such as steel housing or mounting hardware. | Mike Coleman | 8 | 2024-07-31 14:12 | 2024-08-06 09:45
20240813 | 20240813009 | 9 | Field Office Clarifications | Page 24 of the proposal pdf section 17 states the department will provide primary field facilities and this is where meetings will be held. However on page 92 of the pdf, section 3.2 FIELD OFFICE it states contractor to provide a field office for the E/A and provide a large room for project meetings. Please clarify if this section 3.2 is accurate or if any additional field office will be required beside the department provided facilities. | Only one field office is required for the E/A, and that will be provided by the department as specified. | Mike Coleman | 9 | 2024-07-31 16:07 | 2024-08-05 08:30
20240813 | 20240813009 | 9 | Building Fire Alarm System Specs | Can we please be provided with specifications for the building general fire alarm monitoring system? We see them for the clean agent system but not the general building fire alarm. | he specification for the fire alarm is part of the clean agent specification. They are one in the same. | Mike Coleman | 10 | 2024-08-02 08:52 | 2024-08-05 07:54
20240813 | 20240813009 | 9 | Insulation | 1. Can you confirm that 2â€ rigid insulation is required under the entire slab on grade? 2. 2. Detail 7/A404 shows metal panel over 2 layers of insulation and vertical z-bar. In order for this to work properly, there needs to be an acceptable substrate to fasten into, otherwise the amount of z-bar needed to achieve the required fastening strength, will be astronomical. Please advise if this is the intent or if we should figure plywood or zip sheathing as a substrate. | 1. Provide 2â€ rigid insulation under the entire slab unless noted otherwise. See building for additional information. 2. Provide grid of both vertical and horizontal z-bars as shown in detail 7/A404. | Mike Coleman | 11 | 2024-08-05 10:47 | 2024-08-06 08:34
20240813 | 20240813009 | 9 | Room Finishes | 1. The room finish schedule for the building states that rooms 116, 116A, and 116B are to receive FAF type flooring. However, the finish plan shows 116A receiving a sealed concrete finish. Please confirm the floor finish in room 116A. | To clarify, provide sealed concrete floor in room 116A as indicated on the room finish schedule. | Mike Coleman | 12 | 2024-08-05 11:51 | 2024-08-06 08:33
20240813 | 20240813009 | 9 | room finshes | 2. The hatch for PCT-01 and PCT-02 are difficult to distinguish. It appears on the finish schedule that all rooms receiving tile will be PCT-01 and that there is no PCT-02. Sheet A804 does talk about upper restrooms receiving PCT-02. Please confirm which rooms, if any, will receive PCT-02. | Per the Finish Materials sheet A804, PCT-02 will be used on all upper level restrooms. PCT-01 will be used on the first floor of the building. | Mike Coleman | 13 | 2024-08-05 11:51 | 2024-08-06 08:32
20240813 | 20240813009 | 9 | Building elevations | Elevation 2/A203 and 3/A202 do not match the windows shown on the plan drawings. | Plan sheets A105 & A108 (pages 125 & 128) have been revised so that window tags match exterior elevation information and will be included in an upcoming addendum. | Mike Coleman | 14 | 2024-08-05 12:00 | 2024-08-06 09:48
20240813 | 20240813009 | 9 | Furniture Schedule | Drawing A901 and A902 References a furniture schedule. There is a column that states â€œProvided Byâ€ in that column there are several references to BCE. We cannot find what BCE is a reference to. Is BCE specification Section 12 51 70 Technical Furniture? | BCE is the Wisconsin Bureau of Correctional Enterprises, and that work is not included in the contract. | Mike Coleman | 15 | 2024-08-05 12:46 | 2024-08-06 08:32
20240813 | 20240813009 | 9 | Sanitary lateral | there is a 4&quot; Sanitary lateral called out for on the plan and there is a bid covering this 4&quot; Lateral, my question is as follows is there supposed to be an inside drop bid item for this lateral also the same as the 6&quot; sanitary lateral? Or is this 4&quot; sanitary lateral being installed with no drop? | Page 20 of the plans shows a construction detail for the inside drop and that 6â€ inside drop is required for a 4â€ lateral. Both laterals entering the 5â€™ manhole will require a 6â€ inside drop, an addenda will make this modification to the quantity to reflect this change. | Mike Coleman | 16 | 2024-08-05 15:41 | 2024-08-06 13:19
20240813 | 20240813009 | 9 | Backfill structuire Type B | Special provisions say that 95% of modified proctor dry density (ASTM 1577) is required. It further says that this shall be confirmed per each lift during construction to ensure compliance per CMM 860. Our question is who is paying for these confirmation tests? | Price for testing should be included in the bid price for Backfill structure Type B as it is a requirement for placement of that material. | Mike Coleman | 17 | 2024-08-05 15:49 | 2024-08-06 08:45
20240813 | 20240813009 | 9 | Foundation Wall Rebar | On sheet S003 in the Foundation Wall Schedule, Marks FW1 &amp; FW2, it leads you to believe that there is only one layer of reinforcing with 2 additional #5 top &amp; bottom. However, when you look at the sections, it shows two layers of reinforcing but refers you back to the schedule. Section 4/S801 would be the typical exterior wall. Can you please clarify what is correct? | Walls FW1 and FW2 specify only one layer or reinforcement which is to be placed centered in the foundation wall with (2) bars to be placed at the top and bottom of the wall instead of the single bar. Detail 4/S801 will be updated accordingly via addenda. | Mike Coleman | 18 | 2024-08-05 15:58 | 2024-08-06 10:55
20240813 | 20240813009 | 9 | slab reinforcement | No reinforcing is listed for slab type S4. Please provide. | Slab S4 to match slab S5 reinforcement. #5 @ 12â€ OC EW @ BOTTOM, #4 @ 18â€ OC @ TOP | Mike Coleman | 19 | 2024-08-07 07:28 | 2024-08-09 06:12
20240813 | 20240813009 | 9 | Section 07 46 33 PVC Siding | where spec section 07 46 33 PVC Siding applies. It does not appear to be shown on the drawings anywhere | PVC Siding is to be used as the dumpster enclosure gate cladding, see sheet A-903. | Mike Coleman | 20 | 2024-08-07 10:02 | 2024-08-09 06:18
20240813 | 20240813009 | 9 | BCE provided furniture | does the furniture items noted as by owner or BCE need to be unloaded and installed by the contractor? | BCE will unload and install the furniture. The construction contracted electrician will be responsible for providing and installing the electrical and low voltage needed for the few pieces of systems furniture in the office area. | Mike Coleman | 21 | 2024-08-07 10:04 | 2024-08-12 08:40
20240813 | 20240813009 | 9 | sales tax | Will contractors (and subcontractors) have to pay Wisconsin Sales tax on material used for this project or will the Wisconsin DOT provide a sales tax exempt certificate for this project that the contractors may use for material purchased that is used on this project. | Questions regarding sales tax on state projects should be directed to the Wisconsin Department of Revenue. See this link for FAQs: DOR Vendors Doing Business with Wisconsin | Mike Coleman | 22 | 2024-08-07 10:54 | 2024-08-12 08:02
20240813 | 20240813009 | 9 | Supplementary Conditions | In reviewing Division 00 - Contracting Requirements; Section 00 72 10 - General Conditions, is mentioning Document 00 73 10 Supplementary Conditions. Can you please provide this document for review? Also, mentioned is Standard Terms and Conditions. Is this document the Standard Specifications for Highway and Structure Construction, Edition 2024, Effective with November 2023 Letting? If not, can you please provide this document? Thank you. | Section 00 73 10 Supplementary Conditions is not included in this project. Standard Terms and Conditions referenced in Section 00 72 10 is â€œStandard Specifications for Highway and Structure Construction 2024 Editionâ€. | Mike Coleman | 23 | 2024-08-07 10:57 | 2024-08-12 08:46
20240813 | 20240813009 | 9 | Furniture Schedule | Several items on the furniture schedule noted to be by contractor do not have specs provided including items LC-1, St-1, TC-6, WT-2, AR-1, WC-1, and BSS-2 (quantity of p-lam shelves?). Please provide specs for these items. | â€¢ LC-1: Refer to interior elevation 6/A-507 â€¢ ST-1: Revolving storage tower - refer to 12 51 70 Technical Furniture â€¢ TC-6: Dispatch task chair â€“ revise to be provided by â€œBCEâ€ â€¢ WT-2: Stainless steel worktable â€“ revise 12 50 00 Furniture, 2.02 C, Stainless Steel Tables to: o WT-1: 60â€ x 30â€, Uline H-5000 o WT-2: 36â€ x 30â€, Uline H-8450 â€¢ AR-1: Refer to note #8 on sheet A-104, and precast elevation 3/A-206. Location of AR-1 to be as indicated on A-104. â€¢ WC-1: Revise â€œWC-1â€ designation in the Furniture Schedule on sheet A-901 to SC-1. â€¢ BSS-2: Refer to detail 15/A-581 for additional notes and information. | Mike Coleman | 24 | 2024-08-07 13:51 | 2024-08-09 06:44
20240813 | 20240813009 | 9 | Tower Pad Foundation | Plan Sheet number 91 or building sheet C-501 shows the foundation for the tower and says the soils may need to be excavated and replaced with better material- Note 1.What soil types are considered poor and will need to be removed? Will the excavation and backfill for this be extra work since the Construction Manager will be deciding what is acceptable? There are varied soils throughout this area and anticipated EBS is shown in the plan for the building site. How can the contractor determine depth and limits before the Bid if the area is to be reviewed by the Constr. Mgr. Is there a reason this is not designated for EBS based on the soil borings you have reviewed? | Anticipated EBS is shown on Tower Pad â€˜Tâ€™ cross sections and will be paid under the Common Excavation bid item but final limits will be determined by field staff during construction. The geotechnical report with additional details can be found at the following location: https://wisdot.box.com/s/fx8ye1hi5hbt5uigvb5k5was2el1n64s or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 25 | 2024-08-07 17:49 | 2024-08-12 07:41
20240813 | 20240813009 | 9 | Tile Base | I guess if there is still time can you find out if all tile base is to be the PCT-2? PCT-1 does not list base as a location for that like PCT-2 does on the material list. Also, is this base just a cut piece of field tile to 6â€ or is this to be a cove base? If it is a cut piece do I need to use a Schluter Dilex cove? | On Sheet A-804, omit â€œBase: Tile Wall Baseâ€ from PCT-02. To clarify, tile wainscoting will extend from floor to height indicated on interior elevations. Refer to detail 6/A-803 for more information and the transition between wall and floor. For tile wall base on walls without tile wainscot, provide factory cut 6â€x24â€ pieces with aluminum edge protection at top as indicated on1/A803. | Mike Coleman | 26 | 2024-08-08 11:34 | 2024-08-09 09:40
20240813 | 20240813009 | 9 | Interior Finishes | Sheet A804 Finishes is calling out different products than the spec book. Specifically Sherwin Williams PM 200 series in the spec book to Sherwin Williams Harmony on page A804 finishes. Sherwin Williams doesnâ€™t even make Harmony anymore. The new product that replaces Harmony is Air Purifying Super Paint | Revise Sherwin Williams product line on sheet A-804 to ProMar as indicated in the specifications. | Mike Coleman | 27 | 2024-08-08 11:36 | 2024-08-09 06:42
20240813 | 20240813009 | 9 | Painting Specification | Could I get clarification on the painting spec? Sheet A804 Finishes is calling out different products than the spec book. Specifically, Sherwin Williams PM 200 series in the spec book to Sherwin Williams Harmony on page A804 finishes. Harmony has been discontinued. The new product that replaces Harmony is Air Purifying Super Paint, significant price difference. | Revise Sherwin Williams product line on sheet A-804 to ProMar as indicated in the specifications. | Mike Coleman | 28 | 2024-08-08 12:30 | 2024-08-09 06:45
20240813 | 20240813009 | 9 | Powder Coated Finish | Vestis Manufacturing is listed as an approved manufacturer in the 10 73 16 â€“ Aluminum canopies spec, however, they use a powder coat finish instead of the specified fluorocarbon finish option. Is a powder coated finish acceptable? | Powder coat finish is an acceptable finish if it matches the indicated basis-of-design finish color indicated on the drawings, or as selected by E/A including custom colors. | Mike Coleman | 29 | 2024-08-08 12:30 | 2024-08-09 09:41
20240813 | 20240813009 | 9 | Cove Base | Can you let me know how high you would like the cove base to go in the tunnels? Also, can you let me know if you need the walls coated in the tunnel. If so, how high should I figure? | Tunnel base to be 8â€ high fluid applied flooring and walls to be epoxy paint for the full height of the wall as indicated on A-800. Refer to sheet S-308 for wall heights. | Mike Coleman | 30 | 2024-08-08 12:31 | 2024-08-09 09:42
20240813 | 20240813009 | 9 | Waterproofing Membrane | Is a waterproofing membrane required at the elevator pit or inspection pits? The tunnel access section 1/A131 is the only area that currently shows waterproofing. | Provide continuous waterproofing at all exterior sides of concrete elevator pit and inspection pits. Waterproofing to continue underneath bottom slabs of those areas as well. | Mike Coleman | 31 | 2024-08-08 12:31 | 2024-08-12 06:52
20240813 | 20240813009 | 9 | Sealing | Does the exterior block and/or precast require sealing? First paragraph for exterior finishes lists CMU, precast and metals. In the details there is only a product listed for metals. | There is no exterior block on this project, and the precast does not require sealing. | Mike Coleman | 32 | 2024-08-08 12:46 | 2024-08-12 06:33
20240813 | 20240813009 | 9 | exterior finishes | Does the exterior block and/or precast require sealing? First paragraph for exterior finishes lists CMU, precast and metals. In the details there is only a product listed for metals. | There is no exterior block on this project, and the precast does not require sealing. | Mike Coleman | 33 | 2024-08-08 13:05 | 2024-08-12 06:52
20240813 | 20240813009 | 9 | completion date | We are getting feedback the only viable precaster is saying that it will take 28 weeks to have the precast materials ready to install, plus another 3 weeks to install. That being said, this would push the completion of the building past the project completion date by almost 2 months. Will the state alter the completion date if this event occurs? | Additional time will be granted if it is deemed necessary and can be demonstrated that delays in material delivery, which are beyond the contractor's control, impact the overall project deadline. | Mike Coleman | 34 | 2024-08-12 08:47 | 2024-08-12 11:36
20240813 | 20240813009 | 9 | Plan Sheet Page 346 and Response to Question 25 | A note on this page states &quot;Estimated Building Foundation Excavation (Incidental to SWEF/Post Building, General Construction)&quot; and says this is &quot;For Information Only&quot;. This note also includes estimated quantities for EBS and Structure Backfill. Please confirm, consistent with the response to Question 25, that any EBS and associated backfill for the SWEF/Post Building would be paid for with the unit prices included in the contract (Common Excavation and Structure Backfill). There is nothing indicated in the Special Provisions that this work would be incidental to the bid item for SWEF/Post Building, General Construction and would never be considered incidental to construction with unknown or estimated quantities for the contractor to include under a Lump Sum bid item. | The quantity listed on Page 346 is the estimated amount of material to be excavated directly under the footprint of the building and should be included in the building bid price. Refer to construction detail on page 16 of the project plans. Quantity in excess of this quantity may be paid under the contract bid price for associated items. | Mike Coleman | 35 | 2024-08-12 09:21 | 2024-08-12 10:05
20240813 | 20240813009 | 9 | SP 1130-44-75 | Are the Preliminary Plans for the future project at this site available? |  |  | 36 | 2024-08-12 09:36
20240813 | 20240813010 | 10 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/4omxszps2iqzikos7iwbid9ppobl3dwh or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-26 08:14 | 2024-07-29 08:09
20240813 | 20240813011 | 11 | Culvert Floor Prep | Special Provision #21 - Culvert Preparation indicates that removal of any unsound concrete beyond the scarification limits is included in the item. On bridge deck overlays this work is separated out and paid as Deck Prep Type 1 and Type 2 so that both owner and contractor are protected against quantity changes. Since both culverts were full of water it was not possible to estimate a quantity pre bid. Items to address this work if it exists should be added to the contract. | The removal of unsound concrete beyond the scarification limits will be covered under the Culvert Preparation item. | Mike Coleman | 1 | 2024-08-08 12:09 | 2024-08-12 07:34
20240813 | 20240813011 | 11 | B-37-97 Cut-Off Walls | Will Rock Excavation be paid for separately if required to install cut-off walls to elevations shown on plan sheet #36. High bedrock is anticipated at north end of this culvert but could not be verified due to high water. | It is not anticipated that rock excavation will not be required. The intent is to form the cutoff wall to the top of the bedrock, as needed. See the note regarding the â€œedge of natural bedrockâ€ on Sheet 35 of the plans. | Mike Coleman | 2 | 2024-08-08 12:50 | 2024-08-12 07:34
20240813 | 20240813012 | 12 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/p2i9myvne0808q982prh798mx8803q6x or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-11 09:41 | 2024-07-12 11:06
20240813 | 20240813012 | 12 | Temporary RRFB Systems | Are the RRFB systems a purchase item that are temporary as you will use them elsewhere at a later date? | The Temporary Rectangular Rapid Flashing Beacon with Push Button item is temporary because it will be used for temporary pedestrian accommodations and will not be used elsewhere at a later date. The TRRFB systems will be owned by the contractor at the end of the project. | Mike Coleman | 2 | 2024-07-16 18:01 | 2024-07-24 16:21
20240813 | 20240813012 | 12 | Concrete Joint and Crack Cleaning and Repair | Can the department change the unit of measure and quantify item #214 â€œSpecial 01. Concrete Joint and Crack Cleaning and Repairâ€ to linear feet? | The existing concrete is covered with asphalt. The cracks to be repaired will be determined after milling. The contractor should bid this based on STA per the construction detail and the special provisions within the station ranges provided in the plan. | Mike Coleman | 3 | 2024-07-29 15:15 | 2024-07-31 06:34
20240813 | 20240813012 | 12 | USH 51 and CTH J/Townline Road Intersection | Can the department please provide a traffic control plan at the USH 51 and Townline Rd/CTH J intersection during the milling and paving operations? | The traffic control at the USH 51 and Townline Rd/CTH J intersection should be implemented using the traffic control typical sections as shown in the plan for the various substages and following the project special provisions. Flagging will be required during paving operations within intersection. The special provisions address each substage except that it should be noted Stage 2B also covers traffic conditions in Stage 2C. A traffic control plan detail for the USH 51 and Townline Rd/CTH J intersection will not be provided. | Mike Coleman | 4 | 2024-08-05 11:53 | 2024-08-06 09:47
20240813 | 20240813014 | 14 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/9icczpjjph2zysiujxhmkmvvoy4fkylj or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-11 09:40 | 2024-07-24 15:17
20240813 | 20240813014 | 14 | Work Near Railroad Crossing | Based on the amount of work that needs to occur after FV&amp;LS completed their work at the crossing at station 1399, would the department add 2 days to the allowable time to complete work under project 1590-14-72, increasing it from 2 days after FV&amp;LS completes their work to 4 days? It is anticipated that the grading work takes 1 day, fine grading takes 1 day, and paving takes 2 days to complete. | The Department would like to maintain an expediated schedule to reopen USH 8 to traffic within 2 days of Fox Valley & Lake Superior completing their railroad crossing work. The closed roadway provides the contractor an opportunity for extended work hours. | Mike Coleman | 2 | 2024-07-30 08:02 | 2024-07-31 06:32
20240813 | 20240813014 | 14 | Work by Railroad | Based on the amount of work FV&amp;LS has to complete, how many working days will their work take to be completed? Will contract time be stopped if the contractor cannot continue work due to the railroad work and the concurring detour? | The Fox Valley & Lake Superior (FV&LS) railroad work is expected to take 3 days to complete all of their work. If FV&LS make changes to their work that isnâ€™t part of the WisDOT contract, that would be a change of conditions and the Department would work with the contractor to adjust time accordingly. | Mike Coleman | 3 | 2024-07-30 08:03 | 2024-07-31 08:45
20240813 | 20240813014 | 14 | Temporary Pavement Marking | Does the Department intend to place temporary marking on the milled, lower layer, &amp; surface? Currently there is not enough quantity. | The project is only placing one layer of asphalt on the driving lanes. There is no lower asphalt layer. Temporary pavement marking is intended twice â€“ on the milled surface and final surface. | Mike Coleman | 4 | 2024-08-01 10:35 | 2024-08-05 08:31
20240813 | 20240813014 | 14 | 3/4" BAD Shoulder | Based on the proposed typical section on plan sheet 6 and the miscellaneous quantities, is the intention that the existing ï¿½â€BAD shoulder in the asphalt shoulder widening portion of the project be completely removed and replaced with new ï¿½â€ BAD? If the ï¿½â€ BAD shoulder is to be completely removed and replaced in the widening section, how will the removal of the existing be paid for? Is any ï¿½â€ BAD shoulder work expected to take place in the non-shoulder widening section of the project from station 1389+27 â€“ 996+47? Per the typical section and miscellaneous quantities, no work will be completed in this section. | Shoulder work for the shoulder widening area is paid for under the â€œPrepare Foundation for Asphaltic Shoulders" as indicated on the typical section. Removal all of the existing BAD is unnecessary; grading and supplementing with additional ï¿½-inch material is appropriate. For non-widening sections, the bid item "Shaping Shoulders," will we added via addendum. | Mike Coleman | 5 | 2024-08-02 11:38 | 2024-08-07 05:38
20240813 | 20240813014 | 14 | Dust Control Surface Treatment | Where does the department anticipate Item #74 Dust Control Surface Treatment to be used on the project as the miscellaneous quantities show the entire job? | The Dust Control Surface Treatment item is intended to be used in the base aggregate dense areas. | Mike Coleman | 6 | 2024-08-05 13:09 | 2024-08-07 05:38
20240813 | 20240813014 | 14 | Curb and Gutter Replacements | With the curb and gutter replacements at the USH 8 and CTH U intersection, will the department add a sawing asphalt item and an asphaltic surface patching item to the job? | The â€œSawing Asphaltâ€ and â€œBase Patching Asphalticâ€ bid items will be added through addendum. | Mike Coleman | 7 | 2024-08-05 13:10 | 2024-08-07 05:39
20240813 | 20240813014 | 14 | Distressed Milling | Does the department anticipate any areas of distressed milling currently? With a minimum dimension of 4â€™x4â€™ and a total quantity of 5,000 syds, there could be over 2,800 separate locations of distressed milling. | No specific locations have been identified. Distressed milling locations will be identified by the field engineer during construction. | Mike Coleman | 8 | 2024-08-05 13:11 | 2024-08-07 05:40
20240813 | 20240813014 | 14 | Sawcutting | The construction detail on sheet 12 for the railroad work has &quot;Sawing Concrete&quot; at the joints. Will an item for sawcutting be added to the project? | The Sawing Concrete is in the top detail on sheet 12 which shows the work that will be completed by the railroad. The roadway contractor will not be performing the sawing concrete task. | Mike Coleman | 9 | 2024-08-07 10:57 | 2024-08-08 09:42
20240813 | 20240813015 | 15 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/6375gum9p3ahpyr0rfgjl285y7l2x2g2 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-07-11 09:42 | 2024-07-12 11:10
20240813 | 20240813015 | 15 | Pavement Marking | The current bid item Marking Line Epoxy 6&quot; is being used for surface applied edge lines. Does the Department want to follow the new spec that requires both center lines and edge lines be installed with Grooved Wet Reflective Epoxy? | As part of an upcoming addendum, the permanent edgeline marking will be corrected to show grooved wet reflective epoxy. | Mike Coleman | 2 | 2024-07-25 10:42 | 2024-07-29 09:43
20240813 | 20240813015 | 15 | 48 Hour Milled Surface | Per the specials, an even cross section of milling is needed at the end of the day. Typical existing asphalt is 5â€ â€“ 7.5â€ of HMA. Contractors train consists of milling, widening shoulder, paving shoulder and PWL mainline paving. Contractor is requesting 96 hours on the milled surface instead of 48 hours. | Due to the poor condition of the existing pavement and the potential for only 2.5â€ of existing pavement to remain after milling, the maximum duration that the milled surface can be exposed to traffic must remain at 48 hours as currently noted in the Prosecution and Progress article. | Mike Coleman | 3 | 2024-08-02 10:28 | 2024-08-05 10:18
20240813 | 20240813015 | 15 | Base Aggregate Shoulders Schedule | The contractor has looked at the DOTâ€™s design schedule and their own schedule. Per specials on page 3, will the department suspend time until after September 18th, in order to complete these shoulders at culvert 69 and 72. | No. There is adequate time in the schedule to complete the necessary work and still meet the requirements of the Wood Turtle subsection of the Prosecution and Progress article without suspending time until after September 18th. To help facilitate the contractorâ€™s schedule, the Department can allow the portion of silt fence (for turtle protection) at culverts #69 and #72 to be installed prior to May 1st under a conditional start notice without starting time charges (upon request). In addition, the Department has posted an updated design schedule for the project to the following location: https://wisdot.box.com/s/6375gum9p3ahpyr0rfgjl285y7l2x2g2, or it can be accessed on the HCCI August bid letting page under Supplemental Information. The updated schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions, and any addendum that is developed. | Mike Coleman | 4 | 2024-08-02 10:29 | 2024-08-08 06:23
20240813 | 20240813015 | 15 | Culvert 72 construction schedule | Per the specials on page 2 and 3, it appears that culvert 72 located at STA 798+73 is not constructable with instream disturbance dates shown on page 2 and page 3. Would the department allow the contractor to protect these areas with E-mat prior to the beginning of turtle nesting season, in turn allow the contractor to work in these areas during nesting season? | The intent of the Wood Turtle special provision language in the Prosecution and Progress article is that work may occur in the nesting habitat during the nesting season provided that the silt fence (with Temporary Small Animal Turn-Arounds, per plan details) at those locations is installed prior to May 1st. Therefore, the revised design schedule that was posted in response to prebid inquiry #4 was incorrect and has been removed. The initial design schedule that was posted with prebid inquiry #1 was adequate and has been reposted to the following location: https://wisdot.box.com/s/6375gum9p3ahpyr0rfgjl285y7l2x2g2, or it can be accessed on the HCCI August bid letting page under Supplemental Information. Again, please note that the design schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions, and any addendum that is developed. Also note that e-mat is not an acceptable turtle exclusion device. | Mike Coleman | 5 | 2024-08-09 10:04 | 2024-08-12 11:14
20240813 | 20240813016 | 16 | Geotechnical Report | Can the geotechnical report be provided? | The Geotech report can be found at the following location: https://wisdot.box.com/s/h8m9u54hxtiz7mfk5u6avd6mjocdf9ub or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-07-11 08:33 | 2024-07-24 15:22
20240813 | 20240813016 | 16 | Left-in-Place Steel Casing Size | What size left-in-place steel casing will be allowed for drilled shafts? The plans call for 4â€™-0â€ O.D. steel casing and drilled shaft diameter, and SPV Article 25, section B.3.1 states â€œThe inside diameter of casing shall not be less than the specified size of the drilled shaft. All casing diameters shown on the plans refer to O.D. dimensions.â€ This is contradictory. Will the department allow for casing up to 4â€™-6â€ diameter from top of competent rock to top of drilled shaft elevation to achieve the 4â€™-0â€ rock socket diameter? | SPV Article 25, section B.3.1 will be revised to correct inconsistencies. Drilled shaft diameters are being evaluated and an addendum will be issued. | Mike Coleman | 2 | 2024-07-11 08:34 | 2024-07-24 15:32
20240813 | 20240813016 | 16 | Drilled Shaft Bid Item | The subsurface conditions for the drilled shafts vary between soil overburden, weathered rock with varying blow counts, and very hard competent rock. The drilled shaft item is not divided into drilling in either soil or rock. Can the bid item be subdivided to allow for different unit prices, especially if the rock socket lengths may increase or decrease based on field conditions and test cores? | WisDOT does not intend to create separate pay items for the drilled shaft based on differing subsurface conditions. The boring logs are provided to indicate the expected conditions. | Mike Coleman | 3 | 2024-07-11 08:35 | 2024-07-24 15:30
20240813 | 20240813016 | 16 | Test Core Bid Item | Please provide a bid item per LF for the test cores required in SPV Article 25, section C.3.6.7. The final depth of these cores will vary â€œas directed by the geotechnical engineerâ€ and a specified coring depth/amount therefore cannot be considered as incidental to the shafts. | The intent is to test core 10ft below the drilled shaft tip elevation to confirm rock quality. WisDOT does not intend to include a separate bid item for test coring since the length of the test core is directly related to the length of the drilled shaft. | Mike Coleman | 4 | 2024-07-11 08:36 | 2024-07-24 15:28
20240813 | 20240813016 | 16 | Shaft Spacer Quantity | SPV Article 25, C.3.7 please remove the requirement for 7 shaft spacers per level. 30 inches between spacers on a 4â€™ diameter shaft requires 5 spacers per level at the most. | SPV Article 25, C.3.7 will be revised to show the correct number of spacers. An addendum will be issued. | Mike Coleman | 5 | 2024-07-11 08:37 | 2024-07-24 15:26
20240813 | 20240813016 | 16 | Gradient TIP Wire | SPV Article 22, section C.2, please remove the requirement for an additional TIP wire attached to a longitudinal rebar parallel to and offset from the perimeter reinforcement at a fixed distance. This additional wire, also known as a gradient wire, is not necessary for Thermal Integrity Profiler testing and is a holdover from early days of TIP development as a means of relating a temperature change over a prescribed distance to an effective shaft radius. It has been determined that radius evaluation based on total placed concrete volume is the superior method, and gradient wire evaluation has been essentially disregarded for radius calculations for several years. This gradient wire has been eliminated on previous WisDOT projects with TIP-tested drilled shafts. | The fifth paragraph of Article 22, section C.2 will be deleted. An addendum will be issued. | Mike Coleman | 6 | 2024-07-11 08:37 | 2024-07-24 15:27
20240813 | 20240813016 | 16 | Recreational lane & Temporary construction access â€“ Plans | The Miscellaneous Quantity sheet 20 â€“ Clearing &amp; Grubbing, and sheet 23 - Erosion Control, list quantities for recreational lane with stationing along the temporary construction alignment (Sta 100+15 to 201+40 etc). The typical sections and cross sections show the recreational lane as a widening of the west bound lane of CTH G IE&#58; north side of the mainline. Please clarify this stationing reference | The recreational trail quantities will be updated to reference the CTH G alignment. An addendum will be issued. | Mike Coleman | 7 | 2024-07-11 11:52 | 2024-07-24 15:31
20240813 | 20240813016 | 16 | Treated Timber Rub Rail - Dimensions | Plans show 2 x 8 timber rub rail. special provisions state&#58; -Furnish and attach a nominal 2-inch x 10-inch treated timber to the back of the posts used for MGS guardrail as shown on the plans and as directed by the engineer. Please confirm | The horizontal boards for the rub rail attached to the back of MGS is 2â€x10â€ as stated in note #2 of the â€œTreated Timber Rub Rail at Beamguardâ€ detail in the construction details, which matches the special provision size. This is not to be confused with the 2â€x8â€ Treated Lumber attached to the Type M railing and concrete parapet on the structure plans. Cost of the 2â€x8â€ lumber on the structure is paid incidental to â€œConcrete Masonry Bridgesâ€ as noted (*) at the top of sheet 32 of 33 of the structure plans â€œSingle Slope Parapet 42SS â€˜Modifiedâ€™â€ and incidental to â€œRailing Type Mâ€ as noted in note #16 on page 31 of 33 â€œTubular Steel Railing Type â€œMâ€. | Mike Coleman | 8 | 2024-07-17 13:43 | 2024-07-31 06:34
20240813 | 20240813016 | 16 | Casing Installation | Is an oscillator required for the installation of the permanent casing? | Article 25, C3.5.1 provides the following guidance for casing installation "Advance permanent casing through the unstable condition(s) and to the projected depth by twisting, drilling, or vibrating. Obtain prior approval from the engineer for vibrating the casing. | Mike Coleman | 9 | 2024-07-17 15:56 | 2024-07-31 06:36
20240813 | 20240813016 | 16 | Temporary Shoring for Construction Access | Temporary shoring is shown on the plan detail, page 9 for temporary construction access at piers. There is no associated pay item for temporary shoring nor does the special provisions indicate it is incidental to the Construction Access Item. Please add a line item for temporary shoring as it will be needed for drilled shaft installation | The temporary access shown in the plan was designed and permitted as a possible option. However, the contractor can modify the configuration or type of access within the limits of the permit; i.e. means and methods . All items and work necessary for the contractor's proposed temporary access are to be included in the bid item SPV.0060.05 Temporary Construction Access. Those included items are noted in the â€œTCA Quantities for Information Onlyâ€ table at the end of the Miscellaneous Quantities sheets. The special provisions also note in the payment section under the Temporary Construction Access item â€œPayment, in which one unit includes allâ€¦. installation and removal of temporary shoring if used. | Mike Coleman | 10 | 2024-07-18 17:14 | 2024-07-31 06:41
20240813 | 20240813016 | 16 | Drilled Shaft -Competent Rock | What is the DOT criteria for determining competent rock? Plan notes for the pier indicate &quot;Geotechnical engineer &amp; contractors to verify competent rock elevation&quot;. We ask that &quot;contractors&quot; be removed from this statement, the WDOT geotechnical engineer should be determining the elevation of the competent rock (start of the rock socket) based on rock auger advancement rates or similar criteria; this criteria is not defined in the special provisions. | Competent bedrock is defined as bedrock having an overall core recovery of at least 90% and a rock quality designation (RQD) of at least 50%. This will be added to the special provisions through an addendum and will be issued by 8:00am on Thursday, August 1st. The term "contractors" will be removed from Sheets 93 and 95. | Mike Coleman | 11 | 2024-07-18 17:21 | 2024-07-31 06:45
20240813 | 20240813016 | 16 | Drilled Shaft Permanent Casing, Size and min thickness | Current plans show the permanent casing and rock socket to be the same OD. We echo the same concern a previous contractor stated regarding that the permanent casing will need to be larger than the rock core diameter. Current plan shows a 48&quot; OD casing and 48&quot; diameter drilled shaft; this is not constructable as the casing will be of a certain thickness and the ineer diameter will be less than 48&quot; diameter rock socket. Common practice for adjacent state DOT&#39;s call for the shaft size to be 6&quot; diameter larger than the diameter of the rock socket. No min. wall thickness is specified, please identify a min casing thickness for the permanent casing. | Drilled shaft diameters are being evaluated and an addendum will be issued by 8:00am on Thursday, August 1st. The contractor is responsible for selecting a casing with sufficient strength to resist the pressures imposed by the soil or rock and internal and external fluids. The purpose of the permanent steel casing is to prevent cave-in of the overburden soils and weathered bedrock and does not serve as a means of resisting drilled shaft loads in the final constructed condition." | Mike Coleman | 12 | 2024-07-18 17:35 | 2024-07-31 06:50
20240813 | 20240813016 | 16 | CSL Testing PE Requirement | Special Provision Article 28, Section A.2. Please confirm that a Wisconsin PE is not required to perform the field work for the CSL tests on drilled shafts. In previous projects for WisDOT and in projects for other states, a registered PE is only required to direct the work, interpret the results, and sign the report. The collection of field data is more commonly done by field technicians, who are not usually registered PEs but are qualified to do the work and have multiple years of experience. | A registered Wisconsin PE should oversee, direct, interpret/review the CSL testing results and sign the report, but they do not need to complete the actual field testing. The person completing the field testing should have the requisite minimum 5 project and 3 years of CSL test experience. | Mike Coleman | 13 | 2024-08-06 10:55 | 2024-08-12 07:29
20240813 | 20240813016 | 16 | Rock Core Sample - UCS | The Geotechnical Report provides NQ core information of the rock layer in boring 2A and 3A, but does not contain information regarding the unconfined compression strength. Did AET conduct breaks on the rock cores? If not, what strength of competent bedrock is the Drilling Contractor to expect during socket excavation? | We estimate an unconfined compressive strength of the rock (that we NQ cored) ranging from 20,000 to 35,000 psi. Note that this does not apply to the "weathered bedrock" that was drilled through using soil drilling methods. | Mike Coleman | 14 | 2024-08-07 10:36 | 2024-08-12 07:31
20240813 | 20240813016 | 16 | Drilled Shaft Concrete Air Entrainment | Will the concrete for drilled shafts require air entrainment? If so, please provide the acceptable air content range for concrete placed in drilled shafts. Concrete will likely be placed by pump, which causes air content loss. | Yes, air entrainment is required for the drilled shaft concrete. Although air entrainment is not listed in the Drilled Shaft SPV, which is a supplement to Std Specs 501, 502, 701, 710 & 715, air entrainment is required for all concrete per Std. Spec. 501.3.2.1, with air entrainment requirements listed under 501.3.2.4.2 (6% +/- 1.5%). | Mike Coleman | 15 | 2024-08-07 11:55 | 2024-08-12 07:32
20240813 | 20240813016 | 16 | Obstruction Bid Item | Can the department add a bid item for obstruction drilling, similar to other WisDOT projects with drilled shafts? This provides a definition of what constitutes an obstruction and mechanism for measurement and payment. | WisDOT does not intend to include the obstruction drilling bid item. The drilled shaft SPV, Article C.3.6.1 states that excavations required for the drilled shafts shall be performed through whatever materials are encountered. Naturally occurring materials (rock, cobbles, boulders) are not considered obstructions and are not applicable to the obstruction bid item. | Mike Coleman | 16 | 2024-08-07 21:00 | 2024-08-12 07:33