## qandasearchletting_results
Date | 2024-10-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20241008 | 20241008001 | 1 | Payment of SHES Base | ASP - 6 calls for payment for SHES Base by the cubic yard. Will WisDOT consider changing payment from the square yard, as currently shown in the plan and spec, to the cubic yard. | After further review, an addendum will be submitted to change the bid item to a CY item. | Mike Coleman | 1 | 2024-09-12 10:43 | 2024-09-17 09:19
20241008 | 20241008001 | 1 | Distressed Milling/Associated Asphaltic Surface | Can the Department remove this item from the contract? This item would force contractors to pave binder &quot;hot on hot&quot; and is typically not used on interstate night time projects due to the time constraints each night. | Yes, an Addendum will be prepared to remove SPV.0180.02 Removing Distressed Pavement Milling from the Project. | Mike Coleman | 2 | 2024-09-23 09:40 | 2024-09-24 12:37
20241008 | 20241008001 | 1 | drilled dowels and tie bars | The existing pavement is doweled per note on sheet 19 note 3.Why are there no pay items for drilled loose dowels and tie bars ? | As shown on the existing and finished typical sections, the original concrete pavement along the IH 94 mainline and STH 73 ramps was previously rubblized and overlaid with HMA pavement. There is not an existing concrete pavement slab to dowel/tie the base patches into. | Mike Coleman | 3 | 2024-09-24 09:39 | 2024-09-24 12:35
20241008 | 20241008001 | 1 | Temporary Pavement Marking | The Temporary Marking looks to be over stated. Please advise | Temporary pavement marking quantities will be revised via addendum. | Mike Coleman | 4 | 2024-09-24 11:37 | 2024-09-25 06:17
20241008 | 20241008001 | 1 | More detailed Information on SHES Base Patching. | Can a more detailed breakdown of the SHES Base Patches be provided? It appears the information in the MQ sheets is a summary of more detailed SHES Base Patch measurements. Can the measurements with greater detail be provided? | No, sawing for base patches will be included in Bid Item SPV.0180.01 Base Patching Concrete SHES. An estimated number of SHES Base Patches will be provided in the addendum for bidding purposes only. | Mike Coleman | 5 | 2024-09-24 13:56 | 2024-09-25 12:32
20241008 | 20241008001 | 1 | Sawing for SHES Concrete Base Patches | Can sawing for the Base Patches be added consistent with WisDOT Standard Spec 690? | No, sawing for base patches will be included in Bid Item SPV.0180.01 Base Patching Concrete SHES. An estimated number of SHES Base Patches will be provided in the addendum for bidding purposes only. | Mike Coleman | 6 | 2024-09-25 06:17 | 2024-09-25 12:32
20241008 | 20241008001 | 1 | Rubblization of the Existing Concrete Pavement. | Can the degree of rubblization of the existing concrete pavement be provided? Typically, longitudinal cracks and rutting are in the wheel paths when the existing pavement is rubblized to spec. This is not apparent on this job. We also understand the pavement was more or less was cracked and seated. Can we be provided the degree of rubblization that occurred? It is understood the rubblization spec can be modified in the field to allow for a condition more like cracking and seating. | The level of rubblization that occurred previously is unknown and likely variable. Therefore, a specific degree of the fractured material cannot be provided. The Vermeer cut in the in the construction detail is included to aid in removals if the concrete is not fully rubblized. Please bid accordingly. | Mike Coleman | 7 | 2024-09-27 06:09 | 2024-10-02 08:34
20241008 | 20241008001 | 1 | Base Aggregate for Shoulders. | The special provisions call for crushed stone be used for the shoulder base aggregate crushed. Can the allowable crushed material be expanded to include crushed concrete and/or Crushed concrete with up to 50% asphalt in order to use locally available materials? CBR values of crushed concrete and crushed concrete with up to 50 percent asphalt have been proven to be up to 50% greater than virgin crushed stone. | No. Please bid to the special provisions as advertised for Item 305.0110, Base Aggregate Dense 3/4-Inch. | Mike Coleman | 8 | 2024-09-29 10:34 | 2024-10-02 11:39
20241008 | 20241008001 | 1 | Will the Department require sawing of the centerline or outside shoulder? | If the existing concrete is cracked and seated rather than fully rubblized, will the Department require the centerline to be sawed or not? If the Department does not call for sawing the centerline, will the Department call for sawing the centerline to prevent undermining or other undesirable conditions? Will the outside shoulders be required to be sawed as well. Often times the existing concrete pavement has a battered edge or waste concrete that extends beyond the existing pavement edge and needs to be sawed to avoid damaging the shoulders during removal. | Longitudinal full-depth saw cuts may be allowed by the Engineer only where necessary to fulfill the Construction requirement for Item SPV.0180.01, Base Patching Concrete SHES to â€œRemove the asphalt and concrete pavement without injury to the remaining pavement, without undermining the remaining pavement, and with minimal disturbance to the aggregate baseâ€. As noted in the special provisions, payment of SPV.0180.01 includes â€œsawing asphalt; for sawing concrete; for removing old pavement; for preparing the foundation; for providing, curing, and protecting concrete; for making and testing concrete cylinders and providing test data to the contractorâ€. | Mike Coleman | 9 | 2024-09-29 10:57 | 2024-10-03 05:16
20241008 | 20241008001 | 1 | Temp Regulatory Speed Limit Reduction | Will the Dept utilize a Digital Speed Reduction System for this project? | This item will not be added to the project at this time. Please bid the speed reduction items as shown on the advertised plans. | Mike Coleman | 10 | 2024-09-30 08:06 | 2024-10-02 08:34
20241008 | 20241008001 | 1 | HMA Overlay Polymer-Modified | Per the plans there is 20 tons of HMA Overlay Polymer-Modified required for the project. Due to the staging of this 20 tons, the cost will be very high. Is a Polymer modified mix absolutely necessary for this bridge, or are there cheaper alternatives the Department could propose (ie &quot;regular&quot; HMA overlay, patching etc)? | A polymer modified asphaltic overlay is required for bridge B-13-154. | Mike Coleman | 11 | 2024-10-01 13:58 | 2024-10-03 05:17
20241008 | 20241008001 | 1 | HMA Mixture Table | The HMA Mixture use table shows that mainline SMA is PWL mix testing and PWL Density testing. This is the first time we have seen this for an SMA item, typically it is under the QMP 460 SMA item which is QMP mix testing and QMP Density Testing. Is the HMA Mixture use table correct? Also, the HMA Mixture use table shows mainline ramps are PWL Density testing. Usually Ramps, Ramp Shoulders, and mainline Shoulders and Acceptance testing. Is the HMA Mixture use table correct? | Addendum #2 will be prepared to revise the PWL Mixture Use Table and Miscellaneous Quantities. | Mike Coleman | 12 | 2024-10-02 11:21 | 2024-10-03 05:18
20241008 | 20241008002 | 2 | Railroad Flagging | Can the Department add the item &quot;Railroad Flagging Reimbursement&quot; to the contract due to all the flagging needed on the 2 bridges over the UPRR and the directional boring underneath? | Due to the anticipated short duration needed for railroad flagging, the item of Railroad Flagging Reimbursement will not be used for this project. | Mike Coleman | 1 | 2024-09-23 09:57 | 2024-09-24 08:25
20241008 | 20241008002 | 2 | Temp Regulatory Speed Limit Reduction | Will the Dept utilize a Digital Speed Reduction System for this project? | No, digital speed reductions systems will not be used for this project. Speed reductions will be â€œhard signedâ€ per plan traffic control details. | Mike Coleman | 2 | 2024-09-30 10:11 | 2024-10-01 10:51
20241008 | 20241008002 | 2 | Concrete Pavement Raising and Void Filling | For line items 0380 SPV.0035-Special Cement Slurry Mixture and line item 0394 SPV.0060-Special 07-Concrete Pavement Raising and Filling Void is it acceptable to use Foam-Jacking, Item SPV.0085.0001 as has been used on other WI-DOT projects (See State Project ID 1100-17-76)? | WisDOT prefers to keep in the items as shown, the foam jacking will not be used on this project. | Mike Coleman | 3 | 2024-10-02 14:50 | 2024-10-04 16:47
20241008 | 20241008004 | 4 | Striping | The roadways show to not place HFST on existing striping. however the bridge shows to cover the entire deck, will you add striping bid items for that area? | No. The High Friction Surface Treatment will not be placed over the existing pavement markings on the bridge deck. Striping will not be added, the county will perform this work immediately after the project is completed. | Mike Coleman | 1 | 2024-09-30 11:32 | 2024-10-01 11:16
20241008 | 20241008004 | 4 | Striping on Bridge | As a follow up to the previous question, by placing 2 layers of poymer overlay on the bridge the areas in the center and along edges will create a &quot;drop off&quot; for tires creating sway which could be considered dangerous for a vehicle if they accidentally stray from the 2 layers of polymer overlay. Second this also creates a water trap area in the center lines area. Please reconsider not allowing overlay on the entire deck and haveing striping bid item for this area. | The polymer overlay should be applied per the plans on the bridge deck. No changes are necessary. | Mike Coleman | 2 | 2024-10-04 10:51 | 2024-10-07 07:43
20241008 | 20241008004 | 4 | DBE Participation | Given the limited items of work available on the project can the DBE requirement please be waived on this project. | DBE goals will not be removed. DBE goals are required for projects with federal funding. See Additional Special Provision 3 (ASP-3) in the proposal. | Mike Coleman | 3 | 2024-10-04 14:40 | 2024-10-07 09:16
20241008 | 20241008005 | 5 | Milling/HMA paving restrictions | In the project special provisions, Article 3, Prosecution and Progress, under the milling operations heading, states â€œRestrict nightly construction milling limits so that no edge drop exists at the end of each workday. Place HMA Pavement within 24 hours that milling occurs.â€ Article 4 then states that â€œâ€¦the section of roadway milled shall be repaved in its entirety to avoid any edge drops prior to the conclusion of each workday.â€ Can you please confirm what the time restriction is between milling and paving? Can the window of time be increased to 96 hours between milling and paving? | The design team met and went over this issue. They have decided that allowing for 96 hours between milling and paving is likely appropriate given the site, and they will also include updates to the specials and the Distressed Pavement Milling item. An addenda is being prepared for this change. | Mike Coleman | 1 | 2024-09-16 08:17 | 2024-09-18 06:38
20241008 | 20241008006 | 6 | Schedule | Can designers schedule be shared. | The design schedule can be found at the following location: https://wisdot.box.com/s/m55v4k2d35kxcjxjhiaxxou3q7bpadcs or can be accessed on the HCCI October bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2024-09-10 14:45 | 2024-09-11 07:59
20241008 | 20241008006 | 6 | Pier Widening Access | SPV Article 155 calls for contractor to submit plans to UPRR for review/approval of access. What requirements or guidance are available to meet UPRR standards as there has not been clear direction on things like types of materials allowed, testing or design requirements, etc in the past. Can the department indicate what standards the DOT and UPRR have coordinated on for this in design? | - SPV Article 10 provides guidance on UPRR requirements and AREMA requirements. - SPV Article 21 provides information on what is included in an accepted railroad work plan. This information is available as a response to Question #3 in Bid Express. - SPV Article 27 provides requirements for imported soil to UPRR right-of-way. - The structure plans for B-40-358 and B-40-359 include UPRR notes. - The ID 1100-20-70 plan set includes a construction detail for informational purposes only that shows a possible access route to the bridge substructure areas. - Access to the south side piers is permitted from 112th St. No crossing of the tracks is permitted. - The department is obtaining temporary limited easements to facilitate access on the north side of the railroad tracks and to facilitate work on the center pier line south of the railroad tracks. This is shown in the ID 1100-20-70 plan set. - In general, work within the UPRR right-of-way must conform to the UPRR requirements stated above and work within the state right-of-way must conform to Wisconsin DOT standard specifications or any project related SPVs. o Structural design of the highway bridge over UPRR tracks was completed to WisDOT design standards and specifications and therefore UPRR avoided commenting on those items during the design stage. The Department does not anticipate UPRR comments on the bridge design and materials during the construction stage. o Temporary works that support rail track, or failure of temporary works that could foul rail track, will need UPRR approval of the structural designs before beginning work. - UPRR has approved of the design plans shown in the project plans. The contractor is responsible for developing an acceptable construction work plan. No further coordination beyond what is mentioned in the plans and proposal has taken place pertaining to construction acceptance. | Mike Coleman | 2 | 2024-09-10 15:59 | 2024-09-12 08:57
20241008 | 20241008006 | 6 | UPRR Work Plans | Can you post the UPRR Work Plans as noted in the special provisions? | The UPRR work plans can be found at the following location: https://wisdot.box.com/s/m55v4k2d35kxcjxjhiaxxou3q7bpadcs or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-09-11 07:48 | 2024-09-11 08:01
20241008 | 20241008006 | 6 | Noise wall signs | please provide sign mounting detail for hydrant access holes as well as sign details. | - The sign mounting detail is included in the permanent signing plan detail sheets on page 1065 of the as-let plan. - The sign detail for the identifier sign is included on page 1065 in the upper right-hand section. | Mike Coleman | 4 | 2024-09-11 14:51 | 2024-09-12 12:53
20241008 | 20241008006 | 6 | Permit information for Milwaukee County Parks | Per SPV Article 22, can you post the DRAFT permit information for Milwaukee County Parks. | The Milwaukee County Parks permit information can be found at the following location: https://wisdot.box.com/s/m55v4k2d35kxcjxjhiaxxou3q7bpadcs or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 5 | 2024-09-12 08:54 | 2024-09-12 08:55
20241008 | 20241008006 | 6 | SHES Base Patching Schedule | Can SHES Base Patching be allowed in fall of 2024? 420 cyds per night is shown in the Design Schedule. This production rate with the limited hours allowed seems unrealistic. As a result, can this work be allowed to start earlier and start in the fall of 2023 like occurred on the 894 project? | Base patching will not be allowed in the fall of 2024. Please note the timechart assumed production rate uses square yards per night, not cubic yards. | Mike Coleman | 6 | 2024-09-17 16:02 | 2024-09-19 14:26
20241008 | 20241008006 | 6 | Geotech Reports | Can you post any geotechnical reports for this project? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/m55v4k2d35kxcjxjhiaxxou3q7bpadcs or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 7 | 2024-09-18 06:05 | 2024-09-18 06:06
20241008 | 20241008006 | 6 | SMA on Burleigh | 1100-20-70 Sheet 2 describes a 3&quot;, single lift pavement. Sheet 84 describes 2 lifts @ 1.5&quot; each. Sheet 25 just says mill and replace 3&quot;. Please clarify. | The SMA on Burleigh St should be paved in two 1.5â€ lifts. | Mike Coleman | 8 | 2024-09-19 08:35 | 2024-09-19 14:27
20241008 | 20241008006 | 6 | SMA Test Strips | Special Provision for 460.0120.S. calls for 1 test strip for each thickness and for each layer of SMA. I count 6 different thicknesses/layers. 1.5&quot; lower, 1.5&quot; upper, 1.75&quot;, 2&quot;, 2.25&quot; and 3&quot;. How many test strips do you intend to have the contractor construct? There are a similar # of thicknesses/layers for the 3HT item as well if you would like to address that also. | The following is in response to the question regarding test strips. During the review of the plan, some errors were noted in the PWL mixture use table. These errors will be corrected in a revised table in Addendum #2. - The project currently includes 1 test strip for SMA density and 1 test strip for SMA volumetrics. This covers the 2â€ upper lift of SMA throughout the project. - The 1.5â€ upper and lower lifts only apply to Burleigh St. Acceptance testing on Burleigh St will be based on cores. - The 1.75â€, 2.25â€, and 3â€ layers referenced in the question are labeled incorrectly on the -70 ID general notes sheet. We will update this table in Addendum #2. The upper layer is intended to be 2â€ throughout the mainline paving to reduce the number of test strips required. - A revised PWL mixture use table will be issued in Addendum #2. - For the HMA lower layers with variable thickness, the project is utilizing the core only SPV. One test strip for volumetrics is included in the miscellaneous quantities. - In total, there are three test strips anticipated on the project. | Mike Coleman | 9 | 2024-09-19 08:57 | 2024-09-25 06:21
20241008 | 20241008006 | 6 | SMA Gradation | Apart from the 1.5&quot; lifts on Burleigh, is there a reason for using 5SMA rather than 4SMA? It appears as if all of the surface on I41 could be 4SMA and would likely be more economical for the department. I believe that all of the other projects in the region have specified 4SMA. | The 5 SMA mix allows all the SMA layers to be paved with one mix design for the project. The 2â€ upper lift on the mainline and 1.5â€ lifts on Burleigh St are within spec for the 5 SMA mix. Plan Addendum #2 will include clarifications on paving layer thicknesses. | Mike Coleman | 10 | 2024-09-20 09:38 | 2024-09-25 06:20
20241008 | 20241008006 | 6 | Echelon Paving | Per the Prosecution and Progress â€œEchelon Pavingâ€ there are numerous station ranges that require echelon paving between lane 3 and the outside shoulder and lane 1 and the inside shoulder. It appears that the outside shoulder is not being paved and that the verbiage between lane 3 and the outside shoulder should be removed from the provisions. The ranges that require echelon paving in lane 1 and the inside shoulder will be extremely costly due to the space constraints between the existing permanent wall and the temporary wall as it will be difficult to get HMA to the two material transfer vehicles in this space. Will the Department consider removing the section â€œEchelon Pavingâ€ from the prosecution and progress? | The echelon paving requirement is no longer required on the contract. Per SPV.0055.0003, the contractor may still pave in echelon at their own discretion. | Mike Coleman | 11 | 2024-09-24 16:24 | 2024-10-01 07:20
20241008 | 20241008006 | 6 | Question 10 | In regards to question #10, there is a large savings by changing the 5 SMA to a 4 SMA. Would the Department reconsider changing the paving on IH 41 to a 4 SMA and leaving Burleigh at 5 SMA? | The region has determined that the 5 SMA will remain as shown in the plans. | Mike Coleman | 12 | 2024-09-26 13:39 | 2024-09-29 10:24
20241008 | 20241008006 | 6 | Micropile Loads | Please provide lateral loads for the micropiles. Please confirm the minimum micropile casing lengths are not given and are determined by micropile design engineer. | The micropile cased length design requirements are provided on the micropile data tables on the â€œMicropile Detailsâ€ sheet found on both bridge B-40-358 and B-40-359. The bottom of casing elevation was designed to extend through fill and terminate in the glacial till-Intermediate Geomaterials (IGM). The bottom of steel casing elevation provided accommodates the combination of axial and flexural demands as summarized in the geotechnical report appendix. The maximum lateral load per micropile (without group effects) is provided below for each substructure unit. STRENGTH 1 B-40-358 B-40-359 F_lat (kips) F_lat (kips) S Abut 11.1 5.2 Pier 1 4.5 3.4 Pier 2 3.7 3.4 Pier 3 3.7 3.4 Pier 3 Protection Wall 0.0 0.0 N Abut 11.1 5.2 SERVICE 1 B-40-358 B-40-359 F_lat (kips) F_lat (kips) S Abut 16.8 8.7 Pier 1 6.7 5.8 Pier 2 5.6 5.8 Pier 3 5.6 5.8 Pier 3 Protection Wall 0.0 0.0 N Abut 16.8 8.7 The contractor is advised that the design, special provisions, and plan information shown in the bid documents has previously been reviewed and approved by UPRR. Expect that any design changes must be submitted to the DEPARTMENT and UPRR for approval. | Mike Coleman | 13 | 2024-09-30 13:11 | 2024-10-04 06:58
20241008 | 20241008006 | 6 | Item 678.0501 Communications System Testing | Schedule of pricing has quantity 3 for item 678.0501 Communicaitons System Testing but only able to locate one in the plant set. Please clarify. | The proposal has a total quantity of 3 for 678.0501 Communications System Testing. The items are split between the 1100-20-70 and 1100-20-71 plans. - 1100-20-70: 1 testing item for FTMS (pg 431) - 1100-20-71: 1 testing item for signals (pg 1362) - 1100-20-71: 1 testing item for FTMS (pg 1366) | Mike Coleman | 14 | 2024-10-01 23:24 | 2024-10-02 07:40
20241008 | 20241008006 | 6 | Chord Pipe Unavailability | Proposal line numbers 300, 302, &amp; 304 require chord material size 4.5&quot;od x .375&quot;w. This size is not produced in a domestic product. Can the department advise an alternate size or can foreign material be used? Proposal line numbers 306 &amp; 308 require chord material size 5&quot;od x .375&quot;w. This size is not produced in a domestic product. Can the department advise an alternate size or can foreign material be used? | Bureau of Structures has rechecked the designs and ASTM A500 Grade C 4.5x0.337 would work for the S-40-3060, 3061, and 3062 (lines 300, 302, 304). For structures S-40-3085, 3088 (lines 306 and 308) either ASTM A500 Grade C 5.5x0.313 or ASTM A500 Grade C 5.5x0.375 would work. | Mike Coleman | 15 | 2024-10-02 08:51 | 2024-10-03 09:34
20241008 | 20241008006 | 6 | Micro Pile compression tension load test | Can the compression/tension load test be performed on installed verification test piles, or is a separate test pile required for this test. | Article 151, paragraph A.1 of the special provisions states the following: â€œVerification Load Test: â€¦.At the contractorâ€™s option and assumption of risk, this pile load test may be performed on a first production pile prior to installation of any other production piles. Alternately, perform the pile load test on a sacrificial test pile prior to the installation of production piles.â€ If the Verification Load Test is on a production pile, then that can serve as the Proof Load Test also. Note that the plans require one test location at each substructure location, totaling five tests for the project. | Mike Coleman | 16 | 2024-10-02 11:25 | 2024-10-03 08:03
20241008 | 20241008006 | 6 | Micropile retaining wall footings | Specifications call out drilling through existing retaining wall footings. Please clarify location of retaining wall footings to be cored through, and as builts of existing retaining wall footings. | The micropiles were located to miss existing footing based on available as-builts and survey. Article 170 section C.3.1 was included when it was expected that a new road and retaining wall were going to be in place between piers 2 & 3. That project has been postponed. Article 170 section C.3.1 can be referenced if undocumented footings are encountered unexpectedly. | Mike Coleman | 17 | 2024-10-02 12:05 | 2024-10-03 09:35
20241008 | 20241008006 | 6 | Reply To Question #15 (Pipe Unavailability) | Would 5.563&quot;od x .375&quot;w A500 Grade C pipe work in lieu of the two alternative options provided (5.5&quot;x.313&quot; &amp; 5.5&quot;x.375&quot;)? Supplier says these sizes are currently only available in Canadian material. | Yes, 5.563x0.375 A500 Grade C would work as well. | Mike Coleman | 18 | 2024-10-03 11:10 | 2024-10-04 09:32
20241008 | 20241008006 | 6 | Polymer Overlay | All but one of the bridge decks to receive a Polymer Overlay are adjoined to sections of roadway to receive High Friction Surface Treatment, will bauxite aggregate be required on the Polymer Overlay for uniformity? |  |  | 19 | 2024-10-03 11:32
20241008 | 20241008006 | 6 | 614.0905 Temporary Crash Cushion back width | The Miscellaneous Quantity table for 614.0905 Crash Cushions Temporary on project ID 1100-20-71 shows that three of the cushions have a required back width of 10&#39;. The crash cushions shown in the plan all appear to protect single runs of temporary barrier wall, which the standard back width of 2&#39; would provide sufficient protection. Was the wider width inadvertently added to this table, or is there a need for three temporary crash cushions with a back width of 10 feet? If the wider cushions are needed, can a SPV item be added to the project for &quot;wide&quot; temporary cushions? | The 10â€™ widths are incorrect. All back widths behind temporary crash cushions are 2â€™. | Mike Coleman | 20 | 2024-10-03 14:05 | 2024-10-04 11:42
20241008 | 20241008006 | 6 | Winter Shutdown - Pavement Markings | What pavement marking items will be used for the winter shutdown? The only temporary pavement marking items on this contract are waterborne paint items, which typically are not permitted for over-winter use. Cold Weather Epoxy lines would be the best application for the time of year the staging is expected to switch into the winter shutdown alignment. |  |  | 21 | 2024-10-03 15:26
20241008 | 20241008006 | 6 | Addendum 1 Fire Hydrant Signs | Addendum 1 added signing quantities for installing fire hydrant signs on the noise barrier wall. The plan sheets of the addendum state (see detail). Where is this detail found? | The detail is on page 1065 of the plan. Itâ€™s the last sheet in the 1100-20-71 permanent signing plan. | Mike Coleman | 22 | 2024-10-07 10:04 | 2024-10-07 10:46
20241008 | 20241008007 | 7 | Onsite Crushing of Existing Pavements | Will WISDOT allow onsite crushing on this project? | WisDOT and the Village of Shorewood will not allow on-site crushing. | Mike Coleman | 1 | 2024-09-08 12:48 | 2024-09-16 14:29
20241008 | 20241008007 | 7 | Borings - Geotechnical | Are there borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/yq2ee6o9j4by4g2zoctgrvyr2fdnmngx or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-09-16 10:08 | 2024-09-19 12:01
20241008 | 20241008007 | 7 | Traffic Control | On Project ID 2225-15-70 Lake Drive From Newberry Drive to Edgewood Drive there was a detailed traffic control plan in the contract bidding documents. This Traffic control plan included several stages for stakeholder access and traffic access through out the project. The road is now completely closed to traffic for full width removals and construction operations. For Contract ID 2225-13-70 Lake Drive from Edgewood to Kensington Drive also includes a detailed traffic control plan with multiple stage and accommodations for the stake holder access in the contract bidding documents. Will the same accommodations to shut the roadway down to traffic for construction operations and full width removals be granted for Project ID 2225-13-70 Lake Drive from Edgewood Drive to Kensington Drive? | WisDOT and the Village of Shorewood will not allow full width pavement removals. Per the Prosecution and Progress, maintain a minimum 11-foot travel lane for local and emergency access on existing or proposed pavement surfaces. | Mike Coleman | 3 | 2024-09-20 13:56 | 2024-09-24 09:29
20241008 | 20241008007 | 7 | Existing Concrete Pavement Thickness | The Geotech says the existing pavement is 6&quot; thick and the plans say it is 9&quot; thick, which is correct? | The existing concrete pavement thickness varied between 5â€ and 7â€ across the 18 borings. An addendum will be forthcoming to correct this discrepancy. | Mike Coleman | 4 | 2024-10-03 09:16 | 2024-10-04 07:00
20241008 | 20241008007 | 7 | Concrete Joint Sealing | Will Concrete Joint sealing be required? | Concrete Pavement Joint Filling is required. An addendum will be forthcoming to add this bid item. | Mike Coleman | 5 | 2024-10-03 10:07 | 2024-10-04 07:01
20241008 | 20241008007 | 7 | Storm Sewer | The proposed combined sewer from STA 27+75 to STA 45+40 along the mainline alignment in STH32/Lake Drive is located directly adjacent to a traffic control stage line between stages 1 &amp; 3. The sewer requires a 17-foot deep excavation and there is not sufficient room for the equipment needed to excavate the sewer trench in either stage, or adequate clearance from live traffic lanes. Will the department consider revising the traffic control plan or alignment of the combined sewer to provide access and a safe clearance from live traffic lanes? | STH 32 will be closed to through traffic during construction. As a result, any live traffic would be local traffic only. All combined sewer work between Edgewood Avenue and Shorewood Boulevard is planned to occur in the Stage 1 traffic control configuration where there are 11â€™ separating local traffic and the combined sewer alignment. Depending on the contractorâ€™s means and methods, a dedicated flagger may be needed. A construction detail is included on sheet 16 for lateral trenching, and note #3 is â€œflag traffic through the work zone as neededâ€. No revisions to the combined sewer alignment and traffic control are planned. | Mike Coleman | 6 | 2024-10-04 09:27 | 2024-10-07 10:36
20241008 | 20241008008 | 8 | Transformer Bases Breakaway Lead Times | How will the long lead times on this item be handled if it goes past the project completion date? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 1 | 2024-09-25 14:17 | 2024-10-03 09:36
20241008 | 20241008008 | 8 | Design Schedule | Please provide a copy of the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/qartsoxzlc11n63e6qi8sadgf6sviw3e or can be accessed on the HCCI October bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-10-02 08:23 | 2024-10-02 09:43
20241008 | 20241008008 | 8 | Utilities | Within the utilities special provision both WE Energies-Electric and Charter Communications indicate a conflict with their existing facilities. Please provide an updated status/schedule for the relocation of these impacted facilities. | WE Energies-Electric has completed its relocation. Charter Communications has a Utility Permit approved by the City of Oak Creek with an anticipated start date of 9/30/2024, with an anticipated completion date of 12/31/2024. | Mike Coleman | 3 | 2024-10-02 08:49 | 2024-10-03 10:22
20241008 | 20241008008 | 8 | Temporary Structure | Will the department allow for temporary bypass pumping in lieu of the diversion structure during the channel work? | The Department may be open to that option, but it would have to be vetted with the Wisconsin Department of Natural Resources through the ECIP process. The Department makes no guarantee that the option will ultimately be feasible or approved. | Mike Coleman | 4 | 2024-10-02 21:24 | 2024-10-04 16:49
20241008 | 20241008008 | 8 | Temporary Creek Diversion Structure | Will the department allow for the removal of the concrete channel &amp; placement of the streambed riprap to be complete in the wet â€“ with an allowable one-time release of sediment? Per the plan details, sediment release will be inevitable during the installation &amp; removal of the diversion structure &amp; the earthen dam/etc in each stage. The plan details as-shown have considerable cost/constructability implications and may not achieve full â€œin the dryâ€ scenario called out in the plan. If this exception is allowed, removal and replacement of the sanitary sewer &amp; installation of channel cutoff wall could still be completed in the dry. | The Department may be open to that option, but it would have to be vetted with the Wisconsin Department of Natural Resources through the ECIP process. The Department makes no guarantee that the option will ultimately be feasible or approved. | Mike Coleman | 5 | 2024-10-03 07:07 | 2024-10-04 16:49
20241008 | 20241008008 | 8 | Locate Utility Line | Locations for the locate utility line item are not given in the misc. quantities. Is the intent to use this item in conjunction with the pre-boring item for piling installation near the sanitary line, or elsewhere? | The intent for this item was to confirm the sanitary sewer location next to the piles. The structure plan quantity table lists one at each abutment. Now that the sanitary sewer line is being removed via Addendum 1, this item will no longer be needed for those two locations, but will remain in the contract in case itâ€™s needed at any other locations as directed by the engineer during construction. | Mike Coleman | 6 | 2024-10-03 09:15 | 2024-10-04 16:48
20241008 | 20241008009 | 9 | Rail Road Flagging | Per the special Provisions Item 7 Railroad Insurance and coordination. Section A3 Flagging Contact It states &quot; See Construction Contact. If More than 30 Days of Flagging is required contact UP 30 days prior to needing a flagger on site.&quot; Is Railroad Flagging costs being covered by the department or the RR on the Project? If Not can the UP RR Flagging rates be provided? | Flagging will be at the expense of the contractor and not reimbursed by the department. Our current flagging rates, subject to change, appended. Rates - Union Pacific The following rates, reimbursement provisions, and excluded conditions will be used to determine the contractorâ€™s cost of flagging: - $1,150 daily rate for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses), - $1,500 "Rest Time" or nightly rate for weekday overnight work for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $1,260 daily rate for an eight-hour day on Saturdays, Sundays, or holidays (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $1,500 "Rest Time" or nightly rate for weekend overnight work for an eight-hour day (including wages, labor surcharges, lodging, vehicle and mileage expenses) - $175 per hour overtime rate for all time worked before or after the regular assigned eight hours on any day, or for a minimum three hour call on Saturdays, Sundays, or Holidays. The railroad or its third-party flagging contractor www.up.com/flagging will require pre-payment and a minimum 30-day notice. The flagger is required to set flags each day in advance of the contractor commencing work that will require flagging. The flagger must also remove the flags each day after the completion of work that required flagging. Any time worked before or after the minimum eight-hour flagging day to set or remove flags will be billed at the overtime rate. The contractor is responsible for knowing the requirements of the railroad for arranging and terminating flagging services and for the associated costs of those services. | Mike Coleman | 1 | 2024-09-26 17:18 | 2024-10-01 10:53
20241008 | 20241008009 | 9 | Soil Borings | Are there soil borings available for this job? | The design schedule can be found at the following location: https://wisdot.box.com/s/3obem3enkjmtjwczlcaeolt03ycdrk1i or can be accessed on the HCCI October bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2024-10-04 09:56 | 2024-10-07 09:19
20241008 | 20241008013 | 13 | 530th Ave Typical Section | The typical section on Sheet 7 states 4MT 58-34S for the 530th Ave Overlay. The Miscellaneous Quantities and General Notes state that 5MT 58-34S should be used for 530th Ave. The department may also want to consider changing this to an Asphaltic Surface item. | The HMA mix type to use for the overlay on 530th Ave is 5 MT 58-34 S. | Mike Coleman | 1 | 2024-09-12 07:47 | 2024-09-12 12:48
20241008 | 20241008013 | 13 | Soil Borings | Are soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/pxypj1a8splddcuxfeb4g906x6hxibck or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 2 | 2024-09-17 10:58 | 2024-09-18 06:41
20241008 | 20241008014 | 14 | 1 1/4" Base | Plan shows 1350 TON of 1 1/4&quot; BAD. Where is it being used? | Used in removing asphaltic surface driveways and field entrances. Called out on the Removing Asphaltic Surface Detail â€“ Driveways | Mike Coleman | 1 | 2024-09-27 14:29 | 2024-10-02 06:22
20241008 | 20241008014 | 14 | Cleaning Culvert Pipe | The plan calls out for the twin box culverts at STA 1234+51 at Ten Mile Creek to be cleaned. The structure currently has a significant amount of water standing in it and what appeared to be less that a foot of sediment throughout the structure. Please verify that the Department wants these structures dewatered and cleaned. | The work came from the scoping culvert list document. Upon some investigation, two of the culverts on that list are C# structures on Ten Mile Creek. The scoping culvert information is about nine years old. There are inspection reports from 2020 on HSI for C-55-0031 at STA 1216+74 and C-55-0032 at Sta 1234+51 that do not call out needed cleaning. ISG will issue an addendum to remove the cleaning at these two locations. | Mike Coleman | 2 | 2024-09-27 15:18 | 2024-10-02 06:33
20241008 | 20241008014 | 14 | Lower Layer HMA Pavement Type | The department may want to consider changing the lower 1.75-inch pavement layer to a 4MT instead of a 5MT. | The proposed pavement type is from the Pavement Design Report. It is suitable for this project and is appropriate to provide long term performance. The pavement types will remain as shown in the plan. | Mike Coleman | 3 | 2024-09-27 16:39 | 2024-10-02 06:30
20241008 | 20241008014 | 14 | Asphaltic Surface Items | Clarification on the intent of the undistributed asphaltic surface and asphaltic surface patching quantities would be helpful. Specifically, which item will be used for the concrete curb and gutter areas? | The use of undistributed asphaltic surface and asphaltic surface patching items was recommended in the pavement design report to mitigate miscellaneous repairs that often get discovered during construction. The pay item in the curb and gutter areas is intended to be asphaltic surface patching. We will pull the portion used for the curb and gutter patch out for clarity in the addendum. | Mike Coleman | 4 | 2024-09-27 16:44 | 2024-10-02 06:40
20241008 | 20241008014 | 14 | Pavement Removals | How will the pavement removals at the curb and gutter locations be paid? | The intent for payment is with Removing asphaltic surface Upon investigation, it looks as though this removal area was not included in the quantities. The additional quantity is as follows: 35 SY to Project 8949-00-75 175 SY to Project 1540-02-78 This adjustment will be included in an addendum. | Mike Coleman | 5 | 2024-09-30 10:03 | 2024-10-02 06:36
20241008 | 20241008015 | 15 | Soil Borings | Are soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/390erjnlv7zcroivhvpga9g0jcbgrd4o or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-09-17 10:58 | 2024-10-01 10:49
20241008 | 20241008016 | 16 | Soil Borings | Are soil borings available for this project? | No borings are available for this project. | Mike Coleman | 1 | 2024-09-17 10:57 | 2024-09-18 07:14
20241008 | 20241008016 | 16 | Borrow | Is the borrow needed for the grading on 690th Ave and 799th Ave included in the quantities? Cross sections are in the plans but there is not any information in the earthwork summary. | Yes, the borrow needed for 690th ave and 799th Ave is accounted for and included with the adjacent grading areas paralleling USH 63. Earthwork comps on Pages 33 and 210-215 only reference USH 63 alignment stationing due to how grading was modeled. | Mike Coleman | 2 | 2024-09-18 06:45 | 2024-09-18 12:15
20241008 | 20241008016 | 16 | Base Ag 1 1/4-Inch | Is there a typical section that shows the BAD 1 1/4-inch in the grading areas? Neither the cross sections nor the typical sections show a shoulder notch but there is quantity of 1 1/4-inch at each of these areas. | There is no typical section that shows the BAD 1 ï¿½-inch in the grading areas. 12-inches was assumed for 1 ï¿½-inch BAD thickness. It was assumed no cutting would be done to install 1 ï¿½-inch BAD at grading areas. | Mike Coleman | 3 | 2024-09-18 07:28 | 2024-09-18 12:19
20241008 | 20241008017 | 17 | soil borings | Are soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/zuxdlf3fo8apd6ud7duxlww6zwinwwbh or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 1 | 2024-09-17 10:57 | 2024-09-18 06:37
20241008 | 20241008017 | 17 | III-B | III-B isn&#39;t on the PAL list what does the DOT want quoted for this project. | Erosion Mat Class III Type B should be a TRM for use on slopes 1:1 or flatter (slopes of 0â€™ to 30â€™ in length) that has a minimum permissible shear stress of 2.0 lbs/ft2 based on FDM requirements. | Mike Coleman | 2 | 2024-09-19 15:01 | 2024-09-25 06:19
20241008 | 20241008018 | 18 | Traffic Control 643.5000 | It appears that the item Traffic Control 643.5000 has been omitted from this project. Can the item be added on? Thanks | An addendum will be issued in the future to add the item. | Mike Coleman | 1 | 2024-09-16 10:44 | 2024-09-17 05:53
20241008 | 20241008018 | 18 | Milled Surface Time Restriction | Please consider extending the allowed time between milling and paving. Polk County just completed the same mill and overlay project on CTH F from STH 65 to Deronda/Amery. The county completed the milling a week before paving started with no issues. Time is also needed to complete the superelevation wedging corrections between milling and paving. One suggestion would be to start paving within one week (7 calendar days) after milling starts. | The listed time restriction between milling and paving will remain as shown. | Mike Coleman | 2 | 2024-09-27 17:50 | 2024-10-01 07:19
20241008 | 20241008019 | 19 | Steel Railing Retrofit | Can a 7/8&quot; diameter hex bolt with washer be used to bolt the wood block to the post instead of threaded road with a welded nut? | Yes, a 7/8-inch diameter hex bolt with a washer may be used to attach the wood block to the steel post instead of the threaded rod with a welded nut. Both methods are acceptable. | Mike Coleman | 1 | 2024-09-12 09:29 | 2024-09-16 07:50
20241008 | 20241008019 | 19 | Proposal Book | The items listed in the Proposal are for proposal 20241008018 instead of 20241008019. Thanks, | An addendum will be issued to add the correct schedule of items. | Mike Coleman | 2 | 2024-09-12 09:58 | 2024-09-16 07:48
20241008 | 20241008019 | 19 | Soils Report | Please provide a copy of the soils report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/hmhal8urdol01m0yt138z59xjw2tdcgh or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 3 | 2024-09-25 10:36 | 2024-10-01 07:09
20241008 | 20241008019 | 19 | Earthwork | Please provide a copy of the computerized earthwork in excel format. | The earthwork data in Excel format can be found at the following location: https://wisdot.box.com/s/hmhal8urdol01m0yt138z59xjw2tdcgh or can be accessed on the HCCI October bid letting page under Supplemental Information. | Mike Coleman | 4 | 2024-09-26 11:59 | 2024-10-01 07:12