## qandasearchletting_results
Date | 2025-03-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250311 | 20250311001 | 1 | Earthwork | Why does the Excavation Common Table in the MQ assume 0% of cut is reused for Divisions 1,2 & 5? | Soil borings and soil types indicated that the soil was not sufficient to be reused. | Mike Coleman | 1 | 2025-03-03 14:17 | 2025-03-05 06:18
20250311 | 20250311001 | 1 | Water | A water item is not included in the MQ, please add the item. |  |  | 2 | 2025-03-04 07:42
20250311 | 20250311001 | 1 | Salvaged Topsoil | Item salvaged topsoil is listed as a quantity of 105 square yards, yet the erosion mat is 13,857 square yards. Are these quantities correct? How is the remaining topsoil to be paid? |  |  | 3 | 2025-03-04 18:52
20250311 | 20250311001 | 1 | Geotechnical Report | Please provide a copy of the full geotechnical report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/r3p9i7jfgcxmckc30epcdi2c8lgps3j8 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 4 | 2025-03-05 06:47 | 2025-03-05 10:44
20250311 | 20250311003 | 3 | Project Schedule | Could the Department provide the Schedule developed during design? | The design schedule can be found at the following location: https://wisdot.box.com/s/2qous83co6xovyhrbg7r56350ma5p7q5 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 13:42 | 2025-02-17 08:56
20250311 | 20250311003 | 3 | HMA in Pipe Patches | Sheet 9 shows 5 ï¿½ inches of HMA in the pipe patches. Page 43 shows asphaltic surface tonnages for culvert lower layer. Based on the removal areas shown in the plan sheets, there should be more tonnage than shown in the MQâ€™s? Also, the MQâ€™s show only the lower layer. Could the department update the MQâ€™s to show the full quantity of 5 ï¿½â€ of HMA? |  |  | 2 | 2025-02-20 09:14
20250311 | 20250311003 | 3 | Pipe Patch Excavation | Sheet 9 shows that transition excavation and backfill is incidental to the pipe culvert. Per sheet 9, the limits are to be determined in the field by the engineer. Without knowing the engineerâ€™s limits this makes estimating the required excavation and backfill impossible. Could an item for the required excavation and backfill be added for anticipated quantities? |  |  | 3 | 2025-02-20 09:18
20250311 | 20250311004 | 4 | Design Schedule | Could the Department provide the schedule that was developed during design? | The design schedule can be found at the following location: https://wisdot.box.com/s/uqp8exhcuibfndl1otge1925tmrtwjsp or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 13:43 | 2025-02-17 08:48
20250311 | 20250311004 | 4 | 72 Hour Rule | Based on PWL, milling 3 ï¿½â€, contractor will need time to get the mill out front, pave the test strip, and then start main line. In addition, the road is closed to through traffic, the contractor is requesting that the 72-hour be adjusted to 108-hour. | An addendum will be issued to revise the requirement of paving the lower layer of HMA pavement within 96 hours of milling in lieu of 72 hours. | Mike Coleman | 2 | 2025-02-20 09:23 | 2025-02-24 06:13
20250311 | 20250311007 | 7 | Installing & Maintaining Bird Deterrent 999.2000S | The bid item is for Installing and Maintaining Bird Deterrent. The Special Provision indicates the bridge has an existing deterrent that was installed by the county, if this is the case the bid item should be Maintaining Bird Deterrent System. Who is responsible for install? County or Contractor? | The item is being changed via emergency addendum. | Mike Coleman | 1 | 2025-03-06 10:44 | 2025-03-07 15:23
20250311 | 20250311009 | 9 | Working Days | With the Temporary Structure, the current 40 WD schedule is very difficult/not possible to meet. Would the Department allow a revised schedule of 5 WD for temp bypass install, 40 WD for new bridge construction, 5 WD for temp bypass removal, total of 50 WD for the project? | After further consideration, it was determined that 40 working days will remain as the time for completion. | Mike Coleman | 1 | 2025-03-07 07:59 | 2025-03-10 09:43
20250311 | 20250311010 | 10 | soil borings | Are soil borings available for the project? | The soil borings can be found at the following location: https://wisdot.box.com/s/6np32r2vnl6pwnzt19m100brsxj66kpz or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-03-03 07:38 | 2025-03-04 06:51
20250311 | 20250311010 | 10 | Grade 1 sand | Could you please provide more information concerning the need/purpose for the grade 1 sand? | Can the bidder please provide more details? We have looked over the estimate and specials and do not see any references to grade 1 sand. | Mike Coleman | 2 | 2025-03-05 10:02 | 2025-03-05 14:10
20250311 | 20250311010 | 10 | Grade 1 Sand - follow up | Item 12 (209.15 - Grade 1 sand) is listed in the MQs and is a pay item. In the MQs, the location is listed as project wide. It's also listed under the 5998-00-01 ID and not the 5998-00-02 ID, which is related to the municipal underground work... so it doesn't seem related to the underground work. It's unclear as to what this pay item is for... (ie. SW EBS? SS BF?). Further info would be helpful. | Thank you for the follow up, the confusion stemmed from the fact that the item is not called out as sand, but is instead listed as â€œBackfill Granularâ€ as the official bid item name. Having spoken with the design team, our answer is as follows: â€œThat bid item was for the backfill for storm sewer removed beneath the roadwayâ€ The removing storm sewer spec is what drove the decision to add this item. | Mike Coleman | 3 | 2025-03-05 14:21 | 2025-03-07 10:06
20250311 | 20250311011 | 11 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/1lk100ah0xbjau4oj1uhq0t9oa9q39qy or can be accessed on the HCCI February bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 08:44 | 2025-02-17 08:39
20250311 | 20250311011 | 11 | SPV.0060.11 Inlet Adjustment Castings | Can you please provide a detail or a component number for the Inlet Adjustment Castings that are specifed? | The intent of the inlet adjustment casting is to eliminate temporary removal of concrete barrier in order to adjust inlet cover to proposed roadway grade. Details and dimensions for the adjustment risers to be used on existing Type V inlet covers are the responsibility of the contractor to verify based on field conditions encountered. It is anticipated that the steel adjustment device used will be or similar to custom steel inlet/catch basin risers from American Highway Products. Acceptance of proposed device to be used will be required by engineer. | Mike Coleman | 2 | 2025-02-27 15:51 | 2025-02-28 09:53
20250311 | 20250311011 | 11 | Maintain and Salvage Temporary Barrier | For SPV 82, Maintain and Salvage TBW, can WisDOT confirm the year the TBW was manufactured? As the quantity identified is intended to be utilized on a subsequent stage as Delivered, it is assumed that WisDOT will want barrier to be in specification to current APL. | The temporary wall that was left in place was fabricated in 2018 according to previous contractorâ€™s submitted certificate of compliance. | Mike Coleman | 3 | 2025-02-28 12:36 | 2025-03-04 13:30
20250311 | 20250311011 | 11 | SB Silver Spring Exit Ramp Closure | In stages 1B-1 and 1B-2, general notes for traffic state that 43 SB Silver Spring exit ramp will be short term closure when work is occurring. This is interpreted as a full closure for a duration of days potentially as approved by the engineer as opposed to other closures that are noted as night time/off peak for daily closures. Please confirm. | The intention of this note is to allow the closure of the IH 43 SB Silver Spring exit ramp when there is rehabilitation work on the ground mounted portion of N-40-28 that is along the exit ramp or in an area upstream or downstream of the ramp that would require the closure of the ramp to allow access and appropriate work zone area for contractor to complete work. The engineer may approve full closure of this ramp for localized work for a short term duration up to 3 continuous days and nights, such that a posted detour or temporary pavement markings would not be required, per SDD 15D16-06. | Mike Coleman | 4 | 2025-02-28 12:38 | 2025-03-04 13:31
20250311 | 20250311011 | 11 | R-40-160 Access | For access for proposed scope of work for R-40-160, has the Department arranged with private property owners to allow access or is the expectation to come from overtop of the parapet to locate and complete repairs and joint sealing? | No arrangements have been made with private property owner to allow access. The expectation is that contractor will access R-40-160 from IH 43 NB outside shoulder. | Mike Coleman | 5 | 2025-02-28 12:39 | 2025-03-04 13:32
20250311 | 20250311011 | 11 | N-40-28 Access | For N-40-28 footing erosion repairs, is it anticipated to work on the back side of the segment of wall along the river? | It is anticipated that the majority of work for the footing erosion repairs can take place from the roadway side. Dependent on the equipment used, there may be a need to guide the material from the river side. The area behind the noise walls was cleared early 2025 and there is an ability to access the back side of the wall on public right of way, if the means and methods chosen make it necessary to properly place breaker run per construction detail. | Mike Coleman | 6 | 2025-02-28 12:40 | 2025-03-04 13:35
20250311 | 20250311011 | 11 | Staging progression | Article 3, Prosecution and Progress, states â€œDo not move to the next stage until all the work in the current stage is complete or as approved by the engineer.â€ Based on the provided design schedule, it is the Departments intent to work on Stage 2A/2B NB while still working on stage 1B SB. Additionally, the design schedule shows to allow for stages 2C during stage 2A/2B? Will the Department allow the Contractor to schedule/sequence stages NB/SB, as approved by the engineer, as they feel best fits sequence of operations more closely to the design schedule as opposed to prosecution and progress language? | It is assumed that overlapping work will be necessary, including IH 43 NB mainline and ramp rehabilitation work beginning ahead of the completion of the IH 43 SB structure mounted noise wall replacement work, as shown on the design schedule, in order to complete the project in one construction season. Approval from engineer will be required to move to the next stage, but from bidding perspective, it should be understood that the goal of project is to complete project in one construction season and flexibility will be provided, more similarly to design schedule, so long that sequencing of work is coordinated with engineer ahead of time to limit additional impacts to travelling public. | Mike Coleman | 7 | 2025-02-28 12:45 | 2025-03-04 13:34
20250311 | 20250311011 | 11 | B-40-578 Joint Cover Plate | B-40-578 calls to salvage existing expansion joint for edge of deck replacement. Plan shows new cover plate for single slope parapet. How is new cover plate paid for? | The new cover plate is incidental to 509.1000 Joint Repair. | Mike Coleman | 8 | 2025-02-28 12:46 | 2025-03-07 10:03
20250311 | 20250311011 | 11 | MSE Panel surface repair | Surface repair for MSE wall panels are identified on structures R-40-159 and R-40-160. As the MSE walls panels are precast typically around 6â€ thick with a single mat of reinforcement, there is concern that standard specifications for surface repair are applicable for this scope of work. There is concern that in removing deteriorated concrete, the repair could go through the depth of the panel to the backfill in order to expose the reinforcement. Additionally, the strapping anchors cast into the panel could be compromised if located in a repair area. Could the Department review surface repair of MSE panels as a special scope and how to best repair the panels without compromising their integrity. | An addendum will be issued to provide additional clarification for concrete surface repairs for MSE wall panels. | Mike Coleman | 9 | 2025-02-28 12:47 | 2025-03-07 10:09
20250311 | 20250311011 | 11 | Traffic - Bender Rd | The special provisions indicate that only 2 full closures are allowed for Bender Rd: for demolition and for the deck pour. There are other operations that will require full closures over Bender due to the limited roadway space below in order to complete the work safely: i.e. noise wall panel & post removal, wall post & panel installation, deck forming stripping. Will the department allow these required closures and will the traffic control be compensated for? | An addendum will be issued to provide additional quantity for full closures for bridge work at Bender Road. | Mike Coleman | 10 | 2025-03-03 14:51 | 2025-03-05 14:06
20250311 | 20250311011 | 11 | Lane Closures on I 43 | Can further consideration be provided for the lane closure periods which are currently being restricted from 9:30pm to 5:30am. This short duration leaves little time to perform Base Patching and Asphalt paving and very significantly increases pricing. Can WisDOT please consider extending the time frames and at least allow an earlier start in lanes 1 or 3? Are there times in the evening or mornings when time frames can be extended in either of the directions? Can more hours be provided during certain days of the week like Sunday nights when there is very little traffic? Typically, we see a lot of drop off in traffic around 7:30 pm Monday through Thursdays and very little traffic on Saturday mornings until 10:00am. If it takes a half hour to put up barricades, a half hour to take down barricades and it takes 4 hours to get breaks on the SHES Base Patches This leaves 4.5 hours to actually work. | The lane closure hours were defined as shown to provide consistency with other ongoing adjacent projects within the corridor. Therefore, changes to the lane closure hours will not be considered. | Mike Coleman | 11 | 2025-03-06 08:18 | 2025-03-07 15:26
20250311 | 20250311011 | 11 | Concrete Pavment Under Barrier Wall | Is the concrete pavement 10-Inch under the S42 and Single Faced 32-Inch barrier wall paid as concrete pavement 10-Inch, as it is called out in the proposed finished sections, or is it incidental to each barrier wall item? | Concrete pavement 10-inch under S42 and Single Faced 32-inch Barrier wall, 24â€ wide concrete pavement 10-inch pad in front of barrier, and 4â€ wide concrete pavement 10-inch behind barrier wall is all considered incidental to barrier wall item. | Mike Coleman | 12 | 2025-03-07 09:20 | 2025-03-07 15:25
20250311 | 20250311011 | 11 | 643.4100 Traffic Control Interim Lane Closure | Will this item be paid per lane that is closed or just once per direction per night? | This item will be paid per lane that is closed per night. | Mike Coleman | 13 | 2025-03-07 12:20 | 2025-03-10 09:44
20250311 | 20250311011 | 11 | Follow up to Call Order 11 | Very limited nighttime lane closure restrictions are very challenging for SHES Base Patching and paving. On USH 41 from the Zoo to Silver Spring (SP 1100-20-70 & 71) a single lane closure can begin at 7:00pm. On I 94 constructed in 2024 from Roughly STH 16 to STH 83 single lane closures were allowed to start at 7:00pm. On I 43 at Mooreland Road (SP 1090-09-76 lane closures could begin at 8:00pm. Every hour and every minute counts with nighttime lane closures for SHES Base Patching that have to achieve strength and open to traffic in the morning. Costs increase dramatically as hours are reduced and few contractors are bidding on work with these extremely and often times unnecessarily short hours. Additionally this project has permanent single lane closures that are allowed at day and night for other activities. The restrictions on this project are the most restrictTive land closures we have seen in the Milwaukee area for this type of work. | As stated below, the Department is allowing permanent single lane closures that are allowed at day and night for other activities. For Stage 1A work, there are significant portions of inside shoulder and Lane 1 that are closed long term for both directions. For Stage 1B work, there are significant portions of Lane 3 and outside shoulder that are closed long term for SB direction. It is not stated anywhere that base patching cannot be completed in these areas during these long-term closures in Stage 1A/1B, and based on previous response from Department related to staging and overlapping of work, flexibility will be provided so long that sequencing of work is coordinated with engineer ahead of time to limit additional impacts to travelling public. The contractor is also allowed two weekend inside single lane closures and two weekend outside single lane closures. The special provisions state additional work other than drainage structure work, barrier work and noise wall repairs may also be allowed during the single lane closure as approved by the engineer. The nighttime hours were defined to be consistent with the adjacent IH 43 â€“ Brown to Capitol project that is also under construction at the same time as this project. It is understood that Lane 2 base patching and paving operations will be affected by the nighttime hour restrictions; however, there are other aspects of this project where the staging allows for a greater window for base patching SHES than typically seen. | Mike Coleman | 14 | 2025-03-09 14:34 | 2025-03-10 09:35
20250311 | 20250311012 | 12 | Geotextile Type DF Schedule A | The underdrain trench detail on sheet 16 shows Geotextile Type DF Schedule A. There doesn't appear to be a bid item for it. Will you be adding one via addendum? | The item 645.0111 Geotextile Type DF Schedule A was not included in the contract. An addendum will be released that will add the item to the contract and better define the dimensions. | Mike Coleman | 1 | 2025-03-04 13:35 | 2025-03-05 06:42
20250311 | 20250311012 | 12 | Contaminated Soil Excavation | On Sheet 21 of the plan it's indicated that the contaminated soils excavation can reach depths of up to 10' from the ground surface. If this is the case how is the contractor expected to prevent the ground from undermining the adjacent pavement? What type of material is being proposed to use for backfilling the excavation? | The excavation depths listed on the sheet 21 of the plans are the depths at which contaminated soils were found by soil borings. The maximum depth to excavate to would be dictated by the cross sections. The intent is not to remove all of the contaminated soil but if there is contaminated soil within the excavation limits it needs to be properly handled. | Mike Coleman | 2 | 2025-03-07 16:10 | 2025-03-10 10:12
20250311 | 20250311013 | 13 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/fv2yizxokeab8yiueyovq04iq98bcro5 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 08:45 | 2025-02-17 08:42
20250311 | 20250311013 | 13 | Soils Report | Can the Soils Report be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/fv2yizxokeab8yiueyovq04iq98bcro5 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-02-13 15:47 | 2025-02-17 08:46
20250311 | 20250311013 | 13 | Curb | Is there going to be an item for the integral curb? | Integral curb is not mandatory for design purposes, therefore, there wonâ€™t be a specific bid item for integral curb. We show integral curb in the plans because we typically allow it if the contractor asks if it can be used. All curb and gutter will be paid for under the appropriate standard bid item for curb whether it is integral or not. | Mike Coleman | 3 | 2025-02-21 10:20 | 2025-02-25 07:28
20250311 | 20250311013 | 13 | 678.0200 Fiber Optic Splice Enclosure | Who is supplying the Fiber Optic Splice Enclosure? | Milwaukee County DOT â€“ Traffic Engineering (See General Notes, Sheet 3 for contact information) will supply the Fiber Optic Splice Enclosure. | Mike Coleman | 4 | 2025-02-24 12:59 | 2025-02-27 07:25
20250311 | 20250311013 | 13 | 678.0300 Fiber Optic Splice | CV2 What fibers are being spliced at this location? Buffer tubes, cables, fiber designation/colors? CV4 same question? CV9 same question? | Per the splice diagram on the last sheet of the COMMUNICATIONS PLANS (Sheet 119), the following fibers are to be spliced in the following communication vaults: â€¢ CV2 (2 Splices): o Existing 12SM (CV1 to CV2), Blue Buffer Tube/Blue Fiber spliced to New 12SM (CV2 to CV4), Blue Buffer Tube/Blue Fiber o Existing 12SM (CV1 to CV2), Blue Buffer Tube/Orange Fiber spliced to New 12SM (CV2 to CV4), Blue Buffer Tube/Orange Fiber â€¢ CV4 (4 Splices): o New 12SM (CV2 to CV4), Blue Buffer Tube/Blue Fiber spliced to New 12SM Drop Cable (CV4 to 10th St CB1), Blue Buffer Tube/Blue Fiber o New 12SM (CV2 to CV4), Blue Buffer Tube/Orange Fiber spliced to New 12SM Drop Cable (CV4 to 10th St CB1), Blue Buffer Tube/Orange Fiber o New 12SM (CV4 to CV9), Blue Buffer Tube/Blue Fiber spliced to New 12SM Drop Cable (CV4 to 10th St CB1), Blue Buffer Tube/Brown Fiber o New 12SM (CV4 to CV9), Blue Buffer Tube/Orange Fiber spliced to New 12SM Drop Cable (CV4 to 10th St CB1), Blue Buffer Tube/Green Fiber â€¢ CV9 (4 Splices): o New 12SM (CV4 to CV9), Blue Buffer Tube/Blue Fiber spliced to New 12SM Drop Cable (CV9 to Pump Station), Blue Buffer Tube/Blue Fiber o New 12SM (CV4 to CV9), Blue Buffer Tube/Orange Fiber spliced to New 12SM Drop Cable (CV9 to Pump Station), Blue Buffer Tube/Orange Fiber o Existing 12SM (CV9 to 6th St CB1), Blue Buffer Tube/Blue Fiber spliced to New 12SM Drop Cable (CV9 to Pump Station), Blue Buffer Tube/Brown Fiber o Existing 12SM (CV9 to 6th St CB1), Blue Buffer Tube/Orange Fiber spliced to New 12SM Drop Cable (CV9 to Pump Station), Blue Buffer Tube/Green Fiber | Mike Coleman | 5 | 2025-02-24 13:01 | 2025-02-27 07:27
20250311 | 20250311013 | 13 | 678.0400 Fiber Optic Termination | Termination locations who is supplying the termination panels and what are the requirements for each panel if being supplied by Contractor splicing and terminating? NOTE: About 6 years ago WisDOT banned Undistributed quantities as they only need a quantity change approved by the Project. | Milwaukee County DOT â€“ Traffic Engineering (See General Notes, Sheet 3 for contact information) will supply the termination panel for the Fiber Optic Terminations at the Pump Station. The Fiber Optic Terminations at the 10th St Signal Cabinet (CB1) will be done to the existing termination panel in the cabinet. | Mike Coleman | 6 | 2025-02-24 13:03 | 2025-02-27 07:28
20250311 | 20250311013 | 13 | TRAFFIC CONTROL | Is it anticipated that traffic control equipment will be removed for the winter of 2025 then brough back in 2026? | Yes- it is anticipated that the traffic control equipment will be removed for the winter of 2025 and brought back in spring of 2026. The miscellaneous quantities for traffic control equipment coincide with that notion. The roadway needs to be clear for Ã¢â‚¬Ëœcurb-to-curbâ€™ snow plowing operations during the winter months. | Mike Coleman | 7 | 2025-02-25 11:12 | 2025-02-27 07:29
20250311 | 20250311013 | 13 | Undistributed Quantities | The common excavation item includes EBS, undistributed cut, and undistributed EBS totaling more than 30% of the total quantity. With so much uncertainty in the quantity the contractor will be forced to provide an unbalanced unit price. Please clarify what they designers intent was for including an undistributed quantity for nearly every bid item on the project. | We are removing all undistributed items from the Miscellaneous Quantities with an upcoming addendum but the item totals will largely remain unchanged. In regards to the EBS, we have encountered large amounts of poor subsoil on previous projects in the area, and we area anticipating that on this project as well. | Mike Coleman | 8 | 2025-03-04 13:29 | 2025-03-07 10:04
20250311 | 20250311013 | 13 | Concrete Surface Repair - Temp. Water Diversion | There appears to be more than 1' of sediment in the bottom of structure B-40-389. Will this need to be cleaned out in order to inspect for concrete surface repair areas, or will all the work be done above the sediment in the structure? | The intent of the project is to make concrete surface repairs above the sediment of the structure. | Mike Coleman | 9 | 2025-03-04 15:17 | 2025-03-06 07:19
20250311 | 20250311013 | 13 | Rubblized Existing Pavement | Please confirm the west bound side of the roadway is also rubblized. | Based on our observations during the extensive utility work along the westbound side of W. Rawson Ave, the existing pavement was NOT rubblized and will be paid for under Item 204.0100 â€œRemoving Concrete Pavementâ€. Utility trenches, from S. 13th St to S. Howell Ave, showed the concrete pavement was cracked but not rubblized. The existing typical sections will be revised accordingly in an upcoming addendum. | Mike Coleman | 10 | 2025-03-04 20:58 | 2025-03-06 07:20
20250311 | 20250311013 | 13 | Degree of Rubblization of the Existing Concrete Pavement | Please confirm the Existing Concrete Pavement was rubblized to the former specification sizes of 9 inches in the bottom half of the slab, 3 inches in the top half the slab, and 2 inches at the surface of the slab. Please provide a plan or map of the areas that were not rubblized to the degree provided above. | Based on our observations during the extensive utility work along W. Rawson Ave, the existing pavement was NOT rubblized and will be paid for under Item 204.0100 â€œRemoving Concrete Pavementâ€. Utility trenches, from S. 13th St to S. Howell Ave, showed the concrete pavement was cracked but not rubblized. The existing typical sections will be revised accordingly in an upcoming addendum. | Mike Coleman | 11 | 2025-03-04 21:22 | 2025-03-06 07:20
20250311 | 20250311013 | 13 | Confirm Pavement Removal will be paid when the existing pavement is rubblized. | Please confirm or deny the existing pavement on this project will be paid as Pavement Removal. The existing concrete pavement is shown as being rubblized. We are asking this question due to concern the rubblized concrete pavement will not be paid as pavement removal and only paid as common excavation. | Based on our observations during the extensive utility work along W. Rawson Ave, the existing pavement was NOT rubblized and will be paid for under Item 204.0100 â€œRemoving Concrete Pavementâ€. Utility trenches, from S. 13th St to S. Howell Ave, showed the concrete pavement was cracked but not rubblized. The existing typical sections will be revised accordingly in an upcoming addendum. | Mike Coleman | 12 | 2025-03-04 21:25 | 2025-03-06 07:20
20250311 | 20250311013 | 13 | cored holes | what underdrain is to be connected to the 40 units of Cored Holes 6 Inch? | No underdrain will be installed with the project, therefore, the Cored Holes 6-Inch bid item will be removed from the project in an upcoming addendum. | Mike Coleman | 13 | 2025-03-05 12:40 | 2025-03-07 10:10
20250311 | 20250311013 | 13 | TRAFFIC CONTROL DEVICES | TC equipment count in miscellaneous quantities should be reviewed. Stage 2A/2B and 3A/3B has equipment qtys doubled for the same stage duration. Can this be reviewed and corrected? | The traffic control equipment was reviewed and found to be accurate across all construction stages. Traffic control equipment is paid by calendar days, not working days. No corrections will be required. | Mike Coleman | 14 | 2025-03-06 12:47 | 2025-03-07 15:27
20250311 | 20250311013 | 13 | Undistributed Concrete Pavement qty | What was the designers intent in providing +5,000sy of undistributed concrete pavement? Can additional locations be provided, where this quantity might be used? Thank you, | An addendum was issued to remove the undistributed quantities. | Mike Coleman | 15 | 2025-03-06 13:55 | 2025-03-07 10:43
20250311 | 20250311013 | 13 | Further Clarification of Call Order 13. | Can WisDOT confirm that Pavement Removal will be paid as the plan provides where the plan calls out the existing pavement to be removed? Call Order 13 is not entirely clear to us, and we ask that this issue be made 100% clear. | An addendum was issued to remove the undistributed quantities. | Mike Coleman | 16 | 2025-03-06 14:11 | 2025-03-07 10:43
20250311 | 20250311013 | 13 | Concrete Pavement 10 Inch Quantity | ON Sheet 197 of the plan set Misc quantities it shows a quantity of 5020 SY Undistributed under the Concrete Pavement 10-inch item. What is the designers intention for this additional quantity of 10" Concrete Pavement? Is this to be used for patching or extension of Pavement limits? Or is this a error in the quantities listed? | An addendum was issued to remove the undistributed quantities. | Mike Coleman | 17 | 2025-03-06 15:00 | 2025-03-07 10:43
20250311 | 20250311013 | 13 | 301.0331 31" Curb & 602.0410 5" Concrete Sidewalk | These items include an undistributed quantity of 3,802 LF & 5,756 SF, or 17.5% and 7.5% of the bids items. Please provide a location for these quantities as it is impossible to provide accurate pricing when the method of placement and location are unknown at the item of bid due to the high value. Please clarify. | An addendum was issued to remove the undistributed quantities. | Mike Coleman | 18 | 2025-03-06 15:45 | 2025-03-07 10:43
20250311 | 20250311013 | 13 | 205.0100 Common Excavation | This item includes an undistributed quantity of 6765 CY, or 13.9% the bid item. Please clarify the intend of this undistributed quantity - it is listed under CUT and not EBS. | An addendum was issued to remove the undistributed quantities. | Mike Coleman | 19 | 2025-03-06 15:57 | 2025-03-07 10:43
20250311 | 20250311014 | 14 | 3MT lift thickness | The planned lift thickness for 3MT 58-28 S asphalt (item #60) is 1.75". This is below the minimum of 2.25" in WisDOT specs. Will the mix type be changed to 4MT 58-28 S? Or lift thickness changed? | The mix type will be changed to 4MT 58-28 at the same thickness (1.75â€). Changes to the proposal book/plans will be made â€“ if possible, we would like to wait to include other clarifications/questions. | Mike Coleman | 1 | 2025-02-11 13:10 | 2025-02-20 06:52
20250311 | 20250311014 | 14 | Alternate | Will you accept an alternate to the TAPCO RRFB system? | Alternate equipment which meets the project specifications will be accepted. | Mike Coleman | 2 | 2025-02-14 10:13 | 2025-02-20 06:53
20250311 | 20250311014 | 14 | Marking Speed Hump Epoxy 12-inch | There are 2 lines items for Marking Speed Hump Epoxy 12-inch. One is for each and the other is for lineal feet. Why is that? | Item SPV.0060.10 Marking Speed Hump Epoxy 12-Inch (White) EACH â€“ This Item is only for the Arrow portion of the Marking Item SPV.0090.05 Marking Speed Hump Epoxy 12-Inch (White) LF â€“ This Item is for all the individual transverse lines leading up to the Arrow | Mike Coleman | 3 | 2025-02-14 14:01 | 2025-02-20 07:31
20250311 | 20250311014 | 14 | 678.0200 Fiber Optic Splice Enclosures | 1. What vaults will the Fiber Optic Splice Enclosures 678.0200 be located in? | There are Communication Vaults shown on the Proposed Lighting Plans at or near each Signal Cabinet locations. This Pay Item will change to SPV.0060.XX. | Mike Coleman | 4 | 2025-02-24 12:50 | 2025-02-28 06:57
20250311 | 20250311014 | 14 | 678.0300 Fiber Optic Splices | How many Fiber Optic Splices 678.0300 are required in each Splice Enclosures? | There will be 6 Fiber Optic Splices at each intersection and the Pay Item will change to SPV.0060.XX. This will require the quantity to increase to 30 and will also require that an additional Pay Item SPV.0060.XX be added (6-CT Fiber Optic Cable Connector 100-FT) to each intersection. There will also be a Plan Sheet for this item of work. | Mike Coleman | 5 | 2025-02-24 12:51 | 2025-02-28 06:57
20250311 | 20250311014 | 14 | 678.0300 Fiber Optic Splice | How are the splices to be configured (buffer tubes and colors)? | The splices will be configured using buffer tubes and colors. | Mike Coleman | 6 | 2025-02-24 12:52 | 2025-02-28 06:58
20250311 | 20250311014 | 14 | 678.0300 Fiber Optic Splice | Is the Fiber being spliced to an Active fiber run? | The Fiber run is all new and there are no connections to active fiber runs. | Mike Coleman | 7 | 2025-02-24 12:53 | 2025-02-28 06:58
20250311 | 20250311014 | 14 | 678.0400 Fiber Optic Termination | What cabinets are the Fiber Optic Terminations 678.0400 to be completed in? | The Terminations will be in the Signal Cabinets via the 6-CT Fiber Optic Connector Cable 100-FT which is being added to the Bid Items. | Mike Coleman | 8 | 2025-02-24 12:54 | 2025-02-28 06:58
20250311 | 20250311014 | 14 | 678.0400 Fiber Optic Termination | Does the Fiber contractor supply the Termination panels? | The contractor will furnish and Install the Termination Panels at each intersection. This will be an updated Pay Item SPV.0060. XX | Mike Coleman | 9 | 2025-02-24 12:55 | 2025-02-28 06:58
20250311 | 20250311014 | 14 | 678.0400 Fiber Optic Termination | How many Fiber Optic Termination 678.0400 are required at each location? | There will be 1 Fiber Optic Termination Panels at each intersection. This will require an additional Pay Item to be added (6-CT Fiber Optic Cable Connector 100-FT) to each intersection. There will be an updated Pay Item SPV.0060. XX and Interconnect Plan Sheet for this item of work. | Mike Coleman | 10 | 2025-02-24 12:55 | 2025-02-28 06:59
20250311 | 20250311014 | 14 | 678.0501Communicaiton System Testing | Are you asking for a Communication System Testing 678.0501(OTDR) be completed for each location? Or, did you mean (1) for the span? | Communication testing will be completed at each intersection. There will be an updated Pay Item SPV.0060. XX | Mike Coleman | 11 | 2025-02-24 12:56 | 2025-02-28 06:59
20250311 | 20250311014 | 14 | 678.06 | Who suppling the Ethernet switches and SPFâ€™s? 678.0600 | Contractor Supplying and Furnishing. There will be an updated Pay Item SPV.0060. XX for both of these items and Plan Sheet for this item of work. | Mike Coleman | 12 | 2025-02-24 12:57 | 2025-02-28 06:59
20250311 | 20250311014 | 14 | Asphaltic Surface Temporary | Other than the misc. quantities on sheet 238, there is no indication where the 510 tons of asphaltic surface temporary will be used. The layout sheets 28-42 show it in the legend but not on the plan itself. Where is this to be placed and in what stage(s) of work? | The Temporary Asphalt will be used for bridging the elevation difference at the raised intersections prior to final asphalt pavement being placed. This will be used at the end of Stage 1 and Stage 2. | Mike Coleman | 13 | 2025-02-25 10:08 | 2025-02-28 07:00
20250311 | 20250311014 | 14 | HMA Staging | Is the intent of the staging to not pave permanent HMA until 2026? For clarification, the only HMA to be placed in 2025 is the temporary asphalt to bridge the raised intersections thru the winter of 2025-2026? | Correct. Temporary HMA at the raised intersections will be placed in 2025. Permanent HMA will be placed in 2026. | Mike Coleman | 14 | 2025-03-03 14:03 | 2025-03-05 06:20
20250311 | 20250311014 | 14 | 4MT oil and final quantity | An earlier question was answered regarding changing the 3MT mix to 4MT due to lift thicknesses. The plans/proposal call for 58-34 S oil for the current 4MT item. Will this also be changed to 58-28 S? Once changed, will item #62 become "HMA Pavement 4MT 58-28 S" with a quantity of 7,740 tons? | This Item is being resolved through an Addendum and will be modified to 4 MT 58-28 S (Not 4 MT 58-34 S). The total quantity will be 7,740 Tons. | Mike Coleman | 15 | 2025-03-04 08:39 | 2025-03-05 06:43
20250311 | 20250311014 | 14 | Milling depth | Is the intent of the asphalt milling item to remove 3.5"? Or will there be variable depth milling? There are a few stretches shown on the plan and profile pages where the new finished surface is below existing (ie: Sta 269+50 to 271+50). | The intent is to variable depth mill the roadway from outside to inside at the cross slopes provided in the Cross Sections. The milling begins on the curb flange (EOP) of the 36-inch curb and gutter towards the median. The area that was specifically cited in the question is actually in the bike lane where all pavement will be removed and replaced with new. | Mike Coleman | 16 | 2025-03-04 10:02 | 2025-03-05 06:44
20250311 | 20250311015 | 15 | Pavement Stockpiling, Crushing/Recycling on project | Will the stockpiling of concrete & asphalt rubble for the purpose of crushing into project aggregates be permitted on the project footprint? | Material stockpile information is provided in Article 15. Please see Article 15 for detail. | Mike Coleman | 1 | 2025-03-03 15:36 | 2025-03-07 10:13
20250311 | 20250311015 | 15 | Design |  |  |  | 2 | 2025-03-06 07:25
20250311 | 20250311015 | 15 | Design Schedule | Please provide the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/ov21p49eor5qv9pzztxb4bshy4cds5ck or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-03-06 07:27 | 2025-03-07 10:17
20250311 | 20250311015 | 15 | Staging. | Would WisDOT consider allowing the project to start after the 4th of July and combining stages 1 and 2. This would be much more efficient and cost effective. | The intent is to complete Stage 1 prior to July 4th to minimize or avoid construction disturbances to the Zoo during summer as much as possible, therefore combining stages 1 and 2 will not be allowed. The project area is an integral part of the staging for the 4th of July parade and fireworks traffic. We also looked at several options of construction staging to accommodate the 4th festivities and the only version that allowed for completion of the project within a calendar year was the option presented in the plan. | Mike Coleman | 4 | 2025-03-06 07:28 | 2025-03-07 10:22
20250311 | 20250311015 | 15 | Soils Report | Can the soils report be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ov21p49eor5qv9pzztxb4bshy4cds5ck or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 5 | 2025-03-06 07:29 | 2025-03-07 10:19
20250311 | 20250311015 | 15 | Lighting Materials | To have the street lighting completed by 6/27 is not possible with the lead times on the T-bases. What are we doing to get Main Street opened with lighting without these items by 6/27 so there is no LDs? | WisDOT does not recognize a shortage in transformer bases at this time. Contractors are to adhere to the project completion date in the proposal unless directed otherwise by the Department. | Mike Coleman | 6 | 2025-03-10 09:35 | 2025-03-10 13:35
20250311 | 20250311018 | 18 | EBS | Per the miscellaneous qtys there is a borrow item and an 1 1/4" DGB item to fill the undistributed EBS. Which item is to be used? | It is anticipated that borrow will be placed up to the adjacent base at the EBS locations and then BAD would match what is currently on the project on top of the borrow. | Mike Coleman | 1 | 2025-03-03 09:00 | 2025-03-04 13:29
20250311 | 20250311018 | 18 | Traffic Control | With all of the pipe crossings and potential EBS, shouldn't this road be at least "Closed to through Traffic" to provide a safer work zone for the contractors and travelling public? It would also provide savings to the Department as every operation would not need flagging. | The project is not signing a detour, so it is planned to construct the project under flagging operations and keep the project open to traffic. | Mike Coleman | 2 | 2025-03-03 09:04 | 2025-03-04 13:28
20250311 | 20250311018 | 18 | EBS- 2 | Shouldn't this be at the bare minimum a select borrow? Per the standard specs, borrow is a broad range of materials that could be used. "Suitable borrow" may not be "suitable" after it is wet but would pass the borrow spec. and in most cases would never be used in this application. Most projects similar to this scope use select crushed, breaker run, or 1 1/4" DGB to backfill the void. | The material needs to meet the specifications for borrow. Base aggregate dense is anticipated to be used on top of the borrow to match adjacent pavement structure and is included in the bid items. | Mike Coleman | 3 | 2025-03-05 10:25 | 2025-03-07 10:20
20250311 | 20250311018 | 18 | Traffic Control 2 | This question is a follow up to question 2 and has 2 entries in bidx due to the size of the questions(s): 1.There are no barricade, drums, light, PCMS etc items in the contract. Wouldnâ€™t the Department want staggered Type 3 barricades at each intersection to slow traffic and let the travelling public know there is work ahead? 2.Per the plans, when contractors are milling the 4-5 of existing asphalt, there will be a drop off. Contractors could â€œsquare upâ€ at the end of the day, but how are contractors supposed to protect their workers and the travelling public under only flagging operations of an open to traffic roadway w/ 5" dropoffs? 3.Per the plans, contractors are supposed to mill off the asphalt, proofroll, and potentially EBS. This operation, based on the quantities, will take multiple days. Is it anticipated for live traffic to run on the existing base with no delineation for an extended period? | 1. Traffic control will follow the SDD that were included in the plans. 2. For the end of the day, see standard spec 104.6.1.2.3. "Eliminate vertical drop-offs greater than 2 inches and edge slopes steeper than 3:1 between adjacent lanes open to traffic." During construction, see standard spec book 104.6.1.2.1. "Delineate and shield abrupt drop-offs and other hazards." "Work required solely to accommodate the contractor's means and methods is incidental to the contract." 3. Live traffic will need to run on the existing base during proof rolling prior to paving. | Mike Coleman | 4 | 2025-03-05 13:38 | 2025-03-07 10:21
20250311 | 20250311018 | 18 | Traffic Control 2 Continued | 4.After binder, there is no temporary pavement marking or delineation in the contract for open to traffic conditions. Wouldnâ€™t the Department want temporary delineation between binder and surface operations? 5.There is no time frame for culvert work. Is the intent to fill the trench with 1 ï¿½â€ DGB until patching can occur and simply put bump signs? The way this project is to be built puts an unnecessary liability on the Department and Contractor, is costly to the County/Department and as it reads now does not protect on-site staff and the public. The cheapest/safest solution would be to "Close the road to thru traffic", add additional traffic control measures, and add reasonable time frames to close the road for culvert/EBS work. | 4. Temporary pavement marking is not anticipated. 5. See the detail for culvert replacements in the plan. It is anticipated that culvert replacements will take place prior to milling. | Mike Coleman | 5 | 2025-03-05 13:42 | 2025-03-07 10:22
20250311 | 20250311019 | 19 | Grubbing clarification | The bid item listed is grubbing 94 ID, however in the special provisions, #3 Prosecution and progress, at the very bottom of that section it states "the department has contracted with others and will perform the following operations: cutting down, removing, and GRUBBING trees." Usually grubbing means stumps- not sure what it means in this case?.? | The advanced contract by others will include cutting down and removing the trees. The grubbing will be done by 20250311019. That line in prosecution and progress should be edited to remove the reference to grubbing. | Mike Coleman | 1 | 2025-02-27 10:19 | 2025-03-03 12:28
20250311 | 20250311019 | 19 | TRAFFIC CONTROL & DETOUR PLAN | Do these plans currently exist or are we to assume that they will need to be created for the Kenosha County permit process? | The detour sheet can be found at the following location: https://wisdot.box.com/s/d20ytuxegwd6zechwstpdhfp09nn38oi or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-03-07 12:32 | 2025-03-10 13:38
20250311 | 20250311020 | 20 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/5k5q3d7obd38l9qxjp9v4yi2mtyfzw0g or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 08:46 | 2025-02-19 06:57
20250311 | 20250311020 | 20 | PEDESTRIAN PUSH BUTTONS, ITEM 658.0500 | Will Campbell Co. MOAB push buttons, which are on the WisDOT QPL, be accepted as an approved equal for this project? | The City of Kenosha prefers to use the Polara Enterprises LLC, Bulldog III Series Vandal Resistant ADA Compliant Push Button as shown in the Special Provisions. This product is used throughout the city at signalized intersections and the City prefers use of this item for consistency and continuity. | Mike Coleman | 2 | 2025-02-17 14:00 | 2025-02-24 06:12
20250311 | 20250311020 | 20 | Soils Report | Can the Soils Report be provided? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/5k5q3d7obd38l9qxjp9v4yi2mtyfzw0g or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-03-06 14:13 | 2025-03-10 07:04
20250311 | 20250311021 | 21 | Guardrail Quantities | Is it possible to get a 'per corner' breakdown for the MGS Guardrail quantities on this project? The quantities in the plan aren't matching up to the SDD requirements for lengths of these bid items. | A discrepancy was found related to the guardrail and will be fixed in a future addendum. | Mike Coleman | 1 | 2025-02-18 11:31 | 2025-02-24 06:14
20250311 | 20250311021 | 21 | Utility conflicts | The plan and specifications indicate that the AT&T Wisconsin pedestal at station 12+59, 44 RT will be adjusted to finish grade. The pedestal appears to be in conflict with the temporary shoring and excavation required to construct the SW wing of B-51-162. Does the "adjustment" include moving the pedestal out of conflict prior to construction and then moving the pedestal back after the wing construction? Additionally, the plans and specifications do not indicate that the overhead WE Electric lines will be moved at all. In order to maintain OSHA safe clear distances to install the plan temporary shoring and driven SW wing piles of B-51-162 the overhead lines need to be moved. Can all of the overhead lines be moved prior to construction and if not when can the contractor expect for the lines to be moved perform the work? |  |  | 2 | 2025-03-01 10:09
20250311 | 20250311021 | 21 | Guardrail Addendum Follow-Up | With the addendum, the SW corner has no MGS Thrie Beam Transition listed. Does the MGS Short Radius get connected to the bridge railing? If so, is there a detail available for how to connect to the new bridge railing on this corner? |  |  | 3 | 2025-03-06 13:11
20250311 | 20250311022 | 22 | Additional Working Days | Because of the large amount of crack sealing on the projects is it possible to allow for more working days? Assuming the crack sealing needs to be done prior the the Protective Surface Treatment application, we would need to allow time for the Crack Sealing material to dry before the Protective Surface Treatment was applied. | WisDOT will not be adding working days to this contract. Based on prior work performed by the WisDOT Maintenance Unit via County crews, WisDOT has experience with typical bridge deck crack sealing drying times and production rates for the items in this contract. The approved products for these items also indicate fast drying times. The contract time for this project was based on conservatively higher drying times and conservatively lower production rates than what have typically been achieved in the field by County crews. | Mike Coleman | 1 | 2025-03-04 09:06 | 2025-03-05 14:09
20250311 | 20250311023 | 23 | Geotech Report | Can you make the geotech report availavble for this project? looking for the borings that show the excess topsoil in the median. | No soil borings were completed for this project, but soil probes were taken to determine locations and depths of soft soils and rock. The soil probe work for the soft median soils is explained on the bottom of page 3 of the projectâ€™s soils report. The soils report can be viewed at the following link: https://wisdot.box.com/s/chfwvkrm9hi5g89c3jfdnlye937vhdd9. Also, rock depth information is noted in blue on the preliminary plan at the following link: https://wisdot.box.com/s/chfwvkrm9hi5g89c3jfdnlye937vhdd9. | Mike Coleman | 1 | 2025-02-27 09:37 | 2025-03-03 12:47
20250311 | 20250311023 | 23 | Aggs Conversion | What conversion factors were used for the 1.25" Base, the 3/4 Inch Base and the Select Crushed materials for this project? | Conversion factors used for determining quantities for the 1-1/4â€ base, 3/4â€ base, and select crushed materials are as follows: â€¢ 305.0110 Base Aggregate Dense 3/4-Inch => 2.0 Tons/Cubic Yard â€¢ 305.0120 Base Aggregate Dense 1 1/4-Inch => 2.0 Tons/Cubic Yard â€¢ 312.0110 Select Crushed Material => 1.9 Tons/Cubic Yard | Mike Coleman | 2 | 2025-02-27 09:39 | 2025-03-04 06:53
20250311 | 20250311023 | 23 | SPV 15 - Shallow Rock | Please consider removing SPV 15 or clarifying that excavation of rock is not incidental to Excavation Common or pipe installation which is in line with the Standard Specs. | An addendum will be issued to remove the second sentence of Article 15. The contract includes the bid item of Storm Sewer Rock Excavation, and roadway excavation will be classified according to standard specification 205. Excavation of rock is incidental to other items unless the contract says it will be paid for as extra work. | Mike Coleman | 3 | 2025-03-04 13:12 | 2025-03-05 10:46
20250311 | 20250311024 | 24 | Guardrail Timing | Article 4 states the 5 days or noon on Friday scheduling for guardrail. For the locations at Fisk Ave and at Ripple Ave, does the Department assume the curb and gutter will be removed and replaced with the existing guardrail in place or was it assumed that the new guardrail will be installed before the curb and gutter replacement? | Contractor question involves means and methods, and WisDOT is unable to dictate contractor means and methods for these types of situations. WisDOT will only enforce the contract requirements under Article 4 that requires new guardrail and terminals to be installed within 5 calendar days or before noon on Friday after removing existing guardrail. | Mike Coleman | 1 | 2025-02-19 09:26 | 2025-02-20 10:15
20250311 | 20250311025 | 25 | Miscellaneous Quantities - EBS | Note (3) EBS Excavation is anticipated in the existing ditchline. To be backfilled with select borrow material. It further says this is designers choice, can be backfilled with borrow, or cut as well. Note (7) says EBS to be backfilled with Breaker Run. Can you please verify EBS backfill and/or payment intentions? | An addendum will be issued to clarify the backfilling of EBS. | Mike Coleman | 1 | 2025-02-27 10:48 | 2025-03-03 06:40
20250311 | 20250311025 | 25 | Topsoil | Would the department consider converting the section 625 Topsoil item to section 625 Salvaged Topsoil? | Salvaged topsoil is acceptable for bid item 625.0100 provided it meets the required specifications. Additional topsoil may be necessary for areas where salvaging is not feasible. Please use the bid items included in the current documents. | Mike Coleman | 2 | 2025-02-27 12:17 | 2025-02-28 09:49
20250311 | 20250311026 | 26 | schedule | Contractor is request a copy of the initial design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/snpj77x89kd7d2rnwuc5jyo5lmwyrs1j or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-17 11:33 | 2025-02-18 07:02
20250311 | 20250311026 | 26 | 96 hour surface restriction | The common ex quantity is 14,100 cy. Sheet 14 of the miscellaneous quantities states that the quantity is undistributed. The common ex quantity will need to be completed after milling. Due to the potential amount of unknown, undistributed work that has to be completed after milling and prior to the construction of the final surface within the restriction is unattainable. Could this restriction be removed from the special provisions? | There are some areas of thin pavement, and the intent of the special provisions is to protect the milled surface from prolong traffic on such a thin layer of asphalt. Work with the engineer on timeframes needed in construction at the EBS locations. An addendum will be issued to clarify locations where EBS will be more likely and update quantities to better reflect the anticipated work. | Mike Coleman | 2 | 2025-02-20 14:25 | 2025-02-28 06:55
20250311 | 20250311026 | 26 | Soil Borings | Has soil borings/cores been performed on the project to determine the areas of EBS? Can that information be provided to bidders? What are the EBS dimensions in terms of the road lengths anticipated (100 feet long, 1000 feet long, etc)? | The Soil boring information can be found at the following location: https://wisdot.box.com/s/snpj77x89kd7d2rnwuc5jyo5lmwyrs1j or can be accessed on the HCCI March bid letting page under Supplemental Information. The assumptions for the EBS quantity were: â€¢ 20% project length = (5.07 miles)(5280ft/mile)(0.20) = 5,350 ft â€¢ Depth = 2â€™ below 23â€ subgrade of reconstructed pavement section â€¢ XS Area = 71 sf â€¢ Volume = (5,350 ft)(71 sf)(1/27) = 14,100 CY | Mike Coleman | 3 | 2025-02-21 09:00 | 2025-02-25 07:27
20250311 | 20250311028 | 28 | Soil Borings | Are there any soil borings that were done in the design process that could be shared with potential bidders ?? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/eooipwt5smjn89t4yyyrtrng21zj6qq4 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-02-13 11:38 | 2025-02-17 13:16
20250311 | 20250311028 | 28 | integral curb | The specials discuss WPS electric moving the new poles from Sta 100+00 to 120+90 between the back of curb and the sidewalk on the west side of the road. The terrace in this area is shown to be 3' wide from Sta 100+00 to 116+50. It appears that the new poles will be in conflict with integral pavement clearance. If there is not at least 2' from the back of curb to the poles will integral curb be required? | Integral curb will be required, an addendum will be issued to address this. | Mike Coleman | 2 | 2025-02-17 12:15 | 2025-02-20 10:11
20250311 | 20250311028 | 28 | Sanitary and Water Lateral Replacement | Per article 6 of the special provisions, the City of Green Bay sanitary and water laterals are being replaced. Who is replacing the laterals? When will the laterals be replaced? Are all the laterals going to be replaced to fix all conflicts with the proposed storm sewer work? | The City of Green Bay replaced all sanitary and water laterals in 2024. The roadway contractor is required to replace one sanitary lateral at Station 133+65LT in conjunction with the storm sewer as shown in plans. | Mike Coleman | 3 | 2025-02-28 13:19 | 2025-03-03 12:52
20250311 | 20250311028 | 28 | Storm Sewer Televising | According to page 188 of the Green Bay Specification, the storm sewer is required to be televised and the City of Green Bay pays for the televising work. Is the storm sewer going to be televised on this project? Is the City of Green going to pay for the televising on this project? There is not a bid item for televising the storm sewer on this project. | The storm sewer is to be televised and an addendum will be created to clarify. | Mike Coleman | 4 | 2025-03-05 16:27 | 2025-03-07 10:12
20250311 | 20250311028 | 28 | Underground retention system SPV 0060.10 | IS the only information in the contract as defined in special provision article 26 which starts on page 19 of 29 and plan sheet 17? | Page 16 of the plan has a detail of the underground retention system. | Mike Coleman | 5 | 2025-03-09 09:13 | 2025-03-10 08:49
20250311 | 20250311028 | 28 | Storm Laterals | Miscellaneous quantities and special provisions both refer to SPV 0060.15 Reconnect storm sewer Laterals starting on page 23 of 29. Did this item get overlooked on the bid form and will we still get paid this item as a change order because this item was overlooked? | This bid item was missed and will be added by a change order post let. Bid plans and specials accordingly. | Mike Coleman | 6 | 2025-03-09 09:18 | 2025-03-10 09:43
20250311 | 20250311029 | 29 | Geotechnical Report for Structure R-70-07 | Will a geotech report be made available for this structure? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/f2ir79bsyosl7hs00ui3bvhrk0mc47vx or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-02-28 12:15 | 2025-03-03 12:24
20250311 | 20250311031 | 31 | Department Design Schedule | Can the department's construction schedule used in design be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/5l40tmdaviag0sf1ssx7jlnwubmoh688 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-18 13:04 | 2025-02-20 06:51
20250311 | 20250311031 | 31 | Lane Shift Item | Due to the depth of the pipes at STA 146+40, 164+18 and 189+10 and the fact that these pipes have to be replaced under flagging operations we fill that item of Temporary Lane Shift has to be created for each location for the safety of the traveling public and contractors' crews. | Response to question #2: We believe the question actually intends for the three identified locations to be STA 146+40, STA 165+18, and STA 183+10 where the culvert replacements involve deeper excavation. After reviewing these locations, we concur that item 208.1500.S Temporary Lane Shift During Culvert Work would be appropriate. An addendum will be forthcoming to include this item at those three locations. | Mike Coleman | 2 | 2025-02-27 16:35 | 2025-03-03 12:42
20250311 | 20250311031 | 31 | STH 91 Open To Through Traffic, Culvert Asphaltic Surface | Would the department consider allowing the culverts that are completed while STH 91 is open to through traffic, to be paved withing 72 hours, rather than at the end of each day? |  |  | 3 | 2025-03-04 15:15
20250311 | 20250311032 | 32 | Median Barrier Wall | Are there any as built drawings or original construction details showing the dimensions of the median barrier walls? What is the distance from the toe of the barrier to the edge of the PCC pad it sits on? | The as-builts can be found at the following location: https://wisdot.box.com/s/iwle8yei5opqneay8md6q86ugyoj23kc or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-02-27 10:00 | 2025-03-03 12:31
20250311 | 20250311032 | 32 | SMA | Does the department want to consider using HT asphalt in lieu of SMA in the area where the High friction surface treatment will be going down? Placing the treatment over the SMA takes away from some of the benefits SMA provides and the HT mix will be a lower cost. It may also impact the amount of epoxy needed on the high friction surface treatment as the SMA has more voids to fill | The Region has confirmed with BTS that the project should proceed with the SMA as shown in the plans. | Mike Coleman | 2 | 2025-03-03 11:08 | 2025-03-04 06:52
20250311 | 20250311033 | 33 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/kyii1yqu2717afs19a595mm676k3iifv or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-13 08:47 | 2025-02-17 08:53
20250311 | 20250311033 | 33 | Traffic Control | Would the department look at a different option for traffic control that might save money? | Traffic Control plan will remain as shown. Please bid accordingly. | Mike Coleman | 2 | 2025-02-18 07:20 | 2025-02-18 07:21
20250311 | 20250311033 | 33 | Barrier System Grade Shape Finish | It appears this bid item in the MQs is now including the silt fence and temporary ditch checks as incidental to item 614.0010. In the SS for 614.0010, these items are not included for payment. Can the Department either create an Article in the Specials to state what is included for payment under 614.0010 or put these two items in the quantities for their respective bid item? | An addendum will be issued to put these items in their respective bid items, not incidental to item 614.0010. | Mike Coleman | 3 | 2025-02-19 12:11 | 2025-02-24 06:09
20250311 | 20250311033 | 33 | Paver | will a concrete paver be required to be used on the concrete pavement work? | Bid according to the requirements in section 415 of the Standard Specifications, slip-form work that is 300 feet or more in length, a minimum of 10 feet in width or greater, and a constant width. | Mike Coleman | 4 | 2025-03-01 09:51 | 2025-03-03 12:57
20250311 | 20250311033 | 33 | Removing Asphaltic Surface | The MQ's include a quantity of Removing Asphaltic Surface for the Spruce Street / Maple Road Ramp. However, there is Excavation Common in this area. Please remove the bid item for Removing Asphaltic Surface if it is within the limits of Excavation Common. | An addenda will be issued to update these quantities. | Mike Coleman | 5 | 2025-03-03 08:30 | 2025-03-05 10:49
20250311 | 20250311033 | 33 | West End Cross Over Removal | The Earthwork Items table in the MQ's does not have a corresponding table in the Earthwork Data or Cross Sections. Please provide both and confirm the quantity of 2760 cy. | An addenda will be issued that includes an earthwork table. | Mike Coleman | 6 | 2025-03-03 08:39 | 2025-03-05 10:51
20250311 | 20250311034 | 34 | schedule | Contractor is request a copy of the initial design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/zzent56l2h9tpfattclyrmvwqvdh1eaa or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-17 11:34 | 2025-02-18 07:04
20250311 | 20250311035 | 35 | Pedestal Push Button | Will the pushbutton on the 3.5' pedestal pole on the west side of the street be hardwired to the control box on the trombone pole nearest it? | Yes, the pushbutton on the west side of the street is to be hardwired to the control box on the trombone pole nearest it. The item Conduit Special is included, and paid for separately, to provide a conduit connection under the southbound STH 13 travel lanes (see plan page seven). | Mike Coleman | 1 | 2025-02-14 10:21 | 2025-02-17 12:51
20250311 | 20250311036 | 36 | Finished Pavement Typical Section | The finished typical sections at the bottom of Sheet 7 and also on Sheet 8 show a driving lane pavement structure of 2.5" 4MT58-28S over 3.5" of 3MT58-28S. The typicals also show the 3' and 4' paved shoulder as 6" of 4MT58-28S. The Asphalt Quanitites tabulation on Sheet 24 seems to support a 2.5" 4MT58-28S over 3.5" 3MT58-28S for the entire pavement section (driving lane and shoulder). Can the department clarify the pavement structure for the paved shoulders. | We will be issuing and addenda which will change the Typical Sections to show the shoulder having the same pavement structure as the lanes. | Mike Coleman | 1 | 2025-02-18 11:06 | 2025-02-20 07:29
20250311 | 20250311036 | 36 | 1 1/4" base | Please clarify if the 1 1/4" base item is to cover the placement of the material salvaged under the 204.9180.S item and not to provide offsite base? The typicals show salvaged material in the widening areas and 1 1/4" base. |  |  | 2 | 2025-03-07 10:25
20250311 | 20250311037 | 37 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/badaoao35gufarxazxriac6lykl245i3 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-18 09:07 | 2025-02-20 06:48
20250311 | 20250311037 | 37 | 1 1/4" in driveways | Per the misc. quantities, sheet 105, there is 1,535 ton of 1 1/4" being placed in the driveways and field entrances. The only excavation shown is removal of blacktop, with no common excavation quantity. There is not a detail shown for driveway work in the plan. Please clarify what we are to construct at the drives requiring the large quantity of base. | See SDD 08D22-01, sheet #31 of the "71" ID plan set. | Mike Coleman | 2 | 2025-02-18 13:23 | 2025-02-20 06:54
20250311 | 20250311037 | 37 | Driveway excavation | In follow up to the previous question, how will the excavation for the base and asphalt be paid for? There is easily 800cy plus of excavation to make room for the base alone. | The design intent is to top-off driveways to address profile raise only, and not fully reconstruct them. Excavation at driveways will not be required. We will put together and submit an addendum with a driveway construction detail that reflects design intentions better than the SDD and updated base aggregate quantities. | Mike Coleman | 3 | 2025-02-20 10:38 | 2025-02-25 07:15
20250311 | 20250311037 | 37 | Asbestos Mitigation | Can you post the asbestos report for this project? | The Asbestos Report can be found at the following location: https://wisdot.box.com/s/badaoao35gufarxazxriac6lykl245i3 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 4 | 2025-02-26 05:45 | 2025-02-26 05:47
20250311 | 20250311037 | 37 | Sawcut at Butt Joints | On sheet 5 of the plan set for project ID 9876-00-71, the butt joint detail shows that a sawcut is required but that any sawcut used is incidental to the Removing Asphaltic Surface Butt Joint item. If the contractor uses a small mill to cut a clean 3.5â€ deep joint, will a saw cut be required? If a sawcut is still required, can the department add this quantity to the existing Sawing Asphalt item? | A sawcut is required as stated in the construction detail. The cost of the sawcut is included in the bid item Removing Asphaltic Surface Butt Joint. It will not be added to the Sawing Asphalt item and paid for separately. | Mike Coleman | 5 | 2025-02-27 08:15 | 2025-02-28 08:16
20250311 | 20250311037 | 37 | Clearing | Can the department please clarify on the added clearing item in Addendum No. 1. Is it still to be done by others like stated in the SPVs. | The County will cut the trees and leave them on site. The contractor is responsible for clearing the felled trees and grubbing. | Mike Coleman | 6 | 2025-02-28 11:05 | 2025-03-03 12:19
20250311 | 20250311039 | 39 | N-55-2 Wall Plans | Are the general plan and borings shown in the plans for the existing N-55-2 wall and not the proposed extension? | Additional information will be provided for the proposed N-55-02 extension via an addendum. | Mike Coleman | 1 | 2025-02-06 13:57 | 2025-02-17 08:40
20250311 | 20250311039 | 39 | Geotech Reports for Noise Wall Founations | Will the geotech reports for walls N-55-2, N-55-3, and N-55-4 be made available for review? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/rmnq3oahumeyjsu1nl0enmnkyafctjej or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-02-28 14:47 | 2025-03-03 12:40
20250311 | 20250311039 | 39 | Noise Wall Aesthetics | On all 3 walls - on the Elevation and Aesthetic Details sheet - They have a note for the panel Color: No Color. Surface Texture Shall be Natural Stone to Match Existing Nose Wall When looking at the Existing wall, the color of the Existing Concrete Texture is pretty light in color. Crest Precast concrete texture color will be more Gray. Not sure if over the years the wall has cured out and gotten lighter. Just want clarification on if Crest Gray Concrete Texture color will be OK or if we will need to stain the panels to match. | No stain is preferred. The intent was to match the existing wall panel color in that it had no color when it was first built. | Mike Coleman | 3 | 2025-03-04 13:57 | 2025-03-05 14:08
20250311 | 20250311039 | 39 | Lane/Ramp Closures | Will lane or ramp closures be allowed at all? ie. material delivery, guardrail installation, etc | No. Ramps or lanes shall not be closed. Shoulder closures are allowed, however. | Mike Coleman | 4 | 2025-03-05 13:50 | 2025-03-06 07:22
20250311 | 20250311039 | 39 | Noise Barrier Post Spacing | The plans call for post spacing of the noise wall to be 12' (typ). Precast fabricator has a standard panel size (design and fabrication) of 15' wide. Please confirm that 15' standard panels can be used in lieu of the 12' post spacing shown on the plans. Stamped calcs/plans will be submitted to confirm the design meets the intent of the specifications. |  |  | 5 | 2025-03-07 12:26
20250311 | 20250311039 | 39 | Access for Noise Walls | Industry standard for building noise walls includes building a 30â€™ wide access road as a work platform for the drillers, material delivery, and panel setting. Walls N-55-02 and N-55-03 are adjacent to existing culvert pipes (STA 12+60 H for N-55-02 & STA 17+60 H for N-55-03) and ditches that would need to be backfilled to get access to the walls. Please confirm this is acceptable. If not, what methods were anticipated to provide access for the wall installations? |  |  | 6 | 2025-03-07 14:14
20250311 | 20250311040 | 40 | 0408. SPV.0060 Special 03. Temporary Support B-3-16 | B-3-16 Temp Deck Support: Please confirm purpose/design intent of Temp Deck Support. If a system was designed to support the deck and only attached to Girder #3, would that be allowable (ie. Does some of the loading need to transfer to Girder #2 to share the load?) Please confirm Girder #3 has been checked for this scenario. Please provide Design Calculations that were used to determine the need for a Temporary Deck Support. This would ensure bidders have all the information and not put design responsibilities on the contractor to figure out during the short bid process. | Girder #3 has been analyzed to support the staged deck construction. The temporary support for the deck may be provided from a support system attached to Girder #3. Lateral bracing at the bottom of the girder to resist torsion from a deck overhang bracket would need to be reviewed and designed by the contractor based on the temporary support design. Design calculations will not be provided. | Mike Coleman | 1 | 2025-02-14 13:53 | 2025-02-20 10:11
20250311 | 20250311040 | 40 | 0410. SPV.0060 Special 04. Temporary Support B-3-18 | B-3-18 Temp Deck Support: Please provide Design Calculations that were used to determine the need for a Temporary Deck Support, and Calculations to prove the concept shown in the plans is adequate. Question on the design concept shown in plans: how do you ensure load share between girders #2 & #3 during the different sequences (Deck Removal & Deck Pour) of Stage 1 Construction. For example, Girder #3 will deflect during state 1 deck pour, while Girder #2 will not. This will create a gap between the existing deck and the temp support beam. The opposite will be happen during the deck removal, when you will induce extra load into the temporary support beam. Is this the intent of the design and has it been considered when checking the concept? Additional Diaphragms may be necessary between Girders #2 & #3 to adequately support the load. This will take drilling or welding to the existing structure and could potentially impact the longevity and bridge rating of the structure. Please consider designing and including details for the Temporary Support, so these discussions could take place prior to bid. | The temporary support requirement to spread the deck overhang support between Girders #2 and #3 is based on a low load rating for Girder #2 if the deck overhang in the first stage is supported entirely by Girder #2. The varying deflection conditions during the different construction operations is acknowledged and must be addressed by the contractorâ€™s temporary support system design. The temporary support design needs to include connections to the bottom of the deck and at the existing diaphragms as needed. Design calculations will not be provided. There is approximately 16 inches of clearance between the bottom of existing deck and the top of diaphragms. Based on structural analysis of the support concept shown in the staging plan, there is adequate clearance to fit a suitable temporary support beam that can span between the existing diaphragms. Additional temporary diaphragms are not anticipated, but if the temporary support design developed by the contractor requires additional diaphragms, the proposed location and connection will be reviewed by WisDOT. | Mike Coleman | 2 | 2025-02-14 13:55 | 2025-02-20 10:12
20250311 | 20250311040 | 40 | 0414 SPV.0060.06 Temporary Support B-3-30 | B-3-30 Temp Deck Support: Please provide Design Calculations that were used to determine the need for a Temporary Deck Support, and Calculations to prove the concept shown in the plans is adequate. Question on the design concept shown in plans: how do you ensure load share between girders #2 & #3 during the different sequences (Deck Removal & Deck Pour) of Stage 1 Construction. For example, Girder #3 will deflect during state 1 deck pour, while Girder #2 will not. This will create a gap between the existing deck and the temp support beam. The opposite happens during the deck removal, when you will induce extra load into the temporary support beam. Is this the intent of the design and has it been considered when checking the concept? Additional Diaphragms may be necessary between Girders #2 & #3 to adequately support the load. This will require core drilling through the existing girder and could potentially impact the longevity and bridge rating of the structure. Please consider designing and including details for the Temporary Support, so these discussions could take place prior to bid. | The temporary support requirement to spread the deck overhang support between Girders #2 and #3 is based on a low load rating for Girder #2 if the deck overhang in the first stage is supported entirely by Girder #2. The specific design and methods to achieve this are to be developed by the contractor in accordance with the specifications. Rather than a continuous beam the length of the bridge, the overhang support could be provided by blocking on joists spanning transversely between Girders #2 and #3. Design calculations will not be provided. | Mike Coleman | 3 | 2025-02-14 13:58 | 2025-02-20 10:13
20250311 | 20250311040 | 40 | SPV.0060.04 Temporary Support B-3-18 (Existing Deck) | B-3-218 (Existing Deck) Temp Deck Support: Please confirm purpose/design intent of Temp Deck Support. If a system was designed to support the deck and only attached to Girder #3, would that be allowable, or would the girder be over-stressed? Please provide Design Calculations that were used to determine the need for a Temporary Deck Support. This would ensure bidders have all the information and not put design responsibilities on the contractor to figure out during the short bid process. | The temporary support system for the existing deck can be attached to Girder #3 only. This condition was analyzed during the design process. Design calculations will not be provided. | Mike Coleman | 4 | 2025-02-14 14:01 | 2025-02-20 10:14
20250311 | 20250311040 | 40 | 0416 SPV.0060.07 Temporary Support B-3-218 (New Deck) | B-3-218 (New Deck) Temp Deck Support: Please confirm purpose/design intent of Temp Deck Support. If a system was designed to support the deck and only attached to Girder #4, would that be allowable, or would the girder be over-stressed? Please provide Design Calculations that were used to determine the need for a Temporary Deck Support. This would ensure bidders have all the information and not put design responsibilities on the contractor to figure out during the short bid process. | Temporary support of the new deck overhang is not required for the deck dead load but rather to support construction loading on the overhang. The overhang may be supported from a system attached to Girder #4 only. The designers anticipated the deck overhang brackets for Stage 1 deck construction could remain in place to support the overhang until the rest of the deck is constructed in Stage 2. Design calculations will not be provided. | Mike Coleman | 5 | 2025-02-14 14:03 | 2025-02-20 10:14
20250311 | 20250311040 | 40 | 0418 SPV.0060.08 Temporary Pier Support B-3-218 | B-3-218 Temp Pier Support: a note in the project specifications states: â€œContractor may design and submit alternative pier support system to department for review in accordance with standard spec 526.3.4â€. Can the Design Calculations for the temp support system in the plans please be provided? This would ensure bidders have all the information and not put design responsibilities on the contractor to figure out during the short bid process. | The standard spec referenced above should have been 526.3.3 which provides requirements for submitting temporary support designs to the Bureau of Structures for review. The intent of the note in the special provision is to allow the contractor to develop an alternative temporary support method, if desired. The plans include a temporary pier support system which can be bid as shown. Design calculations will not be provided. | Mike Coleman | 6 | 2025-02-14 14:05 | 2025-02-20 10:14
20250311 | 20250311040 | 40 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/lwr1d4uuhr949jbdt4du326tcmq6z568 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2025-02-14 14:08 | 2025-02-17 12:41
20250311 | 20250311040 | 40 | B-3-26 bearing removal | The bearings on the north abutment for B-3-26 appear to be epoxied to the girders. It looks like the existing bearings are to be re-used, is there any guidance on how they are to be re-attached to the girders? | An addendum will be issued with plan revisions to clarify that the existing bearings should remain in place. The fiber wrap will need to be notched and installed around the existing bearings. | Mike Coleman | 8 | 2025-02-20 12:02 | 2025-02-27 07:31
20250311 | 20250311040 | 40 | SPV.0060.04 Temporary Support B-3-18 | If the temporary support system is blocked tight the full length of the deck overhang as shown on B-3-18 sheet 3 of 17 will it overstress the permanent members during all phases of construction i.e. deck removal, deck pour etc.? | The general staging concept was analyzed to evaluate the permanent members of the bridge for transfer of the deck overhang loads (dead and live load) through the diaphragms to girder 3. The analysis did not include â€œall phases of constructionâ€ as requested in the question. The construction loading conditions are variable and must be accounted for in the contractorâ€™s design of the temporary support system. | Mike Coleman | 9 | 2025-02-25 16:20 | 2025-02-27 07:30
20250311 | 20250311040 | 40 | Geotech Report for Structure B-3-218 | Will the geotechnical report for structure B-3-218 be made available? |  |  | 10 | 2025-02-28 09:14
20250311 | 20250311040 | 40 | Pre-phase HMA Shoulder | The Pre-Phase HMA shoulder paving will be either removed during Phase 2, or used as a lower lift for the shoulder that will be surfaced during Phase 2. With the nature of the Pre-phase paving being widening patching and shoulder lower layer, would the DOT consider changing the mix type from 4MT58-34S to Asphaltic Surface (4MT 58-34S) for either the entirety of Pre-phase or at least the widening patching portion? | Mix type 4MT58-34S was selected based on the Regionâ€™s preference for density requirements since it will be subjected to traffic loading during the staged condition. Proceed per plan. | Mike Coleman | 11 | 2025-03-02 15:51 | 2025-03-06 07:01
20250311 | 20250311040 | 40 | CTH I Asphalt Mow Strip | The asphalt mow strip area on CTH I, Sheet #17 shows that common will be used to build up the area. Will there be any improvements to the subgrade prior to paving such as adding CABC or was the expectation to pave over "Excavation Common Material"? | An addendum will be issued to clarify that Base Aggregate Dense 3/4-Inch is required within the CTH I median at Guardrail Mow Strip Emulsified Asphalt and Guardrail Mow Strip Asphalt areas. | Mike Coleman | 12 | 2025-03-02 16:11 | 2025-03-06 07:11
20250311 | 20250311040 | 40 | HMA Type | The typical sections on Sheets #6 & 7 show the lower layer mix as a 1.25â€ 5MT 58-34V and the upper layer mix as 1.75â€ 4MT 58-28S. Confirming this is what was intended and wanted. | Proceed per plan as this is consistent with the design intent. (Note: The upper layer will eventually be milled an overlaid as part of a separate future roadway resurfacing project.) | Mike Coleman | 13 | 2025-03-02 16:15 | 2025-03-06 07:06
20250311 | 20250311040 | 40 | Notice to Contractor, Electronic Load Tickets: 509.2500 Concrete Masonry Overlay Decks | Will the Department accept load tickets printed onsite during batching from the Concrete Masonry Overlay Mobile Mixer Trucks? | Electronic Load Tickets are required per Article 13 of the Special Provisions. The contractor can fill out an e-Ticketing Exemption Process (DT1373) form providing reasoning why electronic ticketing cannot be provided per the contract, and what the contractor can provide to the department to document payment for bid items that require measurement and payment by weight. The exemption form provided by the department must be submitted to the project team for review and acceptance prior to incorporating the bid items into the work. | Mike Coleman | 14 | 2025-03-03 09:26 | 2025-03-07 10:07
20250311 | 20250311041 | 41 | Structure Backfill Units + Borrow Item | Sheet 32 shows structure backfill quantities by the ton, however the proposal shows it by CY. Also, the earthwork breakdown in the MQ's show that borrow is needed. Should a borrow item be added? | Our intent was to utilize the structure excavation material for the shown 11 CY of borrow since it was such as small quantity therefore, we will not be adding an item for borrow since the fill material will already be onsite. An addendum will be issued to clarify. | Mike Coleman | 1 | 2025-02-17 10:25 | 2025-02-20 07:28
20250311 | 20250311045 | 45 | Soil Borings | Are soil borings available for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/4cfw8q73qqnhjwtrdkleny1abhfsyn1n or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-03-04 06:46 | 2025-03-04 13:06
20250311 | 20250311046 | 46 | Geo technical | Would the Geo technical reports be available to share? | A geotechnical report was not produced during the design phase. | Mike Coleman | 1 | 2025-03-04 06:47 | 2025-03-04 13:09
20250311 | 20250311046 | 46 | Common Excavation | Could the designer give more information concerning the common excavation? It's a pulverize and relay, which means the material stays in place. There's a special item to remove excess pulverized material, so the cut for common would not be that material. The profile doesn't seem to change. It is not clear where there is 873 CY of cut. Please advise. | The majority of the common is for the removal of the 4â€ of excess pulverized asphalt. There was a Salvaged Pulverized Material item originally in the plans but that was removed as part of Addenda 1 for this project. The quantity should be correct as shown. | Mike Coleman | 2 | 2025-03-06 16:14 | 2025-03-07 15:24
20250311 | 20250311047 | 47 | Base Aggregate 1 1/4-Inch | Can this quantity be verified? Is there any new 1 1/4-inch base being placed from 151+30 to 170+00? | The Base Aggregate Dense (BAD) 1 ï¿½-Inch quantity was reviewed, and will be corrected via an addendum. The placement of new BAD 1 ï¿½-Inch is limited to the guardrail replacement locations. These locations are STA 150+51 to STA 153+00 LT and STA 290+50 to STA 300+07 RT. | Mike Coleman | 1 | 2025-02-14 10:50 | 2025-02-20 06:55
20250311 | 20250311047 | 47 | Removals of Driveways | How are the removals at the driveways being paid since there is no â€œRemoving Asphaltic Surfaceâ€ Item and no quantities shown in the â€œRemoving Asphaltic Surface Butt Jointâ€ Item? | The existing driveway asphalt removal will be paid under the Removing Asphaltic Surface Milling item. | Mike Coleman | 2 | 2025-03-04 16:08 | 2025-03-07 10:13
20250311 | 20250311047 | 47 | Gaurdrail timing requirement. | Can the climbing lane from station 291+00 to 300+00 be barreled off/ closed and guardrail left down for more than a week while the curb and gutter work is being completed? | The climbing lane may be closed using SDD 15D20-09b (Traffic Control, Single Right Lane Closure, Undivided Non-Freeway/Expressway) and guardrail left down for more than a week to complete the curb and gutter work. | Mike Coleman | 3 | 2025-03-04 16:10 | 2025-03-07 10:11
20250311 | 20250311047 | 47 | Asphaltic Surface and Asphaltic Surface Patching. | What are the intended uses of the Asphaltic Surface and Asphaltic Surface patching items under this project? | These items are to supplement the Prepare Foundation For Asphaltic Paving item to cover any miscellaneous repairs needed after the surface mill and prior to the first HMA layer being placed. | Mike Coleman | 4 | 2025-03-04 16:13 | 2025-03-07 10:10
20250311 | 20250311047 | 47 | Lower Lift HMA | Would the DOT entertain changing the lower lift HMA Pavement to 4MT 58-28S? | No, WisDOT will utilize the binder mix per the project plans â€“ HMA Pavement 4 MT 58-34 V. | Mike Coleman | 5 | 2025-03-04 16:13 | 2025-03-10 07:46
20250311 | 20250311048 | 48 | Schedule | Can the department provide the anticipated schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/8j81eetwii95uywfsok0mt7tis9f0u00 or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-02-19 11:39 | 2025-02-20 10:09
20250311 | 20250311048 | 48 | Withdrawn Proposal 20250211017 Questions | Will the department be providing an addendum with the questions and answers that were previously asked for last month's Proposal 17 that was withdrawn? With those questions and answers be applicable to this re-posted proposal? |  |  | 2 | 2025-02-19 11:42
20250311 | 20250311048 | 48 | SOI Quantities | The proposal schedule of items quantities do not match the quantities in the plan set: ESTIMATE OF QUANTITIES, MISCELLANEOUS QUANTITIES or the TOTAL ESTIMATED QUANTITIES for structure B-40-548. Which ones are correct? | We have not identified any items that do not match, could you ask the contractor to provide a specific list of items that do not match? Please verify you have downloaded the updated proposal on the HCCI Site. | Mike Coleman | 3 | 2025-02-19 13:14 | 2025-02-24 06:11
20250311 | 20250311048 | 48 | Pictures of Existing Bridge Machinery | Are there any photos available of the existing conditions of the bridge machinery? If not, can a site visit be arranged to observe the bridge machinery? | Yes, a site visit can be arranged. Please contact Karen Forlenza, City of Milwaukee Bridge Operator Supervisor, at 414-286-3450 at least 2 business days before requested site visit. Proper PPE is required for all individuals to enter the pier areas of the bridge. And the contractor can find the pictures in the recent inspection folder in HSI. | Mike Coleman | 4 | 2025-02-19 14:31 | 2025-02-24 06:12
20250311 | 20250311048 | 48 | Heel Block Refurbishment - Alternative Shock Absorber | Will the state allow for an alternative shock absorber to the Jarret Shock Absorber #BC1C if alternative were to match dimensions and stroke distance? | The existing heel block should be refurbished. There is no need for an alternative new product to be considered. | Mike Coleman | 5 | 2025-02-20 11:33 | 2025-02-25 07:27
20250311 | 20250311048 | 48 | Bascule leaves permanent time closures | Does the DOT require the (8) weeks of closures to be concurrent? Will the DOT allow for the closure time be divided up into portions/segments if the timeframe/schedule doesn't conflict with special events? | The 8 (weeks) closure is participated to occur after the festivals, and holidays. Based on the schedule the closure doesnâ€™t conflict with the special events. | Mike Coleman | 6 | 2025-02-25 07:51 | 2025-02-28 09:50
20250311 | 20250311048 | 48 | Heel Block Refurbishment - Heel Block Components | Bid item #104 calls for the refurbishment of the heel block. The specials do not clearly define all components of the heel block and/or the limits of refurbishment. Can the Department clarify if the following pieces for each heel block are to be removed and refurbished and to what extent: - 10" diameter steel forging with acme threads - 18-3/8" square forged block with center hole and acme threads | An addendum will be issued to clarify. | Mike Coleman | 7 | 2025-02-27 09:46 | 2025-03-05 10:53
20250311 | 20250311048 | 48 | Location for required Office | Can the State allow for the project office trailer to be located in the concrete parking area or grassy area SW of the bridge? Currently the bridge tender is using one parking place for the City pickup truck, leaving space for a trailer. | The property at the southwest corner of the bridge where the bridge operator vehicle is typically parked is a private parcel. Interested contractors will need to coordinate with the private property owner to discuss access or storage options. | Mike Coleman | 8 | 2025-02-27 13:03 | 2025-03-03 06:38
20250311 | 20250311048 | 48 | Bridge Balancing | A bridge balancing item should be added to this project since all repairs are not replacing materials in-kind. | The bridge balancing item will not be added to this project. | Mike Coleman | 9 | 2025-02-27 14:48 | 2025-03-03 12:53
20250311 | 20250311048 | 48 | Heel Block Component Refurbishment-further information requested | To follow up on the previous question asked & answered; Previous question; Will the state allow for an alternative shock absorber to the Jarret Shock Absorber #BC1C if alternative were to match dimensions and stroke distance? Follow-up question; Can the DOT please give more guidance regarding what is expected for the refurbishment of the Jarret shock absorber? I'm been told & seen in writing that the OEM is stating a 40-50 week lead time for parts, pushing the overall completion date into spring of 2026. Thank you in advance | An addendum will be issued to clarify. | Mike Coleman | 10 | 2025-02-28 12:48 | 2025-03-05 10:53
20250311 | 20250311048 | 48 | SOI Quantities / Question #3 Above | The SOI quantities in the pdf proposal file for Prop 48 starting on pages 171-175 is for the previous let proposal 17 and is still labeled as proposal 17 with different quantities? |  |  | 11 | 2025-03-03 11:34