## qandasearchletting_results
Date | 2025-04-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250408 | 20250408005 | 5 | Prepare Foundation for Asphaltic Shoulders | If a mill is used for the prepare foundation for asphaltic shoulders item and a vertical edge is made, can the sawcut be eliminated? | A new vertical edge is required at the location of the saw cut as shown in the plans to remove the rolled edge on the existing bituminous pavement. Using a mill to create this vertical edge and removing the rolled edge bituminous pavement would be an acceptable option as a substitute of the sawcut. Applying tack coat to the new vertical edge is a requirement of either option. | Mike Coleman | 1 | 2025-03-21 15:28 | 2025-03-25 08:04
20250408 | 20250408007 | 7 | Railroad | Does the Contractor need Railroad insurance even though the rails have been removed from the road and discontinued? | During the design phase of this project the Department in coordination with the railroad company determined that railroad protective liability insurance coverage would be required for this project. | Mike Coleman | 1 | 2025-03-28 09:43 | 2025-03-31 06:49
20250408 | 20250408007 | 7 | Asphalt removal | Pages 44-62 show saw cutting and asphalt pavement removals. However, there is no asphalt removal item in the miscellaneous quantities other than milling. Are we to remove this asphalt to construct the curb. If so, how will this removal and replacement be paid? | An addendum will be issued to add Removing asphaltic surface. | Mike Coleman | 2 | 2025-04-01 16:24 | 2025-04-03 07:05
20250408 | 20250408007 | 7 | Asphaltic Surface | Per SPV 17, the Department is requiring a 4 MT in the distressed patches. 87% of the mix on the project is a 4 LT. In order to eliminate unneeded costs, would the Department consider getting rid of this SPV and revert it back to the Standard Spec.? | Please bid the items the way they are presented in the plan and special provisions. Any proposed changes can be discussed with construction staff during the project. | Mike Coleman | 3 | 2025-04-03 13:12 | 2025-04-04 15:17
20250408 | 20250408008 | 8 | Available Documents | Can you provide available documents listed in SPV 10, SPV 17 and design schedule. | All files from article 10 can be found at the following location: https://wisdot.box.com/s/m0btnfkdxr00hvx6b5d5eov6j6hjcq5z or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-03-27 09:46 | 2025-03-31 08:50
20250408 | 20250408008 | 8 | Seaside Crowfoot Survey | Prosecution and Progress note for structures B-40-304, B-40-305 and B-40-322 that work under the structure cannot begin until a rare species survey have confirmed that the seaside crowfoot is not present. Who is completing this survey? When can/will this survey be completed? IF found, what is the anticipated timeline for an incidental take authorization and would the additional BMPs be compensated as a change order or under existing bid items? | The department has coordinated a plant survey to be completed (by others) by June 15th. In the event seaside crowfoot is found (low risk): -The contractor would avoid areas where the population is present. Work on B-40-304 and B-40-305 is anticipated be completed next year. -If impacts are unavoidable, the department would submit an incidental take authorization to the WDNR. In most cases it takes about two weeks to get comments and address those before it gets published for a 30-day public notice. Following the public notice, DNR will issue the authorization to move forward with the proposed action, which would include relocating plants prior to contractor disturbance. -While the public notice is in its 30-day comment period, the department would move forward with the relocation of the plants (by others). -If impacts are avoidable, the contractor would need to fence off these areas to ensure no accidental disturbance. These areas could be fenced off with the orange safety fence. This would be compensated as a change order, if needed. | Mike Coleman | 2 | 2025-04-01 14:28 | 2025-04-04 07:13
20250408 | 20250408008 | 8 | Utility Work Durations | Under Utilities article for project 1100-05-73, it is noted that various utilities will be performing work during and in coordination with the project. No durations for working day windows are outlined. This could allow for no claim against a utility delay under current specification 108.10.3. Were durations for utility work included in their work scope? | Please refer to Addendum 1 and Addendum 2 for revisions to the Utility article, including durations. | Mike Coleman | 3 | 2025-04-01 14:29 | 2025-04-02 13:48
20250408 | 20250408008 | 8 | Wetland Access | SPV 22, Notice to Contractors â€“ Temporary Impact to Wetlands, notes that access to listed locations will require timber matting or access when the ground is frozen. Accessing during frozen ground contradicts limitations for ground disturbance during RPBB nesting season between 10/10 and 4/10. Will access when ground is frozen be allowed? | We want to avoid impacts to foraging and nesting habitat impacts during the overwintering period. Overwintering is not known to occur in wetlands, bees overwinter under leaf litter in closed canopy wooded areas so the wetlands would not be considered suitable habitat. With this said, access when the ground is frozen is allowed in areas of unsuitable habitat such as wetlands and areas where the trees have been cut down this winter by the tree clearing contract. This was addressed in addendum #03 | Mike Coleman | 4 | 2025-04-01 14:30 | 2025-04-04 09:38
20250408 | 20250408008 | 8 | Rapid Set Patch | SPV 68 states to furnish a product from the APL for â€œRapid Setting Concrete Patch Materials.â€ This list expires 4/4/25. Please confirm if we will be required to furnish a product from the new â€œHorizontal Rapid Set Concrete Patch Materialâ€ list. | WisDOT is going to suspend the expiration until after the April 8 letting. | Mike Coleman | 5 | 2025-04-01 14:31 | 2025-04-02 14:06
20250408 | 20250408008 | 8 | Removing Concrete Pavement Item | The plans have 1200 SY of removing concrete pavement, but no concrete pavement item for pouring them back in. Is a concrete pavement item missing or is the 1200 SY of removing concrete pavement unnecessary | This was addressed in addendum #03 | Mike Coleman | 6 | 2025-04-02 12:38 | 2025-04-04 09:38
20250408 | 20250408008 | 8 | Special 002. Special Concrete Joint Repair | The special provisions refer to a detail in the plans, it appears that this construction detail has been missed. Please adivse. | This was addressed in addendum #03 | Mike Coleman | 7 | 2025-04-02 13:56 | 2025-04-04 09:53
20250408 | 20250408008 | 8 | B-40-303 Slope Paving | For structure B-40-303 in regards to slope paving, the existing fence is embedded in the slope paving that is proposed to be removed and replaced. There is no scope of work in the contract to address the fence in order to complete the slope paving work. Existing fence appears to be in poor condition. |  |  | 8 | 2025-04-04 14:43
20250408 | 20250408008 | 8 | Concrete Repair | Due to lack of Concrete Masonry Overlay Decks, DOT is utilizing Concrete Masonry Bridge for repair type work (i.e. curb repair and column jacket). Contractor is looking for confirmation that DOT would view the scope of this work as â€œrepair workâ€ and allow for use of concrete grade C and/or 100% passing 1â€ sieve mix if situations warrant (502.2.2 and 501.2.7.4.1). This is being asked due to interpretations of high early strength concrete in superstructures or what is considered structure repairs. |  |  | 9 | 2025-04-04 14:45
20250408 | 20250408009 | 9 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/hx4wxjcfwbur6dni8acbwe3vhfkb62kw or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-03-27 08:57 | 2025-03-27 12:21
20250408 | 20250408009 | 9 | Noise Wall Panel Supply | In speaking to the precast concrete industry, current production schedules do not have enough available space for all the panels for this project to be produced in time to meet the Stage 1 and 2 interim completion dates as set forth in the prosecution and progress. Will the department adjust interim completion dates due to the known industry wide shortage of materials or allow for adjustment of scope of work required to be completed in the 2025 interim completion windows and allow for contractual calendar days to carry into the 2026 season? | Interim completion dates will be removed via addendum. | Mike Coleman | 2 | 2025-03-27 17:10 | 2025-04-02 07:50
20250408 | 20250408009 | 9 | Geotech Reports for Noise Walls | Can we obtain a copy of the geotech reports for all 3 noise walls? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/hx4wxjcfwbur6dni8acbwe3vhfkb62kw or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-03-31 14:36 | 2025-04-02 06:15
20250408 | 20250408009 | 9 | Midday Closures | Are there designated times that "midday closures" are allowed in stage 3? | The allowable times for â€œmidday closuresâ€ have been added as part of Addendum 2. | Mike Coleman | 4 | 2025-04-01 09:02 | 2025-04-03 06:58
20250408 | 20250408009 | 9 | Entrance ramp from S. 60th St. | In the MQ's sheet 77, Traffic Control Detour Items, list a 20 day closure of the entrance ramp from S 60th St to the EB I-894. I was not able to find a detour plan showing what will be required during this closure. Can you supply a detour plan for the closure of the S 60th St entrance ramp? | The Traffic Control Detour Items to close the 60th Street entrance ramp in Stage 2 have been revised to 10 days. Refer to Addendum 2. These ramp closures are intended to be used for interim nighttime closures only as needed during Stage 2 for items such as setting or removing temporary barrier, delivering noise barrier panels, setting noise barrier panels, etc. The detour plan should follow S.D.D. 15C02-09d. | Mike Coleman | 5 | 2025-04-01 10:16 | 2025-04-03 06:59
20250408 | 20250408010 | 10 | Top Flange cleaning and coating | Can the department specify the measurements of the top flange cleaning and coating? Is it the whole length of the bridge of each girder or just the end 6ft on these as well? | The measurements for Preparation and Coating of Top Flanges B-51-0064 is to the top surface and edges of the top flanges within the joint repair areas. | Mike Coleman | 1 | 2025-04-01 14:10 | 2025-04-02 13:30
20250408 | 20250408011 | 11 | Small Animal Fence | There is a conflict between the construction detail (sheet 15) and SPV description for Small Animal Fence. The detail calls shows an independent fence with vinyl coated fabric on steel posts with a fence cap. The SPV calls for 304 welded stainless steel woven wire fabric tied onto the existing woven wire fence. Please advise if the small animal fence will be vinyl coated on steel posts with a cap or if it will be tied on to existing fence. | An addendum will be issued to clarify. | Mike Coleman | 1 | 2025-03-25 10:28 | 2025-04-01 07:08
20250408 | 20250408011 | 11 | Soil Boring Information | Can you make the Soil Boring Information available for the CTH A & CTH J roundabout project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/qgijzd3vi657h68guq418ln6wmxohcr2 or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-04-02 11:37 | 2025-04-04 09:49
20250408 | 20250408011 | 11 | Addendum #1 Removing Utility Pole | We want to verify that the utility company is going to remove the pole added to addendum #1. All of the poles in that area on the drawing are utility-owned. | This pole is not a utility pole. It is owned by Racine County and previously supplied power to flashing beacons. We Energies will remove the electrical connection, but the pole itself will remain and need to be removed as part of this project. | Mike Coleman | 3 | 2025-04-03 08:53 | 2025-04-04 15:16
20250408 | 20250408012 | 12 | 643.0910 and 643.0920 Quantities | Please review the quantities for items 643.0910 Traffic Control Covering Signs Type 1 and 643.0920 Traffic Control Covering Signs Type 2. It appears that the quantity was calculated as "Days" instead of as "Each". The Type 1 quantity should be (2) and the Type 2 quantity should be (39). Thanks | Yes, your are correct. If you keep EACH as units, you have calculated the correct sign quantities, 2 EACH Ty 1 sign coverings and 39 EACH Ty 2 sign coverings. An addendum will be issued to correct. | Mike Coleman | 1 | 2025-03-28 13:20 | 2025-04-01 07:15
20250408 | 20250408013 | 13 | Street Name Sign Brackets | Several of the 'Erecting State Owned Signs' are street name signs that are being mounted either on top of Stop Sign posts or banding a bracket on new poles. I can't find a detail for what style of bracket is required for each of these situations. Will the City of Kenosha be providing these brackets for installing these signs? | The Erecting State-Owned Signs Type II bid item only applies to the â€œNo Parking During Snow Emergencyâ€ signs. Street name signs are quantified under the Signs Type II Reflective H bid item. The City of Kenosha will not provide brackets for street name signs. For numbered street signs, the City typically uses a 16â€ metro wing L bracket. For street name signs mounted above stop signs, the City standard is an 18â€ cross bracket. In both instances, the City would want the brackets to be â€œrawâ€ material and not black or powder coated. Brackets and mounting hardware are incidental to the sign bid items. | Mike Coleman | 1 | 2025-03-24 10:02 | 2025-03-28 09:32
20250408 | 20250408013 | 13 | Breaking Pavement | SPV 28 states a multi-head hydraulic hammer is allowed unless a structure is located within 50 feet of the roadway. All the existing houses are within 50' of the roadway. How are Contractors allowed to break the pavement? Please consider revising or removing this SPV. | The contractor will determine means and methods for removing and breaking existing pavement. Article #28 will be removed via addenda. | Mike Coleman | 2 | 2025-03-26 07:43 | 2025-03-26 14:32
20250408 | 20250408013 | 13 | Soil Borings | Please provide a copy of the soil borings. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/m5bmvim3gi3fuvcpm2cywkh6gsy0qptg or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-03-26 08:56 | 2025-03-27 07:35
20250408 | 20250408013 | 13 | Design Schedule | Please provide the Design Schedule. |  |  | 4 | 2025-03-29 11:24
20250408 | 20250408015 | 15 | Electrical Equipment Lead Times | The project being let in April and a completion date of August 29th, it is very doubtful that the the poles, arms and especially Transformer bases will arrive in time. The Department has been made aware that lead times on these items are long, T Bases are at 28 months or so. How is this going to be handled? Will Liquidated damages be charged if the equipment does not arrive in time. | An addendum will be created to clarify this situation. | Mike Coleman | 1 | 2025-03-12 11:05 | 2025-03-17 12:43
20250408 | 20250408015 | 15 | Semi Traffic in the Roundabout | How is the equipment transport company that hauls with a four axle tractor and a nine axle trailer expected to maneuver through this RAB? Was this considered in the design? | Thank you for your question. Bid the plan as shown. | Mike Coleman | 2 | 2025-03-19 09:01 | 2025-03-25 08:00
20250408 | 20250408015 | 15 | Select Borrow | Select Borrow is supposed to have a SPV with the material specifications. There is no SPV for Select Borrow. Please clarify. | An addendum will be created to clarify. | Mike Coleman | 3 | 2025-03-24 12:15 | 2025-03-26 08:27
20250408 | 20250408015 | 15 | Salvaged/Unusable Pavement Material | The Earthwork Table in the MQ states that Salvaged / Unusable Pavement Material is included in the cut. However, the quantity provided appears to be entire quantity of existing pavement material, even when some of the existing pavement material is located in a fill area. For example, the RAB is located in a fill and states that 445 cy of pavement is located in the cut of 85 cy. Please verify the existing pavement quantities located in the cut or if the Department is intending to pay Common Excavation for removing pavement in fill areas. | Salvaged/unusable pavement material includes concrete pavement removal. Concrete pavement removal is paid under Removing Concrete Pavement, 204.0100. | Mike Coleman | 4 | 2025-03-25 08:39 | 2025-03-27 09:17
20250408 | 20250408015 | 15 | 643.5000 Item Missing | Item 643.5000 Traffic Control is not included with the bid items for this project. Can this be added on? | An addendum will be created to clarify. | Mike Coleman | 5 | 2025-04-01 09:25 | 2025-04-02 14:07
20250408 | 20250408015 | 15 | Removing Concrete pavement | Per 204.4 (4) the department will make no deductions from the volume measured under the excavation bid item for pavement removed under the Removing Concrete Pavement bid item. It seems like the areas of concrete pavement where it is in the excavation has been removed from the excavation volume and the plan is not following the Wis Dot standard specification. Please clarify. | No deduction was made for Removing Concrete Pavement from the Excavation Common item in cut areas. There is no payment for Excavation Common in locations where concrete pavement is in fill areas. In the fill locations the contractor is only paid for Removing Concrete Pavement and either Borrow or Base Aggregate Dense to bring the ground up to subgrade. | Mike Coleman | 6 | 2025-04-01 17:37 | 2025-04-02 14:07
20250408 | 20250408015 | 15 | Construction Staking Concrete Pavement - Missing | There is no item for Construction Staking Concrete Pavement. Could this item be added? |  |  | 7 | 2025-04-07 11:46
20250408 | 20250408016 | 16 | Symbol Epoxy/Paint | The proposal and miscellaneous quantities say 646.5205 Marking Symbol Paint. The plan drawing on page 125 shows Marking Symbol Epoxy (white) for the handicap symbols. Which one is it supposed to be? | The symbol should be epoxy. An addendum will be submitted to add the correct bid item to the contract. | Mike Coleman | 1 | 2025-03-14 14:28 | 2025-03-19 07:52
20250408 | 20250408016 | 16 | Curb Patching | Is the curb patching going to be 2' or 4' wide? Page 5 & 6 of the plans contradict on the width. | Curb patching to be 4â€™ wide per the finished typical section on p. 5 of the plans. Quantities already reflect the 4â€™ width. | Mike Coleman | 2 | 2025-03-31 13:24 | 2025-04-01 07:52
20250408 | 20250408016 | 16 | Drainage Inlets | I do not see an item for adjusting inlets in the new curb? Is this incidental? | The item was added in addendum #02. | Mike Coleman | 3 | 2025-04-02 17:06 | 2025-04-04 09:41
20250408 | 20250408018 | 18 | Special Provision Discrepancies | It appears that the special provisions are for a different project. Can you please update to be specific for STH 111? | The correct special provisions have been added to the online proposal. Please re-download the proposal. https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2025/20250408.aspx | Mike Coleman | 1 | 2025-03-12 12:18 | 2025-03-17 12:29
20250408 | 20250408018 | 18 | Highway Work Proposa | Could the department upload the correct Highway Work Proposal for the job. It appears to be for job # 12 not # 18. | The correct special provisions have been added to the online proposal. Please re-download the proposal. https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2025/20250408.aspx | Mike Coleman | 2 | 2025-03-13 09:38 | 2025-03-17 12:41
20250408 | 20250408018 | 18 | Detour Duration/Base Patching | The MQ's show 21 days for the detour under Traffic Control Items, but the proposal shows 12 consecutive calendar days: Can you specify which is correct? In addition, can you provide a construction detail for the Base Course Patching? | Traffic Control: The closure is allowed for up to 12 consecutive calendar days as noted in the Special Provisions. All traffic control items are dailky items which will be counted/paid for in the field depending on contractor schedules. Totals in the MQ's are conservative. Base Patching: The Region does not have a typical construction detail for base patching and a project specific detail is not needed for this project. | Mike Coleman | 3 | 2025-03-18 10:45 | 2025-03-21 05:42
20250408 | 20250408018 | 18 | Asphalt Base Patching Partial Depth Question | Could the department clarify why the language in the Proposal Special Provision (21. Asphaltic Base Patch Partial Depth, Item SPV.0180.01) states "Patch with asphaltic mixture and consolidate the mixture in two layers. Do not exceed a 2 1/2 inch thickness for any layer." when Spec 460.3.2 states for both No. 4 & No. 5 mixes that the Max Lower Layer Thickness is 3 inches? Would the department consider changing this language to "not exceed 3 inches" for efficiency purposes and due to the fact that it will be milled afterwards? Also, could the department please specify a minimum width for these patches? Mills come in 2ft, 4ft, 5ft, 7ft, 8ft, 10ft, and 12ft widths and we want to make sure we are bidding accordingly. Lastly, if two lifts are needed and pending the answer the width of the patches, would the department consider adding 5 Working Days to the contract? | 1. Yes, this can be updated to improve efficiency for this project. Updated Specifications will remove note requiring two lifts and note that any lift can be 3" max. 2. No change or clarification, fit to field conditions and means and methods. 3. No change to timing for this project will be made. | Mike Coleman | 4 | 2025-03-31 16:02 | 2025-04-02 13:35
20250408 | 20250408018 | 18 | Asphaltic Base Patch Partial Depth - Special Provisions Language | Would the department please consider changing the following language in B Materials from "Use an asphaltic surface mixture... that meets the requirements for HMA Pavement Type MT or greater" to "Use an asphaltic surface mixture... that meets the requirements for HMA Pavement Type LT or greater". The mix type we are paving with on the project is a 4 LT and in Proposal 20250408019 in the same area of the Special Provisions for that project states "HMA Pavement Type LT or greater." for the same type of work. |  |  | 5 | 2025-04-02 16:10
20250408 | 20250408019 | 19 | Asphalt Base Patch Partial Depth Question | Could the department clarify why the language in the Proposal Special Provision (21. Asphaltic Base Patch Partial Depth, Item SPV.0180.01) states "Patch with asphaltic mixture and consolidate the mixture in two layers. Do not exceed a 2 1/2 inch thickness for any layer." when Spec 460.3.2 states for both No. 4 & No. 5 mixes that the Max Lower Layer Thickness is 3 inches? Would the department consider changing this language to "not exceed 3 inches" for efficiency purposes and due to the fact that it will be milled afterwards? Also, could the department please specify a minimum width for these patches? Mills come in 2ft, 4ft, 5ft, 7ft, 8ft, 10ft, and 12ft widths and we want to make sure we are bidding accordingly. Lastly, if two lifts are needed and pending the answer the width of the patches, would the department consider adding 5 Working Days to the contract? | 1. Yes, this can be updated to improve efficiency for this project. Updated Specifications will remove note requiring two lifts and note that any lift can be 3" max. 2. No change or clarification, fit to field conditions and means and methods. 3. No change to timing for this project will be made. | Mike Coleman | 1 | 2025-03-31 16:03 | 2025-04-02 13:47
20250408 | 20250408020 | 20 | Lane Closure Schedule | Can we get clarification on the lane closure schedule? Are single lane closures allowed on EB outside of the designated 3L times? When are single lane closures allowed on WB, the 3L line is blank? | During the Pre-Stage work in 2025 one EB and one WB lane can be closed during night work which is anticipated to be between 6:00 pm and 5:00 am. For Stage 1, Stage 2, Stage 3, and Stage 4 in 2026 WB traffic can be reduced from 3 lanes to two lanes. EB traffic is to have 3 lanes maintained. The I94 Peak Hour table in the Traffic Section of the special provisions shows when additional lanes can be closed (during non-peak times). A new I94 Peak Hour table will be added by Addendum. | Mike Coleman | 1 | 2025-03-07 10:03 | 2025-03-17 11:00
20250408 | 20250408020 | 20 | As-builts | Are the bridge as-builts available for download? | The as-built structure plans for both bridges can be downloaded from the WisDOT Highway Structures Information System (HSI). https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/strct/hsi.aspx | Mike Coleman | 2 | 2025-03-12 12:03 | 2025-03-17 11:16
20250408 | 20250408020 | 20 | Completion Date | Are the project completion date and dates listed in the Prosecution and Progress correct? | Dates in the Prosecution and Progress are correct. The Pre stage work is to be completed in the 2025 construction season. Work must begin before September 2, 2025 so that it can be completed before any cold-weather asphalt restrictions. The remainder of the work will be completed in the 2026 construction season starting in April and being completed by October 31, 2026. An addendum will be issued to correct the contract completion time. | Mike Coleman | 3 | 2025-03-14 06:38 | 2025-03-17 12:06
20250408 | 20250408020 | 20 | Slope Paving Repair - B-55-61 | Is the slope paving repair shown on page 204 of the plans on the MN side? All of the concrete slope paving will be replaced on the WI side? | Structure B-55-61 and R-55-29 are replacing all of the slope paving on the east end of the structure on the WI side. Structure B-55-61 has slope paving repair called out on the west abutment on the MN side as well. The detail on page 204 shows the anticipated slope paving repair area on the MN side. This detail also shows the standard detailing for the overall slope paving that would be used on the WI approach as well. | Mike Coleman | 4 | 2025-03-14 09:43 | 2025-03-19 07:47
20250408 | 20250408020 | 20 | Curb and Shoulder Work - WB IH 94/SB WI 35 On Ramp | When does the temp widening get removed and the curb installed for the WB on ramp? Will that ramp get closed to install the curb? | Special provisions are being modified via an Addendum that will include language on when this final work can be done on the WB on-ramp. | Mike Coleman | 5 | 2025-03-14 10:58 | 2025-03-18 07:52
20250408 | 20250408020 | 20 | Light Pole at EB Sta 651 RT | This light pole is only about 11' from the back of the retaining wall. The plans show the shoring to be installed on the north side of the light pole. Is removing and reinstalling the pole and it's base incidental to the retaining wall? | Based on the wall height at this area, it is anticipated that the light pole should be outside of the estimated excavation area required for the tie-backs / geogrid of the wall. It is however close. As part of an upcoming Addendum for the project, an additional piece of Temporary Shoring is being added immediately south of the light pole to protect the base. | Mike Coleman | 6 | 2025-03-14 11:02 | 2025-03-19 07:48
20250408 | 20250408020 | 20 | Retaining Wall As-Builts | Are there As-Builts for the existing retaining wall? | Existing retaining wall plans for R-55-21 are available on the Wisconsin DOT Highway Structures Information System (HIS) website for this structure. https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/strct/hsi.aspx | Mike Coleman | 7 | 2025-03-19 07:18 | 2025-03-19 09:58
20250408 | 20250408020 | 20 | MSE Wall Construction | From the back of the existing wall to the abutment, there is about 10' of room. The As-Builts of the bridges show the lower abutment footing to extend 1'9" in front of the abutment beam seat face. The wall drawings and SPV's require a minimum 8' reinforcement length and Type B backfill to extend 1' beyond the reinforcements. I don't think there would be enough room to build this wall to the required specifications. Also, the As-Builts show bottom of bridge footings to be approx elev 698. The finished grade chart for the front of the wall shows 694.02 and the wall needs minimum 1.5' of bury, so 692.5. To install the reinforcement, we would need to excavate 5.5 below the bottom of the bridge abutment, which may result in exposing the CIP piling. The existing bridge girders will prevent any type of shoring to be installed along the back of our reinforced soil zone. Would a gravity wall work at this location? | The wall was originally constructed under and in front of these same abutments so it could be done with the aid of non-standard shoring. It wonâ€™t be able to be conventional driven sheets. The exposed height of the replacement retaining wall is to match the exposed height of the existing wall. The plan elevations will be reviewed and an addenda issued for new plan elevations. The new retaining wall in front of the bridge abutments will be modified to allow for an option of a gravity wall instead of a mechanically stabilized earth wall for that segment. | Mike Coleman | 8 | 2025-03-19 07:24 | 2025-03-26 06:44
20250408 | 20250408020 | 20 | Does WisDOT have the shop drawings for the existing wall? | The elevations on the As-Builts are identical to the new wall but the existing wall only has about 4ft of exposed face and the new wall is calling for 6ft from finished grade to top of wall. So, changes must have been made either to the trail elevation or top of wall elevation. The As-Builts for the bridge show the beam seats at about elev 703 and the top of the slope paving is about 3ft below that, with 2 large ducts conflicting with installing the new slope paving. The top of wall is approx 2ft below the top of the slope paving, so possibly about 698, which would make sense with the 694 trail elevation noted in the plans. Also, I am not sure what was required for wall construction in 1995. Were walls built as shown in the details, not requiring reinforced soil fill to 1ft beyond the end of the reinforcement? Was the reinforcement 8ft? If not, that could explain how these walls were built without requiring shoring or risking the integrity of the piling and abutment. | We do not believe there are shop drawings for this. The only drawings we have are the as-built which are located on the Wisconsin DOTâ€™s Highway Structures Information System (HIS) site. The exposed height of the replacement retaining wall is to match the exposed height of the existing wall. The plan elevations will be reviewed and an addenda issued for new plan elevations. The new retaining wall in front of the bridge abutments will be modified to show an option for a gravity wall instead of a mechanically stabilized earth wall for this segment. The as-built structure plans for both bridges can be downloaded from the WisDOT Highway Structures Information System (HSI): https://wisconsindot.gov/Pages/doing-bus/eng-consultants/cnslt-rsrces/strct/hsi.aspx | Mike Coleman | 9 | 2025-03-19 10:20 | 2025-03-26 06:51
20250408 | 20250408020 | 20 | Payment for Joint Repair Concrete, B-55-61 | Per the double starred note on sheet 191 of the plans, the CONCRETE MASONRY DECK REPAIR item is to include the concrete for the joint repairs areas. The pay quantity is not sufficient to cover the joint work. The assumption is that the joint concrete is included with the CONCRETE MASONRY BRIDGES pay item. Please confirm or revise plan quantities. | The assumption that the joint concrete is included with the CONCRETE MASONRY BRIDGES pay item is correct. The note will be revised and shown on an upcoming addendum. | Mike Coleman | 10 | 2025-03-26 10:57 | 2025-03-27 12:33
20250408 | 20250408020 | 20 | B-55-126 - Jonit Repair Limits | Please provide limits for joint repair work on this structure at abutments and hanger joint. | Joint repair limits will be shown on the plan as part of an upcoming addendum. | Mike Coleman | 11 | 2025-03-26 12:49 | 2025-03-27 12:33
20250408 | 20250408020 | 20 | Concrete Masonry Bridge Quantity Verification | Please provide breakdown of CONCRETE MASONRY BRIDGE quantity calculation. We are not finding the quantities listed in estimated quantity table. |  |  | 12 | 2025-03-26 12:52
20250408 | 20250408020 | 20 | B-55-126 Railing Anchorages | Due to the extreme corrosion of the existing anchors, nuts and washers, there is no chance of reusing the existing railing anchorages for the new rail. Provide a different detail for attachment to the existing parapet walls. | The plan will be updated to show the existing anchors being removed and the new railing with larger base plates attached with adhesive anchors. | Mike Coleman | 13 | 2025-03-27 16:01 | 2025-04-01 07:10
20250408 | 20250408020 | 20 | Railing layout details | Has any consideration been made for general layout of the railing? Is there a detail for expansion and contraction at the modular joints? Having one plan sheet showing the max panel length and one standard detail plan sheet for 2,382' of railing seems inadequate. | The spacing of the rail posts is to match the existing spacing as shown on the plans of approximately 10â€™-0â€ o.c. max. The detail for the expansion joint is shown on the plan. | Mike Coleman | 14 | 2025-03-27 16:08 | 2025-04-01 07:11
20250408 | 20250408020 | 20 | WI Side Slope Paving - Utility Ducts | Fiber Optic Utility ducts are currently resting on or nearly touching the existing slope paving. Will the utilities be raised to allow for removal and replacement of slope paving? Can the new slope paving be placed lower than the existing to allow for concrete placement and finishing? | The existing slope paving under the fiber optic utility ducts can remain in place. | Mike Coleman | 15 | 2025-03-27 16:20 | 2025-03-31 08:52
20250408 | 20250408020 | 20 | Utility Details & Conflicts | There are a number of utilities suspended from both structures that will be in conflict with the joint repair and backwall replacement work scopes. Section 7. of the special provisions seems to indicate that no conflicts are anticipated. Will these utilities be removed during construction and reinstalled after the new backwall is constructed? Can a detailed plan sheet be provided showing where each of the utilities are located and if the contractor is expected to work around them. Will temporary supports be required for the existing utility that runs through the backwall of B-55-61 bridge that is to be repalced. | On both of the structures there is a conduit that contains the storm sewer. The SE corner of WB structure (B-55-61)- this storm sewer goes through the backwall of the structure and will be impacted. This is addressed in the structure plans. There is a conduit package (2 steel conduits) located on the north side of the WB structure (B-55-61). These conduits are suspended on the lateral bracing between the girders. These conduits should be located below the work that is required at the joint replacement locations and should not be impacted. There is conduit on the backwall of the east abutment of the WB Structure (B-55-61). This is for the WisDOT weather station. WisDOT will disconnect this from the weather station prior to construction and this can be removed with the backwall. | Mike Coleman | 16 | 2025-03-28 14:09 | 2025-04-01 07:15
20250408 | 20250408020 | 20 | Design Schedule | Can the department provide the schedule used in design. | The design schedule can be found at the following location: https://wisdot.box.com/s/t8v8v7e0lhcd63ib06jgg4yn4cznhn3m or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 17 | 2025-04-01 14:01 | 2025-04-02 09:04
20250408 | 20250408020 | 20 | Addenum 2 Traffic Control language | The revised Special Provisions for (5) Traffic Control has a note that states: "The traffic control contractor must review the project once every day as per the standard spec 643.3.1(5)". However, Standard Spec 643.3.1(5) states that a review must be done immediately after each setup - not daily. Since this project will have long-term traffic control setups, would the department consider adding an item for Daily Maintenance and Surveillance? | The intent is to check the traffic control daily. Standard Spec 643.3.1(5) states â€œDo additional reviews as necessary to provide a safe work zoneâ€ the traffic control spec is written to let the contractor know that we anticipate this review to be completed daily so there are no questions about the work effort. This work effort is covered by the item 643.5000 Traffic Control. | Mike Coleman | 18 | 2025-04-02 08:17 | 2025-04-04 09:43
20250408 | 20250408020 | 20 | Installing and Maintaining Bird Deterrent Systems | If swallows are not present why are the structures required to be netted? If netting cannot be eliminated please clarify how much of the structure will be required to be netted. | Due to the nature of the St. Croix River waterway, it was determined that even though no migratory birds were seen, there is the possibility that there could be some at this structure. Therefore, bird netting was required as part of the environmental assessment that was completed for the project. The netting is only required at the work areas under the structure (joint replacement areas). | Mike Coleman | 19 | 2025-04-02 10:57 | 2025-04-04 07:44
20250408 | 20250408020 | 20 | B-55-126 Railing baseplates | Addendum #2 changed the rail baseplates to a width across the parapet of 1'- 2 1/2" and a bolt spacing center to center of 10 1/2". Based on the section detail and as-builts the parapet is only 11" wide. | The base plate was widened in the wrong direction. The intention is to widen the base plate along the length of the railing to miss the existing anchor plates. A revised detail will be issued with an upcoming addendum. | Mike Coleman | 20 | 2025-04-02 10:59 | 2025-04-04 09:42
20250408 | 20250408020 | 20 | Pedestrian Shuttle Service | Would the department consider removing this item from the contract? Contractor insurance policies typically do not cover the transportation of the general public. Therefore, it would be more appropriate to address this matter through a separate service contract with the state and the designated transport service provider. | During the design process pedestrian accommodations was identified as a need. Average pedestrian usage is approximately 100 per day. A shuttle service has been used in the past on a previous project at this location. Reconstruction of the retaining wall as well as replacement of the pedestrian railing on the bridge will require the trail to be closed for the duration of the project. WisDOT does not have the means to provide this shuttle service. This item will stay as a bid item. | Mike Coleman | 21 | 2025-04-02 11:11 | 2025-04-04 10:07
20250408 | 20250408020 | 20 | AS - ASTemp | AS vs AS Temp â€“ The bid form shows 125 ton of Asphaltic Surface and 2,228 ton of Asphaltic Surface Temporary. The Misc Quantities on Sheet 48 mentions 2,230 ton of Asphaltic Surface. Can these two items be clarified as to which locations are paid for under asphaltic surface vs asphaltic surface temporary? | The Temporary Asphaltic Surface had been removed and replaced with Asphaltic Surface in the plans. The bid form is incorrect. An addendum will be issued that will eliminate the Temporary Asphaltic Surface and move the quantity to Asphaltic Surface in the bid form. The plan is correct. | Mike Coleman | 22 | 2025-04-02 11:21 | 2025-04-04 09:43
20250408 | 20250408020 | 20 | SPV #43 | SPV #43 â€“ Fill & Restore Existing Concrete Rumble Strips â€“ Can this provision be altered to allow a concrete or slurry type mixture to fill the rumble strip indentations? This will allow the contractor to choose the product with their means and methods on filling and restoring the concrete rumble strips. | Fill & Restore Existing Concrete Rumble Strips should be bid as shown in the plans and specifications. | Mike Coleman | 23 | 2025-04-02 11:23 | 2025-04-04 09:59
20250408 | 20250408020 | 20 | C2 Rail | Is the intent for the railing to be fully welded together in the field rather than sliding slip connections as the current rail is? | No, as indicated on sheet 14 of 15 the railing is to be fabricated in 3 or 4 posts and then the FIELD ERECTION JOINT DETAIL is to be used to assemble the railing. | Mike Coleman | 24 | 2025-04-03 14:22 | 2025-04-04 15:18
20250408 | 20250408020 | 20 | Addendum #2: Adhesive Anchors 5/8-Inch Quantity | Addendum #2 added 7,146 adhesive anchors 5/8-Inch. If the posts are spaced at 10' max the quantity is overstated. | Agreed the ADHESIVE ANCHOR QUANTITY should be 964 EACH. This was revised as part of an emergency addendum. | Mike Coleman | 25 | 2025-04-03 14:24 | 2025-04-04 15:19
20250408 | 20250408020 | 20 | C2 Rail | The drawings do not indicate spacing for pickets. What should this dimension be? | The spacing of the pickets should be 6-inch max. | Mike Coleman | 26 | 2025-04-03 14:46 | 2025-04-04 15:20
20250408 | 20250408020 | 20 | Temporary Shoring Qty | Addendum 2 increased the quantity of temporary shoring, however, it appears the temporary shoring under the bridge was eliminated by switching to a gravity block retaining wall. Please review the quantity. | The quantity for Temporary Shoring is still accounted for in front of the abutment as it is anticipated to still being required for the wall construction. | Mike Coleman | 27 | 2025-04-04 08:29 | 2025-04-04 15:20
20250408 | 20250408020 | 20 | Follow-up to Question #16 | Owners response to previous question #16 is that the storm water collection system conflict is addressed in the plans is inadequate. The only thing shown in the plan is that the contractor is to provide a hole through the backwall and a construct a concrete collector on the face of the backwall. There are not any quantities for new piping, no indication if the system needs to be maintained or where to temporarily route water to, etc. In addition, the temporary shoring shown on the south side of the EB lanes on plan sheet 220 is called out as temporary steel sheet piling and is shown crossing an electrical line and the Comcast/AT&T/Legacy fiber optic line. There are clearly conflicts at these locations unless the intent is to have these utilities moved prior to construction. | The Comcast/AT&T/Legacy bundle can not be impacted. The intent with the shoring is to not impact this. The temporary shoring shown on the plans is a general location and can be adjusted or gapped as needed for construction operations or activities. With regards to the storm sewer on the structure, it was the intent to leave the existing storm pipe and connect back up using the concrete collar. If this is not feasible, then this will need to be looked at that during construction. | Mike Coleman | 28 | 2025-04-04 12:16 | 2025-04-07 13:12
20250408 | 20250408021 | 21 | Post Labor Day Peak Hours - Traffic | Are there different peak times post labor day? | An addendum will be issued to add Post Labor Day Peak Hours. | Mike Coleman | 1 | 2025-03-05 11:00 | 2025-03-19 07:49
20250408 | 20250408021 | 21 | Nurse Seed | Should there be nurse seeding to accompany the Seed 75 and Seed 80 mixes or is the temp seed being applied at nurse crop rates? | Item 630.0400 Seeding Nurse Crop will be added to proposal 20250408021. This item will accompany the Seed 75 and Seed 80 mixes. A total quantity of 219 LBS will be added between the two projects. An Addendum #2 will be sent to add this item. | Mike Coleman | 2 | 2025-03-31 09:40 | 2025-04-02 06:12
20250408 | 20250408022 | 22 | Borrow | Is the 524 CY of borrow that is shown for the southbound lane to be used just for shoulder fills or to achieve a subgrade elevation throughout the southbound lane? | The borrow shown is for the shoulder fill areas. | Mike Coleman | 1 | 2025-03-26 06:52 | 2025-03-26 14:33
20250408 | 20250408022 | 22 | 4MT & 5MT QTY | Please double check your 4MT & 5MT quantities. It appears that the QTY of 4MT & 5MT is switched around. | The contractor was correct. The two asphalt quantities where flipped. Total amount of asphalt is the same, but the distribution between 4MT and 5 MT is incorrect. An addendum will be issued to correct. | Mike Coleman | 2 | 2025-03-28 14:06 | 2025-04-01 07:01
20250408 | 20250408027 | 27 | Asphalt Repair | Can the Department double check the quantity of Asphalt Repair item? It seems as though the plan qty is almost double the areas shown in the plan. | The quantity for Asphaltic Repair has been reviewed, and will be updated via Addendum. | Mike Coleman | 1 | 2025-03-31 17:01 | 2025-04-03 06:57
20250408 | 20250408027 | 27 | Barrier System Grading Shaping and Finishing | Are there detailed cross sections available for the area where the Barrier System Grading Shaping and Finishing is going to take place? | Detailed cross sections are not available for this work. Barrier System Grading Shaping and Finishing should be completed according to the applicable Standard Detail Drawings. It is estimated that approximately 50 CY of embankment is required for this grading. | Mike Coleman | 2 | 2025-04-04 11:21 | 2025-04-07 06:42
20250408 | 20250408027 | 27 | Design Schedule | Can the Design Schedule be provided | The design schedule can be found at the following location: https://wisdot.box.com/s/b7cnublwnn1s2fla5fcjxjfpt5cls237 or can be accessed on the HCCI April bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-04-05 19:10 | 2025-04-07 08:35
20250408 | 20250408028 | 28 | Geotech report | Can the geotech report be made available for review? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/s5bz26bubd4gqxrnnqfd4lk8c0radt0v or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-03-31 14:37 | 2025-04-02 06:29
20250408 | 20250408029 | 29 | Restoration | The plan shows 288 SY of Topsoil and 288 SY of Sod. What are the #60 Seed (wetland mix), Temp Seed, and Seed Watering items for? | The seeding items will not be needed and will be removed via addendum. | Mike Coleman | 1 | 2025-03-26 10:56 | 2025-03-28 09:01
20250408 | 20250408030 | 30 | PCC Pavt 10" | What page shows pcc pavt 10" location on Arcadian Ave 649 sy.Are there any joint detail layout for this location. | The 10-inch concrete pavement from station range 242+62 to 245+81 on STH 59 is shown on page 97 and has been quantified under the STA 236+75 to STA 255+00 station range in the MQs. The 649 SY of PCC listed on Arcadian Avenue on sheet 635, Item 415.0100, should not be included. Please note that there is no 10-inch concrete pavement on Arcadian Avenue, therefore, kindly disregard the 649 SY listed for STA 242+62 to STA 245+81. | Mike Coleman | 1 | 2025-03-13 15:12 | 2025-03-19 07:52
20250408 | 20250408030 | 30 | Select Crushed | The unit of measure for select crushed is cubic yard. Would the Department consider changing the unit of measure to tonnage? | The unit rate will be changed to ton in an upcoming addendum. | Mike Coleman | 2 | 2025-03-17 13:02 | 2025-03-24 07:50
20250408 | 20250408030 | 30 | Overhead Sign Structures | The plan has drawing for S-67-982 but not the other three structures, -985, -986, -987. Also,are there soil borings available for the structure locations | These missing structure plans will be added via addendum. There are no soil borings at the structure locations. We have limited soil boring information that is discussed in the Soil Exploration Report. | Mike Coleman | 3 | 2025-03-19 11:33 | 2025-03-24 07:52
20250408 | 20250408030 | 30 | Excavation | Does the plan include an excavation quantity for the temporary pavement areas? | Division 1 in the earthwork table includes excavation needed for the temporary crossovers and temporary widening south of Sunset. Placement of temporary pavement in existing medians will require additional excavation. The remaining larger areas of pavement replacement are needed for early storm sewer installations, and the associated excavation is incidental to the storm sewer pipe per Standard Specification 608.5.2. | Mike Coleman | 4 | 2025-03-19 14:41 | 2025-03-24 07:52
20250408 | 20250408030 | 30 | ASPHALTIC SURFACE TEMPORARY | In special provision #37 "Asphaltic Surface Temporary" it states temp asphalt shall be 5 MT. With the assumed intent to ensure the use of 5 MT for the temp wedging for winter shutdown. Would all of all the other temp, not pertaining to the wedging, be allowed under the standard 465 specifications? Thanks, | Yes, the temporary asphalt shall be 5 MT for the wedging associated with the winter shutdown, in accordance with the intent outlined in the provision. For all other temporary asphalt not related to the wedging, the use of material complying with the Standard 465 specifications would be acceptable. | Mike Coleman | 5 | 2025-03-21 12:11 | 2025-03-26 06:37
20250408 | 20250408030 | 30 | Asphaltic Surface Temporary - Wedging for Winter Shutdown | On sheet 33 of the plan set the construction detail for the temporary wedging shows the utilization of a paper joint. Would the omission of the paper joint be allowed being that there is a substantial area that would require paper and also there is a removing asphaltic surface milling item (that pertains to removing the ramping) that will make the paper obsolete in aid of removing the ramping. | Thank you for your inquiry regarding the use of a paper joint as described in the construction detail on sheet 33 of the plan set for temporary wedging. After review, the omission of the paper joint would indeed be allowed, considering the substantial area that would otherwise require paper. Moreover, the inclusion of the removing asphaltic surface milling item, which pertains to the removal of the ramping, renders the paper joint unnecessary as it will be made obsolete in this process. | Mike Coleman | 6 | 2025-03-21 12:21 | 2025-03-25 08:06
20250408 | 20250408030 | 30 | Excel Miscellaneous Quantities | Can the miscellaneous quantities for the Drainage Items and the earthwork tables be provided in Excel format? | The Miscellaneous Quantities excel file and earthwork sheets excel files can be found at the following location: https://wisdot.box.com/s/3spr9k1heguccib46p1myss10dne9ziw or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 7 | 2025-03-21 14:11 | 2025-03-25 08:10
20250408 | 20250408030 | 30 | Asphaltic Surface Patching for Adjusting Manhole Covers | In special provision #38 "Adjusting Manhole Covers" it states "The department will measure and pay for the items of asphaltic pavement mixture, temporary cover plate, milling, and paving separately". However this is not shown anywhere in the miscellaneous quantities of Asphaltic Surface; how do you intend to pay for this asphaltic surface patching? | To clarify, the asphaltic pavement mixture is paid for and quantified under the Asphaltic Surface Temporary item. This item covers work such as removing medians and installing temporary surfaces for traffic control purposes. | Mike Coleman | 8 | 2025-03-28 09:49 | 2025-04-04 09:55
20250408 | 20250408030 | 30 | Geotechnical | Please provide a copy of the soil borings. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/3spr9k1heguccib46p1myss10dne9ziw or can be accessed on the HCCI April bid letting page under Supplemental Information. | Mike Coleman | 9 | 2025-03-28 10:49 | 2025-04-02 06:11
20250408 | 20250408030 | 30 | Pipe Slurry Backfill | Will the Department allow clear stone chips in lieu of slurry backfill for storm sewer construction? Because slurry backfill is only needed up to the spring line of the pipe, a small amount of slurry would be needed. For example, a 65' run of 24" pipe only needs roughly 5 CY of slurry. To avoid excessive small load delivery charges, the contractor must leave long stretches of trenches open so the pipe can be backfilled with slurry. In addition, is there a detail for slurry around manholes or is slury only required around storm sewer pipe? | The original planned use for slurry backfill remains unchanged, especially for larger diameter pipes. The detail explicitly states that slurry backfill is only required for pipes with a diameter of 24 inches or larger. Therefore, the requirement to use slurry backfill remains in effect as outlined in the specifications. | Mike Coleman | 10 | 2025-04-01 11:17 | 2025-04-03 07:02
20250408 | 20250408030 | 30 | Removing Underdrain | Will the Department consider adding an item for removing underdrain? | Removal of the underdrain is considered incidental to common excavation per Section 204. | Mike Coleman | 11 | 2025-04-01 13:30 | 2025-04-03 07:05
20250408 | 20250408030 | 30 | Conversion Rates | What conversion rates are being used for 1-1/4", select crushed, Backfill Granular Grade 2, and Open Grade? | The following conversion rates were used in the quantities. 1-1/4" base aggregate â€“ 2.3 ton/cy 3/4" base aggregate â€“ 2.4 ton/cy Select crushed material â€“ No conversion as this is CY. Will use 2.2 ton/cy in Addendum #2 Backfill Granular Grade 2 â€“ 2.0 ton/cy Open Graded â€“ 2.2 ton/cy | Mike Coleman | 12 | 2025-04-02 08:41 | 2025-04-03 07:03
20250408 | 20250408030 | 30 | Granular Backfill | This project has an item for Backfill Granular Grade 2. Some of that quantity is used to backfill Marsh Excavation, the contaminated soil excavation, and the removal of the pedestrian underpass. The rest of the quantity is shown on page 634 of the plans, and it states that it will be used for the proposed storm sewer. A construction detail on Page 23 states that Granular Backfill is incidental to the pipe when placed within the traveled way. Will the Granular Backfill pay item be paid for granular backfill placed during storm sewer installation? Will the Granular Backfill pay item be paid for storm sewer removals if granular backfill is directed by the engineer per Standard Spec 204.5.1(4)? Please clarify the intent of this item. | Granular backfill for proposed pipes will be incidental per the construction detail. The MQ sheet incorrectly states that this is for proposed storm sewer when it should be for existing storm sewer. The granular backfill item will be paid for when backfilling the trenches left by the removal of the existing storm sewer except when there is proposed storm sewer going in the same trench. | Mike Coleman | 13 | 2025-04-02 08:49 | 2025-04-03 06:54
20250408 | 20250408030 | 30 | Drain Slotted Vane | Can more detail be provided on the length of the Drain Slotted Vane? The item is bid by the each, and there is no plan detail to show the length of the required drain slotted vane. |  |  | 14 | 2025-04-05 09:20
20250408 | 20250408031 | 31 | Special Provisions are for the wrong job. | Specials are wrong, please replace with the correct document. | The correct special provisions have been added to the online proposal. Please re-download the proposal. https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2025/20250408.aspx | Mike Coleman | 1 | 2025-03-14 09:09 | 2025-03-17 12:41
20250408 | 20250408031 | 31 | Prosecution and Progress - Start Date | In the Prosecution and Progress it says do not start work prior to April 6th,2026. Is all this work scheduled to be complete in the Year 2026? | Correct, the intent is to complete all work associated with the project during 2026. | Mike Coleman | 2 | 2025-03-17 10:16 | 2025-03-18 07:52
20250408 | 20250408032 | 32 | Breaker Run | Will the Department consider changing the "Breaker Run" Item to 3" dense base course? |  |  | 1 | 2025-04-01 16:46