## qandasearchletting_results
Date | 2025-07-07
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250708 | 20250708001 | 1 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/fpeirm61lh7lny21qae5o6jvygqk1zip or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-06-14 13:08 | 2025-06-16 08:55
20250708 | 20250708001 | 1 | Schedule | Would WisDOT allow constructing this project in 2025? | Tree removal restrictions and utility relocates would prevent the project starting in 2025. We did not anticipate 2025 construction due to light pole/electrical components deliveries, so we did not account for tree removal/utilities being completed in 2025. | Mike Coleman | 2 | 2025-06-14 13:11 | 2025-06-23 07:48
20250708 | 20250708001 | 1 | Utility work plan | The special provisions state that the utility work plan can be requested for this project; can this be provided in the same location as the design schedule? | The utility work plans can be found at the following location: https://wisdot.box.com/s/fpeirm61lh7lny21qae5o6jvygqk1zip or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-06-27 11:10 | 2025-07-07 10:13
20250708 | 20250708002 | 2 | Foam Jacking | 1. In the fourth paragraph of article 70 (subsection B) of the special provisions, contractors are to submit with the bid documents the general certification from the HDP manufacturer. Where/How are prospective bidders supposed to submit this requirement at bid time? 2. Does the Department have a list of subcontractors that have successfully performed this work on previous DOT projects that could be provided to prospective bidders? | 1. Submittal at bid time is not required. The Special Provision will be revised via Addendum #1. The Special Provision will be revised to: Ã¢â‚¬Ëœâ€¦must be submitted to the engineer two weeks prior to the start of the foam jacking work. 2. The Design Team does not have a list of subcontractors. | Mike Coleman | 1 | 2025-06-24 07:38 | 2025-07-02 12:18
20250708 | 20250708002 | 2 | Design Schedule | Please provide a design schedule for this project. | The design schedule can be found at the following location: https://wisdot.box.com/s/8dxo4givnxd68hfnzccm51zclj1mgk3q or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-06-24 16:54 | 2025-06-25 10:34
20250708 | 20250708002 | 2 | Base Patching Schedule | Is there a reason the base patching cannot occur after November 15th? Historically there are plenty of favorable weather days after November 15th, along with plenty of available workforce for this scope of work . Given this is late season base patching and work occurs during night closures is it possible to move the 2025 interim completion to a later date? | The Special Provision will be revised via Addendum #1. The Prosecution and Progress Special Provision, Fall and Winter Work Restrictions section, will be revised to add the following: â€œTo revise the start date of the winter shutdown for Project ID 1030-43-71 and/or 1030-43-72, submit a written request to the Engineer at least two weeks before November 15, 2025. The engineer will approve or deny that request based on the conditions cited in the request. Additional Holiday restrictions for Christmas and New Years will apply.â€ | Mike Coleman | 3 | 2025-06-24 16:57 | 2025-07-02 12:18
20250708 | 20250708002 | 2 | Liquidated Damages November 2025 | What does the $5000.00 per calendar day liquidated damages for the interim November 2025 date represent? Given there is already lane rental assessments in place to protect peak traffic flow, is an additional interim completion date with liquidated damages necessary? Would it be more conducive to the contract to require all base patching to be completed before 2026 milling? This would allow for more scheduling flexibility of night operations from a risk and liability standpoint in avoiding night operations during unfavorable late season weather when safety concerns increase and would give the department the opportunity to assess pavements after winter traffic and freeze thaw months for potential base patching needs not visible the year prior. | The interim completion date will remain, but the winter shutdown start date may be revised pending approval from the Engineer as detailed in Question #3 Response and in Addendum #1. | Mike Coleman | 4 | 2025-06-24 16:59 | 2025-07-02 12:19
20250708 | 20250708002 | 2 | SPV 85 | SPV 85 section B refers to material requirements more in alignment with partial depth pavement repairs or bridge deck surface repairs. In addition, section C provides more guidance of a partial depth repair scenario. Given the construction details illustrate these area as full depth repairs consistent with the pavement patching occurring on the project, would using mix more consistent with SHES pavement patching be more suitable for thicker pavement sections as described in the plans? The overall quantity and depth of these repairs donâ€™t align with prepackaged rapid setting product usage, and the aggregate extension options in these prepackaged options require of use pea gravel size aggregate particles rather than aggregate sizes typically seen in full depth pavement sections. Additionally, is it necessary for this material to obtain 3000 psi in 3 hours if mix can achieve 3000 psi before opening to traffic? |  |  | 5 | 2025-06-24 17:01
20250708 | 20250708002 | 2 | Staging Language | Prosecution and Progress - page 5-12 describes what appears to be permanent staging configurations (stages 1-22). These are shown on the planset pages 145-290. Prosecution and Progress - page 12 lays out peak hour/off-peak hour and nighttime lane requirements. These two sections appear to be in conflict with one another. Is the staging as laid out in the plans intended to be permanent? | The staging plans typically show off-peak conditions. The plans are not typically intended to be permanent staging due to the lane closure requirements. There are exceptions for this, such as the barrier wall repairs. Refer to the Schedule of Operations section within the Prosecution and Progress article for detailed lane closure restrictions. | Mike Coleman | 6 | 2025-06-27 15:02 | 2025-07-02 12:37
20250708 | 20250708002 | 2 | Jacking | Can WisDOT provide a list of approved products for the foam jacking? | The material within the Foam Jacking item is not on the APL and the SPV does not require it to be an APL product. Requirements for the item are outlined in the Foam Jacking article. Addendum 1 will include the general certification from the HDP manufacture to be submitted to the engineer two weeks prior to the start of the foam jacking work. | Mike Coleman | 7 | 2025-06-29 08:56 | 2025-07-03 09:17
20250708 | 20250708002 | 2 | Project Schedule & Milestones | The design schedule for this bid only shows time to complete the NB/WB portion of 1030-43-71. Will the interim/completion dates be adjusted to compensate for the work needed to be done on SB/EB for 1030-43-72 or is the contractor expected to work on both projects simultaneously for this contract? | An updated design schedule can be found at the following location: https://wisdot.box.com/s/8dxo4givnxd68hfnzccm51zclj1mgk3q or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 8 | 2025-06-30 10:52 | 2025-07-02 12:41
20250708 | 20250708002 | 2 | Drainage | Per the staging for milling and paving, the intent is to mill and place binder in stages 1-6, and then stages 7-12 will be surface. This will leave drainage issues on the roadway for multiple weeks as there will be a 1.75" in the bottom edge of the supers and at the barrier wall footing. Will the Department allow the start of a stage to mill and pave binder and then subsequently place surface prior to switching to the next stage to minimize this timeframe? | The Contractor is responsible for maintaining drainage during construction. Revisions to the staging and surface layer placement timing must meet the approval of the engineer. | Mike Coleman | 9 | 2025-07-01 10:44 | 2025-07-03 09:18
20250708 | 20250708002 | 2 | Foam Jacking Voids | How were the voids and/or quantity take offs determined for the Foam-Jacking scope of work? Are there any void dimensional limitations with the material specified? Size of voids, # of lifts etc? | The foam-jacking quantities were estimated by multiplying the average observed settlement depth over the area identified on the Construction Details - Road Repair sheets, multiplied by the unit weight of the foam. The foam-jacking special provision notes that â€œThe pavement slabs are not to be raised above existing elevations. During the active foam jacking operation, as soon as the existing pavement slabs begin to rise in elevation, the foam jacking operation shall be completed.â€ | Mike Coleman | 10 | 2025-07-01 15:05 | 2025-07-03 09:19
20250708 | 20250708002 | 2 | Foam-Jacking Pavement Cracking | Is the Contractor liable for any cracks in the pavement during the operations of the Foam Jacking scope of work? If so, what will the remediation required be? It is not unusual for the pavement to crack during these lifting procedures depending on many variables. Please advise. | The Foam Jacking article states under the C. Construction section â€œPerform work in a manner that avoids pavement blowout, cracking, excessive lifting, uneven pavement, or excessive lateral pressure on adjacent retaining walls. Damage caused by the contractorâ€™s operation must be repaired to a like condition at no cost to the department.â€ | Mike Coleman | 11 | 2025-07-01 15:07 | 2025-07-03 09:17
20250708 | 20250708002 | 2 | Staging Conflict with Miscellaneous quantities | For the HFST the staging indicated in the plans don't line up with the staging identified in the miscellaneous quantities. Which is correct? | The traffic control configurations for Stages 1-5 in Project ID 1030-43-71 and Stages 1-6 in Project ID 1030-43-72 are used multiple times throughout the project. Please see the traffic section of the special provisions and the traffic control staging overview narrative in the plan for further information | Mike Coleman | 12 | 2025-07-02 10:51 | 2025-07-03 09:19
20250708 | 20250708002 | 2 | System Ramp Work | Can system ramp work be performed in lane closures or must the system ramps be entirely closed to perform any work. For example, can sawing pavement occur in a lane closure or do the entire system ramps have to be closed to saw pavement If single lane closures are allowed,, please clarify the times that single lane closures may occur including for the tile removal. |  |  | 13 | 2025-07-06 09:35
20250708 | 20250708003 | 3 | S-40-240 Removal | Is footing removal needed with this structure as it's in the median with barrier walls? If so, how much concrete removal will be required? | Complete footing removal is not required. The new structure is located at STA 365+00. The top two feet of the current footing can be removed and the rest can be left in place as long as it does not interfere with other operations. | Mike Coleman | 1 | 2025-06-17 13:38 | 2025-06-24 07:09
20250708 | 20250708003 | 3 | Storm Sewer Manholes & Inlets | Manholes & Inlets called out on the bid tab do not have profiles shown on plans; how should precast riser material be calculated for bid? | The contractor is to measure the existing storm sewer structures in the median under the Reconnect Storm Sewer bid item, SPV.0060.0160 (article 110). The structures requiring measurement are noted in the MQ table. | Mike Coleman | 2 | 2025-06-18 13:30 | 2025-06-24 07:12
20250708 | 20250708003 | 3 | Barrier Wall M1 M2 M3 | Could you please provide the construction details for the M1, M2 and M3 barrier wall items. | The construction details for the M1, M2, and M3 barrier transitions will be provided in Addendum #1. | Mike Coleman | 3 | 2025-06-25 07:02 | 2025-06-26 07:55
20250708 | 20250708003 | 3 | Pay Item | There is currently no pay item in the contract for Removing Asphaltic Surface Butt Joints. Will this item be quantified and added in an addendum? | The item will be added via addendum. | Mike Coleman | 4 | 2025-06-25 10:06 | 2025-06-26 07:56
20250708 | 20250708003 | 3 | Base Patching Qty | In the plan set for Project #1100-21-70 & 2984-13-77 Miscellaneous quantities Plan sheet 449 it states 7923 CY of Base patching Undistributed. Can a clarification be provided on the Quantity of Concrete Base Patching that has to be completed in Stage 1 of Construction year 2025? | There is no minimum required quantity of base patching to be placed in Stage 1. The focus of Stage 1 is to complete the crossover construction. The inside shoulder is available for base patching if a contractor would like to complete work there. Please review Addendum #2 when issued which will include revised staging sequencing. The structure work currently shown in Pre-Stages 1A and 1B will now be completed in Stages 2A and 2B. | Mike Coleman | 5 | 2025-06-26 11:50 | 2025-07-02 12:13
20250708 | 20250708003 | 3 | Interim Completion Date - Patching | Can the Base Patching for the project occur after the November 15th interim completion date? Based on History there are favorable weather days after November 15th with available work force to accomplish the work. Given this is late season base patching and work occurs during day and night closures is it possible to move the interim completion to a later date on the project? | There will be no changes to the interim completion dates. The contractor may request a revised winter shutdown start date in writing at least two weeks prior to November 15, 2025. Revised prosecution and progress language will be provided in Addendum #2. | Mike Coleman | 6 | 2025-06-26 12:25 | 2025-07-01 11:57
20250708 | 20250708003 | 3 | Re-epoxy bearing anchor bolt SPV 0060.260 | How will it be determined in the field which and how many of these anchors will need to be pulled and re-set? Just the anchors that are visibly pushed up away from the masonry plates or will there be some other requirement? | Per the structure plan general notes, the final location and quantity of this item will be determined by the engineer in the field. | Mike Coleman | 7 | 2025-06-27 07:27 | 2025-07-01 11:49
20250708 | 20250708003 | 3 | Contract Proposal | Underneath the Prosecution and Progress section of the Special Provisions, it is stated that once the Asphaltic Surface Milling is completed to perform crack repair. There is no detail for this crack repair or a pay item for it. What is this task in the Special Provisions referencing and how is it compensated? Please advise. | The Crack Repair item is no longer needed. This is removed in the Addendum #2 SPV revisions. | Mike Coleman | 8 | 2025-07-01 14:41 | 2025-07-07 07:15
20250708 | 20250708003 | 3 | Qualifications for Structural Steel HS Item | Could you please confirm the required qualifications for the fabricator for the Structural Steel HS item? | The contractor needs to use the Primary Members APL in Standard Spec 506.3.1.1. Fabricator approval is required prior to bid closing for use on any given WisDOT project. See CMM Ch. 228 for Buy America provision and guidance. | Mike Coleman | 9 | 2025-07-02 09:49 | 2025-07-07 07:15
20250708 | 20250708003 | 3 | Re-epoxy anchor bolts, SPV0060.260 | There will be very limited clearance to try and remove these anchor bolts. The end steel diaphragms are located directly above many of the existing anchors. Attempting to re-use the existing anchors will also be almost impossible and not cost effective. This work is all going to be cast into the new concrete abutment diaphragms as well. Would it be acceptable to: Cut off the existing anchors flush with the masonry plate Weld a clip to the side of the masonry plates with a hole for a new anchor bolt, offset enough to clear the diaphragm. Drill and install new anchors as is typically done with a bearing replacement. |  |  | 10 | 2025-07-02 10:55
20250708 | 20250708003 | 3 | Removing Concrete Slope Paving | How is the removal of concrete slope paving paid at the following locations: 1. Ã¢â€°Ë†STA 370+50 NB & SB under Florist Ave for temp shoring and new barrier wall construction? 2. Ã¢â€°Ë†STA 398+50 NB & SB under bridges B-40-348 & B-40-349 at Mill Road? |  |  | 11 | 2025-07-02 14:10
20250708 | 20250708003 | 3 | Removing Asphaltic Longitudinal Notch Wedge Milling for 5SMA | The Department has not included an item for removing the notch wedge in the surface. Will one be added? |  |  | 12 | 2025-07-03 08:55
20250708 | 20250708003 | 3 | UPRR Submittal Review | Does the Department have an executed agreement/contract with UPRR so that UPRR and its consultants can start review of submittals immediately? | Yes, an executed construction agreement is in place. | Mike Coleman | 13 | 2025-07-03 13:05 | 2025-07-07 12:47
20250708 | 20250708003 | 3 | Rusty Patch Bumble Bee | Per SPV 3, Rusty Patched Bumble Bee, â€œConstruction ground disturbance activity will occur during the beeâ€™s active season (April 15 through October 10) to avoid the overwintering period.â€ This provision does not state work can NOT occur but will DOT limit any work off of paved surface prior to April 15 and after October 10 as has been interpreted on other contracts in this corridor? | Work that does not disturb off-roadway ground will be permitted prior to April 15th and after October 10th. The DOT will limit any off-roadway ground disturbing activities prior to April 15th and after October 10th. | Mike Coleman | 14 | 2025-07-03 13:08 | 2025-07-07 10:09
20250708 | 20250708003 | 3 | Design Documents | Please provide all documents listed in SPV article 24 and article 25. |  |  | 15 | 2025-07-03 13:09
20250708 | 20250708003 | 3 | Design Schedule | Can the designers anticipated schedule be shared. |  |  | 16 | 2025-07-03 13:11
20250708 | 20250708003 | 3 | Full Closure | There is no detour shown for IH-41 full freeway closures. How will traffic be handled for full closures required for various operations? |  |  | 17 | 2025-07-03 13:14
20250708 | 20250708003 | 3 | ECIP Question | In many recent jobs, an adler tank or sediment basin have been required during ECIP reviews. Should the Contractor consider this work incidental to the SPV ECIP article and bid accordingly, or will the Department consider adding bid items as required by DNR through ECIP reviews? |  |  | 18 | 2025-07-03 14:30
20250708 | 20250708003 | 3 | Railroad Flagging SPV Question | The railroad flagging SPV states that flagging is needed within 25' of the C/L of any railroad track. However, the right of entry agreement that the Contractor has to sign has a requirement of 50' of the C/L for flagging. Is there any reason why these requirements are different and how should the Contractor approach this? | The railroad companyâ€™s right of entry agreement requirement supersedes the railroad flagging SPV article. | Mike Coleman | 19 | 2025-07-03 14:31 | 2025-07-07 13:47
20250708 | 20250708003 | 3 | Railroad Track Montoring & As-Builts | Please advise if railroad track monitoring AND pre and post construction as-built survey shots of the tracks are incidental to the SPV articles? Please provide more details if so. |  |  | 20 | 2025-07-03 14:33
20250708 | 20250708003 | 3 | B-40-1022 Temporary Shoring | B-40-1022 is shown being constructed to the median center line with temporary shoring shown east of the center line (i.e. B-40-1022 is being built over top of the shoring) 1. To allow for construction to go to the center line will the department add partial demo items into the contract to allow for shoring to be installed on the west side of the centerline or adjust the construction limits east of the centerline to account for physical construction limitations due to the temporary shoring? 2. Will the department add traffic control (temp barrier wall, etcâ€¦) around this temporary shoring in stages 2A and 2B? | 1. The Department does not plan to add partial demolition items to facilitate staging. The entire width of the existing SB Bridge B-40-348 is required to accommodate bi-directional traffic during NB Bridge B-40-1022 construction. The temporary shoring location shown is schematic and there is flexibility in this contractor designed element. The purpose of the shoring is to retain the existing shoulder slope between the exiting piers and abutments while allowing for the excavation and construction of the new MSE reinforced zone and temporary wire faced wall. The top of the temporary shoring within the limits of the MSE zone is well below the bottom of the existing structure. The temporary shoring may be installed beneath the existing bridge B-40-348. See the snip below for a schematic concept layout showing potential temp shoring alignment in red. The shoring wall type and installation methods should consider low overhead installation temporary shoring systems. 2. The traffic control assumes that the temp shoring will be located immediately east of the I-41 R/L at each end of the existing bridge B-40-348. No additional traffic control quantities or plans will be provided for a substage not currently included in the contract. | Mike Coleman | 21 | 2025-07-03 14:44 | 2025-07-07 13:45
20250708 | 20250708004 | 4 | Design Schedule | Can the construction design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/q312qau45grsp8p5zjk0i8aawzc63ydl or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-06-03 15:03 | 2025-06-10 12:24
20250708 | 20250708004 | 4 | Bridge Temporary Widening | It does not appear the structure plans for the bridge widenings were included in the project plan set. Can these plans be provided? | The temporary bridge widening will be designed by the contractor. An addendum will be issued to add structure sheets and special provisions for the bridge widening locations. | Mike Coleman | 2 | 2025-06-06 11:21 | 2025-06-12 07:03
20250708 | 20250708004 | 4 | Data Packets | When are the data packets going to be released for the project? Are we able to get pipe sheets in excel, earthwork data in excel and geo-tech reports included with that? Thank you | Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. The earthwork, storm sewer, soil borings, and Geotech reports can be found at the following location: https://wisdot.box.com/s/q312qau45grsp8p5zjk0i8aawzc63ydl or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-06-09 08:55 | 2025-06-17 08:40
20250708 | 20250708004 | 4 | Storm Sewer Items - Miscellaneous Quantities | Can the miscellaneous quantities for the storm sewer and culvert pipe items be provided in Excel format? |  |  | 4 | 2025-06-09 11:50
20250708 | 20250708004 | 4 | S56 Barrier Wall | Should there be a separate bid item for CONCRETE BARRIER FIXED OBJECTION PROTECTION TYPE S56 SPECIAL? Or is this incidental to the bid item S56 Special? | The project does not have any locations where Concrete Barrier Fixed Object Protection S56 is necessary. | Mike Coleman | 5 | 2025-06-13 05:59 | 2025-06-16 07:24
20250708 | 20250708004 | 4 | Utilities | Where can we get the detailed work plans for the utilities? Are there actual dates given for the utility work plans? | The approved utility workplans can be found at the following location: https://wisdot.box.com/s/q312qau45grsp8p5zjk0i8aawzc63ydl or can be accessed on the HCCI July bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-06-18 07:39 | 2025-06-23 08:57
20250708 | 20250708004 | 4 | Stage 1A Interim Completion Requirements | Per the Stage 1A winter shutdown interim completion date the contractor is to complete all work necessary to shift traffic to their respective locations as shown in the 2025 Winter Shutdown typical sections, and open to traffic by November 15, 2025. Per the traffic control cross sections for stage 1A and winter shutdown configuration, the NB traffic lanes at the bridge widenings are not to shift between stages. The only change in traffic control between stages at these structures is the movement of the temporary barrier wall. With this being said, would the construction of the temporary structure widenings be allowed to be completed after the stage 1A completion date of 11/15/2025 and not incur LDâ€™s? | Yes, the stage 1A winter shutdown language will be revised to allow the temporary structure widenings to be worked on beyond the 11/15/2025 date. | Mike Coleman | 7 | 2025-06-20 11:22 | 2025-06-23 09:15
20250708 | 20250708004 | 4 | Ingress/Egress Locations | In stage 1A what is the ingress location for the work zone at CTH JJ/Edgewood Dr bridge? Would a crash cushion be needed if the barrier wall is shortened on the south end? Would this be paid item? Would this be similar to the Wrightstown Rd barrier set up? | The outside shoulder is not wide enough for long enough to meet standards for an ingress/egress access. Deliveries will need to be made during approved lane closure hours. Workers will be able to access from I-41 and park behind barrier wall. The contractor can submit an access request for review. | Mike Coleman | 8 | 2025-06-20 11:31 | 2025-06-27 07:32
20250708 | 20250708004 | 4 | Work Stages | In Stage 1B work for the UCTA line - Temp C Ramp- in the Traffic Ctrl plan it says median work to be performed in 1B from 1390 to 1405. The earthwork tables list the work from 1390+40 - 1411 as being in Stage 1C.Which stage does this work need to be done? Does the paving for 1390 -1405 median need to be completed in 1B? | UCTA line - Temp C Ramp is generally designated to be built in stage 1C for use in stage 2A. The plan and profile correction (will be included in addendum #1), earthwork and cross sections all designate stage 1C, i.e. the stage in which the ramp would be completed. The median portion of the ramp is available for work in stage 1B, but does not need to be completed until the end of stage 1C | Mike Coleman | 9 | 2025-06-22 15:20 | 2025-06-27 07:34
20250708 | 20250708004 | 4 | Stage 1B Grading | In Stage 1B for the grading from 1407-1415NB at the new structure, is there a typical for this area for this stage? Will there be 24 inches of select crushed here as was done on the previous project or will it just be 16 inches per final detail? Will there be any median EBS as was done on the previous project per detail sheet #11 lower left sta 1405-1409 Existing Typ Sect IH NB 41? | EBS work in this median will be completed in the previous TMP project (1130-67-71). A typical section will be added via addendum #2. Quantities for select crushed material and base aggregate will be updated as well. | Mike Coleman | 10 | 2025-06-22 15:29 | 2025-06-27 07:33
20250708 | 20250708004 | 4 | Stage 2C | On Sheet 903 there is grading shown in 2C for sta 1442+50 to 1457+90. Are there quantities for this work? I do not see anything in the on the Earthwork Summary Sheet. | Yes. The work is to remove the temporary SB Off-Ramp constructed in 2A. Row 1420'UDTB'+12.96 of the earthwork summary table will be revised to the correct station range of 1443'UDTB'+07.62 to 1456'UCTD'+31.56. This will be updated in addendum #2. | Mike Coleman | 11 | 2025-06-23 14:22 | 2025-06-27 07:33
20250708 | 20250708004 | 4 | French Road Cross Over | Does the plan include quantities for select crushed and base aggregate? | Quantities being verified and will be updated in addendum #2 | Mike Coleman | 12 | 2025-06-23 15:10 | 2025-06-30 07:32
20250708 | 20250708004 | 4 | Pipe Underdrain Wrapped | The structure plans show pipe underdrain wrapped under the slope paving that is backfilled with 3/4" clear. Is the 3/4" clear incidental or will it be paid under the bid item for Open Grade? | The ï¿½â€ clear stone is incidental. | Mike Coleman | 13 | 2025-06-23 15:13 | 2025-06-27 06:34
20250708 | 20250708004 | 4 | Geotextile Type HR | The MQ on plan page 1126 shows a large quantity for Pond 1435, 1365, and 1391. There also appears to be some errors in the totals and subtotals. Please verify these are accurate. | The quantities will be updated in addendum #2. | Mike Coleman | 14 | 2025-06-23 15:16 | 2025-06-27 07:24
20250708 | 20250708004 | 4 | Removing Retaining Wall R-44-10/11 | In what stage will the Department allow removal of the existing retaining walls? | Both retaining walls will need to be removed in stages. During stage 1, portions of both walls can be removed between the temporary shoring for constructing stage one of B-44-0345. In stage 2, once all I-41 traffic is moved to the NB lanes, the portions north of the temporary shoring approx STA 125+80 CTH U SB can be removed to construct the new B-44-0346. In stage 3, once all traffic is placed on the new SB lanes, the remaining sections of both walls can be removed. | Mike Coleman | 15 | 2025-06-23 15:18 | 2025-06-27 07:36
20250708 | 20250708004 | 4 | Excavation for Structures | Nearly all the structure plans include the note "The upper limits of Excavation for Structures shall be the existing ground line". However, the cross sections for CTH U appear to show the slopes under the two existing bridges as being paid as common excavation. Please confirm the excavation under the CTH U bridges will be paid as common and the excavation under the CTH JJ/Wrightstown/Apple Creek bridges is incidental to Excavation for Structures. | CTH U sections updated and will be included in addendum #2. Excavation under the CTH U bridges is the same as CTH JJ/Wrightstown Road/Apple Creek bridges and incidental to Excavation for Structures. | Mike Coleman | 16 | 2025-06-23 15:26 | 2025-07-01 11:51
20250708 | 20250708004 | 4 | Plan Quantities and Data Sheets | Could you provide the following: Agg Qtys Stage 1B FRCO-S FRCO-N UTA Agg Qtys Stage 2A UCTB-R Temp On Ramp At SB U UCTG-C Temp On Ramp at U UCTB-C Temp Off Ramp at U UDBT-R Temp Off Ramp at SB U Earthwork Data Sheets UCTA Rem Temp On Ramp SB Ramp at U UTDA Rem Temp SB Off Ramp UCTB Rem Temp SB On Ramp at U UDTB Rem Temp SB Off Ramp at U Thank you. | Stage 1B Agg quantities will be added in addendum #2 Stage 2A Agg quantities are shown as part of SB. Remarks will be added to clarify location in addendum #2 For removing temporary ramp earthwork, the quantities are equal to the earthwork (cut + fill) for constructing the temporary ramp. | Mike Coleman | 17 | 2025-06-23 15:30 | 2025-06-30 07:34
20250708 | 20250708004 | 4 | HMA Q's | 1. Sheet 19 shows LT mixes to be used. With the ESAL counts on IH 41 would a HT mix be more suitable for that application? 2. There does not appear to be a typical section or thickness of HMA for any of the temporary asphalt in the plans. Could a typical section be added? | The LT mix will be changed to an MT mix. Typical sections will be added for temporary pavement areas. They will be included with Addendum #2 | Mike Coleman | 18 | 2025-06-24 16:23 | 2025-06-27 07:28
20250708 | 20250708004 | 4 | Frontage Roads | Will ingress/egress be allowed from the East and West Frontage Roads? Does the Department intend to repave the East and West Frontage Roads on a future project? | Ingress/Egress from the frontage roads may be allowed. The contractor will need to fill out an access request form for review and approval. There currently is not a project scheduled to repave the east and west frontage roads. Please refer to section 618 of the standard specification for maintenance and repair of haul routes. | Mike Coleman | 19 | 2025-06-24 18:26 | 2025-06-27 07:29
20250708 | 20250708004 | 4 | Aggregate Conversion Rates | What are the conversion rates used for all aggregates? | Our conversion factors are â€¢ Aggregate is 2.1 TONS per cubic yard. â€¢ Select Crushed is 1.75 TONS per cubic yard. | Mike Coleman | 20 | 2025-06-25 09:13 | 2025-06-25 12:04
20250708 | 20250708004 | 4 | Aggregate Conversion Rates | Regarding question 20, the Department stated that 1.75 is being used for select, but 1.9 appears to be used in the earthwork tables for 1130-67-76/86 to backfill the EBS with Select. Please clarify. | Project 1130-67-72 will be updated to use a conversion factor of 1.9 for select crushed. | Mike Coleman | 21 | 2025-06-25 12:43 | 2025-07-01 11:53
20250708 | 20250708004 | 4 | Apple Creek Instream Disturbance | Please confirm there are no instream disturbance restrictions on Apple Creek. | There shall be no in-stream disturbance between March 1 and June 15, with both dates inclusive of the timeout period. This language will be added via addendum. | Mike Coleman | 22 | 2025-06-25 14:13 | 2025-06-27 06:38
20250708 | 20250708004 | 4 | Traffic Control on Wrightstown Road and CTH JJ | Can the Department provide additional plan details and language regarding traffic control at the Wrightstown Road and CTH JJ bridges during the construction of the bridge structures? Currently there are no plan details showing how traffic control is to be handled during construction. If traffic is to be maintained during construction, plans and quantities for any temporary roadway or traffic devices will be required. Additionally, the Local Street Work Restrictions do not state what hours the closures are allowable. The provisions make mention to closures being allowable during off peak hours, but these are not typically the same as IH-41 traffic. Please specify. | Outside of allowable closures, the intent is to keep the roadways open during construction of the bridges over them. Additional traffic control details will be provided in Addendum #2. Local Street Work Restrictions will be included in Addendum #2. Off peak hours for Wrightstown and CTH JJ are 6 PM â€“ 6 AM and 8 AM â€“ 3 PM. Off peak hours for CTH U are 6 PM â€“ 6 AM | Mike Coleman | 23 | 2025-06-25 14:23 | 2025-06-30 07:37
20250708 | 20250708004 | 4 | Yardage Calc SB Lane | In the cross section of the SB Lane from station 1335 to 1384 the subgrade line does not close out on the left side. Would the yardage calculate correctly for this area. | Yes, the yardage is calculated correctly in this location. | Mike Coleman | 24 | 2025-06-26 14:05 | 2025-07-01 11:55
20250708 | 20250708004 | 4 | SB Cross Sections | On the SB cross sections from STA 1335 to STA 1384 the cross sections show excavation of the West Frontage Rd. I do not see any Traffic Control for this area in stage 2A. Will the Frontage Rd be closed for this work? Do the cross sections really represent the existing conditions in this area? It would almost appear the the representation of the existing SB lane is not correct/wide enough? | Per the contract special provisions, frontage roads are allowed to be closed as long as one is open at all times. Contractor may close or flag depending on their operations. The new alignment of I41 is shifted towards the existing frontage road and the frontage road shoulder is being widened. | Mike Coleman | 25 | 2025-06-26 14:11 | 2025-06-30 07:36
20250708 | 20250708004 | 4 | CBSS Missing SDD | Please provide SDD for CBSS as construction details reference it. | Necessary SDDs will be added in addendum #2. | Mike Coleman | 26 | 2025-06-27 08:03 | 2025-07-01 11:55
20250708 | 20250708004 | 4 | CBSS Fixed Object Construction Detail | Please provide plan locations for CBSS Construction Detail on Sheet 53. If no locations exist please delete constrcuction detail. | Construction detail for fixed object protection will be removed in addendum #2 | Mike Coleman | 27 | 2025-06-27 08:07 | 2025-07-01 11:56
20250708 | 20250708004 | 4 | CBSS End Sections | Are end sections required for Mediano CBSS at STA 1253, 1273, and 1450 where future barrier may connect? | Yes, for all barrier types shown, anchor is required at concrete barrier ends and at interruptions in concrete barrier. SDD for end sections added in addendum #2. | Mike Coleman | 28 | 2025-06-27 08:13 | 2025-07-01 11:56
20250708 | 20250708004 | 4 | CBSS Transition Detail | Should there be a CBSS transition detail from 1356â€™NBâ€™+00 to 1357â€™NBâ€™+00 RT. | The 42â€ barrier wall on the SWEF ramp has been revised to eliminate the need for a transition. Changes will be included in addendum #2. | Mike Coleman | 29 | 2025-06-29 11:40 | 2025-07-02 12:50
20250708 | 20250708004 | 4 | Interim Completion Dates | In response to question 22 regarding the instream disturbance restrictions at the Apple Creek Bridges, the Departmentâ€™s proposed schedule shows demolition and construction to be occurring during the instream disturbance restrictions. Additionally, the instream disturbance restrictions start on March 1st of each year. Per the special provisions, construction is not to resume until March 16th in 2026 and March 15th in 2027. This would restrict any instream work until after June 15th of each year. This causes conflicts with the staging and completion requirements of several stages during the project especially stage 2 where the bridge completion is critical to the stage 2B traffic switch and overall completion for work in 2026. | The date should be March 1st as the question proposer noted below. The start date for spring will be modified to March 1st of each year. The contractor can request to start work prior to the resume work date as noted in the contract special provisions. Modifications to the date will be made in addendum #2. The Department has evaluated the schedule reflecting a June 16 start date on the Apple Creek structures and the interim completion dates/staging provide requisite time to complete the work on the Apple Creek Structures. | Mike Coleman | 30 | 2025-06-30 11:38 | 2025-07-02 12:48
20250708 | 20250708004 | 4 | Apple Creek In-Stream Disturbance Follow Up | The 2026 and 2027 winter shutdowns both end (mid-March) after the in-stream disturbance dates start (March 1). The design schedule shows removal of the B-5-80 and B-5-53 structures during the in-stream disturbance restrictions. Likewise, work on the B-5-694 and B-5-695 structures is shown during the in-stream disturbance restrictions. Provided the departmentâ€™s response to question 22, in-stream work associated with the removal of the B-5-80 and B-5-53 structures cannot begin until after the June 15 date with work on the new structures following completion of demolition. Will the department reevaluate the project schedule to determine if work restrictions, interim completion dates, and/or staging can be modified to provide requisite time to complete work on the Apple Creek structures? | The date should be March 1st as the question proposer noted below. The start date for spring will be modified to March 1st of each year. The contractor can request to start work prior to the resume work date as noted in the contract special provisions. Modifications to the date will be made in addendum #2. The Department has evaluated the schedule reflecting a June 16 start date on the Apple Creek structures and the interim completion dates/staging provide requisite time to complete the work on the Apple Creek Structures. | Mike Coleman | 31 | 2025-06-30 14:42 | 2025-07-02 12:50
20250708 | 20250708004 | 4 | Local Street Work Restrictions | SPV Article 4 states off peak full closures of CTH JJ, Wrightstown Rd, and CTH U will be allowed for bridge construction in stages 1-3. What timeframe is considered off peak for each roadway? | Hours provided in addendum #2 Wrightstown Road: 6 PM â€“ 6 AM and 8 AM â€“ 3 PM. CTH JJ: 6 PM â€“ 6 AM and 8 AM â€“ 3 PM CTH U: 6 PM â€“ 6 AM | Mike Coleman | 32 | 2025-06-30 14:47 | 2025-07-02 12:51
20250708 | 20250708004 | 4 | Night Work | The contract includes work that must be completed at night; however, the SPV does not modify 107.1 to waive the requirement of the contractor to comply with local noise ordinances. | The local noise ordinances have an exemption for public construction on behalf of the State. | Mike Coleman | 33 | 2025-06-30 15:11 | 2025-07-02 12:51
20250708 | 20250708004 | 4 | Existing Typical Sections | The existing typical sections for the median ditch on plan pages 8-10 appear to show 24" of select crushed that was utilized for EBS. Please verify if 24" is present or if 12" was actually constructed. | This project is currently under construction and the only work in the median was at the crossover locations and they were built per plan. | Mike Coleman | 34 | 2025-07-01 10:31 | 2025-07-02 12:47
20250708 | 20250708004 | 4 | Concrete Placement | Does all the concrete pavement need to be placed with a placer. | Per article 10.5 - Spread concrete uniformly across the subgrade or subbase as close as possible to its final position prior to the concrete mix reaching the concrete paving machine. The contract does not dictate how the contractor achieves. | Mike Coleman | 35 | 2025-07-02 14:43 | 2025-07-07 07:13
20250708 | 20250708004 | 4 | Addendum 1 - Prosecution and Progress | Under the 2025 winter restrictions it indicated "Work on B-44-0341, I-41 NB bridge over JJ, B-44-0343, I-41 NB bridge over Wrightstown Rd, and B-44-0345, I41 NB over CTH U can continue through the winter, with the abutment and deck pours occurring in the spring of 2026". It is understood that the west side of B-44-0345 can be worked on over the winter but what work can be completed on B-44-0341 and B-44-0343? | The intent was to allow the temporary widening of existing structures B-44-072 and B-44-074 to continue beyond the winter shutdown date in 2025. Structure B-44-0341 is the replacement structure for B-44-072 and B-44-0343 is the replacement structure for B-44-074 | Mike Coleman | 36 | 2025-07-02 18:42 | 2025-07-03 09:56
20250708 | 20250708004 | 4 | Existing Typical Sections | The existing typical sections for the median ditch (excluding the median cross overs) on plan pages 8-10 appear to show 24" of select crushed that will be utilized for EBS in the bottom of the existing median ditch. Upon reviewing the cross sections for the current project, only 12" of select is shown. Please verify if 24" or 12" of select will be installed as EBS backfill for the existing median ditch. |  |  | 37 | 2025-07-03 08:01
20250708 | 20250708004 | 4 | Bid date extension | Considering the size and timing of Addendums 1 and 2 along with the holiday weekend, would the DOT consider moving this project to the August Letting? |  |  | 38 | 2025-07-03 11:45
20250708 | 20250708005 | 5 | Backfill Structure Type A | The item of Backfill Structure Type A is shown on the structure table for B-8-121 but no item is included in the contract. Please clarify. | Backfill Structure Type A is required for Structure B-8-121 as shown on the plans. Backfill Structure Type B was inadvertently entered into AWP instead of Type A. An addendum will be issued to address the discrepancy. | Mike Coleman | 1 | 2025-06-19 09:28 | 2025-06-23 11:02
20250708 | 20250708006 | 6 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/vk1qjfk2ye420ufhcik7o5r5qdvxxv2e or can be accessed on the HCCI July bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-06-14 13:09 | 2025-06-16 08:57
20250708 | 20250708007 | 7 | Heavy Riprap | Would the department consider amending the heavy riprap item to medium riprap? Placement under the bridge would be hand placed. | The department will keep the spot supplemental riprap under the bridge along the abutments as riprap heavy for slope and erosion protection. | Mike Coleman | 1 | 2025-06-27 15:40 | 2025-07-01 11:57