## qandasearchletting_results
Date | 2025-08-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20250812 | 20250812001 | 1 | Traffic Control - Basic Traffic Queue Warning System | Hello - the Traffic Control staging sheets in the plan reference "SDD 15D12-D Traffic Control, Lane Closure, Basic Traffic Queue Warning System". However, there are not bid items for a Queue System or any Smart Work Zone devices. Is there supposed to be SWZ items on this project or was this note in the TC plans added by mistake? Thanks. | Yes the Basic Traffic Queue Warning System is required for this project. An addendum will be issued to add the item and quantity. | Mike Coleman | 1 | 2025-07-22 10:26 | 2025-07-24 08:02
20250812 | 20250812001 | 1 | C2 Railing | Is there a detail page for the C2 Railing? Is there any layout, details, cross sections of the approaches of where the C2 Railing is mounted/installed? Is it mounted on a concrete path, wall, or seperate footings? | An addendum will be put together with the details and plan sheets for the railing. | Mike Coleman | 2 | 2025-07-23 12:52 | 2025-07-29 10:19
20250812 | 20250812001 | 1 | Bird Detterent Limits | Please clarify the limits for required bird deterrent. These structures are 562' long with only 8' of the deck being removed/replaced at the abutment joints. Containing the two abutment areas is a significantly different undertaking than containing the entire length of each structure. | The bird deterrent system limit is the full length of the structure. | Mike Coleman | 3 | 2025-08-06 10:09 | 2025-08-08 08:21
20250812 | 20250812001 | 1 | Bird Deterrent | Will the contractor be required to install bird deterrent on the entire structures such as B-32-34/35/46/47? |  |  | 4 | 2025-08-06 22:25
20250812 | 20250812001 | 1 | Fill and Restore Existing Concrete Rumble Strip | Is the expectation that no tack/ asphalt mix remain once the rumble strips have been restored? This item is going to be difficult to perform as the plan is calling for rumble strips to be reground in the exact location. It is unlikely this can be achieved as called out. | The expectation is that most of the mix and tack is removed. Some will remain after regrinding. | Mike Coleman | 5 | 2025-08-06 22:29 | 2025-08-11 09:35
20250812 | 20250812001 | 1 | Design Schedule | Please provide design schedule. 5 month total duration does not seem reasonable for completing all steel repairs, deck repairs, and full repaint of 5 structures that are completed in stages. | The design schedule can be found at the following location: https://wisdot.box.com/s/znaax94rcoe5zf096bz1cdyt4poa0qww or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2025-08-07 08:31 | 2025-08-08 08:18
20250812 | 20250812001 | 1 | Steel Fabricator Designation | What designation will be required for the fabricator of the Structural Steel cover plates if Primary Steel member fabricators are required? Since these are fairly simple flat plates would the Department allow vendors approved for fabricated bridge components to provide this material? | For the cover plates that are included in the Expansion Device bid item, and per standard spec 502.2.7.3 (1), expansion devices shall be fabricated by an approved fabricator selected from the APL for Fabricated Bridge Components, not from the Primary Steel Members APL. For these cover plates on the girders for bridges B-32-34/35/46/47, although they may be fairly simple as suggested in the question, it is preferred the requirement be maintained to utilize an approved fabricator selected from the Primary Steel Members APL. | Mike Coleman | 7 | 2025-08-07 12:04 | 2025-08-08 14:04
20250812 | 20250812001 | 1 | Schedule/Completion Date | After reviewing the design schedule, it appears not to take in consideration the durations for the painting operations. Plus the design schedule does not have work going on during the weekends. The durations are to short for all the work needed at each bridge. Can the completion date be adjusted to 11/15/2026 or to a date the departments sees appropriate. Thank You. |  |  | 8 | 2025-08-08 16:49
20250812 | 20250812001 | 1 | Question #7 Follow-up - Fabricator Designation | By answering question #7 with: 'For these cover plates on the girders for bridges B-32-34/35/46/47, although they may be fairly simple as suggested in the question, it is preferred the requirement be maintained to utilize an approved fabricator selected from the Primary Steel Members APL.' The department is being ambiguous and leaving room for problems down the road. The suppliers who are on the Primary Steel Member APL are historically not interested in this type of work and price it significantly higher that others who are approved for Fabricated Bridge Components. This puts the contractor in a dilemma on whether to price the work with the "preferred" supplier or the low bidder. Furthermore, the response does not indicate which product key will be requires (1,2,3 or 4). Please clarify further. | Cover plates for bottom flange splices as shown on the plans for B-32-34/35/46/47 shall be bid as Product Key 1 from the Steel Bridge Primary Members APL. | Mike Coleman | 9 | 2025-08-08 20:36 | 2025-08-12 05:31
20250812 | 20250812003 | 3 | Designer's Schedule | Could the Department provide the designer's schedule for this project? |  |  | 1 | 2025-07-28 13:01
20250812 | 20250812003 | 3 | Prestressed Beams | Would it be acceptable to provide all new prestressed beams in lieu of attempting to salvage, clean off tops, transport, store, reload and transport back to toe project for placement? | Project bids shall assume the beams will be removed, salvaged, and reset as shown in the plans. A request to substitute new 36â€ prestressed beams in lieu of salvaging the existing beams can be made after the project is awarded. At minimum new 36â€ beams would need to match all details and dimensions of the existing beams shown on the existing plans. | Mike Coleman | 2 | 2025-07-28 13:04 | 2025-08-04 07:51
20250812 | 20250812003 | 3 | Prestressed Beams - 36-inch | Would it be acceptable to provide 36W prestressed beams in lieu of 36" I beams? The forms for 36" I beams may not be available. | 36Wâ€ prestressed beams may not be substituted for this project. The beam seats are not wide enough to accommodate the width of a 36Wâ€ beamâ€™s bottom flange along the skew. | Mike Coleman | 3 | 2025-07-28 13:05 | 2025-08-04 07:52
20250812 | 20250812003 | 3 | Cofferdams at piers | Current projects tend to provide for cofferdams around solid shaft pier construction for more positive erosion control measures. Would the Department consider adding cofferdams at the solid shaft pier extensions while still allowing the concrete to be placed under water? | The contractor may elect to install a cofferdam to accommodate their means and methods for constructing the pier extensions. If a cofferdam is installed at the contractorâ€™s option, it will be incidental to the contract. Dewatering will not be required. | Mike Coleman | 4 | 2025-07-28 13:09 | 2025-08-04 07:52
20250812 | 20250812003 | 3 | Possible Lane Closures | Would the Department consider lane closures to provide access to spans 2 and 3 for salvaging the 8 prestressed girders? | Lane closures are not permissible during peak volumes. Short term lane closures may be allowed during non-peak hours utilizing flagging operations as approved by the engineer in the field. An addenda will be issued with updated lane closure and peak volume timeframes. | Mike Coleman | 5 | 2025-07-28 13:11 | 2025-08-04 07:53
20250812 | 20250812003 | 3 | Existing Pier Bull Nose removal requirements | Does the removal limit extend below the water line requiring underwater saw cutting and underwater chipping? | The removal limit for the existing pier noses extends to the bottom of the existing piers. The contractor may elect to dewater this area to accommodate their means and methods. If a cofferdam is installed at the contractorâ€™s option, it will be incidental to the contract. | Mike Coleman | 6 | 2025-07-28 13:20 | 2025-08-04 07:54
20250812 | 20250812003 | 3 | Driveway Assistant Devices | For stage 1B of the traffic control, the plan shows 7 Driveway Assistance Devices, but the quantities call out 6. Which one is correct? | An addendum will be issued clarifying the quantity. | Mike Coleman | 7 | 2025-07-30 14:04 | 2025-08-04 07:54
20250812 | 20250812003 | 3 | Project Schedule | The project schedule seems very aggressive, especially in stage 1 for bridge B-32-163. It seems very unlikely to begin phase 1 of the structure in mid May and be completed in 19 working days considering the access, removal, 2 abutment additions, 3 pier additions, beam salvaging, deck and parapet. Stage 2 also seems unlikely at 19 working days due to the careful removal and beam salvaging, beam seat adjustments, decking and parapet. Would the department consider adjusting the time frames allowed for working on this structure? | The bridge construction timeline may be extended if necessary, as it is not considered a controlling item in the overall project schedule. Bridge construction is expected to begin in Stage 3A, which includes more than 19 available working days, based on the controlling roadway items. Furthermore, Stage 3B may be completed before Stage 3A, which would allow an additional 7 working days to be made available in Stage 4, if needed. | Mike Coleman | 8 | 2025-08-04 09:04 | 2025-08-07 06:37
20250812 | 20250812003 | 3 | Culvert Pipe Steel Thickness | Can you confirm the steel thickness for the Culvert Pipe Class III-A 30-Inch (Line 0140) and the Culvert Pipe Class IV 12-Inch (Line 0158)? The culvert pipe summary on sheet 143 does not list the steel thickness for these line items. | The steel thickness for Bid Item 520.3330, Culvert Pipe Class III-A 30-Inch, is 0.079 inches. Steel thickness is not applicable for Culvert Pipe Class IV 12-Inch. The culvert pipe summary miscellaneous quantities table will be updated to reflect the specified steel thickness as part of an addenda. | Mike Coleman | 9 | 2025-08-04 13:16 | 2025-08-07 06:38
20250812 | 20250812004 | 4 | Item#SPV.0090.02 Transverse Joint and Crack Plunge Milling and Patching. | In Section A Description; plunge cut work to be performed is defined as transverse joints and cracks. In Section D Construction; the work to be performed defines transverse joints only. Please clarify if cracks are to be included in the plunge cut milling? Please note that depending on the track of the crack it may be nearly impossible to follow the crack with a milling machine without an excessive amount of overgrind and/or infringement on the live lane. In Section C, 3rd paragraph, 2nd to last sentence the text states â€œRemove the pavement without injury to the remaining pavementâ€ While following the depth parameters defined in the special provision, what happens if rebar or wire mesh is milled into and the mill tears up some of the adjacent payment outside of the plunge cut? Who is responsible for this repair? | Plunge cut milling is for the transverse joints only. Damage to nearby pavement is the responsibility of the contractor to repair. | Mike Coleman | 1 | 2025-07-30 17:05 | 2025-08-04 11:24
20250812 | 20250812004 | 4 | Mill & Relay - Profile Drop | Notes on typical sections state: â€œMill & Relay Profile to be 1â€ - 2â€ below existing profile. Maintain existing slopes as best as practical.â€ Where is the excess material expected to go to create the drop in profile? The existing shoulders are not low enough to accept this material. Will the existing shoulder need to have a trench excavated to make room for excess material to lower the profile? If so, what pay item is used for this work? If the mill and relay mills 11â€™ x 4â€ and a 1â€ profile drop is required then 2â€™ x 5.5â€ of existing shoulder material will need to be removed on the outside edge of the lane to make room for the 6.7 TON/STA of millings generated by lowering the profile 1â€. | The proposed mill & relay width is wider than the existing pavement width. Item 211.0101 Prepare Foundation for Asphaltic Paving (project) 01. 5790-02-72 covers removal of excess material if the material cannot be worked into the shoulder slopes. An addendum will be issued to revise the proposed typical sections. | Mike Coleman | 2 | 2025-07-30 17:06 | 2025-08-04 11:24
20250812 | 20250812004 | 4 | Mill and Relay - Limits | Are the mill and relay limits 22â€™ wide as defined on sheet 6 in the plan (top typical section) or should the limits be expanded to cover the additional widths resulting in a 26â€™ to 32â€™ wide pavement that is also shown in the typical sections on this sheet? Please clarify what the pay dimension(s) for the mill and relay on this sheet is as well? Misc quantities on sheet 116 of the plans support the wider dimensions. | An addendum will be issued to revise the typical sections. | Mike Coleman | 3 | 2025-07-30 17:08 | 2025-08-04 11:25
20250812 | 20250812004 | 4 | B-12-137 | I believe the wrong bridge drawings are on the plan set. The plans show structure B-12-37 Hwy 60 over Clear Creek. | An addendum has been issued to add the correct structure plans. The full size plan can be found at the following location: https://wisdot.box.com/s/wt84p84toak00m141l9hvbg6dglbb3fi | Mike Coleman | 4 | 2025-07-31 10:13 | 2025-08-01 07:42
20250812 | 20250812004 | 4 | Earthwork Data Charts | Could you please provide the earthwork data charts in Excel format? Some of the charts in the current drawing set are difficult to read and donâ€™t convert wellâ€”they appear to be raster images rather than vector-based PDFs. Thank you in advance. | The earthwork data sheets are available in the contractor data packet in excel format. | Mike Coleman | 5 | 2025-08-04 16:43 | 2025-08-05 12:36
20250812 | 20250812004 | 4 | Grade, Shape, Finish for Curb and Gutter | Why couldn't this restoration be paid out under the applicable bid items? When is erosion mat needed or when can mulch be used? What type of erosion mat is needed? What type of seed is needed? There is a big difference between mulching these areas and having to lay erosion mat for 20,000 feet. |  |  | 6 | 2025-08-11 07:29
20250812 | 20250812005 | 5 | Geotech Report for B-22-315 | Could the geotech report for B-22-315 be made available to review? | The geotech report can be found at the following location: https://wisdot.box.com/s/q4zn1rp4tqmlr4o2lw7w1okwuryfve63 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-07-30 08:03 | 2025-07-30 10:06
20250812 | 20250812006 | 6 | Non-Intrusive Detection System | Would the Econolite Autoscope Vision video detection system be accepted as an approved equal for this project? | â€¢ The City will only accept the product listed in the special provision article â€¢ A Proprietary Product Justification for the requested item has already been submitted and approved | Mike Coleman | 1 | 2025-07-10 11:03 | 2025-07-21 07:51
20250812 | 20250812006 | 6 | CAD Files | Are CAD files available for this project? | This is a local program project. On local program projects, there is no requirement for contractor data packets. | Mike Coleman | 2 | 2025-07-10 16:16 | 2025-07-11 11:19
20250812 | 20250812006 | 6 | Schedule | Could the anticipate schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/dc9wcw6tdbu9nmhrvjfx188834tr30i3 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2025-07-16 14:24 | 2025-07-21 12:31
20250812 | 20250812006 | 6 | Geotechnical Report | Is there a geotechnical report available for this project? | The geotech report can be found at the following location: https://wisdot.box.com/s/dc9wcw6tdbu9nmhrvjfx188834tr30i3 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 4 | 2025-07-18 07:48 | 2025-07-21 12:37
20250812 | 20250812006 | 6 | Design Schedule | Can the Design Schedule be provided for this project? |  |  | 5 | 2025-07-18 07:49
20250812 | 20250812006 | 6 | Shoreline Revetment Stone | Is a cofferdam required to install the shoreline revetment stone or can excavation and stone/fabric placement take place underwater? | A cofferdam is not required to install the shoreline revetment stone. Stone and fabric can be placed under water. If a contractor chooses to use a cofferdam, no compensation will be given for the cofferdam. | Mike Coleman | 6 | 2025-07-22 07:58 | 2025-07-23 06:56
20250812 | 20250812006 | 6 | Field Pour & Precast Storm Structures | In the specifications Special Provision #27 General Provisions for City of Madison Storm Sewer calls out to bid all structures (manholes and inlets) as field poured, however on the storm sewer plans and in the miscellaneous quantities only a handful of structures are called out as field poured. Are we to bid all structures as field poured? | All storm sewer structures are to be bid as field poured. Structures called out to be field poured in the plans cannot be precast and are not applicable to the Precast Approval Process in Article 27. The language regarding the noted field poured structures is in paragraph 2 of Article 27. | Mike Coleman | 7 | 2025-07-22 08:05 | 2025-07-22 11:14
20250812 | 20250812006 | 6 | John Nolen Drive Stage 1: 10 Nights | Per the Special Provisions, the pipe crossing are to be done on "10 consecutive nights". Is the intent to work weekend nights to adhere to the consecutive nights requirement or could the language be changed to "10 nights total"? | The requirement for consecutive nights will be removed. This will be addressed through an addendum. | Mike Coleman | 8 | 2025-07-23 09:34 | 2025-07-25 07:17
20250812 | 20250812006 | 6 | Permanent Sheet Piling | Permanent sheet piling at B-13-932/933/934 is called out as a PZ27 sheet pile section. Would alternate hot or cold rolled sections be allowed here? Provided they meet or exceed the properties of the PZ27. | Alternative sections may be allowed if they meet or exceed the properties (fy, section modulus, etc.) of the PZ27. This will be clarified through an addendum. | Mike Coleman | 9 | 2025-07-24 10:46 | 2025-07-25 07:13
20250812 | 20250812006 | 6 | 404 Permit | Can the 404 permit for the project be provided? | The 404 Permit can be found at the following location: https://wisdot.box.com/s/dc9wcw6tdbu9nmhrvjfx188834tr30i3 or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 10 | 2025-07-31 10:30 | 2025-08-04 07:48
20250812 | 20250812006 | 6 | City of Madison Work Hours | Is this entire project exempt from following the City of Madison work hours (7 am to 7 pm)? | An addenda will be issued clarifying that the intention is that the project will follow Madisonâ€™s standard hours (Sunday is 10-7 in the city. Other days are 7 to 7 ) with some exception for a specified number of expected night work days. | Mike Coleman | 11 | 2025-08-04 13:58 | 2025-08-05 13:05
20250812 | 20250812006 | 6 | Work Zone Access | Will the Contractor be allowed to access the work area from the adjacent live lanes of traffic by utilizing temporary median access points? If so, will there be time restrictions associated with this movement? | An addendum will be issued to add the following language: Construction Access All construction access is subject to approval of the engineer. Obtain approval form the engineer for the location of any ingress or egress area access points for construction vehicles. The engineer will have the ability to suspend work activities in the event any undesirable traffic congestion develops that has the potential to cause lengthy motorist delay or unsafe working conditions. Construction operations affecting the traveling publicâ€™s safety will not be allowed during snow and ice conditions, or any other adverse weather conditions, unless approved by the engineer. | Mike Coleman | 12 | 2025-08-04 14:17 | 2025-08-05 13:04
20250812 | 20250812006 | 6 | Permanent Retaining Wall Quantities | The plan quantities for the permanent sheet piling wall and respective concrete retaining wall for structures B-13-933 & B-13-934 appear to be inflated compared to our takeoff quantities per the details shown on the plans. Please review and advise as to correct quantities. | An addendum will be issued to correct the quantities. | Mike Coleman | 13 | 2025-08-05 11:14 | 2025-08-06 09:06
20250812 | 20250812006 | 6 | Cofferdams | Will turbidity barrier be acceptable to use in lieu of steel sheet piling for all cofferdam bid items? | No. This is a high-quality water resource and a number of permits and approvals were sought with sheet piling shown as a mitigation. Please bid as presented. | Mike Coleman | 14 | 2025-08-05 13:57 | 2025-08-06 09:01
20250812 | 20250812006 | 6 | 503.0137 B-13-934 Bid Qty | Bid quantity says 481.7 but there are 8 beams over 96'. Please clarify which quantity is correct. | An addendum will be issued to correct the quantities | Mike Coleman | 15 | 2025-08-05 15:59 | 2025-08-06 09:05
20250812 | 20250812006 | 6 | Underwater Concrete Placement | Will underwater placement of concrete for the abutments, sheet pile cap, pier cap, etc. be allowed? | The environmental process and analysis was done with assumption of using cofferdams and the special provisions for this project reflect that. Please bid as shown | Mike Coleman | 16 | 2025-08-06 10:16 | 2025-08-07 13:40
20250812 | 20250812006 | 6 | Permanent Steel Sheet Piling Coating | Will coating of the permanent steel sheet piling be required? | The concrete pile caps extend below the winter low elevation and the sheeting will not be exposed. The specification for steel sheet piling, in reference to section 550 only requires coating/painting if a portion of the sheeting is exposed in the final condition. No coating of the permanent sheet piling is required. | Mike Coleman | 17 | 2025-08-06 10:20 | 2025-08-07 13:39
20250812 | 20250812006 | 6 | Bore and Jack casing pipe 12" | Plans show runs under the WSORR of 46, 41, 35 and 31 feet for the 12" Steel casing. Project Specifications call out to be 25 feet MIN from the CL of the WSORR tracks with the nearest corner of the pit or outside of the RR ROW. Which I have not found yet. Can you clarify how we are to proceed with these conditions. |  |  | 18 | 2025-08-07 07:44
20250812 | 20250812006 | 6 | Revised revetment spec | Please confirm the revisions to the revetment spec in addendum 1 includes removal of the language requiring limestone sourced from Fond du Lac formation and meeting the water absorption, density, modulus of rupture and compressive strength specs originally posted. This is all to be deleted. |  |  | 19 | 2025-08-07 10:28
20250812 | 20250812006 | 6 | Cofferdam Installation | The response to previous question indicated that cofferdams are required for the demo of the substructure as shown on the plans. For the removal of piers at the SB structures 3 sides of a cofferdam can be installed, but the continuous piers for the NB and SB structures that extend below the water elevation will not allow them to be closed without at least some demo completed in the water prior to the full cofferdam being installed. Please advise on intent at these locations. | The design team is confident the pier can be removed without demolition in the water. | Mike Coleman | 20 | 2025-08-07 10:32 | 2025-08-08 08:23
20250812 | 20250812006 | 6 | Navigational Channel | The specifications mention that the navigational channel will be allowed to be temporarily closed between March 15th and November 1st during specific construction operations. Please confirm that the navigational channel will be closed each season from November 1 until March 15th. | Yes, the intention was to be closed each season. | Mike Coleman | 21 | 2025-08-07 10:40 | 2025-08-08 07:58
20250812 | 20250812006 | 6 | Traffic Signal Timing/Handling Outside the Project Limits | John Nolen experiences heavy traffic and frequent backups to the Beltline with the current number of open lanes. Does the Department plan on adjusting signal timings/traffic devices beyond the project to ease the increase in congestion once the number of lanes is reduced? | The Department is unlikely to have any role in signals, however the City of Madison Traffic Engineers will. To quote them: â€œObserving traffic with our cameras and adjusting timing for signals outside the project limits is something we normally doâ€ | Mike Coleman | 22 | 2025-08-07 12:05 | 2025-08-08 10:54
20250812 | 20250812006 | 6 | Work Zone Access Additional Question | Will the Contractor be able to have trucks turn across lanes? If so, will flaggers be required (or allowed) to assist with this movement? | Addendum #02 addressed this question. | Mike Coleman | 23 | 2025-08-07 12:09 | 2025-08-08 08:21
20250812 | 20250812006 | 6 | Causeway at Bridges | Is it acceptable to install temporary causeways in the lake for access to the bridges? If so, what permits and submittals are required to get approval? | Causeways will not be considered with this project. | Mike Coleman | 24 | 2025-08-07 21:01 | 2025-08-08 10:55
20250812 | 20250812007 | 7 | Transition Cut Common Excavation Quantitiy | On sheet 6 of the plan there's a note stating that the transition cut cubic yardage is included in the common excavation quantity. After doing a takeoff, it appears that isn't the case. Can you review the quantity and make adjustments if needed? |  |  | 1 | 2025-08-08 06:39
20250812 | 20250812008 | 8 | 41. Install Camera Assembly, Item 677.0200. | What pole will it be attached to? How much cable is required? Shouldnâ€™t the pay item read like this? Install Camera Assembly Temporary Signal Pole, Item SPV.0060.19. A Description This special provision describes delivering department furnished CCTV camera assembly and camera bracket and hardware, installing on existing temporary signal poles, maintaining the camera and hardware, salvaging and returning department-furnished equipment to the department. B Materials The department will furnish the CCTV camera assembly, bracket and hardware. Pick up the state furnished materials at the departmentâ€™s Electrical Shop located at 935 South 60th Street, West Allis. Notify the departmentâ€™s Electrical Field Unit at (414) 266-1170 and arrange for picking up the materials five working days prior to picking the materials up. | On the Temporary signal the camera is attached to the closet pole to the cabinet. The contractor takes care of how much cable to use. | Mike Coleman | 1 | 2025-08-08 14:33 | 2025-08-11 12:22
20250812 | 20250812009 | 9 | Living Snow Fence | The Specials state that there will be no traffic control needed for this years work. This involves discing or rototilling, placing weed barrier, planting the bare root plants, and delivering and installing the incidental pea gravel around each plant. Access for the equipment and the delivering of supplies across 7 different planting beds will be challenging, but to require that all of this is completed in 8 days seems unreasonable. Would the department consider modifying the traffic control to allow for shoulder closures during this time and also increasing the time allotment to something more practical? | Addendum1 is being developed to add more permanent signing, as well as to provide shoulder closures for living snow fence installation and move the planting schedule from Fall 2025 to Spring 2026. In addition, the construction start date in the Prosecution and Progress was moved to April 1, 2026, for all work including installing the living snow fence, and the time allotment also was increased for this work. The original proposal had living snow fence work beginning in the Fall of 2025 for deciduous shrubs. Scheduling the planting to the spring season should facilitate procurement of plant materials. | Mike Coleman | 1 | 2025-07-21 07:48 | 2025-07-25 07:25
20250812 | 20250812009 | 9 | Project Schedule | Can the department provide the construction schedule used in design? | The design schedule can be found at the following location: https://wisdot.box.com/s/zxooptml2j2n9i7i91gpg5xk7rejlnl3 or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-07-23 13:05 | 2025-07-24 12:58
20250812 | 20250812009 | 9 | HMA Pavement 3 MT Oil Type | Would the department consider changing the 107 TN of 3 MT 58-34S item to a 3 MT 58-28S to match the oil type of the 4 MT mix? | The lower layer should be 3 MT 58-28 S. Using 3 MT 58-28 H is acceptable but will be paid as 3 MT 58-28 S. The 4 MT 58-28 H can not be placed at the required 4 inches per the spec. | Mike Coleman | 3 | 2025-08-01 11:18 | 2025-08-08 10:55
20250812 | 20250812009 | 9 | Asphaltic Base Widening | The standard specification for Asphaltic Base Widening requires a 1" (25mm) nominal mix design. With these locations only being constructed 2" thick would the department consider changing this to an Asphaltic Surface item or allow a 19mm or 12.5mm HMA mix design for this paving | The asphaltic base widening (see typical section for EAT Replacements Sta. 1249+11 â€“ 1249+61 LT; Sta. 1262+64 â€“ 1262+14 LT), review of the thickness table in Standard Specification 460.3.2 indicated that a 12.5 mm mix (4 MT) can be placed in up to 4 inches in a single layer. The 12.5 mm mix(4 MT) may be placed in I1 layer or 2 layers depending on staging. However, the department does not want the surface layer to consist of the 19mm mix (3 MT). | Mike Coleman | 4 | 2025-08-01 11:24 | 2025-08-08 08:22
20250812 | 20250812009 | 9 | Uneven Cross Section Profile | Is the seventh paragraph under the Prosecution and Progress section of the Special Provisions, requiring an even cross section of the roadway at the end of each day, only applicable to the milling operation? Will an even cross-sectional profile be required while paving if the contractor utilizes a notched wedge per the standard specifications? | The even cross section of the roadway would be applicable to the milling operation. For paving, if the contractor utilizes a notched wedge per the Standard Specifications, the wedge can remain provided the drop off protection requirements in 104.6.1.2.3, as well as per updates in ASP 6, are followed. Uneven lane signs would be required. | Mike Coleman | 5 | 2025-08-01 11:33 | 2025-08-08 14:05
20250812 | 20250812010 | 10 | Typical Section sheets 5 - 7 | Sheets 5 - 7 of the plan set appear to be in a different language. Can these be replaced? | The advertised plan set has been updated and is available for download on the HCCI site. | Mike Coleman | 1 | 2025-07-23 13:03 | 2025-07-23 13:08
20250812 | 20250812010 | 10 | 72 HR Milled Surface Open to Traffic | Can the department change the 72 hour paving requirement over the milled surface to 96 hour to allow time for milling operations to get ahead of the shoulder widening and paving operation as well as allow time for the PWL test strip? | The Department will extend the restrictions to 96 hours. An addendum will be issued to address the change. | Mike Coleman | 2 | 2025-08-04 19:24 | 2025-08-06 09:46
20250812 | 20250812012 | 12 | As-Builts | Can we get the as-builts for the box culverts? Thank you. | Unfortunately, the Department has been unable to locate any as-built plans for either of the existing structures C-15-3252 or C-15-3254. | Mike Coleman | 1 | 2025-07-18 08:38 | 2025-07-22 09:43
20250812 | 20250812013 | 13 | Geotech Report for B-8-122 | Could the geotech report for B-8-122 be made available to review? | The Geotech report can be found at the following location: https://wisdot.box.com/s/5oxzwjvi2xqporpdo3ngkmqpukw48a7m or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-07-30 08:08 | 2025-07-31 07:51
20250812 | 20250812014 | 14 | Design Schedule | Can the Design schedule be provied? | The design schedule can be found at the following location: https://wisdot.box.com/s/g2s6dmf8zyzfhnr3szqr82j62fhit3ui or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-07-14 14:09 | 2025-07-22 09:42
20250812 | 20250812014 | 14 | distressed milling | In the miscellaneous quantities, the distressed milling quantity for STH 29 is an undistributed quantity of 3,040 sy. Based on the detail, this may require over 1500 patches. Are there quantities associated with stationing, and could the quantity table be adjusted if available? | There is no stationing associated with quantities for the distressed milling item. As noted in the detail, the locations and limits will be determined by the Engineer in the field after asphaltic surface milling is complete. The estimated quantity was based off a visually determined percentage of the Removing Asphaltic Surface Milling areas with more notable distress. No revisions to the quantity table are anticipated. | Mike Coleman | 2 | 2025-07-29 09:52 | 2025-08-01 06:17
20250812 | 20250812014 | 14 | Common Excavation | In the area of Concrete pavement removal and Paving 1173 EB to 1193 EB the track line for the paver will need to be excavated. This area has been paid in past jobs as common excavation and would need to be backfilled with 1.25" BAD. This area is not shown on the typical. Is there a reason this wouldn't be paid for on this project? | Trimming, shaping, and compacting the base course for concrete pavement to a width equal to the intended pavement or base width plus at least one foot is required and is incidental to Item 211.0201, Prepare Foundation for Concrete Pavement, in accordance with Standard Spec 211.3.4.1(3). Excavating material beyond the one-foot width for paver track lines or other needs is considered means and methods and will not be paid for separately. Dispose of any remaining surplus or unsuitable material in accordance with 211.3.6. An addendum will be issued to reflect this change. An addendum will be issued to clarify. | Mike Coleman | 3 | 2025-07-31 21:52 | 2025-08-07 06:35
20250812 | 20250812014 | 14 | Concrete Joint and Crack Repair | In the Misc quantities for the SPV Concrete joint & Crack repair it lists 28 STA within the stations of 1054+95 - 1241+14, all to be done on the STH 29 WB Inside lane and 3 STA undistributed. It's clear with this not being defined that it essentially is an undistributed item. Would the department consider changing this to be measured by the Linear Foot instead of Station with this being so vague | The unit of measure was changed from STA to LF for the SPV Concrete Joint and Crack Cleaning and Repair item. An addendum was submitted to address this change. | Mike Coleman | 4 | 2025-08-06 12:56 | 2025-08-07 13:41
20250812 | 20250812014 | 14 | SPV.0060.04 Coring of Existing Concrete Pavement | Perform coring in accordance with AASHTO T24/ASTM C42 to preserve the integrity of the pavement and underlying base materials. Extract full-depth cores to include the pavement and underlying base layers. Clearly mark each core with its location and orientation Will samples of the underlying base need to be collected, or are you looking for a thickness? If you are looking for a thickness, any means to gather that information will work? | Underlying base material will not need to be collected. Intact cores are required for petrograph, hardened air and strength testing. | Mike Coleman | 5 | 2025-08-12 08:12 | 2025-08-12 10:53
20250812 | 20250812015 | 15 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/bm9pcqzl0wnoiul8u9n0nk99qw5obqxk or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-07-14 14:10 | 2025-07-22 09:21
20250812 | 20250812015 | 15 | Transition Cut | On page 10 of plan it states to backfill the transition cut with foundation and trench backfill as specified in spec 520. Even though the pipe is storm sewer, spec 608, are you stating that the transition cut and trench backfill can be from the typical roadway section, because you are referencing 520? If that is correct not sure why you are using 608 pipe items? | The pipe is under 608 due to its connection to a median inlet structure. The intent is to follow the construction detail on page 10, utilizing the 520 specifications as shown. The already included 608 SPV will be revised to clarify the use of 520 backfill, and the construction detail title will be revised to also reference storm sewer for clarity. An addendum will be submitted to address these clarifications. | Mike Coleman | 2 | 2025-07-21 11:38 | 2025-07-28 08:13
20250812 | 20250812015 | 15 | Concrete Joint & Crack Repair | In the Misc quantities for the SPV Concrete joint & Crack repair it lists 10 STA within the stations of 674+99 - 906+53, all to be done on the STH 29 EB Inside lane. It's clear with this not being defined that it essentially is an undistributed item. Would the department consider changing this to be measured by the Linear Foot instead of Station with this being so vague | The unit of measure will be changed from STA to LF for the SPV Concrete Joint and Crack Cleaning and Repair item. An addendum will be submitted to address this change. | Mike Coleman | 3 | 2025-08-04 15:52 | 2025-08-07 06:40
20250812 | 20250812016 | 16 | Earthwork | Can you give more information on the earthwork for the "lane shift"? cut/fill every 100 ft or a cross section showing where the common excavation is? Is the Pvmt removal being paid as common in this area? How many yards are in the last stage of removal of the shoulder widening? Something so we know what the depth and width of the cut is. | 1. There are cross sections from station 1914+00 to station 1968+50 that will be added via addendum. To calculate the lane shift quantities from station 1908+33 to 1914+00 where there are not cross sections, it was assumed the cross sections are similar to station 1914+00 and this is included in the excavation common quantity. The common quantity also includes removing the inside asphalt shoulder The quantity for Item 204.0110 Removing Asphaltic Surface will be updated via addendum to not include removing asphaltic surface on the inside shoulder. The earthwork summary table will be updated via addendum to show additional information/breakdown for the installation of the lane shift and the removal of the lane shift. The quantity for Item 205.0100 Common Excavation did not change. 2. Concrete pavement removal is being paid under item 204.0100 Removing Concrete Pavement for this area. Removal of existing asphalt inside shoulder and temporary asphalt pavement is paid for under excavation common. Removal of existing outside shoulder is paid for under item 204.0110 Removing Asphaltic Surface. 3. The earthwork summary table will be updated via addendum to show additional information/breakdown for the installation of the lane shift and the removal of the lane shift. | Mike Coleman | 1 | 2025-07-23 14:04 | 2025-07-30 06:25
20250812 | 20250812016 | 16 | Project Schedule | Can the Department provide it's project schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/xo182wzh3o7gc5t7tumq0p3h7tcz5w0l or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-07-28 06:38 | 2025-07-29 10:18
20250812 | 20250812016 | 16 | Temporary Crossover | Page 46 of the plans calls out the temporary asphaltic surface as 6.25â€. Per spec 460.3.2(3) maximum thickness for any HMA is 6â€. Would the Department consider changing the thickness to 5â€, one lift, as the spec does allow for this and a single 5â€ lift does allow for some minor deflection in the base that tend to happen in these temporary situations? | The pavement design for the temporary crossover is 6.25 inches temporary asphalt surface over 13 inches base course. It is anticipated that the crossover paving will be in two lifts. The contractor will be required to provide the pavement structure in the plan for temporary crossover. | Mike Coleman | 3 | 2025-07-29 09:59 | 2025-07-31 08:22
20250812 | 20250812016 | 16 | Soils Report | Can you post the soils report? | The soils report can be found at the following location: https://wisdot.box.com/s/xo182wzh3o7gc5t7tumq0p3h7tcz5w0l or can be accessed on the HCCI August bid letting page under Supplemental Information. | Mike Coleman | 4 | 2025-08-04 08:26 | 2025-08-04 08:27
20250812 | 20250812016 | 16 | Embankment Special Compaction | Please clarify that contractors are or are not responsible for the compaction testing. The specials seem to contradict itself in construction and payment sections. Please clarify your quantity of 7600 SY of compaction area. This quantity doesn't make sense, coming up with 1423 SY less than that... | The special provision for Embankment Special Compaction states testing frequency in the Construction section â€œTest compacted embankment and compacted subgrade at a frequency of one test per 2,500 SF per lift. Document and review in-place dry density test results with the engineer as tests are completed.â€ It also includes payment for testing in the Payment section. Therefore, the contractor must test. The quantity for special compaction was reviewed and will be corrected via addendum. | Mike Coleman | 5 | 2025-08-05 15:01 | 2025-08-07 06:39
20250812 | 20250812016 | 16 | Distressed Milling & Asphaltic Surface Patching | Can these 2 items be quantified in the miscellaneous quantities instead of undistributed. Removing Distressed Asphaltic Surface Milling â€“ 50,830 SY and the item that goes with that is Asphaltic Surface Patching â€“ 5,850 ton. These are enormous quantities to have as undistributed with no real way for the contractor to quantify. According to the detail, the smallest patch could be a 3â€™x3â€™ which equals 1 sy. So that could be 50,830 patches if they were all 3x3 or as much as 15 miles long for 1 patch in the 6â€™ shoulder. | Removing Distressed Asphaltic Surface Milling and Asphaltic Surface Patching were estimated to be approximately 25% of the overall asphalt shoulders. This was included to provide a means to fix bad areas that may be discovered after the milling the shoulders. The actual areas are unknown. | Mike Coleman | 6 | 2025-08-05 18:40 | 2025-08-07 06:39
20250812 | 20250812019 | 19 | Reference Staking | For reference staking is it expected that the super transitions will need staking? The super tables are listed in the plans but state that they reflect existing conditions. | Reference staking would be at the contractorâ€™s request. The information is provided if they want the locations staked based on the existing field survey and referenced as-builts. The intent of the construction operation is solely to mill and pave to the specified depths, with no superelevation correction. | Mike Coleman | 1 | 2025-07-16 06:56 | 2025-07-24 07:54
20250812 | 20250812019 | 19 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/jaq26salq6sb05i1v426949v6lye084s or can be accessed on the HCCI August bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special | Mike Coleman | 2 | 2025-07-25 12:09 | 2025-07-28 10:45