## qandasearchletting_results
Date | 2026-01-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260113 | 20260113001 | 1 | Holiday and special event | It states Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 67 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the road need to be fully opened during the dates stated? | No. You just can't be hauling or working on the highway during the time period. | Mike Coleman | 1 | 2025-12-25 16:12 | 2026-01-05 14:26
20260113 | 20260113001 | 1 | Flagging Operations | The traffic section of the special provisions states, â€œDuring flagging operations, limit the single lane restriction to a single continuous length not exceeding 1 mileâ€. With all the operations that need to happen (milling, shoulder widening, distressed milling, and paving) multiple flagging operations will be needed to construct the project efficiently. Considering the road is already closed, will multiple closures be allowed? | Our design consultant for the Southwest Region team will be addressing this with a forthcoming Addendum. | Mike Coleman | 2 | 2026-01-05 14:43 | 2026-01-06 13:33
20260113 | 20260113001 | 1 | Pavement Marking Same Day | The pavement marking operations section of the special provisions discuss applying centerline pavement markings on the same day before opening the work zone to two lane traffic. Is this saying centerline markings need to be applied in order move a flagging operation? To the contractorâ€™s knowledge, this has never been required with flagging operations and would be extremely difficult and costly to coordinate. If the road is closed to through traffic, will it be allowed for the pavement marking to be applied once at the end of the day? There hasnâ€™t been a job where this wasnâ€™t the standard procedure with a flagging operation especially since the road will already be closed to through traffic. | This will be addressed via addendum. | Mike Coleman | 3 | 2026-01-05 14:44 | 2026-01-07 06:38
20260113 | 20260113001 | 1 | 72 Hour Milled Surface | Based on the operations needed for paving, i.e., milling, shoulder widening, distressed milling/paving, and PWL test strips, would the department consider allowing 96 hours to cover the milled surface with the same note allowing the engineer to revise if there are pavement failures? | This will be addressed via addendum. | Mike Coleman | 4 | 2026-01-05 14:45 | 2026-01-07 06:37
20260113 | 20260113001 | 1 | Culvert/Curb/RR Patching (Asphaltic Surface) | The asphaltic surface quantity only appears to be figured for the 2â€ lower lift of the culvert patches. The specials require the culverts and railroad crossing to be completed prior to milling and paving. This will leave a significant bump in the road if only 2â€ of the 6â€ total is paved on these small patch locations. The 3 MT 58-28 S mix would not be able to be paved until the test strip could be completed after milling. Considering this, would the department consider figuring both binder lifts of the culvert patch with asphaltic surface as well as the railroad patch and curb and gutter patch? The specials already require the asphaltic surface to be a 3 MT 58-28 S mix design. | This will be addressed via addendum. | Mike Coleman | 5 | 2026-01-05 14:45 | 2026-01-07 06:39
20260113 | 20260113001 | 1 | Adjusting Steel Plate Beam Guard | Would the Department consider writing an SPV for the reinstallation of the class A rail, radius class A rail, short radius rail, and the short radius terminals? The Adjusting Steel Plate Beam Guard standard specification is not the correct bid item for the reinstallation of the multiple types of salvaged rail on the project. | The department is comfortable with the item as called out | Mike Coleman | 6 | 2026-01-06 14:43 | 2026-01-07 16:56
20260113 | 20260113003 | 3 | 680.0100 Public Land Reference Monument Verify and Reset | There is no section 680 of the Standard Specification for this work. Can the Department Clarify what is needed for this item? | Section 680 was added to the Standard Specifications effective with the November 2025 letting. This information can be found in the current version of ASP 6. | Mike Coleman | 1 | 2025-12-31 10:50 | 2026-01-05 14:17
20260113 | 20260113004 | 4 | Holiday and special event | It states Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Hagedorn Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. The bridge needs to be reopened during this time? | No work or hauling may be performed during the specified dates but the bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 16:19 | 2025-12-30 08:59
20260113 | 20260113005 | 5 | low steel temp structure | Why is the low steel elevation given for the temp structure above HW100 when the bridge manual states HW5 should be sufficient? The structure as shown on the plan views would be near impossible to construct without a pier or sheeting in front of the abutments. The required minimum opening is achievable at a much lower low steel elevation. | The minimum low chord elevation will be revised to 858.2 feet. The minimum bridge opening will be revised to 80.33 square feet. Changes to the special provision will be made via addendum. | Mike Coleman | 1 | 2025-12-17 09:42 | 2025-12-22 11:54
20260113 | 20260113005 | 5 | Type M Railing Quantity | The current bid quantity for railing is 109.8 LF. According to CMM specification 232.4 should the correct quantity be 110 LF? CMM specification 232.4 states all pay measurement shall be rounded to the nearest full unit of measure unless listed in table 232-2. It creates issues during pay apps as the field engineer is advised to follow CMM 232.4. | Per the rounding rules in CMM specification 232.4, the bid quantity for railing rounds up to 110 LF. | Mike Coleman | 2 | 2025-12-23 10:19 | 2025-12-29 08:54
20260113 | 20260113005 | 5 | Utilities | The plan view for B-13-912 shows an AT&T underground line passing through wing 2. Is this line the line to be discontinued (as referred to in the special provisions)? If so, why is it dark on the plans and not referred to as discontinued. If it is the other line, which is the newly buried line (to replace the overhead line), is this line anticipated to be in conflict with wing 2 B-13-912? Is there any way for this line to be moved outside of the bridge limit? | The line passing through wing 2 is the existing AT&T line to be discontinued in place prior to construction. AT&T utility relocation information is correct as shown in the special provisions. | Mike Coleman | 3 | 2026-01-07 11:00 | 2026-01-08 16:41
20260113 | 20260113006 | 6 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The soil boring data can be found at the following location: https://wisdot.box.com/s/nkc7rhrc5ygjslaqp0vm09kpjxguza9i or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-12-11 13:41 | 2025-12-18 07:25
20260113 | 20260113006 | 6 | HES Mix Requirements | If we demonstrate that we can achieve the required opening strength with a standard mix in 3 days, as required for the HES Pavement spec, can the regular mix be used instead (without the additional cement)? This would provide a cost savings to the Department while also improving the quality of the surface. | The intent of the HES pavement is to open to local traffic as quickly as possible when strength is achieved to provide homeownerâ€™s access. Please bid as posted. | Mike Coleman | 2 | 2025-12-16 13:04 | 2025-12-19 12:01
20260113 | 20260113006 | 6 | Sanitary and Water bedding, Initial cover and trench backfill material | Can we obtain the sanitary and water bedding, pipe cover material and trench backfill from a permitted non metallic mine that does not have a wear and soundness test? | For bedding, cover, and backfill applications mentioned below, it is ok to obtain material from sources that do not have wear and soundness testing. | Mike Coleman | 3 | 2026-01-06 16:29 | 2026-01-08 16:33
20260113 | 20260113007 | 7 | Earthwork Summary | In earthwork summary at bottom of list it shows PE/CE/FE with a cut of 8956 CY and a fill of 5433 CY. Please explain where this cut and fill is and how much in each spot. Obviously this number was calculated so explain where. | These quantities are the estimated earthwork values for all of the unnamed driveways, and field entrances that do not have an alignment and profile. They are lump sum estimates that are not broken down by location. In addition, the estimated earthwork for these unnamed driveways and field entrances also includes some rounding of the overall earthwork volumes to get the totals to line up with the rounding requirements outlined in the FDM. | Mike Coleman | 1 | 2025-12-11 13:27 | 2025-12-18 07:27
20260113 | 20260113007 | 7 | Dust Control Surface Treatment | Will the department pay for water for dust control with the surface treatment bid item? I assume the dust control surface treatment will only be used in areas of residents and/or areas of complaints? | We have included the item Dust Control Surface Treatment (623.0200) as requested by the Monroe County Highway Department (64,000 SY). The Monroe County Highway Department requested the use of Calcium Chloride to aid in dust control. In addition, the item Water (624.0100) was also included (1,020 MGAL). | Mike Coleman | 2 | 2025-12-17 15:00 | 2026-01-02 08:46
20260113 | 20260113007 | 7 | Mowing Item | Consider adding a mowing item on a per each or acre basis of a reasonable amount for the areas called out in the special provisions for the upland sandpiper. | Our intent is that the required mowing be incidental to the bid item â€œMobilizationâ€ as outlined in the special provisions. | Mike Coleman | 3 | 2025-12-19 14:50 | 2025-12-24 08:39
20260113 | 20260113007 | 7 | Traffic Control Base | Consider adding a reasonable quantity to the 1 1/4" base aggregate item (or separate item) to be used for traffic control for access for the project. This would be the easiest and fairest way for all prospective bidders. | We will be releasing an Addenda to revise the quantity of Base Aggregate Dense 1 ï¿½-Inch to include an estimated amount to be used for traffic control access. | Mike Coleman | 4 | 2025-12-23 10:35 | 2025-12-29 09:02
20260113 | 20260113007 | 7 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH PC traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic Does the road need to be reopened during the stated events? |  |  | 5 | 2025-12-25 16:27
20260113 | 20260113007 | 7 | Soil Borings | Please provide a copy of the Geotechnical Report. | The Geotech report can be found at the following location: https://wisdot.box.com/s/52xz4hoqmtvvz6ojsdzj9h4q75wc9wcw or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-12-30 12:06 | 2026-01-05 14:07
20260113 | 20260113007 | 7 | Breaker Run in bottom lift of 1 1/4" | A Breaker Run item and quantity is included in the proposal for EBS. Would the DOT allow Breaker Run to be used as an option for the bottom lift (+/-8 inches) of the total 14" of 1 1/4" dictated in the typical. The Breaker Run for the bottom lift would be paid under the bid item price of 1 1/4" BAD. It would be a savings as Breaker would be cheaper to produce and no QMP placement costs would need to added to the unit price. The current Breaker Run item (4500 tons) included in the bid proposal would still be used for EBS only and those costs would be included in that bid item. | In coordination with the Monroe County Highway Department, please prepare bids for aggregate materials based on the typical sections shown in the plan. | Mike Coleman | 7 | 2026-01-05 10:04 | 2026-01-07 16:45
20260113 | 20260113007 | 7 | Earthwork Tables | Can you please provide the earthwork tables in excel format. Thank you. | The earthwork tables can be found at the following location: https://wisdot.box.com/s/52xz4hoqmtvvz6ojsdzj9h4q75wc9wcw or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 8 | 2026-01-05 14:39 | 2026-01-07 07:02
20260113 | 20260113007 | 7 | Prosecution and Progress - Structure B-41-333 | It is stated in the SPV Article 3 Prosecution and Progress Structure B-41-0333 "Do not remove existing structure or construct Structure B-41-0333 from September 15th through May 15th, both dates inclusive to avoid/minimize impacts to this cold-water resource, which is a Class I trout stream. However, the stream is dry can the restrictions be removed? | The Contractor shall abide by Article 3 Prosecution and Progress of the contract special provisions. The conditions for removal of the existing structure and new structure construction were determined after in-depth coordination with WDNR during final concurrence process. The restrictions noted in the Prosecution and Progress article detail the conditions requested by WDNR during this process. | Mike Coleman | 9 | 2026-01-07 10:53 | 2026-01-08 16:40
20260113 | 20260113007 | 7 | Aggregate Conversion Rates | What are the conversion rates used for Base Aggregate Dense 3/4" and Base Aggregate Dense 1 1/4"? | 2.1 Tons/CY was used for calculating the estimated quantity of Base Aggregate Dense ï¿½-Inch. 2.0 Tons/CY was used for calculating the estimated quantity of Base Aggregate Dense 1 ï¿½-Inch. | Mike Coleman | 10 | 2026-01-07 11:07 | 2026-01-12 07:48
20260113 | 20260113008 | 8 | Type M Railing Quantity | The current bid quantity for railing is 88.8 LF. According to CMM specification 232.4 should the correct quantity be 89 LF? CMM specification 232.4 states all pay measurement shall be rounded to the nearest full unit of measure unless listed in table 232-2. It creates issues during pay apps as the field engineer is advised to follow CMM 232.4. | The correct quantity is 89 LF. This quantity will be corrected via addendum. | Mike Coleman | 1 | 2025-12-11 14:21 | 2025-12-18 07:29
20260113 | 20260113008 | 8 | Geotech Report for B-41-339 | Will the geotech report for B-41-339 be made available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/7drhkj0mkb56z37yuza3kyneuee5uv59 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-12-17 11:56 | 2025-12-18 13:54
20260113 | 20260113008 | 8 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Interior Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the bridge need to be reopened during the dates called out? | No, the bridge does not need to be reopened during the holiday and special event dates. | Mike Coleman | 3 | 2025-12-25 16:30 | 2026-01-05 14:33
20260113 | 20260113008 | 8 | Construction Schedule | 35 working days does not seem to be an adequate amount of time to complete this project considering the amount of work and curing days required in the contract. Pre-boring, concrete approach slabs, and limited site access due to OH lines will limit productivity. 35 working days is not enough time to complete this work. Would the Department consider adding additional working days to the contract? | Yes, the Department will allow an additional 20 working days, for a total of 55 working days, to complete the project. This change will be covered in an addendum. | Mike Coleman | 4 | 2026-01-06 08:15 | 2026-01-08 16:34
20260113 | 20260113009 | 9 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH A traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the bridge need to be reopened during the events called out? | The bridge does not need to be open to traffic during the Holiday and Special Event time frames. | Mike Coleman | 1 | 2025-12-25 16:32 | 2025-12-29 11:17
20260113 | 20260113010 | 10 | B-53-0154 Quantities | Quantities for structure B-53-0154 are not included in the Estimate of Quantities. | The structure plans were inserted in the plan set on accident. An addendum will be issued to remove the structure plans. | Mike Coleman | 1 | 2025-12-15 15:54 | 2025-12-18 07:19
20260113 | 20260113010 | 10 | UPRR Flagging | Due to the significant dollar value that will be required on this project for railroad flagging, can the Department add the administrative item of railroad flagging to the contract to share the risk with prospective bidders? | The Department considered the request and is electing to not add the administrative item, bid accordingly. | Mike Coleman | 2 | 2025-12-19 09:01 | 2025-12-23 09:19
20260113 | 20260113010 | 10 | Asbestos Inspection Report for B-53-154 | Is the Bridge Asbestos Inspection Report for B-53-154 available for review? | The Asbestos Inspection Report can be found at the following location: https://wisdot.box.com/s/zcszgj4hhd6q9kpg852nn6hux81sjqfd or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-12-23 09:12 | 2025-12-23 09:15
20260113 | 20260113010 | 10 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying USH 51 or W Delavan Drive traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the entire work zone need to be reopened, and Traffic control equipment removed from site during the dates stated? | The work zone does not need to be reopened and traffic control equipment installed per plan does not need to be removed during the holidays and special events. | Mike Coleman | 4 | 2025-12-25 16:37 | 2025-12-30 09:02
20260113 | 20260113010 | 10 | Railroad Agreement | Has the Department secured a signed stipulation or other form of agreements with the Railroad for the work that is to be performed on the B-53-135 structure? |  |  | 5 | 2026-01-06 08:35
20260113 | 20260113011 | 11 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Mill Park Drive traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the entire work zone need to be reopened, and all traffic control equipment removed from site for the called-out dates? | No work or hauling may be performed during the specified dates but the bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 16:40 | 2026-01-06 13:27
20260113 | 20260113012 | 12 | Holiday Restrictions | It states to close STH 78 from STH 81 to STH 39 to through traffic for the duration of the project. Then under Holiday and Special Event Work Restrictions it states to clear the entire traveled way and shoulders of all equipment,barricades etc that may impede the free flow of traffic. Will the road need to be fully opened during such events? | The detour will remain in place for the duration of the project and not be taken down during the holiday and special events. During Holiday and Special events, no construction activities will be allowed within the project limits. An addendum will be issued. | Mike Coleman | 1 | 2025-12-17 15:41 | 2025-12-19 11:58
20260113 | 20260113012 | 12 | Storing Equipment on job site | On page 5 of 50 in the Traffic article, it states that equipment, vehicles, construction materials can not be stored within 30 feet of the lanes of STH 78. Can you clarify that this does not mean or include in the reconstruct areas?... that it only is intended for the rural milling/paving areas? This isn't reasonable or feasible for the reconstruct areas so I'm guessing that this is not the intent for that area. | This requirement is intended for the section from Center Street, Station 14+00 to the north project limits, Station 546+21. An addendum will be issued. | Mike Coleman | 2 | 2025-12-18 07:57 | 2025-12-19 11:59
20260113 | 20260113012 | 12 | Epoxy Crack Sealing, Item 509.9020.S | Is it the intent for this to be pressure injected (where crack is ported and capped), or is it to be gravity fed? | The intent is for the epoxy crack sealant is to be gravity fed. | Mike Coleman | 3 | 2025-12-18 16:29 | 2025-12-24 08:38
20260113 | 20260113012 | 12 | 509.2100.S-Concrete Masonry Deck Repair | For these repairs, is it acceptable to use horizontal rapid-set concrete patch material from the approved product list in place of the Grade C or E concrete? | This item is an STSP item which specifies grade C or E concrete, bid per the contract requirements. | Mike Coleman | 4 | 2025-12-29 15:30 | 2026-01-06 13:26
20260113 | 20260113012 | 12 | MGS Thrie Beam at B-33-40 | Can this connection location be redesigned or can someone answer a few questions... Page 25 states that the first 5 posts are to remain and replace rail. Under what bid item is this work done? What is it being replaced with? How does the MGS Thrie Beam Transition connect in this location? How is contractor to use the existing clipped wood posts with no blocks while maintaining guardrail SDDs? And lastly, if the rail over the first 5 posts is supposed to be MGS Thrie Beam when completed, it doesn't appear that the concrete pad is low enough for the new panel to fit above it while maintaining standard guardrail heights. | Removing the rail is paid for under the removing guardrail bid item, 204.0165. Installation of a new MGS Thrie Beam transition is paid for under 614.2500, utilizing the existing first 5 posts. New posts will be required past the first 5 posts and paid for as part of item 614.2500. | Mike Coleman | 5 | 2025-12-30 10:18 | 2026-01-12 06:46
20260113 | 20260113012 | 12 | B-33-40 Traffic Control | Will the Bridge be allowed to be closed to any traffic during Concrete Repairs and the associated cure times, or will the Department require flagging and/or temporary stop lights to direct traffic over the bridge? | The bridge work will be completed half at a time. A 12-foot lane needs to be maintained at all times through the work zone. An addenda will be issued to address this item. | Mike Coleman | 6 | 2026-01-02 10:56 | 2026-01-06 13:33
20260113 | 20260113012 | 12 | Bird Deterrent Systems-B-33-40 | In regard to B-33-40 the anticipated concrete surface repair work is at the wing walls and near the abutments. With no work anticipated on the underside of the structure between pier 1 and pier 2. If this is the case, will the bird deterrent system be required between pier 1 and pier 2? Or would it only be required between the east abutment and pier 1 and the west abutment and pier 2 where the work is being performed? | The contractor should bid the project to net the bridge as noted in the proposal. | Mike Coleman | 7 | 2026-01-08 12:34 | 2026-01-12 06:50
20260113 | 20260113012 | 12 | Addendum #1 | Can the Department provide the design schedule with the updated Add. #1? |  |  | 8 | 2026-01-09 13:35
20260113 | 20260113013 | 13 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH E traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed during stated events? | All traffic control devices do not need to be removed from the site during the dates listed. However, any devices left on site shall not impede the free flow of traffic on the roadway excluding the bridge out hard closure. | Mike Coleman | 1 | 2025-12-25 17:11 | 2025-12-30 08:37
20260113 | 20260113013 | 13 | Frog Biologist | Who is responsible for hiring and coordinating the frog biologist? If it is the contractor, does the Department have a list of qualified biologists they can share? | The frog biologist will be hired by the County or by WisDOT. | Mike Coleman | 2 | 2025-12-28 14:22 | 2026-01-05 14:51
20260113 | 20260113013 | 13 | Causeway or Tramway | Will the Department/DNR allow a temporary causeway and/or tramway to be utilized for removals and construction access? | The Contractor must adhere to the instream and buffer zone restrictions as outlined in the Contract Proposal; Special Provisions Article 3 Prosecution and Progress, Article 10 Environmental Protection, Blanchardâ€™s Cricket Frog and Addenda. Any requests by the contractor must be in accordance with Articles 3 and 10, WisDOT Standard Specification 203.3.2.2.3.4 Debris Capture, and any applicable requirements of the Contract. | Mike Coleman | 3 | 2026-01-06 13:43 | 2026-01-08 16:54
20260113 | 20260113014 | 14 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 130 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed during the dates stated? | The roadway shall remain closed to through traffic. All traffic control devices do not need to be removed from the project during the dates listed. However, any devices left on site shall not impede the free flow of local traffic on the roadway unless it is protecting the traveling public from an obstacle / hazard. | Mike Coleman | 1 | 2025-12-25 17:15 | 2025-12-30 08:58
20260113 | 20260113014 | 14 | Remove and Re-install W-Rail and Timber Rail Post | Paragraph 2 of the Construction section reads, 'If the contractor or engineer discovers steel w-rail, timber rail posts and any associated hardware is damaged or in need of repair prior to removal of said items, the contractor shall replace the item in-kind at no expense to the department.' This is not how salvage and re-install bid items generally read. Question 1. What level of 'damaged or in need of repair' is expected for contractor replacement? Dents or visible rust or more than this level? Question 2. Paragraph 3 discusses contractor replacement if the contractor damages the material. Is this what was intended or is the contractor responsible for damage that occurs or has occurred to this material prior to beginning the work? | 1. The intent of this SPV is to replace items that are damaged beyond their ability to function as a unit. It is not intended to replace dented or rusted components. 2. Paragraph 3 is in reference to contractor damage of the components of the rail and posts that occur during removal, storing and reinstallation. | Mike Coleman | 2 | 2025-12-30 15:15 | 2026-01-05 14:10
20260113 | 20260113015 | 15 | Standard Specifications | Can you please verify that the 2025 spec book is still current for the January letting? Usually the new spec book for 2026 would be current for the November 2025 letting but 2026 is the "reorganized pilot spec" and assuming not official yet? | The department did not release a 2026 standard spec. Use the 2025 standard spec and ASP-6 that went into effect with the November 2025 letting. | Mike Coleman | 1 | 2025-12-11 08:18 | 2025-12-18 13:50
20260113 | 20260113015 | 15 | 63"x98" elliptical pipe | County Materials no longer produces 63"x98" elliptical pipe, however 68"x106" would be an available alternative. Please advise if this proposed size would be an approved alternate. Thanks, | An addendum will be posted to revise the dual 63â€x98â€ horizontal elliptical pipes to dual 68â€x106â€ horizontal elliptical pipes (B-13-922). | Mike Coleman | 2 | 2025-12-15 12:35 | 2025-12-23 09:26
20260113 | 20260113015 | 15 | Geosynthetics for Subgrade Reinforcement | Can a Type SR (Subgrade Reinforcement) Geotextile be utilized in lieu of a Type SR Geogrid? Type SR Geotextiles can offer the same, if not better, performance and provide separation between the subgrade and aggregate layers. Geotextiles can also be made in 15' and 17' wide rolls resulting in more efficient installation, while geogrids are typically 12.5' wide. | At this time, the contractors should bid the project based on the plans and specs as shown. If you are trying to get a product added to the Approved Products List, please refer to standard spec 106.3. | Mike Coleman | 3 | 2025-12-16 14:09 | 2025-12-22 11:51
20260113 | 20260113015 | 15 | Structures C-13-2090 / C-13-2091 Precast Box Culvert | These Structures do not have an allowance for a Precast Concrete Box Culvert stated. Is WISDOT going to allow a precast alternative to be submitted? | Cast in place will be required for Structures C-13-290 & C-13-2091, as they offer increased serviceability for users of pedestrian underpasses. Precast alternatives will not be allowed. | Mike Coleman | 4 | 2025-12-17 11:19 | 2025-12-22 13:11
20260113 | 20260113015 | 15 | Holiday and Special Event Work Restrictions | Under Holiday and Special Event Work Restrictions it states to clear the entire traveled way and shoulders of all equipment,barricades etc that may impede the free flow of traffic. Will the road need to be fully reopened, and all TC equipment removed during such events? | Follow the staging outlined in the Traffic section of the Projectâ€™s Special Provisions. The contractor is to halt any operations that during the Holidays and Special Events time periods listed in the Special Provisions that would impede the flow of traffic through the work zone during those time periods. | Mike Coleman | 5 | 2025-12-17 15:50 | 2025-12-23 09:58
20260113 | 20260113015 | 15 | Earthwork Data | Can the Earthwork Data be provided in Excel format? | The earthwork excel sheets can be found at the following location: https://wisdot.box.com/s/n7mosapftneoiwtrwj9mm2cem7tfjb6a or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 6 | 2025-12-18 13:50 | 2025-12-22 13:16
20260113 | 20260113015 | 15 | SPECIALS #64. SIGNAL CONTROLLER AND CABINET | PAGE 91 B.12.5 TS2 TYPE 1 CONTROLLER: PROVIDE MCCAIN FLEX IS LISTED. WOULD AN ECONOLITE COBALT BE ACCEPTED AS AN APPROVED EQUAL FOR THIS? | Updated response: A plan addendum is being prepared, and the Econolite Cobalt controller will now be the requested controller by the City of Stoughton. | Mike Coleman | 7 | 2025-12-19 12:21 | 2025-12-23 09:58
20260113 | 20260113015 | 15 | Rock Excavation | Presplit rock table shows a quantity of 350 LF for 673+50-677+00 NB LT, but the cross section shows this area as sloped and not a presplit wall. Which is correct? | Bid Item 205.1300 Presplitting Rock was inadvertently quantified (350 LF) between Station 673+50 NB and 677+00 NB LT and is not anticipated to be required within this rock excavation area to establish proposed slopes. An addendum will be prepared to clarify this. | Mike Coleman | 8 | 2025-12-22 11:13 | 2025-12-23 09:27
20260113 | 20260113015 | 15 | Asbestos Report and Geotech Report | Can you post the asbestos report and geotech report? | The Asbestos Report and Geotech report can be found at the following location: https://wisdot.box.com/s/n7mosapftneoiwtrwj9mm2cem7tfjb6a or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 9 | 2025-12-22 13:03 | 2025-12-22 13:10
20260113 | 20260113015 | 15 | Stage 4 removals/excavation | On the 73 project, how are the stage 4 removals/excavation accounted for in the MQs for the needed sidewalk construction? We're not seeing them accounted for in the removal items or the Earthwork Summary table. | Concrete sidewalk removal is included in item 204.0155 on page 1 of the MQ sheets. All necessary excavation or earthwork for the sidewalk is covered under the Common Excavation item and information is contained in the plans. | Mike Coleman | 10 | 2025-12-23 15:30 | 2025-12-29 09:59
20260113 | 20260113015 | 15 | Utility Relocation | Given some of the longer durations of utility relocation. Do the utility companies that will still be working on the relocations during construction of the project have a schedule and work plan showing what order they are intending to perform their work that can be provided to the contractor? | An addendum will be issued to provide additional clarification regarding anticipated AT&T - Communication and City of Stoughton Utilities - Electricity private utility work timelines within the respective working days indicated in the special provisions. | Mike Coleman | 11 | 2025-12-26 10:43 | 2026-01-06 07:04
20260113 | 20260113015 | 15 | Earthwork Data Tables | There does not seem to be an Earthwork Data Table for the 5845-16-73 plans. Could this be added to break down earthwork by stage? |  |  | 12 | 2025-12-30 08:54
20260113 | 20260113015 | 15 | Color of signals, mounting hardware & audible push buttons | 2 of the 3 intersections in this project are currently showing yellow signals, mounting hardware and buttons, but the specifications in the proposal do not note what color the new replacement signals, mounting hardware and buttons should be. Can you please confirm if these should all be yellow? |  |  | 13 | 2025-12-30 09:24
20260113 | 20260113015 | 15 | Designer's Schedule | Can the designer's schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/n7mosapftneoiwtrwj9mm2cem7tfjb6a or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 14 | 2025-12-31 07:58 | 2026-01-05 14:12
20260113 | 20260113015 | 15 | 5845-16-83 Water and Sanitary | It appears that the staging lines from proj ID 5845-16-73 and 5845-16-83 (water/sanitary) do not line up and will be extremely difficult to build and in some instances close to unbuildable. Will the Department review this and provide more insight as to how the Department wants to build this portion of the project? It seems as though items for temporary water services, nighttime work, temporary shoring, and/or bypass pumping items should be added to the contract or the staging should be adjusted. |  |  | 15 | 2026-01-02 12:32
20260113 | 20260113015 | 15 | 5845-16-76: Railing Pipe | Details for Item 0192â€“Railing Pipe were not provided. Can you please provide the detail drawings? |  |  | 16 | 2026-01-05 10:21
20260113 | 20260113015 | 15 | Soils Report | Can the Department provide the Geotechnical Report for this project? | The Geotech report can be found at the following location: https://wisdot.box.com/s/n7mosapftneoiwtrwj9mm2cem7tfjb6a or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 17 | 2026-01-05 12:36 | 2026-01-05 14:47
20260113 | 20260113015 | 15 | City of Stoughton Specifications | Can the Department Provide the applicable City of Stoughton specifications for the water and sewer work on this contract? |  |  | 18 | 2026-01-05 12:37
20260113 | 20260113015 | 15 | Aggregate Conversion Rates | What are the conversion rates used for Base Aggregate Dense 3/4", Base Aggregate Dense 1 1/4", and Select Crushed Material? | For Project ID 5845-16-73: A unit conversion of 1.9 Tons/CY was used for 305.0120 Base Aggregate Dense 1 1/4-Inch. A unit conversion of 1.8 Tons/CY was used for 312.0110 Select Crushed Material. For Project ID 5845-16-74: A unit conversion of 2.1 Tons/CY was used for 305.0110 Base Aggregate Dense 3/4-Inch. A unit conversion of 2.0 Tons/CY was used for 305.0120 Base Aggregate Dense 1 1/4-Inch. A unit conversion of 1.9 Tons/CY was used for 312.0110 Select Crushed Material. | Mike Coleman | 19 | 2026-01-07 12:29 | 2026-01-08 16:39
20260113 | 20260113015 | 15 | Select Crushed Material - EBS Backfill | On project ID 5845-16-74, it looks like the Select Crushed Material to backfill the EBS has not been calculated correctly. Particularly in Division 3 (Stage 2-SB-RD to CTH B) and Division 4 (Stage 3-RB, Stage 3-NB-RD to CTH B) | The Select Crushed Material used for excavation below subgrade (EBS) backfill has been calculated correctly for the two divisions identified in the question. For these locations (â€œSTAGE 2-SB-RD TO CTH Bâ€ and â€œ STAGE 3-NB-RD TO CTH Bâ€), excavation includes EBS required for retaining wall structures R-13-387, 388, 389, 390 (adjacent to pedestrian underpass structure C-13-2090) which is paid for as common excavation; however, this excavation area is being backfilled with 209.1500 Backfill Granular Grade 1 per the associated structure plans (not Select Crushed Material). The Backfill Granular Grade 1 quantities can be found in the Backfill Granular Summary Table on the miscellaneous quantities plan sheets. The â€œFOR UNDERPASS EBSâ€ note in the remarks column of this table refers to the retaining wall structures associated with the pedestrian underpass. | Mike Coleman | 20 | 2026-01-07 12:35 | 2026-01-08 16:28
20260113 | 20260113015 | 15 | Sign Structure Staking | Line Item 0754 covers construction staking for S-13-0618, what about staking for the other five sign structures? |  |  | 21 | 2026-01-08 11:12
20260113 | 20260113015 | 15 | Question #15 | When will question 15 be addressed? The addendums to date have not addressed the issue(s) of how the water and sewer cannot be installed (and keep businesses/residents in service) with the specified staging. |  |  | 22 | 2026-01-12 09:13
20260113 | 20260113016 | 16 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Losey Boulevard traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control equipment removed during the dates stated? |  |  | 1 | 2025-12-25 17:21
20260113 | 20260113017 | 17 | Gravity Wall Questions | Does the leveling pad need to be 12" thick and extend 12" in front of the block as the plans show or 6" thick and extend 6" in front of the block as referenced by the SPV? What are the theoretical pay limits for the wall? Could the pay quantity for the wall be verified? Based on the finish grades given and the 1.5' bury depth that is typically paid, the quantity seems off. | There is a discrepancy between the construction detail and the special provision for this item (16. Wall Modular Block Gravity Landscape (Sta 31+330 LT), Item SPV.0165.01). The plan detail (shown on page 8 of the plan titled â€œDetail for Wall Modular Block Gravity Landscapeâ€ should have shown a 12â€ option for base aggregate and a 6â€ option for concrete for the leveling pad. The special provision is correct and dictates the requirements of the pad. If base aggregate is used, the pad will need to be 12â€ thick and extend 12â€ in front of the wall. If a concrete leveling pad is used the pad will need to be 6â€ thick and extend 6â€ in front of the wall. An addendum will be issued that will modify the plan detail to show both options for the leveling pad. The theoretical pay limits for the wall is the exposed face of the wall. The pay quantity is based on exposed S.F. of the wall. The buried portion of the wall is NOT included in the estimated quantity. The wall is approximately 140â€™ long with an average height of approx. 3.75â€™ tall (exposed face) so the estimated quantity of 530 S.F. should be correct. | Mike Coleman | 1 | 2025-12-17 08:42 | 2025-12-19 06:45
20260113 | 20260113017 | 17 | Gravity Wall Exposed Area | Based on the front of wall elevations and back of wall elevations, the average wall height seems to be about 3.1 FT and a total pay quantity SF of approx 435 SF. Could this be verified and if needed, addressed with the addendum? | The front of wall and back of wall elevations are being confirmed and any adjustments to the S.F. quantity for the retaining wall will be addressed in an upcoming addendum. | Mike Coleman | 2 | 2025-12-19 07:38 | 2025-12-29 08:55
20260113 | 20260113017 | 17 | Holiday and special event | It states,Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH OT traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed during the stated dates? | The intent of this special provision is to make sure there is no work or hauling of materials on CTH OT and that the shoulders are clear of any equipment or materials during these dates. It is understood that traffic control that is in place being used by the various stages will need to remain in place during these holiday periods. | Mike Coleman | 3 | 2025-12-25 17:32 | 2026-01-02 08:39
20260113 | 20260113017 | 17 | geo technical | Is there a Geo-Technical report available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/wqrnievzy1g6ah1vglqi0l8opmw8mpw3 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 4 | 2026-01-05 14:32 | 2026-01-06 07:11
20260113 | 20260113018 | 18 | Item #14 Granular Backfill Grade 2 | In the miscellaneous quantities it shows the grade 2 backfill for culvert replacements. Per the notes on page 18 of the plan where it states that "transition cut to be backfilled with trench backfill as specified in spec 520", which consists of material from the typical roadway section. What is this quantity to be used for? As the miscellaneous quantities and construction detail do not correlate. | The quantity of backfill granular grade 2 is included in the project to be utilized in the event the trench backfill material is found to be unsuitable by the engineer. An addendum will be issued with an updated construction detail and quantities to show all backfill material to be backfill granular grade 2 material. | Mike Coleman | 1 | 2025-12-16 15:16 | 2025-12-19 12:04
20260113 | 20260113018 | 18 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 33 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed from site during the stated dates? | The detour is intended to be in place for the entire duration of the project and not taken down for the holiday weekend. | Mike Coleman | 2 | 2025-12-25 17:36 | 2026-01-02 08:42
20260113 | 20260113018 | 18 | Fence | Per special #11 on sheet 7 contractor is supposed to contact the property owner to have a fence removed. Does the Department have an agreement with the owner? If not, the contractor does not have the authority to request the owner to remove the fence and the contractor is asking for the special to be removed. | The Department does not have an agreement with the property owner yet, but will have one prior to construction beginning. The article will remain in the special provisions. | Mike Coleman | 3 | 2026-01-05 10:16 | 2026-01-07 17:01
20260113 | 20260113018 | 18 | Asphalt Shoulders | The asphalt shoulders show a 4% shoulder. Would it be allowable to mill and pave the shoulders at a 2% grade with the mainline? | No. The 4% asphalt shoulder cross slope is included to account for the 1.5-inch profile increase. | Mike Coleman | 4 | 2026-01-05 10:17 | 2026-01-07 17:00
20260113 | 20260113019 | 19 | Design Schedule | Will the Department please provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/06ix3t0kerxwe0asb3oodskot7ohy382 or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-12-18 10:22 | 2025-12-19 11:03
20260113 | 20260113019 | 19 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 26 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed from site during the stated dates? | Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 26 traffic | Mike Coleman | 2 | 2025-12-25 17:45 | 2026-01-05 14:28
20260113 | 20260113019 | 19 | Distress Milling HMA | Per the detail on sheet 18, distressed milling is calling for 3-4 inches of asphaltic surface. Will the Department add the quantity to Asphaltic Surface? | An addendum will be issued. | Mike Coleman | 3 | 2026-01-05 11:26 | 2026-01-06 06:41
20260113 | 20260113020 | 20 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying USH 12 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed during the called out dates? | The workzone needs to be open and all traffic control devices that may impede free flow of traffic. | Mike Coleman | 1 | 2025-12-25 17:48 | 2025-12-30 08:49
20260113 | 20260113021 | 21 | Aggregate Conversion Rates | What are the conversion rates used for Base Aggregate Dense 1 1/4" and Pit Run? | Base Aggregate Dense 1 1/4": 2 Tons/CY Pit Run: 1.8 Tons/CY | Mike Coleman | 1 | 2025-12-19 09:06 | 2025-12-22 11:53
20260113 | 20260113021 | 21 | Holiday and special event | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 31 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from site during the dates called out? | need to clear devices that may impede the free flow of traffic. Are they asking about whether they have to open the roadway back up to 3 lanes during holiday periods? If so, they do not. | Mike Coleman | 2 | 2025-12-25 17:53 | 2025-12-29 11:16
20260113 | 20260113021 | 21 | Soils Report. | Please provide the soils report | The Geotech report can be found at the following location: https://wisdot.box.com/s/qp96ovqvnhtvtj9mnj0m6vancgk2dw2b or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 3 | 2025-12-26 15:30 | 2025-12-30 08:23
20260113 | 20260113021 | 21 | Bank Run | The local area has limestone for breaker run and existing pavement can be used to make breaker run. The standards specifications allow stone or concrete to be used as breaker run. Can WisDOT please confirm breaker run can be used in Liu of bank run? | Substitute materials will be allowed in accordance to the special provisions and standard specifications for the item Pit Run. | Mike Coleman | 4 | 2026-01-09 05:16 | 2026-01-12 09:53
20260113 | 20260113022 | 22 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying IH 94 or Silvernail Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed from site during the called out dates? | No. The contractor is just not permitted to work or haul. | Mike Coleman | 1 | 2025-12-25 17:57 | 2025-12-29 11:12
20260113 | 20260113022 | 22 | Geotechnical Report | Please provide a copy of the geotechnical report. | The Geotech report can be found at the following location: https://wisdot.box.com/s/xct6ya0ivdaiod5uxecpxzyh47n2ebxr or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-01-09 09:13 | 2026-01-12 13:26
20260113 | 20260113025 | 25 | Prosecution and Progress | When USH 51 through traffic in not detoured, do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying USH 51 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic from 12:00 PM Friday to 6:00 AM Monday. Is this every Friday to Monday? | Yes, this is every Friday to Monday. | Mike Coleman | 1 | 2025-12-18 15:08 | 2025-12-22 12:57
20260113 | 20260113025 | 25 | Design Schedule | Can the department please provide the design schedule for the project? | The design schedule can be found at the following location: https://wisdot.box.com/s/6ed3e48jmjjub5cvhnlzheysz1n52g5c or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-12-23 08:26 | 2026-01-05 14:04
20260113 | 20260113025 | 25 | Masonry Deck Repair | Would rapid set deck repair from the APL be allowed for the Masonry Deck Repair? | No. Rapid set deck repair material from the APL may not be used in place of ready-mix concrete for the Concrete Masonry Deck Repair. | Mike Coleman | 3 | 2025-12-29 14:04 | 2026-01-06 13:30
20260113 | 20260113025 | 25 | Staging for Polymer Overlay | Can the Polymer Overlay be done in stage 1 during the full closure if it falls within that allowed time frame? | Polymer Overlay could be done during stage 1 provided the minimum 28-day concrete cure time in Polymer Overlay, Item 509.5100.S Deck Preparation C.2.1 is met. | Mike Coleman | 4 | 2026-01-05 11:42 | 2026-01-06 13:25
20260113 | 20260113026 | 26 | Pedestrian Curb | Will Pedestrian Curb be required in the ramps at the existing islands? Also at a few of the ramps thru out the project. If Yes, can the pedestrian curb item be added to the project. | The design team reviewed the need for pedestrian curb and agree that the bid item Concrete Curb Pedestrian needs to be added to the proposal. An addendum will be issued to correct this issue. | Mike Coleman | 1 | 2025-12-16 09:35 | 2025-12-19 12:07
20260113 | 20260113026 | 26 | Continuous Diamond Grinding Quantity | Is the intention to only diamond grind the concrete repair and replace patches in the travel lanes per the detail on plan sheet #14? With the exception to WB lanes indicated on plan sheet #157 (Continuous area) That would lower the bid item quantity substantially. | The design intent is to perform diamond grinding on the concrete repairs and replacement patches indicated on plan sheet #14, from the projectâ€™s begin point to 64th Street and from Grant Avenue to the projectâ€™s end. The section between 64th Street and Grant Avenue will undergo diamond grinding across the full width of the concrete pavement for both westbound and eastbound lanes (65 mph section). An addendum will be issued to address and correct the discrepancies currently reflected in the plans. | Mike Coleman | 2 | 2025-12-16 13:17 | 2025-12-19 12:07
20260113 | 20260113026 | 26 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 54 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control equipment removed from the site during the dates specified? | Yes, the intent is that during the specified dates, the work zone must be fully reopened to traffic and all traffic control devices, equipment, and materials removed from the traveled way and shoulders. This ensures the free flow of traffic on STH 54 as required. If there are any exceptions or temporary measures needed, they should be coordinated and approved in advance by WisDOT or the engineer on site. | Mike Coleman | 3 | 2025-12-25 18:09 | 2025-12-30 08:51
20260113 | 20260113026 | 26 | Removing Asphalt Surface | On page 127 in the MQ's it shows asphalt removal at station 237+64-238+28 and 374+39-382+39. But there are no removals shown in the plan. The first area is by a railroad that could add days of railroad flagging. Please clarify if the plan is correct or if the MQ is correct. Will this change the asphalt quantity? | The removing asphalt quantity will change, but the asphaltic surface was quantified correctly. An addendum will be issued to correct the bid item 204.0110 â€“ Removing Asphaltic Surface. | Mike Coleman | 5 | 2026-01-06 18:01 | 2026-01-07 17:07
20260113 | 20260113027 | 27 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH D traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control equipment need to be removed from the site during specified dates? | No work or hauling may be performed during the specified dates but the bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 19:24 | 2025-12-30 08:41
20260113 | 20260113028 | 28 | Geotech Report for B-24-46 | Will the geotech report for bridge B-24-46 be made available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/7aa5x774qot99p68wjcpd46vpr2vuuxy or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-12-17 15:21 | 2025-12-18 13:40
20260113 | 20260113028 | 28 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Mill Street traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed from the site during the specified dates? | All traffic control devices do not need to be removed from the site during the dates listed. However, any devices left on site shall not impede the free flow of traffic on the roadway excluding the bridge out hard closure. | Mike Coleman | 2 | 2025-12-25 19:28 | 2025-12-29 11:18
20260113 | 20260113028 | 28 | Crack & Damage | Will a crack and damage survey, and/or seismograph monitoring be required for this contract due to close proximity buildings? | The plans call for pre-boring rock or consolidated materials at both abutments, therefore pile driving would not be required and would not require a crack and damage survey. | Mike Coleman | 3 | 2026-01-06 08:19 | 2026-01-07 16:40
20260113 | 20260113028 | 28 | Utilities | Is there any available depths provided for the utilities under proposed wings 2 & 3? If so, please provide. | The depths of the utilities in question are unknown; however, as noted in the Special Provisions, Article 6, the Alliant Energy gas main will be discontinued in place prior to construction. | Mike Coleman | 4 | 2026-01-07 10:22 | 2026-01-08 16:32
20260113 | 20260113029 | 29 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH P traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be reopened and all traffic control devices removed from the site during specified dates? | No work or hauling may be performed during the specified dates but the bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 19:36 | 2025-12-29 11:04
20260113 | 20260113029 | 29 | Concrete Seal for Cofferdam | Would the Department consider adding a concrete seal item for the cofferdam to allow for proper dewatering? Given the water depth to the bottom of the proposed pier, pouring concrete underwater appears to be problematic without proper dewatering. Complete dewatering of the cofferdam would be much more achievable with a concrete seal. | Dewatering of the cofferdam through the use of a concrete seal at this site may be warranted, especially if the observed water level is higher than what was surveyed during the design of the project. The concrete seal item, if deemed necessary at the time of construction, would be handled through a contract change order. | Mike Coleman | 2 | 2026-01-06 08:23 | 2026-01-12 09:57
20260113 | 20260113030 | 30 | Geotech Report for B-37-487 | Will the geotech report for Bridge B-37-487 be made available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/by74tdvwgszik5u62b7mlqfqeokb0qzw or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 1 | 2025-12-17 15:40 | 2025-12-18 13:46
20260113 | 20260113030 | 30 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Abe Lincoln Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic Does the work zone need to reopened and all traffic control devices removed from the site during called out dates? | No work or hauling may be performed during the specified dates but the bridge closure may remain in place. | Mike Coleman | 2 | 2025-12-25 19:42 | 2025-12-29 11:05
20260113 | 20260113031 | 31 | Asphaltic Surface | Would the department consider changing the pay item of 3MT 58-28S and 4Mt 58-28H to an asphaltic surface item with a special provision detailing the type of mix it wants for both layers? | The department prefers to keep the plans and specs as shown. | Mike Coleman | 1 | 2025-12-17 16:51 | 2025-12-19 06:38
20260113 | 20260113031 | 31 | Holidays and special events | it states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Buckbee Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from the site during called out dates? | Due to the Buckbee Road bridge being â€œfailed/out of serviceâ€, the work zone does not need to be opened and traffic control devices do not need to be removed from the project site during Holidays/Special Events | Mike Coleman | 2 | 2025-12-25 19:46 | 2025-12-30 09:03
20260113 | 20260113031 | 31 | Traffic Control | Will the department be adding individual bid items for Traffic Control? | Waupaca County is supplying the detour and traffic control. There is a Base Traffic Control Bid Item (643.5000) included to account for miscellaneous Traffic Control items if they arise, for a shoulder closure, etc. | Mike Coleman | 3 | 2026-01-06 14:10 | 2026-01-08 04:56
20260113 | 20260113031 | 31 | Traffic Control Bid Items. | There are no individual Traffic Control Bid Items, Such as: 643.0420 Traffic Control Barricades Type III 643.0705 Traffic Control Warning Lights Type A 643.0900 Traffic Control Signs Should everything be included into the Base TC bid or will these be added in via an addendum? | Waupaca County is supplying the detour and traffic control. There is a Base Traffic Control Bid Item (643.5000) included to account for miscellaneous Traffic Control items if they arise, for a shoulder closure, etc. | Mike Coleman | 4 | 2026-01-06 14:56 | 2026-01-08 04:57
20260113 | 20260113032 | 32 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH D, STH 49 or CTH XX traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from site during the called out dates? | The work zone does not need to be opened to traffic. | Mike Coleman | 1 | 2025-12-25 19:49 | 2026-01-02 08:48
20260113 | 20260113033 | 33 | Temporary Epoxy Marking | There are temporary pavement marking epoxy items on the miscellaneous quantities table but not on the proposal. Are they supposed to be on this project? | Temporary Pavement Marking Epoxy items are not needed on the project. The two columns in the Temporary Pavement Marking table on sheet 127 labeled Marking Line Epoxy 6-Inch Yellow and Marking Line Epoxy 6-Inch White should actually be labeled Paint, not Epoxy. These two columns are informational only to give the breakdown of white vs. yellow paint and the total for the item is in the column labeled 643.3165 Temporary Marking Line Paint 6-Inch. There is a similar issue with the Pavement Marking table on sheet 128 where the first two columns add up to the item total in the 3rd column labeled 646.2040 Marking Line Grooved Wet Ref Epoxy 6-Inch. These tables will be revised and new plan sheets issued via addendum. | Mike Coleman | 1 | 2025-12-15 15:19 | 2025-12-18 07:20
20260113 | 20260113033 | 33 | Schedule | The contractor is requesting the preliminary schedule use for design. | The design schedule can be found at the following location: https://wisdot.box.com/s/kv7a70orgn6f6kb4iq21etgbcye42hzt or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-12-16 10:47 | 2025-12-18 09:11
20260113 | 20260113033 | 33 | Treated Lumber and Timber | Is it the intent to leave the vertical timber pile in place and just replace the bad horizontal boards? Please clarify. | Yes, the vertical timber pile is to remain in place. Only bad horizontal boards are to be replaced. | Mike Coleman | 3 | 2025-12-16 14:19 | 2025-12-19 06:42
20260113 | 20260113033 | 33 | Culvert Pipe List | Could you please provide the correct culvert pipe list. | The culvert pipe list in the miscellaneous quantities will be revised and submitted in an addendum. | Mike Coleman | 4 | 2025-12-18 10:50 | 2025-12-23 09:27
20260113 | 20260113033 | 33 | Stabilized Base Reclamation | Will there be a bid item added for pulverize and relay ahead of the stabilized base reclamation work? Or is this work incidental? | Payment for pulverizing and relaying is included in the item â€œStabilized Base Reclamationâ€. See Section E Payment of the â€œStabilized Base Reclamationâ€ special provision for more information on what is and is not included in this item. | Mike Coleman | 5 | 2025-12-19 07:29 | 2025-12-22 13:13
20260113 | 20260113033 | 33 | Base Repair for Base Stabilization Process | Since there is such a small quantity allotted for this work, does it make sense to eliminate the requirement for re-stabilizing areas repaired after initial stabilization, and replace this with an asphaltic surface patch in the top 3 to 4-inches of the repaired area? The cost of re-stabilizing will be quite high due to the small quantity and the likelihood that the stabilization equipment will no longer be on site by the time these areas are identified. | Depending on the contractorâ€™s operations and equipment on-site, the Department will consider alternate methods to repair the base on a case-by-case approach during construction. | Mike Coleman | 6 | 2025-12-19 07:31 | 2025-12-23 09:18
20260113 | 20260113033 | 33 | Asbestos Report | Can you post the asbestos report for this project. | The asbestos report can be found at the following location: https://wisdot.box.com/s/kv7a70orgn6f6kb4iq21etgbcye42hzt or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 7 | 2025-12-19 11:16 | 2025-12-19 11:56
20260113 | 20260113033 | 33 | Treated Timber | What is the dimensional lumber required for the wing wall repair? Will the repairs be below water level? Can you be more specific on the dimensions that need to be removed and replaced. | The intent of the timber repairs as noted on the C-58-27 plans is to replace deteriorated existing timber wing backwall boards in kind (i.e. the same cross-section size). Underwater repairs are not expected, but that may be affected by water levels at the time of construction. | Mike Coleman | 8 | 2025-12-22 08:32 | 2025-12-23 09:31
20260113 | 20260113033 | 33 | Spray Applied Membrane | Can a Sheet Applied Membrane Waterproofing from the APL be used in place of the Spray Applied Waterproofing membrane? | No, sheet membrane cannot be used. This project is specifically intended as a test bed for the spray applied membrane, to see whether it will be useful as a standard bid item in the future. | Mike Coleman | 9 | 2025-12-30 16:18 | 2026-01-05 13:59
20260113 | 20260113033 | 33 | Concrete Masonry Deck Repair | Would a Rapid set deck repair material from the APL be used in place of ready-mix concrete for the Concrete Masonry Deck Repair? | No. Rapid set deck repair material from the APL can not be used in place of ready-mix concrete for the Concrete Masonry Deck Repair. A full closure is allowed at structure C-58-0027 so the ready-mix concrete can be used. | Mike Coleman | 10 | 2025-12-31 10:28 | 2026-01-06 13:28
20260113 | 20260113033 | 33 | Type 3 Barricades and Type A Warning Lights | There are no bid items for Traffic Control Type 3 Barricades or Traffic Control Type A Flashing Lights | The Traffic Control Type 3 Barricades and Traffic Control Type A Flashing Lights will be added by addendum. | Mike Coleman | 11 | 2026-01-06 11:41 | 2026-01-07 17:02
20260113 | 20260113033 | 33 | LINE ITEM # | There is no line item number listed for the type 2 barricades that were added in the addendum | There will not be any type 2 barricades as part of the project. This was not intended to be in the addendum. Pedestrian barrier was added to the addendum to redirect pedestrians instead of the type 2 barricades. | Mike Coleman | 12 | 2026-01-11 17:43 | 2026-01-12 12:43
20260113 | 20260113034 | 34 | Liner size SPV 20 | I am not clear if the pipe size listed is the existing / host pipe or the desired liner pipe for both the 24" and 30" items. Would DOT be able to clarify? | The pipe sizes listed on the plan set are for existing 24" and 30" corrugated metal culvert pipes. | Mike Coleman | 1 | 2025-12-12 10:19 | 2025-12-22 12:03
20260113 | 20260113034 | 34 | Rubblizing | The note on sheet 11 states, "install profile wedging prior to rubblizing." This cannot be done as it will insulate the blow and not provide the proper finished product. Can this note be changed or deleted? | An addendum will be issued to address the "profile wedging prior to rubblizing". | Mike Coleman | 2 | 2025-12-18 10:42 | 2025-12-22 12:04
20260113 | 20260113034 | 34 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH BE traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from the site during called out dates? | The traffic control devices for the work zone do not need to be removed for any of the holidays listed as the project is closed to through traffic and has an approved detour route established. The work zone must be left open to local traffic (property owners) throughout the project and during the holidays listed the contractor shall ensure that the work zone is as unobstructed as possible to allow free flow for residents, farm equipment and emergency vehicles. | Mike Coleman | 3 | 2025-12-25 19:57 | 2025-12-30 09:04
20260113 | 20260113034 | 34 | Earthwork Limits | The earthwork Summary Lists Common Excav from Sta 152+20 - 158+09. There is no concrete pvmt shown in this section. If EBS needs to be performed in the section where concrete pvmt exists shouldnt you have an undistributed price for Rem Pvmt to account for this? The pvmt structure is very different where concrete exists compared to the rest of the project. | In the section from STA 158+09 to STA 209+04, the Contractor is to rubblize the existing 8" concrete pavement, which will then serve as base for the new asphalt pavement. No EBS is anticipated in this section, therefore no quantity for concrete pavement removal is needed. | Mike Coleman | 4 | 2026-01-02 12:26 | 2026-01-06 13:23
20260113 | 20260113035 | 35 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 86 traffic outside the project limits, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from the site during the called out dates? | No work or hauling may be performed during the specified dates but the CTH O bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 20:15 | 2025-12-29 11:06
20260113 | 20260113037 | 37 | Holidays and special events | It states,Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 17 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from site during the called out dates? | No work or hauling may be performed during the specified dates but the Woodford Road bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 20:18 | 2025-12-29 11:08
20260113 | 20260113038 | 38 | Adhesive Anchor Embedment | Please provide the minimum embedment length for the adhesive anchors as required per WisDOT SSPC 502.3.14.1(3). | The embedment depth should be 6â€ for the adhesive anchors. | Mike Coleman | 1 | 2025-12-22 14:12 | 2025-12-30 08:52
20260113 | 20260113038 | 38 | Vinyl Sheeting Encasement | The details for the vinyl sheeting on Sheet 4 of 4 of the structure drawings are inconsistent. The plan view detail depicts the vinyl sheeting located outside of the grout encasement, while the end view detail shows the vinyl sheeting integral within the grout encasement. In addition, the specifications appear to be based on a specific vinyl sheet pile product. Assuming the dimensions shown in the plan view represent the exterior face of the vinyl sheeting, the basis-of-design sheet pile dimensions do not accommodate the configuration illustrated in the plan view. There are a limited number of domestic suppliers for this type of product, and customization of the vinyl sheeting is not available. Please clarify the Departmentâ€™s expectations for the Contractor regarding the required configuration and product selection. If the Contractor is expected to make the pier encasement larger, how does this affect the measurement & payment for item 52 - Structural Grout? | The vinyl sheeting should be integral within the grout encasement. The additional width of the pier with the structural grout should be 9-inches on either side of the original pier (total finished thickness of 4-feet). The vinyl sheeting should meet or exceed the specification provided. If the contractor elects to utilize a different product size than shown and stated in the specifications it would be considered means and methods and would not receive additional compensation for additional structural grout. | Mike Coleman | 2 | 2025-12-23 10:08 | 2025-12-30 08:54
20260113 | 20260113039 | 39 | Holiday and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Hills Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from the site during called out dates? | No work or hauling may be performed during the specified dates but the Hills Road bridge closure may remain in place. | Mike Coleman | 1 | 2025-12-25 20:29 | 2025-12-29 11:09
20260113 | 20260113040 | 40 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/n9ubgrmeaqtd5hq0s4l40z8boedp3jib or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-12-22 07:47 | 2025-12-23 09:22
20260113 | 20260113040 | 40 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 29 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be opened and all traffic control devices removed from the site during called out dates? | For this project, the travel lanes should be clear of traffic control devices during holiday periods; however they do not need to be removed from the shoulders. | Mike Coleman | 2 | 2025-12-25 20:33 | 2025-12-30 08:47
20260113 | 20260113040 | 40 | Footing & Wingwall Joint | Is the joint between the footing and wingwalls a requirement or could that be optional? | The joint between the wingwall and footing could be optional; however, rubberized membrane waterproofing on the back face would still be required. | Mike Coleman | 3 | 2026-01-08 06:17 | 2026-01-12 09:58
20260113 | 20260113040 | 40 | SPV Article 13 | What are the parameters of a low water flow? | The joint between the wingwall and footing could be optional; however, rubberized membrane waterproofing on the back face would still be required. | Mike Coleman | 4 | 2026-01-08 06:19 | 2026-01-12 09:59
20260113 | 20260113040 | 40 | Impermeable Barrier | Regarding SPV Article 13, an impermeable barrier is required if water is present. Will there be a bid item for this? | Sandbags or other techniques to divert water away from the wing replacement are included in the item "Cofferdams B-9-29" per Sheet 1 of the structure plan. | Mike Coleman | 5 | 2026-01-08 06:21 | 2026-01-12 10:00
20260113 | 20260113040 | 40 | Will the existing shoulders hold up to traffic in stage 1? | We understand there have been issues with the existing shoulders holding up to traffic when single lane closures are installed. Also, we understand the shoulders did not hold up on the Thorp job last year. To overcome this, WisDOT Proposal 41 in the January Letting is requiring the existing shoulders to be removed and replaced first. Will WisDOT do the same thing on this project if the shoulders are expected to not hold up? |  |  | 6 | 2026-01-10 15:49
20260113 | 20260113041 | 41 | Miscellaneous Quantities | Could the department update the Miscellaneous Quantities to include stationing with the items. | An addendum will be issued to update the MQ sheets. | Mike Coleman | 1 | 2025-12-16 14:43 | 2025-12-18 13:48
20260113 | 20260113041 | 41 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/z4p2dg7typvyxzz8q5r662lfbpms6c9a or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2025-12-22 07:48 | 2025-12-23 09:25
20260113 | 20260113041 | 41 | Bridge Repair Completion Requirements | The special provision state, "...migratory bird nests have been observed on the following structures; however, deterrent is not needed because...(2) it has been determined that anticipated construction activities on the structure will not disturb active nests. Can it be clarified if there are or are not time restrictions on the bridge deck repair work? | The concrete masonry deck repairs are to be completed by April 15, 2026 per the traffic section of the special provisions. The structure polymer overlays can occur after the April 15th date. | Mike Coleman | 3 | 2026-01-11 13:53 | 2026-01-12 12:45
20260113 | 20260113041 | 41 | Interim Completion Date | Why is there an April 15th deadline date for the bridge stated on Page 6 of 61 in the Special Provisions under Stage 1 Construction? Will the department consider removing this interim completion date as it wont yield quality concrete patches on the bridges given time of year. | The April 15th deadline date for the concrete masonry deck repairs is to avoid disturbing migratory bird nests. | Mike Coleman | 4 | 2026-01-12 08:54 | 2026-01-12 12:44
20260113 | 20260113042 | 42 | Design Schedule | Can the department provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/uem73mri1zbkj4017amovyvwx8jtgj3j or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2025-12-30 13:02 | 2026-01-05 14:23
20260113 | 20260113042 | 42 | Prosection and Progress - 70 working Days | There does not appear to be enough time in the contract to complete the project as currently staged. The work includes Stage 1 temporary widening, followed by Stage 2 and Stage 3 bridge removal and replacement, each including structural approach slabs. Given the sequencing of the work and the cure time required for superstructure, structural approach, concrete paving, etc. the available contract time is not sufficient to reasonably complete all stages. Please consider adding additional time to allow the work to be completed. | We have reviewed the project schedule internally and with the Adam. We believe that 70 working days is reasonable for completing the construction of this project based on the staging. We are also restricted on this project by DNR requirements for no-instream disturbance restrictions included in the special provisions. Based on this, we are not proposing any changes to the amount of working days allowed for construction of the project. | Mike Coleman | 2 | 2025-12-30 13:13 | 2026-01-05 14:18
20260113 | 20260113042 | 42 | Geotech Report for B-54-131 | Will the geotechnical report for structure B-54-131 be made available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/uem73mri1zbkj4017amovyvwx8jtgj3j or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-01-06 12:58 | 2026-01-07 16:48
20260113 | 20260113043 | 43 | #5 Bar Couplers | The bid item for #5 Bar Couplers should be changed to #5 Masonry Anchors. There are no bar couplers required on this project. | The correct item is 502.4205 ADHESIVE ANCHOR NO. 5 BARS qty = 20 EACH. Not the 505.0905 BAR COUPLE NO. 5. An addendum will be issued. | Mike Coleman | 1 | 2025-12-19 11:00 | 2025-12-22 12:02
20260113 | 20260113043 | 43 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 35 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | The work zone does not need be fully opened . The one-lane two-way temp signal operation will remain in effect during the events and holidays. | Mike Coleman | 2 | 2025-12-26 14:30 | 2025-12-30 08:57
20260113 | 20260113043 | 43 | Type A lights | Will the department be adding an item for Type A lights for the Type 3's? |  |  | 3 | 2026-01-06 16:30
20260113 | 20260113044 | 44 | Incorrect Special Provisions | The SPV's in the proposal are for project 9180-35-71. | An addendum was issued to correct this. | Mike Coleman | 1 | 2025-12-15 08:42 | 2025-12-23 09:30
20260113 | 20260113044 | 44 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 32 or STH 22 traffic (beyond the limits of ID 9180-35-71), and entirely clear the traveled way 9180-35-71 7 of 33 and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic Does the work zone need to be fully opened and all traffic control devices removed from site during the dates specified? | The workzone does not need to be cleared of traffic control items are in use during these time periods. | Mike Coleman | 2 | 2025-12-26 14:34 | 2025-12-29 11:21
20260113 | 20260113045 | 45 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH VV traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | CTH VV will be allowed to remain closed during the holidays and special events listed in the special provisions. In the special provision, CTH VV could be replaced with IH 94, USH 53, USH 12, and USH 10. The intent is to eliminate construction traffic on the state highway system during the peak holiday travel periods. | Mike Coleman | 1 | 2025-12-26 14:37 | 2026-01-02 08:38
20260113 | 20260113045 | 45 | Horizontal Control Points | The plan does not appear to have any horizontal control points. Additionally the Contractor Data Packet does not contain any data. Please provide this information prior to the letting. | Construction/Contractor Data Packets are NOT required for non-State system projects and therefore will not be provided for this project. Four control points were set during preliminary design. Control points will be provided to the Awarded Contractor upon request. | Mike Coleman | 2 | 2026-01-06 09:58 | 2026-01-07 16:57
20260113 | 20260113046 | 46 | Plans & Special Provisions | The Special Provisions describe a different project than the plans. The special provision Title Page matches the plans, the special provisions do not. 7841-00-74 Clark County vs 7878-03-70 Dunn County. Please clarify. | An addendum will be issued to add the correct special provisions. | Mike Coleman | 1 | 2025-12-17 15:54 | 2025-12-24 08:47
20260113 | 20260113046 | 46 | Contaminated Soil Report | Please provide a copy of the contaminated soil report. | The soil sampling and testing to identify extent of excavation, characterization, and disposal requirements is still in progress and is expected to be complete in the Spring of 2026, prior to the start of construction. | Mike Coleman | 2 | 2025-12-23 11:20 | 2026-01-05 14:30
20260113 | 20260113046 | 46 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH P traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened, and all traffic control devices removed from site during the specified dates? | An addendum will be issued to put the correct special provisions in the proposal. However, you do not need to remove the traffic control from the site during the Holiday and Special Event time frames. Just cannot impede free flowing traffic. | Mike Coleman | 3 | 2025-12-26 14:46 | 2025-12-29 11:20
20260113 | 20260113046 | 46 | Salvaged Culvert Pipe | The plan calls for a 36" culvert to be salvaged at approximately STA 9+57. If the salvaged pipe is going to be going back in at the same location, will it be long enough with the slope changes? It appears the intercepts are changing by several feet on each side. | The intent of salvaging the 36-Inch culvert pipe shown in the plan is to supply the Town of Beaver with the existing culvert pipe after it is removed. The culvert pipe will not be re-installed. An addendum will be prepared to clarify this work. | Mike Coleman | 4 | 2026-01-05 06:47 | 2026-01-05 14:32
20260113 | 20260113047 | 47 | AT&T Utility | Article 6 (Utilities) states that AT&T has an existing underground utility running along CTH P from STA 6+00 to STA 17+00 and crossing beneath the creek bed. However, on the Plan and Profile sheets, the buried telephone line appears to transition into an overhead line. Based on the site inspection, this assumption appears to be accurate, as the telephone line seems to rise to an overhead pole, continue as an overhead line, and cross the river. Please clarify whether the AT&T line is entirely underground or if it transitions to overhead. If the line is buried, can a plan sheet be revised to show the buried line? | An addendum will be issued to clarify | Mike Coleman | 1 | 2025-12-18 09:52 | 2025-12-22 12:44
20260113 | 20260113047 | 47 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH P traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened, and all traffic control devices removed from the site during the specified dates? | No work or hauling may be performed during the specified dates, but the bridge closure may remain in place. | Mike Coleman | 2 | 2025-12-26 14:49 | 2026-01-06 13:22
20260113 | 20260113047 | 47 | AT&T Utility | Article 6 (Utilities) states that AT&T has an existing underground utility running along CTH P from STA 6+00 to STA 17+00 and crossing beneath the creek bed. However, on the Plan and Profile sheets, the buried telephone line appears to transition into an overhead line. Based on the site inspection, this assumption appears to be accurate, as the telephone line seems to rise to an overhead pole, continue as an overhead line, and cross the river. Thanks for clarifying Dunn Energy Cooperative (Electric) Line in addendum 1. Please clarify whether the AT&T line is entirely underground or if it transitions to overhead. If the line is buried, can a plan sheet be revised to show the buried line? | The original special provision states that the entire line is underground for AT& T. Addendum 1provided a corrected Plan & Profile sheet which shows the AT&T line corrected to the right location. The is line underground. | Mike Coleman | 3 | 2026-01-09 08:28 | 2026-01-12 12:45
20260113 | 20260113048 | 48 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 25 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | The traffic control devices do not need to be completely removed from the project area/site, they just canâ€™t be impeding traffic during those holiday times. STH 25 will need to be fully opened to traffic during those holiday times, including the bridge approaches. | Mike Coleman | 1 | 2025-12-26 14:52 | 2026-01-05 07:30
20260113 | 20260113048 | 48 | Salvaged Guardrail End Treatments | What is the intent of the Salvaged Guardrail End Treatment item? By spec this would be for dismantling and removing the entire end treatment but the plan does not show new end treatments being installed, only the potential replacement of posts/block or panels/hardware. And both of those items include removal. Please clarify. | The intent is that where existing beam guard needs to be raised, to adjust as much of the existing beam guard as possible, and salvage and reinstall it with replacement posts and blocks where necessary. This also applies to the end terminals, although it was assumed that all end terminals would need to be salvaged and reinstalled. Separate special provision items for reinstalling the salvaged end terminals and reinstalling the salvaged rail will be added, and plan sheets and quantities updated to reflect this, in an upcoming addendum. | Mike Coleman | 2 | 2025-12-30 10:04 | 2026-01-07 07:04
20260113 | 20260113048 | 48 | 1 1/4" Base | The misc quantities show nearly 1000 ton of 1 1/4" base required from STA 607+00 - 823+35. What is that for? | The majority of the quantity of 1 ï¿½-Inch base aggregate in that area is for the replacement of driveways. | Mike Coleman | 3 | 2025-12-30 13:12 | 2026-01-07 07:04
20260113 | 20260113048 | 48 | Approach Slabs | How is the excavation/removals being paid to install the approach slabs at B-17-45? The only common ex shown in the plan appears to be at STA 574+71 - 577+17. | Excavation for the approach slabs will be added to the earthwork quantity table with an upcoming addendum. | Mike Coleman | 4 | 2026-01-02 09:02 | 2026-01-07 07:04
20260113 | 20260113048 | 48 | Excavation | There are notes in the intersection details showing 7 inches of Asphaltic Surface over 8 inches of base. How is the excavation being paid to get to the bottom of the 8 inches of base? The only common ex shown appears to be from STA 574+71 - 577+17. | The excavation for the asphaltic surface adjacent to curb & gutter replacement was considered to be very minor and incidental to the curb & gutter items. The larger area of asphaltic surface at the Cedar Falls Rd intersection is for signal loops and a note will be added that new base aggregate dense is not required for that area in an upcoming addendum. | Mike Coleman | 5 | 2026-01-02 09:06 | 2026-01-07 07:05
20260113 | 20260113049 | 49 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 13 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | Yes, the intent is that during the specified dates, the work zone must be fully reopened to traffic and all traffic control devices, equipment, and materials removed from the traveled way and shoulders. This ensures the free flow of traffic on STH 13 as required. If there are any exceptions or temporary measures needed, they should be coordinated and approved in advance by WisDOT or engineer on site. | Mike Coleman | 1 | 2025-12-26 14:54 | 2026-01-05 14:08
20260113 | 20260113050 | 50 | Holidays and special events | It states,Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying CTH D traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | Yes, the intent is that during the specified dates, the work zone must be fully reopened to traffic and all traffic control devices, equipment, and materials removed from the traveled way and shoulders. This ensures the free flow of traffic on CTH D as required. If there are any exceptions or temporary measures needed, they should be coordinated and approved in advance by WisDOT or engineer on site. | Mike Coleman | 1 | 2025-12-26 14:56 | 2025-12-30 09:01
20260113 | 20260113050 | 50 | Installing and Maintaining Bird Deterrent System Station 16+00, Item 999.2000.S. | Please confirm whether the Departmentâ€™s intent is to require bird netting over the entire bridge, or if netting limited to the work areas associated with abutment joint replacement will be acceptable. | The departmentâ€™s intent is to require bird netting over the entire bridge. | Mike Coleman | 2 | 2025-12-29 11:13 | 2026-01-06 06:42
20260113 | 20260113050 | 50 | Concrete Surface Repair Quantity | Please provide more detail on where all of the anticipated concrete surface repair is located. Based on site visit and observation of the structure, this quantity seems to be way too high. | Concrete Surface repair quantities are based on the bridge inspection report and photos. Most of the quantity is for under deck surface repair which is primarily based on inspection defect item number 1130, which quantifies under deck cracking. The actual repair quantity will be determined by the construction engineer as noted in the plans. Approximate estimated quantity breakdown for concrete surface repair is provided below for information only: Underside of deck: 4,330 sf Sidewalk: 510 sf West Bridge Railing: 215 sf East Bridge Railing: 18 sf Pier Walls: 27 sf Abutments: 33 sf | Mike Coleman | 3 | 2025-12-29 11:30 | 2026-01-06 06:43
20260113 | 20260113050 | 50 | Waterline Surface Repair? | IS any surface repair anticipated to be at or near the waterline on the substructure units? If so, consider adding an SPV item as the work is significantly different than normal surface repair? This has been done on numerous WDOT in the past. |  |  | 4 | 2026-01-06 06:57
20260113 | 20260113050 | 50 | Floor Drain Adjustment Details | Provide details for floor drain adjustment - Bid Item #68. Will new grates or frames be necessary? Profile grade line does not change, are extensions to existing frames anticipated? | The most recent bridge inspection indicates that the drainage structures on the bridge are in good overall condition. Since the plans do not specify new drain frames or inserts, bids should be prepared in accordance with WisDOT Specifications 514.3.2 (2). | Mike Coleman | 5 | 2026-01-06 07:37 | 2026-01-07 17:11
20260113 | 20260113050 | 50 | Project Schedule | Can the project schedule be provided? The large quantity and location of concrete surface repair makes the current 50 WD schedule impossible to meet unless contractor would be allowed to complete this work without work days being charge if the roadway is open to traffic. | The design schedule can be found at the following location: https://wisdot.box.com/s/innajzatyg2bl5n389kuhono59xl944w or can be accessed on the HCCI January bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2026-01-06 07:52 | 2026-01-07 16:43
20260113 | 20260113050 | 50 | Project Schedule - Follow-up Question | The schedule provided indicates a total of 600 sy of deck repairs. Current quantities in the plan indicate 1,392 sy of deck preparation, 79 sy of full depth deck repair, and per previously answered question an additional 4,330 sf (481 sy) of underdeck surface repair. The anticipated duration to get all of this work done is 6 days. The schedule quantities are wrong and durations are ridiculous, this job cannot be completed in 50 working days if all of the repair quantities are there. | An emergency addendum has been processed to revised the contract completion time from 50 working days to a completion date of November 27, 2026 | Mike Coleman | 7 | 2026-01-08 07:31 | 2026-01-12 09:51
20260113 | 20260113050 | 50 | Additional Time | There is not sufficient time to complete the repair quantities provided, will the department consider adding more time? | An emergency addendum was issued to add additional time. | Mike Coleman | 8 | 2026-01-09 11:23 | 2026-01-12 10:35
20260113 | 20260113050 | 50 | Concrete Surface Repair | It is uncommon for concrete surface repair to be detailed on the underside of the bridge deck, except at overhangs. In cases where the deck is in poor condition, repairs are typically addressed through full-depth deck repair. If the Department intends for concrete surface repair to be performed on the underside of the deck, a Special Provision bid item for Overhead Concrete Surface Repair should be added to the contract to properly account for this work. There should be additional time added to the contract to account for this work as 50 days is not sufficient. |  |  | 9 | 2026-01-09 11:37
20260113 | 20260113051 | 51 | Plan Holder List | WIll a plan holder list be made available? | A list of plan holders can be found on the HCCI site at the following location: https://wisconsindot.gov/hccidocs/bid-let/2026/20260113/planholders.pdf | Mike Coleman | 1 | 2025-12-15 10:20 | 2025-12-16 07:49
20260113 | 20260113051 | 51 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 87 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | The workzone does not need to be cleared of traffic control items are in use during these time periods. | Mike Coleman | 2 | 2025-12-26 14:59 | 2025-12-30 08:42
20260113 | 20260113051 | 51 | Binder Lift Mix Type | Would the department consider changing the lower layer from 5LT 58-28S to a more economical 4LT 58-28S as the lift thickness would allow for this? | We have verified the current design with the Regions pavement engineer. No changes to the proposed mix design will be made. | Mike Coleman | 3 | 2025-12-30 11:08 | 2026-01-05 14:14
20260113 | 20260113051 | 51 | Removing Roadway Pavers | Plan only shows 2 locations where pavers are to be removed. Looking at the roadway there appears to be many more paver crosswalks in the project limits that have either been chip sealed over or paved over. Will the department adjust the quantity and time on the project to account for these additional areas? | We have looked into this and also discussed with the City. It appears there are only two existing crossings that have actual pavers (the two identified in the plans). The other cross walks are stamped/colored asphalt that has worn off/deteriorated over time making it appear that they have been chip sealed or overlaid. Should other unanticipated crosswalks with pavers be found during construction, they will be removed using the items currently in the plans. | Mike Coleman | 4 | 2025-12-30 11:10 | 2026-01-05 14:01
20260113 | 20260113052 | 52 | Contaminated Soil Report | Please provide a copy of the contaminated soil report. | A contaminated soil report was not completed for this project. Quantity of Potential Creosote Contaminated Soil is based on all soil within 5 feet of the existing timber abutments. | Mike Coleman | 1 | 2025-12-23 11:28 | 2025-12-29 09:01
20260113 | 20260113052 | 52 | Holidays and special events | It states,Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying Pine Road traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | Pine Road will be allowed to remain closed during the holidays and special events listed in the special provisions. In the special provision, Pine Road could be replaced with STH 29, STH 73, STH 27, and STH 64. The intent is to eliminate construction traffic on the state highway system during the peak holiday travel periods. | Mike Coleman | 2 | 2025-12-26 15:01 | 2026-01-02 08:37
20260113 | 20260113052 | 52 | Horizontal Control Points | The plan does not appear to have any horizontal control points. Additionally the Contractor Data Packet does not contain any data. Please provide this information prior to the letting. | Construction/Contractor Data Packets are NOT required for non-State system projects and therefore will not be provided for this project. Four control points were set during preliminary design. Control points will be provided to the Awarded Contractor upon request. | Mike Coleman | 3 | 2026-01-06 14:51 | 2026-01-07 16:59
20260113 | 20260113053 | 53 | Turbidity Barriers | The quantities listed under Turbidity Barrier in the misc qtys don't seem to add up to the total quantity shown. Can you please verify the accuracy of the quantities shown in the misc quantities? | The turbidity barrier quantity is shown as intended. The assumption is that there would be one installation of turbidity barrier encompassing both the bridge construction and bypass areas for the duration of the project. The quantities shown in the table are split between what is required for the bridge construction and what is required for the bypass construction due to the format of the table. The assumed depth of the turbidity barrier is 9 feet based on the lowest elevation of channel (1012.56â€™), the Q100 high water elevation (1019.57â€™) and an additional 2â€™ as described in the SDD. | Mike Coleman | 1 | 2025-12-29 14:23 | 2026-01-06 07:12
20260113 | 20260113053 | 53 | Traffic Control Bid Item | There is no Traffic Control Bid Item for this project. | An addendum was issued to add the item. | Mike Coleman | 2 | 2026-01-06 11:37 | 2026-01-12 09:56
20260113 | 20260113053 | 53 | Structural Steel Carbon | The plans donâ€™t include any details for the item â€œStructural Steel Carbon.â€ Will this be included in an addendum, or should a standard plan be used as reference? | An addendum was issued to remove the item. | Mike Coleman | 3 | 2026-01-06 15:54 | 2026-01-12 09:55
20260113 | 20260113054 | 54 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 32 or STH 22 traffic (beyond the limits of ID 9180-35-71), and entirely clear the traveled way 9180-35-71 7 of 33 and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from site during the specified dates? | During the specified dates, the work zone does not need to be fully open and all traffic control devices removed. The holiday and special event work restrictions are for any portion of the highway carrying STH 32 or STH 22 traffic beyond the limits of the work zone. | Mike Coleman | 1 | 2025-12-26 15:05 | 2026-01-05 14:34
20260113 | 20260113054 | 54 | Geotechnical Data | Please provide any geotechnical data that may be available for this project. | The Geotech report can be found at the following location: https://wisdot.box.com/s/nfts15tn1ztjtc125rrcrsyexlwzgz3c or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-01-07 10:36 | 2026-01-08 16:37
20260113 | 20260113054 | 54 | Excavation, Hauling, and Disposal of Petroleum and Lead Contaminated Soil | Can you please take a look at the Contact information for Waste management? The phone number listed in the proposal is not correct. Do you have a different one? | Erica Sutherland from the Operations Office for the WM â€“ Menominee Landfill can be contacted at this number: (906) 863-8259. The Waste Management Technical Service Center can be contacted at this number: (800) 963-4776. | Mike Coleman | 3 | 2026-01-08 13:25 | 2026-01-12 09:54
20260113 | 20260113055 | 55 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying STH 13 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic . Does the work zone need to be fully opened and all traffic control devices removed from the site during the specified dates? | The workzone does not need to be cleared of traffic control items are in use during these time periods. | Mike Coleman | 1 | 2025-12-26 15:07 | 2025-12-29 11:21
20260113 | 20260113056 | 56 | Geosynthetics for Subgrade Reinforcement | Can a Type SR (Subgrade Reinforcement) Geotextile be utilized in lieu of a Type SR Geogrid? Type SR Geotextiles can offer the same, if not better, performance and provide separation between the subgrade and aggregate layers. Geotextiles can also be made in 15' and 17' wide rolls resulting in more efficient installation, while geogrids are typically 12.5' wide. | The department is going to keep the geogrid. Please bid according to the plans and specs. | Mike Coleman | 1 | 2025-12-16 14:14 | 2025-12-29 08:58
20260113 | 20260113056 | 56 | R-67-172 Geotech Report | Will the full geotech report for wall R-67-172 be made available? | The Geotech report can be found at the following location: https://wisdot.box.com/s/xjpl32jtd8iqjaqjy9k5bhyfcvhozmk4 or can be accessed on the HCCI January bid letting page under Supplemental Information. | Mike Coleman | 2 | 2025-12-18 08:18 | 2025-12-18 13:58
20260113 | 20260113056 | 56 | Aggregate Conversion Rates | What are the conversion rates used for Base Aggregate Dense 3/4", Base Aggregate Dense 1 1/4", and Breaker Run? | The conversion rates for Base Aggregate 3/4-Inch, Base Aggregate 1 1/4-Inch and Breaker Run are 2.0 TON/CY. This information is listed on page 3 of the plans. | Mike Coleman | 3 | 2025-12-19 09:08 | 2025-12-29 08:59
20260113 | 20260113056 | 56 | Holidays and special events | It states, Do not perform work on, nor haul materials of any kind along or across any portion of the highway carrying IH 43 traffic, and entirely clear the traveled way and shoulders of such portions of the highway of equipment, barricades, signs, lights, and any other material that might impede the free flow of traffic. Does the work zone need to be fully opened and all traffic control devices removed from site during the specified dates? | Any long-term roadway or ramp closures already in place for staged work do not need to be reopened for Holiday and Special Event Work Restrictions and traffic control devices for those closures do not need to be removed. | Mike Coleman | 4 | 2025-12-26 15:11 | 2026-01-06 13:21
20260113 | 20260113056 | 56 | Previous Questions | Please repost all pertinent questions that were answered from last months (12-9-2025, Job # 13) letting for this project before it was pulled. | When the project was withdrawn from the December letting, all Questions and answers were addressed prior to advertisement for the January letting. | Mike Coleman | 5 | 2026-01-02 09:03 | 2026-01-05 07:28
20260113 | 20260113056 | 56 | Old Job to New Job | Why was this project pulled on the December letting? What was changed / redesigned for this plan to now be re-bid on the 01-13-2026 letting? | There were changes that needed to be addressed with an addendum. The department was not comfortable with the amount of changes that needed to be made at the last minute and determined to withdraw the project in order to incorporate the changes properly. | Mike Coleman | 6 | 2026-01-02 09:11 | 2026-01-05 07:29
20260113 | 20260113056 | 56 | Earthwork Data Sheets | There is various plan pages in the earthwork data sheets (pgs 1541-1579) that are incorrect and showing incorrect information. Please revise and post ASAP. | Updated Earthwork Data sheets have been submitted via an addendum. | Mike Coleman | 7 | 2026-01-02 09:20 | 2026-01-07 17:03
20260113 | 20260113056 | 56 | Structural Steel HS Fabricator | Is the supplier of the structural steel piles for R-67-172 required to be on the APL for steel bridge primary members? If so is product key #1 acceptable? | The soldier piles are primary members, and are required to be shown on the list for Approved Fabricators, Steel Bridge Primary Members. They can be considered under the category #1 for Unspliced, Rolled Sections. | Mike Coleman | 8 | 2026-01-05 11:20 | 2026-01-07 16:53
20260113 | 20260113056 | 56 | Base Aggregate | Does the 3/4" base need to be from a quarried rock source? | No, the Base Aggregate Dense ï¿½-Inch item does not need to be from a quarried rock source. Follow the Standard Specs for aggregate requirements. | Mike Coleman | 9 | 2026-01-06 10:04 | 2026-01-12 09:52
20260113 | 20260113056 | 56 | Completion Date | What is the reason for a contract completion date of June 30, 2028? Seems like all work is completed by the end of 2027. | Majority of construction will be completed by the end of 2027 in Stage 5. Anticipated work in 2028 is restoration and permanent pavement marking that are not able to be completed the previous year due to temperatures. | Mike Coleman | 10 | 2026-01-07 11:56 | 2026-01-08 16:55