## qandasearchletting_results
Date | 2026-01-23
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260210 | 20260210003 | 3 | Fertilizer Quantity | Can you please verify if 301 cwt is the correct quantity for fertilizer Type A? 3 cwt seem more accurate. |  |  | 1 | 2026-01-23 08:34
20260210 | 20260210004 | 4 | Geotech for B-56-246 | Will the geotech report for B-56-246 be made available? |  |  | 1 | 2026-01-23 11:03
20260210 | 20260210006 | 6 | Geotechnical Report/Soil Borings | Can the geotechnical report including soil borings be provided? |  |  | 1 | 2026-01-15 10:11
20260210 | 20260210006 | 6 | Geotechnical Baseline Report | Will a Geotechnical Baseline Report (GBR) for this project be provided to establish the assumed baseline geotechnical conditions for bidding and construction? Past Wisdot projects involving tunneling have typically included GBRs. |  |  | 2 | 2026-01-21 15:46
20260210 | 20260210006 | 6 | Obstructions Tunnel Excavation | Can an item for Obstructions in the Tunnel Excavation be added to the project? Wisdot projects involving tunneling typically include item "SPV Obstructions Tunnel Excavation" which compensates the contractor by the hour for removing obstructions. If not, how will removal of unidentified obstructions be compensated? |  |  | 3 | 2026-01-21 15:51
20260210 | 20260210012 | 12 | Temporary Marking | There is a lot of temporary marking on this project. Due to frequent changes in traffic control, we normally do not use temporary marking on these types of projects, and the temporary marking will conflict and slow down changes in traffic control. Is all the temporary marking necessary? |  |  | 1 | 2026-01-14 12:19
20260210 | 20260210013 | 13 | Construction Schedule | Can the Department provide the estimated construction schedule from the design team? The special provisions state that all topsoil, seed, erosion mat, and restoration items must be completed on West Howard Ave between 8/15/26 - 9/15/26 (Unicorn Clubtail Dragonfly provision). This greatly reduces the construction window from the contract completion date of 11/13/26. Please offer clarity on construction scheduling expectations as this has a major impact on the scope of this project. |  |  | 1 | 2026-01-22 08:24
20260210 | 20260210014 | 14 | Milwaukee Harp / Lanterns | The Spec calls out for specific Holophane fixtures for items SPV.0060.867 and SPV.0060.685, These Fixtures are not longer produced. Has the city of Milwaukee approved an alternative? |  |  | 1 | 2026-01-19 10:37
20260210 | 20260210014 | 14 | Onsite Crushing | Will onsite crushing be allowed on this project? |  |  | 2 | 2026-01-19 11:18
20260210 | 20260210022 | 22 | Schedule | Can the design project schedule be shared with a contractors? |  |  | 1 | 2026-01-08 15:02
20260210 | 20260210022 | 22 | Soils Info | Can you post the soils information including anything for the bridges, walls and sign bridges? |  |  | 2 | 2026-01-13 08:52
20260210 | 20260210022 | 22 | Aggregate conversions | What conversions were used for computing 1.25 CABC, 3/4 Inch CABC, Select Crushed? |  |  | 3 | 2026-01-13 08:56
20260210 | 20260210022 | 22 | Design Schedule | Can the schedule developed during design be provided? |  |  | 4 | 2026-01-19 08:30
20260210 | 20260210022 | 22 | Design Schedule | Could the design schedule be uploaded to the data packet? |  |  | 5 | 2026-01-19 10:11
20260210 | 20260210022 | 22 | Schedule | Please provide the design schedule to show that the project can be constructed utilizing the timeframes and constraints shown in the Special Provisions. |  |  | 6 | 2026-01-19 13:35
20260210 | 20260210022 | 22 | Contract Award | Will the Department provide an expedited review, award, and contract execution for the project by March 16th? If not, please the anticipated date. Please verify the DNR will completed an expedited review of the ECIP. |  |  | 7 | 2026-01-19 13:41
20260210 | 20260210022 | 22 | Geotechnical Report | Please provide a copy of the geotechnical report and soil borings. |  |  | 8 | 2026-01-19 14:17
20260210 | 20260210022 | 22 | Schedule | Please post the design schedule for the project. |  |  | 9 | 2026-01-20 07:42
20260210 | 20260210022 | 22 | Earthwork Tables | Can the earthwork tables please be provided in Excel format? |  |  | 10 | 2026-01-20 15:38
20260210 | 20260210022 | 22 | Design Schedule | Can the design schedule be provided for this project? |  |  | 11 | 2026-01-20 15:46
20260210 | 20260210022 | 22 | Removing Existing Piling | For structures B-44-320/321, the plan calls for removing steel piling at the east abutments. What existing piling is this in reference to? It appears that this item would also be needed at piers 1 and 2. |  |  | 12 | 2026-01-22 08:55
20260210 | 20260210022 | 22 | Traffic Control | It appears that there are pages missing from stages 2B and 2D in the traffic control plans. Can these be provided? |  |  | 13 | 2026-01-22 12:33
20260210 | 20260210022 | 22 | R-44-38 and R-44-39 MSE Walls | The following questions pertain to both R-44-38 and R-44-39 MSE Walls. The details on pages 1979 and 1988 show the excavation beyond the MSE Wall Backfill being backfilled with grade 2 granular, with that material being incidental to the cost of the wall. 1. Will the contractor be held to the 1:1.5(min) slope for the excavation, or can the excavation be made steeper if the soil conditions allow? 2. A separate detail shows that grade 2 granular is also required for the excavation performed outside of the roadway alignment. Is there a reason that this excavation can't just be filled with embankment? It seems excessive to backfill an excavation with a structural backfill material when the excavation is outside of the structural limits of the roadway. |  |  | 14 | 2026-01-22 14:47
20260210 | 20260210022 | 22 | STH 47 Bridge Utilities | Can the Department confirm that any utilities in the conduit running through the parapet on the existing STH 47 bridges will be either discontinued or removed prior to work starting as to not delay the bridge construction. |  |  | 15 | 2026-01-22 15:19
20260210 | 20260210022 | 22 | Abandoning Wells | What is the pipe diameter and depth of all the wells to be abandoned? |  |  | 16 | 2026-01-23 11:07
20260210 | 20260210022 | 22 | Trench Backfill for Storm Sewer | Is the detail on page 56 of the plan stating that for storm sewer, trench backfill can be from the "typical roadway section" and would not have to conform to 209.2 or 520.2.5.2 from 1' above the pipe to the subgrade layer as typical standard spec 608 details? |  |  | 17 | 2026-01-23 14:51
20260210 | 20260210024 | 24 | 2" Overlay On Existing Roadway | The finished typicals on sheets 10 & 11 of the plans shows a 2â€ lift of HMA pavement overlayed on top of the existing roadway. In the Traffic Control section of the plans, sheet 44 the typical for stage 3 calls out the existing rumble strips to be filled in during the overlay in a previous stage. The contractor does not believe that overlaying the existing rumble can be achieved without significant quality and workability issues. The project has both Removing Asphaltic Surface Milling and Asphaltic Surface Patching items; would the Department consider milling out the existing rumbles and paving them back in before the overlay is completed. |  |  | 1 | 2026-01-21 14:05
20260210 | 20260210030 | 30 | Design Schedule | Can the department please provide the design schedule? |  |  | 1 | 2026-01-09 12:58
20260210 | 20260210030 | 30 | Schedule | Can we get the designers anticipated schedule please. |  |  | 2 | 2026-01-15 13:52
20260210 | 20260210030 | 30 | Milled Surface | The specials allow traffic to run on a milled surface for 96 hours. However, they also state that the milled surface must be paved by the end of each week. Can the department please eliminate the requirement to pave all milled surfaces by the end of the week to allow the contractor to maintain an efficient and cost effective mainline milling, distressed pavement repair, shoulder widening, and mainline paving sequence? |  |  | 3 | 2026-01-22 09:41
20260210 | 20260210032 | 32 | Line #224 Public Land Reference Monument Verify and Reset | I haven't seen this item listed in this way before and I can't find it in the standard specs, updated changes, or listed in the special provisions. I'm assuming as long as section 680 on page 10 of ASP 6 in the proposal is followed, we would be in compliance, correct? |  |  | 1 | 2026-01-20 11:27
20260210 | 20260210032 | 32 | Prosecution and Progress - Milling and Paving Operations | Does placing the lower of layer of HMA pavement within 96 hours of milling only apply to 204.0120 Removing Asphaltic Surface Milling item? |  |  | 2 | 2026-01-21 11:41
20260210 | 20260210033 | 33 | Temporary access to west side of project | Will the Department permit construction traffic across the newly constructed bridge (after the 7 day wet cure and 3500PSI minimum breaks are achieved) to haul backfill and other materials needed? Will the temporary access be subject to all the DOT specifications of a temporary structure (paved surface, installation inspections, etc), or will it be entirely means and methods of the contractor, subject to engineer approval? |  |  | 1 | 2026-01-16 13:58
20260210 | 20260210034 | 34 | Clarification on Typical Sections, Quantities, and Gravel Thickness at Intersections | Hello, While reviewing the plans for bidding, we have a few clarification questions regarding the intersection work shown in the plan set. The plan sheets show quantities and reconstruction limits for DeLeglise Street, Weix Street, Wausau Road, and Gowan Road; however, there are no cross sections, typical sections, or construction details provided for these intersections. South Mayfair Road includes typical sections and cross sections, but no quantities are shown for that work. The cross sections for South Mayfair Road appear to indicate a full reconstruction, but the typical section does not specify the thickness of gravel. Additional Question: What is the required gravel thickness beneath driveways within the reconstruction limits, including at the intersections noted above? Thank you for the clarification. |  |  | 1 | 2026-01-20 14:36
20260210 | 20260210034 | 34 | Geotech for project | Can you please provide a copy of geotechnical investigations to the contractor? |  |  | 2 | 2026-01-23 10:43
20260210 | 20260210035 | 35 | Residual Sand Cover | Could the Department verify the gradation table listed in the specifications is correct? |  |  | 1 | 2026-01-21 11:29
20260210 | 20260210035 | 35 | Class III-A Culvert & Storm Pipe Bid Items | Class III-A bid items allow for metal, RCP or plastic pipe; however, the miscellaneous quantity tables are listing RCP in the description. If the material is required to be RCP, should the bid item reflect this? |  |  | 3 | 2026-01-21 15:02
20260210 | 20260210037 | 37 | 5MT 58-34V | Would the department consider changing the AC type on the lower lifts as well as upper lifts to 58-28S or 58-34S? |  |  | 1 | 2026-01-19 16:10
20260210 | 20260210037 | 37 | CIR at CTH H Intersection | Is that hatching shown on sheet 32 of the plans correct depicting the CIR limits extending all the way back past the radius points of CTH H to the butt joint? Or is the intersection to receive 2.75 inch milling for anything past 15' off centerline as is the case on other parts of the project? Thanks |  |  | 2 | 2026-01-23 10:25
20260210 | 20260210037 | 37 | CIR Width | Typical sections on plan sheet 7 for CIR show a finished with of 34 feet, 17 feet per lane. Note 6 states that the typ. pay limit for CIR is to be 30 feet. Please clarity. Is CIR to be placed at 34 feet wide with a pay quantity based on 30 feet wide? Is the existing shoulder aggregate to be incorporated into the new CIR pavement? |  |  | 3 | 2026-01-23 12:36
20260210 | 20260210047 | 47 | Wage Rates | Are you able to provide us with the wage rates for the following: Asbestos non-mechanical systems removal â€“ for the siding, sealants window glazing |  |  | 1 | 2026-01-21 16:19
20260210 | 20260210047 | 47 | Presplitting Rock | The quantity for presplitting rock drastically increased from the #15 proposal. Is this a mistake or please identify the new areas. |  |  | 2 | 2026-01-22 10:26
20260210 | 20260210047 | 47 | Asbestos Report | Can you post the asbestos report? | The asbestos report can be found at the following location: https://wisdot.box.com/s/r9314oq58e9d3z6c9kn35kf46esfz78g or can be accessed on the HCCI February bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-01-22 10:50 | 2026-01-22 10:58