## qandasearchletting_results
Date | 2026-02-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260310 | 20260310002 | 2 | Design Schedule | Please provide the Design Schedule | The design schedule can be found at the following location: https://wisdot.box.com/s/leu42bl3gnsy324hewmsq55c4o2zkljz or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-02-07 12:31 | 2026-02-11 07:55
20260310 | 20260310003 | 3 | Climbing Turtle Exclusion Fencing | This project shows 500 feet of this fence on the project. However, the Specials state the active season starts on March 15th. There will be no time to install this fence before the active season starts. I'll note that Proposal 2 in a nearby county states the active season starts on May 20th. Is the date in this proposal wrong, is the fence being installed by others prior to the project starting, or is this item not able to be used? |  |  | 1 | 2026-02-13 09:55
20260310 | 20260310004 | 4 | Geotechnical Information for S-12-15 | Is a geotechnical report available for Structure S-12-15 and could it be released? |  |  | 1 | 2026-02-09 10:35
20260310 | 20260310006 | 6 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 1 | 2026-02-12 13:38
20260310 | 20260310008 | 8 | Geotech Report for B-62-272 | Could the geotechnical report for B-62-272 be made available? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/224gwb81thdw6n3qeapuo8rj4asf2huv or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:42 | 2026-02-10 12:44
20260310 | 20260310009 | 9 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 1 | 2026-02-12 13:38
20260310 | 20260310011 | 11 | Geotech Report for B-13-902 | Could the geotech report for bridge B-13-902 be made available? | The Geotechnical Reports can be found at the following location: https://wisdot.box.com/s/eq7xcnviq4v95rqa47s9kq715jo01hla or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:44 | 2026-02-10 12:40
20260310 | 20260310012 | 12 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 1 | 2026-02-12 13:39
20260310 | 20260310016 | 16 | Geotech Report for Structure S-40-673 | Is there a geotech report that can be released for structure S-40-673? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/4fjoawh1x7ngpbi6ah3wn6jho53hia8u or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:46 | 2026-02-12 07:10
20260310 | 20260310018 | 18 | Design Schedule | Please Provide the design schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/yhm8q17nqli8d11bc7l82a5h1ryqwdjq or can be accessed on the HCCI March bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-02-09 15:45 | 2026-02-11 07:59
20260310 | 20260310018 | 18 | Soils Report | Please provide the soils report. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/yhm8q17nqli8d11bc7l82a5h1ryqwdjq or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-02-09 15:45 | 2026-02-11 08:01
20260310 | 20260310019 | 19 | Geotech Report for Bridge B-66-151 | Could the geotech report for bridge B-66-151 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/1v5tuammwum4mujl9f4uzhgk9qqezwxd or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:47 | 2026-02-11 07:51
20260310 | 20260310024 | 24 | Earthwork Data | The earthwork data is missing from Sta. 352+00 to 394+00. Could the Department please provide the complete Earthwork Data. | An addendum will be issued to add the sheet. | Mike Coleman | 1 | 2026-02-11 08:33 | 2026-02-13 07:22
20260310 | 20260310025 | 25 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 1 | 2026-02-12 13:40
20260310 | 20260310025 | 25 | Earthwork Summary | On page 87 of the -74 plan what does the "Grand Total" row and columns representing in the earthwork summary? Nothing adds up to those totals (EBS, unexpanded fill, expanded fill, waste). Is it an incorrect table? |  |  | 2 | 2026-02-13 09:27
20260310 | 20260310027 | 27 | Contract Completion Time | The contract documents specify a completion period of 50 working days, which is an aggressive schedule for a two-span flat slab structure. However, this project consists of a three-span haunch slab. Considering the size, complexity, and nature of the works, a completion period of 75 to 80 working days would be a more appropriate and realistic schedule. Can the department review the completion time? | An addendum will be issued to change the contract time for completion from 50 working days to 60 working days. | Mike Coleman | 1 | 2026-02-04 08:42 | 2026-02-13 07:27
20260310 | 20260310027 | 27 | Contract Time | 50 WD is unbuildable. 80+ working days is needed. |  |  | 2 | 2026-02-12 12:23
20260310 | 20260310027 | 27 | Schedule | Can the department provide the design schedule? |  |  | 3 | 2026-02-13 15:34
20260310 | 20260310028 | 28 | Wood County Approved Cable Barriers | The current APL does not have any cable barrier manufacturers listed for Wood County. Can the Department advise the two approved manufacturers? |  |  | 1 | 2026-02-06 10:15
20260310 | 20260310028 | 28 | water utilities | I have a few questions regarding the water utility portion. 1. Per SP 36. Valves are being called out as Clow- Would AFC 2500 series valves be allowed? 2. Per SP 46. For the 12â€ HDPE- We would need to know if it is IPS or DIPS as there are different fittings & costs for each. 3. Per SP 47. Water service is being specified as Cross linked PEX pipe with SDR 9, but with Curb & Corp stops for CTS. PEX is typically used in plumbing- Would CTS HDPE Poly water line be acceptable? | 1. Yes, AFC 2500 series valves would be allowed. We are planning to include this in an addendum as the AFC valve is preferred by the Village and remove the Clow valve. 2. DIPS 3. Yes, CTS HDPE water service line would be allowed. Similar to the water valves this is preferred by the Village and plan to include in an addendum and remove the PEX option. | Mike Coleman | 2 | 2026-02-10 08:52 | 2026-02-13 07:23
20260310 | 20260310028 | 28 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 3 | 2026-02-12 13:42
20260310 | 20260310029 | 29 | water utilities | I have a few specification questions on this one that I will need clarification on- 1. Storm laterals are calling to conform to both SCH 40 and 3034- which would be preferred? Furnish Schedule 40 polyvinyl chloride storm sewer pipe, fittings, couplings, and joint materials conforming to A.S.T.M. designation D3034. 2. Gate valve adapter to be made by Waterous? Is this accurate? I believe they mean Adaptor Inc and be compatible with Waterous Valves? To my knowledge, Waterous does not make a gate valve adapter. Gate valve adaptors shall be manufactured by Waterous and shall be compatible with Tyler Union Series 6860 valve boxes or an approved equal. 3. Ductile Iron fittings are being specified as C110. Full body. Would compact C153 fittings be permitted as the cost is significantly lower and SP has allowed these in the past. 4. Sanitary laterals are being specified as conforming to both SCH 40 & SDR35 PVC pipe and accessories shall be manufactured from materials conforming to ASTM D1784. All PVC pipe and fittings shall meet the requirements of ASTM D3034 SDR 35 or ASTM F679 5. Water lateral brass is calling for Ford or approved equal. Would AY be accepted as long as it is comparable to the Ford brass spec. Ford has longer lead times & Mueller Curb boxes are unable to meet the BABA spec as they are manufactured in Canada. |  |  | 1 | 2026-02-10 14:27
20260310 | 20260310029 | 29 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 2 | 2026-02-12 13:43
20260310 | 20260310031 | 31 | Miscellaneous Quanties | Multiple numbers and letters are missing throughout the miscellaneous quantities. Could the Department expeditiously provide the correct miscellaneous quantities for the plan set. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2026-02-11 07:37 | 2026-02-11 08:08
20260310 | 20260310031 | 31 | Geotechnical Report | Can the Geotechnical Report be provided for this project? |  |  | 2 | 2026-02-12 13:43
20260310 | 20260310032 | 32 | Geotech Report for Bridge B-37-495 | Could the geotech report for bridge B-37-495 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/zp28osp5yvi97y0sosi8esaaqiyloz8x or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:49 | 2026-02-11 07:48
20260310 | 20260310033 | 33 | Geotech Report for Bridge B-37-488 | Could the geotech report for bridge B-37-488 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/vw3l8nmrfm0p9g37wryokgh7fjxbqq62 or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:51 | 2026-02-10 12:49
20260310 | 20260310037 | 37 | Geotech Report for B-43-70 | Could the geotech report for bridge b-43-70 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/sp5xgccil99kdgww99b4tmqjsfli19iy or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:52 | 2026-02-11 07:01
20260310 | 20260310040 | 40 | Geotech Report for B-10-259 | Could the geotech report for bridge B-10-259 be made available? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/224gwb81thdw6n3qeapuo8rj4asf2huv or can be accessed on the HCCI March bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-02-09 10:57 | 2026-02-10 12:46