## qandasearchletting_results
Date | 2026-04-24
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20260512 | 20260512002 | 2 | Design Schedule | Can the Department provide the design schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/i2jnquxh6xrgi2qrferzrejbu7qc6ppz or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2026-04-20 09:30 | 2026-04-20 11:42
20260512 | 20260512002 | 2 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/i2jnquxh6xrgi2qrferzrejbu7qc6ppz or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-04-20 09:35 | 2026-04-23 09:18
20260512 | 20260512002 | 2 | HFST | Would the Department consider having the HFST be completed in spring of 2027? The reason for the question is the HFST requires 30 day cure time after placement of the new HMA pavement and the HFST is centered on STH 59 (where traffic is detoured at stage lines). There is not enough time to get the pavement placed in Stage 1, maintain the detour, and meet the manufacturer's temperature requirements. |  |  | 3 | 2026-04-21 08:01
20260512 | 20260512005 | 5 | Geotechnical Data | Please provide the geotechnical report for this project including bedrock core samples and compressive strengths. | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-09 10:24 | 2026-04-14 12:46
20260512 | 20260512005 | 5 | Geotech | Can you please provide a geotechnical report with boring logs? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 2 | 2026-04-10 11:58 | 2026-04-14 13:02
20260512 | 20260512005 | 5 | Geotech2 | Can you please provide a geotechnical baseline report for the tunnel work? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-04-10 11:58 | 2026-04-14 13:04
20260512 | 20260512005 | 5 | Microtunneling | Can you please provide your definition of Microtunneling? | Microtunneling is a trenchless construction method used to install underground pipelines with a remote controlled microtunnel boring machine (MTBM) that excavates the tunnel while pipes are simultaneously placed. The process can be operated entirely from the surface and does not require personnel to enter the tunnel, allowing for high precision and improved safety | Mike Coleman | 4 | 2026-04-10 11:59 | 2026-04-24 06:32
20260512 | 20260512005 | 5 | Microtunneling2 | Can you please clarify the intent of the Microtunneling 108â€ bid item? The bid item calls it microtunneling and the work throughout the documents describes it as microtunneling, but the spec is adversely written. It says that an EPB TBM shall be used. The spec then says things like â€œIf a slurry system is usedâ€¦â€, â€œIf a microtunneling system is to be usedâ€¦â€, and â€œIf a slurry TBM system is usedâ€¦â€ If your intent is for this to be microtunneled, your spec certainly does not read this way. | The intent of the bid item is for the pipe to be microtunneled or a similar trenchless method that is able to meet the specifications. | Mike Coleman | 5 | 2026-04-10 11:59 | 2026-04-23 07:23
20260512 | 20260512005 | 5 | Construction Data Pack | This contained 1 blank text file. Was another attachment intended? | This is a local program project. Construction Data Packets are not required for local program projects. | Mike Coleman | 6 | 2026-04-10 12:00 | 2026-04-14 13:09
20260512 | 20260512005 | 5 | Experience Requirements | The proposal document includes minimum experience requirements for the Project Superintendent (5 installations of 1,500â€™ at least 60â€) and TBM Operator (7 installations of 1,500â€™ at least 60â€). These qualifications are not part of the bid submittal we would like to know how the DOT plans to administer post-award. Will these requirements be strictly enforced as a condition of award or NTP? If the low bidder or its tunnel subcontractor does not meet these requirements exactly as written, will the DOT allow substitutions with comparable experience or require strict compliance? Will the DOT consider equivalent experience like similar diameter with shorter lengths or similar lengths with slightly smaller diameters subject to Engineer approval? The intent of the questions is to understand how the language will be applied because as written, they may significantly limit the pool of contractors. |  |  | 7 | 2026-04-10 13:37
20260512 | 20260512005 | 5 | Precast Concrete Tunnel Segements | Would fiber reinforced precast tunnel segments built per the guidelines of ACI 533.5R-20 Guide for Precast Concrete Tunnel Segments and ACI 544.7R-16 Design and Construction of Fiber Reinforced Precast Concrete Tunnel Segments be considered an acceptable alternative to concrete pipe for the tunneled portion of this project? Concrete Tunnel Segments are a typical industry accepted final tunnel lining for larger diameter tunnels and can be a more cost effective approach than large diameter RCP. |  |  | 8 | 2026-04-15 07:34
20260512 | 20260512005 | 5 | Work Plans | Can you post the utility work plans? | The Work Plans can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 9 | 2026-04-15 07:54 | 2026-04-15 07:58
20260512 | 20260512005 | 5 | Rock Cores | Can photos of the rock cores provided in the geotechnical report be made available? | The rock core photos can be found at the following location: https://wisdot.box.com/s/ce395r0y96rmhakf8z4faxzrakt3vy8n or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 10 | 2026-04-15 09:30 | 2026-04-16 10:51
20260512 | 20260512005 | 5 | Shoring | In addition to the contractor requesting to leaving shoring in place on S. High Point Road, will requests to leave shoring in other areas be accepted by the engineer? Will the engineer accept shoring to be left in place if removed five feet below grade? |  |  | 11 | 2026-04-20 15:46
20260512 | 20260512005 | 5 | WISDOT Red Square | Wondering where the WISDOT red Squares are accounted for? They are not included in the 9.5 inch concrete pavement squares. |  |  | 12 | 2026-04-21 10:48
20260512 | 20260512005 | 5 | RFI â€“ 110" Hobas FRPM Jacking Pipe Approval | Regarding Project No. 20260512005 (Mineral Point Road; USH 12 to High Point Road), the specifications require a minimum 108" ID for jacking pipe. Hobas's 110" FRPM jacking pipe has an ID of 106.9", slightly below the minimum; however, due to its smoother interior surface, it provides superior hydraulic performance to 108" RCP. RCP is designed with a Manning's n of 0.013, while Hobas FRPM pipe has a Manning's n of 0.009. At equivalent slope and flow conditions, a 108" RCP conveys approximately the same flow as a 94" FRPM pipe â€” meaning the 106.9" Hobas pipe far exceeds the hydraulic performance of 108" RCP. We believe this hydraulic equivalency justifies approval of the 110" Hobas FRPM jacking pipe and are happy to provide full supporting calculations for your review. |  |  | 13 | 2026-04-22 10:40
20260512 | 20260512007 | 7 | Formliner for parapets on Retaining Walls | We would like you to give us clarification of what you are looking for regarding the 2" Rectangular Cut Stone you have recommended for the parapet formliners. This would not be your official design choice. We will not hold anyone accountable. We just would like to give you and the community what they are expecting. Do you have any pictures of existing stone structures that might have the "look" you are trying to achieve? | The Village of Lake Delton would like to match the existing parapets for the US 12 bridge over Dell Creek (between N Delavan St and Hines Terrace) and the parapet along the NE side of US 12 adjacent to Fieldâ€™s at the Wilderness which is ~850-ft NE of the intersection with Hillman Rd. A photo showing the parapet can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-09 10:01 | 2026-04-17 09:25
20260512 | 20260512007 | 7 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-04-09 12:46 | 2026-04-17 09:15
20260512 | 20260512007 | 7 | Geotechnical Report | Can the Geotechnical Report be supplied? | The Geotech Reports can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 3 | 2026-04-09 12:46 | 2026-04-20 07:41
20260512 | 20260512007 | 7 | design schedule | can WIDOT please provide the design schedule for this project | The design schedule can be found at the following location: https://wisdot.box.com/s/x82maxxdiqhjjsk3hq2ebthxos7l8i6z or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2026-04-14 12:12 | 2026-04-17 09:16
20260512 | 20260512007 | 7 | Structure plans missing | Are there some structure plans missing? The quantities for the railing for each wall shown do not match proposal totals. | In addition to the R-numbered retaining walls in the structure plans section, there are landscape wall, concrete stair and concrete parapet details located within the Construction Details section that contain railings. | Mike Coleman | 5 | 2026-04-20 13:18 | 2026-04-23 09:19
20260512 | 20260512009 | 9 | Geotechnical Report | Can the Department provide the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: https://wisdot.box.com/s/etwufbo6oconxg4q5q8823nr76rn8mty or can be accessed on the HCCI May bid letting page under Supplemental Information. | Mike Coleman | 1 | 2026-04-21 11:21 | 2026-04-22 06:21
20260512 | 20260512009 | 9 | Clearing Item | What is the reason for item # 2 Clearing of 6.8 acres? It looks like all the trees have been cut down? Are all the felled trees going to be removed prior to construction? If all the felled trees are to be cleaned up and removed under this contract that should be stated in the bid documents. | Trees will not be removed prior to construction. All trees are to be removed or buried a minimum of 1 foot below finished grade. This is stated in Note #4 of the General Notes and is the intent of the clearing bid item. | Mike Coleman | 2 | 2026-04-22 14:48 | 2026-04-24 06:33
20260512 | 20260512011 | 11 | Prosecution and Progress Specs | Special Provisions 3. Prosecution and Progress states, "Do not begin work on IH 41 and US 45 before May 22, 2027.". Is this just referring to structure B-70-269? The next line in Prosecution and Progress references several structure ramps leading to/from IH 41 that need to be completed between July 6, 2026 and September 30, 2026. Are these dates accurate, or is the 2026 intended to say 2027? | Correct, "Do not begin work on IH 41 and US 45 before May 22, 2027." only refers to structure B-70-0269. The next line is accurate as well, requiring structures B-05-0679, B-05-0678, B-05-0671 and B-06-660 to be completed between July 6, 2026 and September 30, 2026. Only structures B-05-0658 and B-05-0661 do not have requirements to construct specifically in 2026 or 2027. | Mike Coleman | 1 | 2026-04-15 12:30 | 2026-04-16 10:53
20260512 | 20260512015 | 15 | Lower Layer Mix Type | The plan typical sections show the lower layer as 1.75 inches of 5MT. Would the department consider changing the lower layer mix type to a 4MT? This would match the typical section of the previously bid section of Hwy 63 1550-04-77 |  |  | 1 | 2026-04-21 08:10
20260512 | 20260512015 | 15 | Design Schedule | Can you provide the design project schedule? | The design schedule can be found at the following location: https://wisdot.box.com/s/12utb51rk9zl9s3nunc9bauf61xug8ye or can be accessed on the HCCI May bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2026-04-21 08:55 | 2026-04-22 06:19
20260512 | 20260512015 | 15 | Bird Deterrent System | Can you confirm that the bird deterrent system installed by the county is functional, and the if the intent of this project scope is to only maintain the system? | I can confirm that the county did the netting and it is installed pretty well per discussion with Nick Schaff. | Mike Coleman | 3 | 2026-04-21 08:58 | 2026-04-22 06:11
20260512 | 20260512015 | 15 | Clearing and Grubbing | Looking like the clearing and grubbing near STA 92 might require some trees to be removed. With clearing exclusion dates of April 15th though October 31st, and this project bidding in the May letting. This project may require special consideration on clearing, if the trees have not already been removed by the county. Would that be possible on this project? | November 1 is the start of the clearing and subsequent work in that area in order to avoid the bat dates. We were anticipating the contractor doing everything they could in the area except the final bit of grading in the ditch near the driveway/culvert where the clearing needs to take place. We anticipated the contractor clearing the two large trees Nov 1, then performing the remaining work in the area prior to Nov 13 completion date. | Mike Coleman | 4 | 2026-04-21 09:22 | 2026-04-23 08:52
20260512 | 20260512015 | 15 | Culvert pipe - liners | Are the culvert sizes listed in the SOI / misc quantities the existing culvert pipe i.d. or the required new liner size? Also, what is the existing culvert material for each pipe? | Culvert sizes listed in the miscellaneous quantities are the existing culvert pipe inside diameters. All existing culvert pipes that require liners are reinforced concrete. This can be verified, as all existing culvert pipes lengths and material types are shown on the plan sheets. | Mike Coleman | 5 | 2026-04-23 07:34 | 2026-04-23 10:40