## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20170912 | 20170912005 | 5 | Granular Backfill | bid item 209.1100 Granular backfill Grade 1 is listed in the Misc. Qty's as being used for Backfill of Storm Sewer removal trenches. Currently the adjacent storm sewer trenches are being backfilled with materials that meet the current standard specification which does not require Grade 1 sand. Why is a different material being used in this case? One would think trenches should be backfilled with similar materials. | According to the sub-section 204.3.2.2.1 (13) of 2017 standard specifications, storm sewer removal trenches should be backfilled with granular material conforming to sub-section 209.2 of the standard specifications. According to sub-section 209.2, granular backfill material is either grade 1 or grade 2, therefore granular backfill grade 1 was used for backfilling storm sewer removal trenches. According to the sub-section 608.2.2.3 of 2017 standard specifications, new storm sewer trenches should be backfilled with granular material conforming to sub-section 209.2 or 520.2.5.2 of the standard specifications. Since the backfill material for trenches for removal and new storm sewer should confirm to 209.2, same grade granular material confirming to sub-section 209.2 could be used for backfilling removal as well as new trenches. | Scott Lawry | 12 | 2017-09-07 14:06 | 2017-09-08 08:49
20170912 | 20170912005 | 5 | Soil Borings | Could soil borings be made available for this project? | The requested file has been posted ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912005/ http://wisconsindot.gov/Pages/doing-bus/contractors/hcci/prelim-plan-se.aspx | Scott Lawry | 4 | 2017-08-18 07:03 | 2017-08-21 16:16
20170912 | 20170912005 | 5 | Existing Pavement | Does the existing 9" Reinforced Concrete Pavement have wire mesh or continuously reinforced rebar (what size)? | Based on the information provided on the as-built plan (Project ID. T058-I(29) dated February 1963, it appears that there is either welded steel wire fabric or expanded metal mesh in the existing pavement. | Scott Lawry | 3 | 2017-08-10 12:04 | 2017-08-15 11:25
20170912 | 20170912005 | 5 | stamped concrete | is the item measured CY or SY? | Bid Item 405.1000 Stamping Colored Concrete is measured by the CY. | Mike Coleman | 6 | 2017-08-24 04:30 | 2017-08-24 06:48
20170912 | 20170912005 | 5 | Soil Boring Reference information | Is the reference line listed in the soil borings the same as the reference line in the plan? | No, the reference line was modified after soil boring was completed. A table that includes the STA and offsets to the soil borings from the reference line included in the plans can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912005/ | Scott Lawry | 8 | 2017-09-05 16:13 | 2017-09-05 16:14
20170912 | 20170912005 | 5 | Project Site Access Uses | Is the site at Layton Avenue and 124th Street available for Staging, stockpiling and crushing? | -The site can be used for a staging area and stockpile area. -The site can be used for crushing provided a permit is acquired from the City of New Berlin. -The site is not suitable for waste. -Restoration of the site is the responsibility of the | Scott Lawry | 11 | 2017-09-05 16:18 | 2017-09-05 16:19
20170912 | 20170912005 | 5 | 659.1125 LED C | Line 632 has 62 LED C Fixtures and Line 840 also has 62 LED C which were added by Addendum 1. Please confirm that this is not a duplicate item. | This will be addressed via addendum. | Scott Lawry | 13 | 2017-09-08 14:29 | 2017-09-11 08:23
20170912 | 20170912005 | 5 | Preformed Thermo | Line item 0726 is Grooved Preformed Thermoplastic 24 inch white. This product is no longer on the approved list. | This item was requested by the Village of Hales Corners. | Scott Lawry | 1 | 2017-08-09 11:57 | 2017-08-11 08:29
20170912 | 20170912005 | 5 | Storm Sewer Adjustment | On Page 37 of the Proposal, is says to use Grade "A" concrete collar for final adjustment. Can Pre-Cast Adjustment Rings be used to get the cover close, then use concrete to make the final adjustment? | Precast concrete grade riser ring could be used to get the cover close. | Scott Lawry | 2 | 2017-08-10 12:00 | 2017-08-15 10:42
20170912 | 20170912005 | 5 | Pavement Marking Items | The bid item 0726 SPV.0090 is for Grooved Thermoplastic 24". The plan pages also have some 24" crosswalks that say 24" Epoxy- there is no bid item for these, Is it suppose to be all Epoxy or Thermoplastic? I thought the state didn't want to use Thermo anymore? | A1) Yes, All 24-Inch Continental style crosswalk are supposed to be Grooved Preformed Thermoplastic Crosswalk 24-Inch. The Pavement Marking Crosswalk Epoxy 24-Inch call out on some plan sheets was supposed to be Grooved Preformed Thermoplastic Crosswalk 24-Inch. The quantity for Thermoplastic Crosswalk is correct, only plan call out are incorrect. A2) This was previously answered for question #1 for this proposal. This item was requested by the Village of Hales Corners. | Scott Lawry | 5 | 2017-08-23 11:01 | 2017-08-23 15:41
20170912 | 20170912005 | 5 | Curb items | There are no bid items for Concrete Curb, Type J or 18â€ Type A c&g. I would assume that these items, if used in the field, would be change order items. | Need for Concrete curb Type J is not anticipated. Any Concrete Curb & Gutter 18-Inch Type A that will be required for the project will need to be done by contract modification. | Scott Lawry | 14 | 2017-09-11 06:57 | 2017-09-11 09:23
20170912 | 20170912005 | 5 | Geotextile Type SR | There are no physical properties for the Geotextile Type SR in the special provisions. | Furnish and install Geotextile Fabric Type SR conforming to standard spec 645 and conforming to the following physical properties: Test Method Value(1) Minimum Tensile Strength ASTM D 4595 300 lb/in (52,500 N/m) Maximum Elongation at Required Strength ASTM D 4595 15 % Minimum Puncture Strength ASTM D 4833 175 lb (779 N) Maximum Apparent Opening Size ASTM D 4751 No. 40 (4.3x10-4 µm) Minimum Permittivity ASTM D 4491 0.26 s-1 1. All numerical values represent minimum/maximum average roll values. Average test results from all rolls in a lot must conform to the tabulated values. stp-645-035 (20161130) New article with the above information will be included in an Addenda | Scott Lawry | 7 | 2017-08-31 17:18 | 2017-09-05 13:15
20170912 | 20170912005 | 5 | Non-Peak hours for lane closures | What are the non-peak hours for lane closures? | The non-peak hours are 9:30 AM - 2:00 PM and 6:30 PM - 6:00 AM | Scott Lawry | 9 | 2017-09-05 16:15 | 2017-09-05 16:15
20170912 | 20170912005 | 5 | Prepare foundation for base aggregate | What is the item â€œPrepare foundation for base aggregateâ€ intended to be used for? | For preparing foundation for 16-Inch breaker run | Scott Lawry | 10 | 2017-09-05 16:16 | 2017-09-05 16:16
20170912 | 20170912005 | 5 | Stamped colored conc. | Will the Stamping Colored Concrete bid item of 405.1000 be measured & paid for as a theoretical yield or actual used in the field based on ready mix tickets? | The item Colored Concrete will be paid by the calculated volume in place, not by the batch tickets. | Scott Lawry | 15 | 2017-09-11 06:58 | 2017-09-11 09:20
20170912 | 20170912007 | 7 | Railroad Flagging | Call the railroad as required. Line has been out of operations for 15 years, but no guarantee they wont open it back up. If the railroad and Department don't know if the line will be operational, how can they expect the contractor to know? If at bid the line is not in operation and the railroad does not have an intent to open the line, would WisDOT revise the contract to add flagging if the line is subsequently opened to service and flagging was required? | Please see addendum #1 that was issued on September 6, 2017. http://wisconsindot.gov/hcciDocs/bid-let/2017/20170912/addenda/007-soi.pdf | Scott Lawry | 1 | 2017-08-29 11:03 | 2017-08-29 13:42
20170912 | 20170912008 | 8 | Pavement Markings | In looking at the temp pavement marking paint item, it appears that this item is to be used as layout for the rumble strips as well as the wet reflective grooved in edge lines on the upper layer of asphalt. If that is the case, the paint in advance of grooving is ok seeing as it will be ground off, but the paint in advance of the rumble strips will not be fully removed which would result in placing epoxy on top of paint which is not the process that is typically followed. The rumble strip layout on the final surface should be a same day or temporary epoxy item rather than a temporary paint item. Your thoughts would be appreciated. Thank you. | The temporary pavement marking is intended to be placed on the reclaimed asphalt pavement after the CIR process. The HMA overlay will not be placed until the moisture content of the reclaimed pavement has reached desirable levels, and the centerline should be delineated. The quantity will be revised in an addenda to only include the centerline marking. Originally the quantity included the edgelines as well. Rumble strips will not be placed on the 3â€™ paved shoulders. | Scott Lawry | 1 | 2017-09-01 13:41 | 2017-09-06 09:22
20170912 | 20170912008 | 8 | Asphalt Surface | Please confirm the use of the Asphaltic surface. | The asphaltic surface will be used at a depth of 5â€ for the culvert replacement areas as well as for 5â€ of top surface in the pavement Base Repair areas. | Scott Lawry | 5 | 2017-09-06 09:45 | 2017-09-06 09:45
20170912 | 20170912008 | 8 | Portable Rumble Strips | Portable Rumble strips. On past projects, these have only been used for stationary work zones. Confirming this will be the same interpretation on this job? | The intention is to use the portable rumble strips at the stationary work zone â€“ the culvert replacement areas. | Scott Lawry | 4 | 2017-09-06 09:44 | 2017-09-06 09:44
20170912 | 20170912008 | 8 | Asphalt Pavement | Q1) There seems to be +- 4,000 ton remaining after figuring quantity for the overlay. Is this for wedging? There are at least 6 â€“ 8 spots that are sags/dips. What is the intention of addressing these areas? Q2) What is the intention of addressing substandard crown? Not all areas are at 2%, and the CIR process cannot correct slope. Q3) Were there any cores taken prior to the design? Q4) Why wonâ€™t the department do a pre-mill on the surface followed by the CIR process, and then a minimal 2.5â€ overlay. Multiple lifts will give you a better end product. Q5) The special provisions call for a CIR Mix design. Not sure why this is continued to be specified as all CIR projects have adjustments made to this initial mix design based the existing hma that is being processed and weather (humidity and temperature play a big role). | A1) We are aware of these spots. We will do what we can with wedging with the extra tonnage in the plans. We will not be adding much additional asphalt to these sag spot and dip areas as there is significant concern that any additional asphalt will increase the weight of the road and cause it to sink even further. A2) Existing cross slope will be evaluated in the field, and corrected where possible. All areas will likely not be brought back to exactly 2% cross slope. The areas that are the flattest will likely be addressed first, to facilitate better drainage. The steeper cross slopes may not be addressed at all, unless they are egregiously out of range and post a hazard. A3) Cores as well as Ground Penetrating Radar were taken over the entire length of the project. The information can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912008/ A4) The desirable design would be to pre-mil the surface, followed with a CIR, and then finished with multiple layers of asphalt. WisDOT is implementing a minimal design here, and the pavement design analysis final report justifies the chosen treatment. A5) This is a WisDOT requirement and will not be waived at this time. | Scott Lawry | 3 | 2017-09-06 09:36 | 2017-09-06 09:41
20170912 | 20170912008 | 8 | Follow Up on Pavement Markings | Thank you for the response on our previous question regarding the temporary markings. To follow that up, are you planning on having any temporary or same day epoxy placed on the upper layer when it is placed? It makes sense that the temporary paint is for the CIR, but there is typically an item on the surface as well. Thank you. | The 2017 Standard Specifications, 646.3.1.3 (2) states toâ€¦â€Apply permanentâ€¦.centerline markings on the upper layer of pavements open to traffic on the same day the layer is placed. â€¦As an option, the contractor may use temporary pavement markings to conform to these same-day requirements.â€ The quantity for epoxy in the plan covers only centerline, the edgelines are grooved wet reflective, therefore the bid for centerline epoxy should be appropriately priced to conform to 646.3.1.3 (2) as well as 646.5 (4). | Scott Lawry | 6 | 2017-09-07 08:24 | 2017-09-08 12:20
20170912 | 20170912008 | 8 | CIR Temporary Markings | Will the temporary markings on the cold in place asphalt be required to be placed daily? | Temporary pavement markers should be bid per the standard specifications 649.3 (5). | Scott Lawry | 7 | 2017-09-07 11:42 | 2017-09-08 09:54
20170912 | 20170912008 | 8 | Culvert Pipes | With the culvert project that has already been let on this section, why are there still 5 culverts being replaced on this project? | This was a matter of timing. The culverts that remain in this particular contract required significantly more DNR coordination, and there was not enough time to complete the coordination before the LET of the culvert project. After the LET, we did explore the possibility of moving the culverts from this project to the other, but due to various reasons, these remaining 5 culverts stayed with the CIR project. | Scott Lawry | 2 | 2017-09-06 09:28 | 2017-09-06 09:28
20170912 | 20170912009 | 9 | Deck Load Calculation | Please provide the anticipated loads to be supported by the temporary support system. What are the requirements for field welding on girders if stiffeners are required to support temporary loads. | We anticipate the UNFACTORED load to be temporarily supported at each girder will be approximately 55 kips. Field welding of stiffeners, if required, is allowable as outlined in Section 506.3.19 of the Standard Specifications. | Scott Lawry | 1 | 2017-08-25 10:28 | 2017-08-31 17:35
20170912 | 20170912009 | 9 | Bid Item 506.2105 - Bearing Pads | Provide details on this bid item. Under item#152, the existing bearings and girder ends in the abutment repair areas are to be cleaned and painted and remain in place. Where are they located and what type of bearing are they? | The three girders that are exposed due to removal operations at the north abutment are subject to the work under the bid item â€œCleaning and Painting Bearings and Girder Endsâ€. These are the same girders that need to be temporarily supported to construct the new portion of the existing abutment. The 1/8â€ bearing pad beneath the existing steel bearings, at these three girder locations, shall be replaced per section 506.2.6 of the Standard Specifications. The bearing pads will be paid under the bid item â€œBearing Padsâ€. | Scott Lawry | 2 | 2017-08-25 12:11 | 2017-08-31 17:36
20170912 | 20170912011 | 11 | CAD drawings | Are there CAD drawings available for the Ryan Road Interchange Project Call Order #11? | The files have been posted here ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912011/ | Scott Lawry | 2 | 2017-08-15 11:22 | 2017-08-18 15:50
20170912 | 20170912011 | 11 | Soil Borings | Could soil borings be made available for this project? | The file can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912011/ | Scott Lawry | 6 | 2017-08-18 07:01 | 2017-08-21 10:25
20170912 | 20170912011 | 11 | Field Facilities Office Space | For SPV0060.0020 Field Facilities Office Space, will the department expect that the contractor-provided office facilities and furnishings required per this provision remain available until the completion of all contract items minus the Landscape Surveillance and Care Cycle bid item (11/23/2018) or will the contractor be expected to provide the field office until the end of the overall contract (11/22/2020)? | Contractor shall provide field facilities for the duration of the contract excluding the landscaping proving period and as directed by the Construction Engineer. | Scott Lawry | 13 | 2017-09-06 19:06 | 2017-09-07 12:30
20170912 | 20170912011 | 11 | Bioinfiltration Device | I have seen the special provisions regarding the bioinfiltration device. I have not seen a construction detail relating to the bioinfiltration device that would help clarify exactly what we are bidding - for example: depth of observation well. could the department please provide a detail or a better clarification as to the components of the bioinfiltration device? Thank you. | See Plan Sheet #183, Bioinfiltration Device Observation Well Detail | Scott Lawry | 7 | 2017-08-18 10:58 | 2017-08-21 14:09
20170912 | 20170912011 | 11 | Barrier Wall | Is there a detail for bid item 603.2132 â€“ Barrier Fixed Object Protection? | The barrier should conform the Standard Detail Drawing 14B 32 which can be found at: http://wisconsindot.gov/rdwy/sdd/sd-14b32.pdf#1 | Scott Lawry | 15 | 2017-09-11 07:02 | 2017-09-11 13:00
20170912 | 20170912011 | 11 | Batch Plant/Aggregate Storage Property | Is there a site that can be used for a concrete batch plant or materials storage? | WisDOT owns property in the NW quadrant of Rawson Avenue/IH 94 Interchange. Contractor may use this property for purpose of housing a batch plant or storage of materials if permits are granted from both the City of Oak Creek and WisDOT. Once these permits are obtained, the WisDOT Construction Engineer shall be the sole point of contact for coordination and use of this property. | Scott Lawry | 3 | 2017-08-15 11:44 | 2017-08-15 13:03
20170912 | 20170912011 | 11 | Pavement Marking Quantities - Wet Reflective Contrast Epoxy | Misc. Quantities page 482 of plans show a total of 30,758' of Contrast Wet Reflective 4" Epoxy, but the numbers only add up to 9,851'. Can you tell me where the other 20,000+' are to be installed, or if the quantity will be adjusted to the lower numbers? | Total is correct. Supplemental quantity data will be provided via upcoming addendum. | Scott Lawry | 10 | 2017-08-29 15:56 | 2017-09-06 15:44
20170912 | 20170912011 | 11 | Fence Decorative Wing Item 952 Quantity | On R-40-388 the quantity listed for bid item 952 Fence Decorative Wing appears to be incorrect. There is no quantity listed for the Phase 1 portion of the project but from the plan it is showing fence to be installed on that stage as well. The total bid item quantity should be approximately 260 LF. | Quantities will be revised in upcoming addendum. | Scott Lawry | 11 | 2017-08-30 15:17 | 2017-09-06 15:44
20170912 | 20170912011 | 11 | Missing Plan Sheets | Structure C-40-33 appears to only have plan sheet 1 of 9 in the plan documents. Could the missing plans sheets be provided as soon as possible? | Sheet 9 of 9 for Structure C-40-32 was also missing. An addendum will be issued to add the missing structure sheets as soon as possible. | Mike Coleman | 1 | 2017-08-09 09:39 | 2017-08-09 10:07
20170912 | 20170912011 | 11 | 39. Disposing of Surplus Material - Oak Creek Storage and Handling (9006 5th Street) | The contact person, given in the special provisions, informs that this site is no longer available and hasn't been for years. Is there another site that will accept surplus material from this project? | The site is closed. This specification will be removed in an upcoming addendum. | Scott Lawry | 9 | 2017-08-18 13:50 | 2017-08-25 16:14
20170912 | 20170912011 | 11 | Salvaged / Unusable Pavement | The cubic yard qty of salvaged pavement per the earthwork summary doesn't seem to jive with the removing pavement square yard qty if the two get computed out using the thickness of pavement material per the existing typical section. Can the salvaged pavement material get updated to jive with each other. Also per the SE detention pond (pg 905) station to station it shows 4287 CY of cut. This qty must be incorrect, per the cross sections that basically shows no grading work. | 1. Salvaged/Unusable Pavement shall be updated in an upcoming addendum. Bidders should be aware pavement for the existing SB exit ramp is removed outside the limits of the grading areas and is not included in the earthwork summary. 2. SE Detention Pond earthwork to be revised in upcoming addendum. | Scott Lawry | 5 | 2017-08-16 15:15 | 2017-08-21 14:10
20170912 | 20170912011 | 11 | Salvaged/Unusable Pavement Material Northeast Park & Ride | The Earthwork Summary on sheet 456 of the plans has two notes regarding salvaged/unusable pavement material. -Note #2: "Salvaged/Unusable Pavement Material is included in Cut." -Note #4: "Salvaged/Unusable Pavement Material - Not shown in Earthwork Detail Sheets." Based on the earthwork tabulation sheets, salvaged/unusable pavement material in cut sections is included in common excavation. Salvaged/unusable pavement material in fill sections is tabulated but not included with common excavation. Regarding the Northeast Park & Ride, is the existing asphalt & gravel included in the 4,730 cy of salvaged/unusable pavement material for the NEPR alignment? If so, it appears the earthwork summary is based on this material being removed - however there is no pay item directing the removal of the asphalt surface of the park and ride. If it is DOT's intentions to remove this surface, please add an item that directs removal. | Earthwork Summary Sheet 456 Note #4 is incorrect and shall be deleted in an upcoming Addendum. Quantity IS shown in Earthwork Detail Sheets. Salvaged/Unusable Pavement Material In the FILL sections, the pavement is removed under item 204.0100 Removing Pavement and not included as CUT. In the CUT sections the pavement is removed under item 204.0100 Removing Pavement but is also included in the CUT quantity. Both are tabulated in the Salvaged/Unusable Pavement Material quantity in the earthwork tables. NE Park & Ride Existing asphalt is included in the Salvaged/Unusable Pavement Material. Asphaltic pavement removal is paid for as Common Excavation. | Scott Lawry | 12 | 2017-09-01 15:29 | 2017-09-06 15:02
20170912 | 20170912011 | 11 | Soil Borings. | The soil borings provided in the response to the prior soiling boring request includes only the soil borings for the bridge. Can borings be provided for the balance of the project? | additional files can be found at: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20170912011/ | Scott Lawry | 14 | 2017-09-09 19:10 | 2017-09-11 12:55
20170912 | 20170912011 | 11 | Missing Earthwork Summary | There seems to be no earthwork tables for temporary ramps RYATA & RYDTA for stage 1B work. Can these be provided. | Revised earthwork tables will be included in an upcoming addendum. | Scott Lawry | 4 | 2017-08-15 16:16 | 2017-08-18 15:51
20170912 | 20170912011 | 11 | Temporary Precast Concrete Barrier Quantities | Upon review of the Temporary Precast Concrete Barrier quantities and locations, is seems there is a disconnect to the Delivered and Installed items. Could the DOT please verify the quantities are correct? | Quantities for Temporary Precast Concrete Barrier Delivered and Temporary Precast Concrete Barrier Installed shall be identical and be reflected in an upcoming addendum. | Scott Lawry | 8 | 2017-08-18 11:00 | 2017-08-21 14:10