## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190212 | 20190212001 | 1 | soil borings | Are there soil boring's available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212001/ | Mike Coleman | 1 | 2019-01-29 11:19 | 2019-02-04 07:58
20190212 | 20190212001 | 1 | lane closures | Can a westbound lane be closed from 6 am to 8 am for work during the eastbound peak hours and vice versa from 4 pm to 6 pm? | Yes, only in segment 1 and 2 as described in the Special Provisions. Segment 3 has work restrictions between Spring Rose Road to CTH PB in both directions for AM and PM traffic. | Mike Coleman | 2 | 2019-01-30 09:20 | 2019-02-04 11:12
20190212 | 20190212001 | 1 | salvaged topsoil | In the select borrow areas there is also the topsoil by cy item, why isn't there a salvaged topsoil item in these areas? There are significant fills in the topsoil by cy areas, why isn't there a select borrow and salvaged topsoil item for these areas? There are limited sources for topsoil and the topsoil comes with significant costs as well as the trucking required to get the topsoil to the project, why not add the salvaged topsoil item and let the contractor bid the work according to if it makes more sense to just place topsoil by the cy in small fill areas and to use the select borrow and salvaged topoil items? | An addendum will be submitted to clarify the topsoil item. The addendum will allow the contractor to use salvaged topsoil in place of topsoil. If storing material in the clear zone, the stored material must meet acceptable grades. This will limit the amount of room within the median to store material. Additional storage and hauling will be incidental to the topsoil item. | Mike Coleman | 3 | 2019-01-30 09:57 | 2019-02-04 11:14
20190212 | 20190212001 | 1 | select borrow | why not allow a clayey material in the fill areas. The areas being filled are NOT under the travelled roadway, but are in the ditches. Why limit the type of fill to granular material grade 1? | An addendum will be submitted to change the select borrow item to borrow. | Mike Coleman | 4 | 2019-01-30 10:02 | 2019-02-04 11:17
20190212 | 20190212001 | 1 | Type of Pipe for line item 608.3018 & 608.3024 | The plans have conflicting information between sheet 18 & sheet 15. Sheet 18 calls out for Storm Sewer Pipe Reinforced Concrete Class III and Sheet 15 calls out Storm Sewer Pipe Class III-A. What type of Storm Sewer Pipe is needed? | Use Storm Sewer Pipe Reinforced Concrete Class III. An addendum will be submitted to modify the plan. | Mike Coleman | 5 | 2019-01-30 16:38 | 2019-02-04 11:18
20190212 | 20190212001 | 1 | Soil Borings | I do NOT find anything for this project at the site given, can we get a better link to the soil boring's please? | The link has been updated. The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212001/ | Mike Coleman | 6 | 2019-02-05 08:10 | 2019-02-06 06:39
20190212 | 20190212001 | 1 | Metadata | Can I obtain a copy of the metadata for proposal 01? | Please contact Derek Potter, 608-884-7135, or derek.potter@dot.wi.gov, to obtain the metadata files. | Mike Coleman | 7 | 2019-02-07 05:38 | 2019-02-07 05:39
20190212 | 20190212002 | 2 | Stage 3 traffic control | How does the traffic control change in stage 3 after the north/south travel on Broadway is open? | The Stage 3 details as currently shown in the plans are the portion of Stage 3 when Broadway Drive south of STH 19 is closed to traffic. Broadway Drive south of STH 19 may be closed for a maximum of 2 weeks. The remainder of Stage 3 Broadway Drive south of STH 19 will allow right turning vehicles. The detail for the portion of Stage 3 when Broadway Drive south of STH 19 is open to right turning vehicles was inadvertently omitted from the plans. An addenda will be prepared to add the omitted detail sheet to the plan set. | Mike Coleman | 1 | 2019-01-23 09:17 | 2019-01-29 07:55
20190212 | 20190212002 | 2 | EARTHWORK & TRAFFIC CONTROL | The miscellaneous quantities table doesn't show any excavation quantities for the temporary widening lanes and removal of these lanes. Can you please clarify this quantity? Also, the table doesn't provide any unusable pavement quantities? Page 2 of the special provisions has a note regarding traffic control staging time frames "Do not begin or continue any work that closes traffic lanes outside the allowable time periods specified in the Traffic article in these special provisions. If the contractor fails to open all lanes of traffic by the specified times for Stages 1A, 1B and 4; a lane rental fee will be assessed according to the Lane Rental Fee Assessment article." however, none are listed, please advise. Also, listed in the specials is a traffic control stage 5, no staging diagram is provided in the plans, please advise. | 1. An addendum will be prepared modifying the Earthwork Summary and Earthwork Tables. The modified sheets will include the quantities for the temporary widening and salvage/unusable pavement materials. 2. In the special provision on page 4 the â€œAll Stagesâ€ narrative explains that flagging operations during daytime and nighttime hours will be limited to the off-peak hours during stages 1A, 1B, and 4. Those hours being from 8:45 AM to 2:00 PM and 7:00 PM to 6:45 AM in the eastbound direction and from 8:30 AM to 3:00 PM and 7:00 PM to 6:45 AM in the westbound direction. On page 5 the â€œLane Rental Fee Assessmentâ€ section details the assessment. The Lane Rental Fee Assessment is $2000 per lane, per direction of travel, per hour broken into 15 minute increments. 3. An addendum will be prepared modifying the narrative of â€œStage 5â€ in the â€œTrafficâ€ section of the special provisions. The modified specials provision will mention utilizing a shoulder closure during Stage 5 construction. | Mike Coleman | 2 | 2019-01-30 21:51 | 2019-02-07 05:50
20190212 | 20190212002 | 2 | Asphalt Path - Agg Base Course | The proposed typical sections for the 10' wide multi use path on plan sheet 8 indicate a 3/4'' agg base course installed at a thickness of 4''. To pave this path we will need to run trucks on it. Will 4'' of 3/4'' base course be enough to support loaded trucks to install asphalt pavement? | Weâ€™ve reviewed the typical with the Region Construction Engineer/Inspector. We believe the 10â€™ wide multi-use path with a 4â€ base of 3/4â€ aggregates will adequately support loaded trucks, if the subgrade is in good condition. If not, a field adjustment will be applied. | Mike Coleman | 3 | 2019-02-01 11:07 | 2019-02-07 05:47
20190212 | 20190212002 | 2 | Multi Use Path - Agg. Base Course | The 10' wide multi use path on plan sheet 8 indicates a 4'' base course using 3/4''. Loaded trucks will need to be used on this path for asphalt paving. Will 4'' of base course be enough to support loaded trucks when asphalt paving is installed? | Weâ€™ve reviewed the typical with the Region Construction Engineer/Inspector. We believe the 10â€™ wide multi-use path with a 4â€ base of 3/4â€ aggregates will adequately support loaded trucks, if the subgrade is in good condition. If not, a field adjustment will be applied. | Mike Coleman | 4 | 2019-02-01 11:12 | 2019-02-07 05:48
20190212 | 20190212002 | 2 | Soils report? | Can the soils report be provided? | The soil report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212002/ | Mike Coleman | 5 | 2019-02-06 11:44 | 2019-02-07 10:30
20190212 | 20190212002 | 2 | Design Schedule | Can the design schedule be provided? |  |  | 6 | 2019-02-09 23:20
20190212 | 20190212002 | 2 | Addendum 1 Traffic Movements. | Addendum 1 shows traffic movements inside the barrelled area area. There are also no barricades on the south end of Broadway. Please clarify. How can there be traffic inside the work zone and barrels? |  |  | 7 | 2019-02-11 05:28
20190212 | 20190212002 | 2 | Concrete Paving. | 1. Is the concrete paving of the tapers on both ends of the project to be performed in Stage 2B or Stage 3 or either Stage? 2. Can a slipform paver be used to pave the tapers? The slipform paver will encroach into the east bound lane shown in the traffic control plans. Is this acceptable or will hand forming and hand pouring be requited for both of the tapers? 3. Will a slipform paver be required to pour the 12' lane that is over 300 feet I length as required in the WisDOT Standard Specifications? |  |  | 8 | 2019-02-11 07:17
20190212 | 20190212003 | 3 | Railing Tubular Steel Galvanized Pedestrian R-40-656/657 | The detail for the Railing Tubular Steel Galvanized Pedestrian on both R-40-656/657 (bid items 384,385) shows the sleeved base plates to be fabricated separately from the rail. and then field bolted to the railing with a carriage bolt. Typically, this style of railing is difficult to install plumb and leave a good quality finished product. Can the railing be fabricated with the rail sections welded directly to the base plates instead of the detail that is shown? | The railing on top of MSE walls (R-40-656 and R-40-657) can be fabricated with the rail sections welded directly to the base plates instead of the detail as shown. An addendum will be issued to clarify. | Mike Coleman | 1 | 2019-01-21 07:45 | 2019-01-25 06:21
20190212 | 20190212003 | 3 | Asphalt / Milling items | Under Prosecution and Progress, pg 3 of 67, the last 2 sentences state that work will be paid under 2 items that do not exist in the proposal. Removing Asphaltic Surface Butt Joints and Asphaltic Surface Driveways and Field Entrances. Please clarify. | The last two sentences will be revised by addendum to state the following: "Work to remove temporary pavements or remove longitudinal wedge/tapered joint to be paid for as Removing Asphaltic Surface Milling. Temporary asphalt wedging placed separately from mainline HMA paving operations to be paid for as Asphaltic Surface Temporary." | Mike Coleman | 2 | 2019-01-28 10:58 | 2019-01-30 06:56
20190212 | 20190212003 | 3 | Asphaltic Surface Patching / Temporary | The Patching item is undistributed and the Temporary item is missing from the Misc. Qty tables. How are you intending to use each of these items? | Exact locations are unknown for the surface patching and will need to be determined in the field. Temporary surface asphalt quantities are provided in the pedestrian accommodations MQ table â€“ same page as traffic control detour items. Locations can also be found in the traffic control plans. | Mike Coleman | 3 | 2019-01-29 11:37 | 2019-02-04 10:57
20190212 | 20190212003 | 3 | Girder #1 haunch Height | The * Note on sheet 16 of the structure plans indicates that a 0" haunch height will be required at girder 1 in both spans to maintain 15'0" vertical clearance. Will standard haunches be allowed since the bottom flanges of the girders will control the minimum clearance. The 1.25" standard haunch could easily be taken out in the approaches. | The need for 0â€ haunch on girder no.1, as mentioned in the note in Bridge plan sht. 16, due to the roadway elevations of N. Port Washington Ave and the W. Capital Dr. over the bridge. The need for minimum vertical clearance under the bridge and the roadway elevations, restrict us to have 0â€ haunch for girder no.1. So we are keeping that note as mentioned in the bridge plan. | Mike Coleman | 4 | 2019-01-30 14:49 | 2019-01-31 12:44
20190212 | 20190212003 | 3 | Vertical Clearance | What is the minimum vertical clearance that has to be maintained during construction? | The current minimum vertical clearance under the N. Port Washington Ave Br. over W. Capitol Dr. is 14â€™-8â€. This is based on the background survey done for N. Port Washington Ave and the W. Capitol Dr. by the Cityâ€™s surveyors. | Mike Coleman | 5 | 2019-01-31 14:00 | 2019-02-07 05:35
20190212 | 20190212003 | 3 | base patching | this operation, have to be done at night? | Base patching operation is scheduled to be done during the day time only. | Mike Coleman | 6 | 2019-02-05 10:10 | 2019-02-06 06:36
20190212 | 20190212003 | 3 | Select Backfill Extents | The typical sections for R-40-656 & R-40-657 show the select backfill only extending to the end of the MSE wall panel reinforcement, however the specifications require the backfill to "extend[] horizontally from the back face of the wall facing to 1 foot minimum beyond the end of the reinforcement...". Are we to assume the walls are to be bid/constructed with MSE select fill extending 1-foot beyond the end of the reinforcement strips? Thank you. | The limit for Backfill behind the MSE walls should be extended â€œ1 foot minimum beyond the end of the reinforcementâ€ as mentioned in the Specification for Wall Concrete Panel Mechanically Stabilized Earth in section B.3.2. | Mike Coleman | 7 | 2019-02-06 15:14 | 2019-02-07 09:51
20190212 | 20190212004 | 4 | Mil Thickness of Pavement Markings | With the new specification in 2018 establishing the mil thickness of 20 mils rather than 15 mils on projects before that, is it possible to revert back to the 15 mil thickness for this project seeing as it is a retrace project rather than a new construction project? It would save significant dollars on this project. Thank you. | The new standard of 20 mils shall be followed. The mil thickness change coincided with the change in glass bead gradation. Please follow the current standard spec for pavement marking. | Mike Coleman | 1 | 2019-02-05 08:33 | 2019-02-06 08:43
20190212 | 20190212005 | 5 | Prosecution & Progress | In the prosecution and progress, it is stated that the closure is from 1368+51.28 to the end of the project. This closure is for the pipe culverts and concrete curb and gutter repair. Sheet 30 of the plan shows the closure starting closer to 1328+00. This would then encompass all the pipe work as well. Please verify the start station of the 12 day closure. | After further review and discussion with NE Region, the specials are correct as written. The triggering event to start the clock on the 12 day closure is either the start of culvert work (at any of the three locations) or the 4â€ mill and pave work after station 1368+51.28. Once either of those events starts, the contractor has 12 days to complete the culvert work at all three locations and the 4â€ mill/pave work after 1368+51.28. In theory, they could perform non-culvert work between stations 1328+00 and 1368+51.28 outside of the 12 day closure. | Mike Coleman | 1 | 2019-01-22 10:07 | 2019-01-23 13:47
20190212 | 20190212005 | 5 | Culvert Transitions | what will be the top width of the culvert transitions? Edge of pvmt to edge of pvmt, 30 ft or edge of finished shoulders, 44 ft or subgrade edge to subgrade edge 54 ft? | The top width for the culvert transition should be 44â€™. | Mike Coleman | 2 | 2019-02-04 10:41 | 2019-02-06 08:42
20190212 | 20190212006 | 6 | Joint Sealing Quantity | Why is the concrete pavement joint sealing quantity 2714 SY more than the concrete pavement quantity? | The Concrete pavement joint sealing quantity is more than the concrete pavement because the joint sealing is also for the 30-inch Curb and Gutter. The municipality does not want the joint sealing. Therefore, it is not needed and will be taken out of the contract. An addendum will be issued to remove the bid item. | Mike Coleman | 1 | 2019-01-23 07:42 | 2019-01-23 14:06
20190212 | 20190212006 | 6 | Alignment Info For Racine Road | Will there be additional alignment information for Racine Road? | Yes, Addenda No. 1 the alignment Detail drawings will be revised to provide additional information. | Mike Coleman | 2 | 2019-01-25 06:18 | 2019-01-25 06:18
20190212 | 20190212006 | 6 | Railroad Work | On Page 29 of the plans there is a note that the Railroad reconstruction work is to be completed by the railroad, however there is quantities for milling and paving between the rail. Is this quantity to be done by the contractor or is this to be done by the railroad? If there is work to be done by the railroad can this work be detailed? | The region railroad coordination engineer said the railroad has not committed on what type of work they will be doing on Racine Rd (construction detail 29) The contractor will be responsible for milling and paving the crossing. Therefore, the quantities for milling and paving are for the contractor. | Mike Coleman | 3 | 2019-01-29 15:25 | 2019-01-31 09:07
20190212 | 20190212006 | 6 | Missing Plan Page | Page 206 of the plans show up to station 32+00, should there be another plan sheet showing up to Station 37+59 for the rest of the resurfacing? | The plan sheet will be added by addendum. | Mike Coleman | 4 | 2019-01-29 15:31 | 2019-01-30 08:02
20190212 | 20190212006 | 6 | Asphalt Driveway QTYs | It appears that the driveway quantities along Racine Rd are too low. Could they be rechecked? | Yes, the equation in the MQâ€™s was not correct for the Racine Rd driveway qtys. This has been revised and will be addressed in Addendum No. 1 | Mike Coleman | 5 | 2019-01-29 15:33 | 2019-01-31 07:24
20190212 | 20190212006 | 6 | Storm Sewer Structure Quantities | There are some inconsistencies between the storm sewer structure totals in the miscellaneous quantities sheets and the structure types noted on the storm sewer details sheets. Which is correct? | Assume the structure quantities in the miscellaneous quantities sheets are correct. | Mike Coleman | 6 | 2019-02-07 05:43 | 2019-02-07 05:44
20190212 | 20190212009 | 9 | Deck Rebar Detail S502 bars | There appear to be only half enough of the S502 bars for the deck. The quantity of S502's should be approximately 520, not the 260 listed. | The S502 quantity is low. An addendum will be issued to correct. | Mike Coleman | 1 | 2019-01-21 07:50 | 2019-01-23 13:59
20190212 | 20190212010 | 10 | Concrete Pavement | Is the concrete pavement doweled or non-doweled? The typical sections show 8-inch concrete pavement (doweled), however the Standard Detail Drawings includes the SDD 13c04-17 Urban non-doweled concrete pavement. | SDD 13c13-9 Urban Doweled Concrete Pavement, should be included with the project replacing SDD 13c04-17 Urban Non-Doweled Concrete Pavement. An addendum will be prepared. | Mike Coleman | 1 | 2019-01-23 08:51 | 2019-01-23 08:52
20190212 | 20190212011 | 11 | Stream Relocation | Because the new structure impacts the existing stream and because the old structure is in the footprint of the realigned stream, can the designer give their vision of the sequence of construction and what environmental controls are expected to be utilized? | While this is a means and methods question, our thoughts on sequencing are as follows: 1. Cut in Creek realignment in dry condition. No connection to existing channel at either end. 2. Remove old Structure 3. Construct downstream connection to existing creek. Existing stream at new bridge location will require a short section of stream bypass while this work is done. 4. Construct upstream connection to existing creek. 5. Divert flow from Beaver Dam Creek to new creek alignment 6. Build new structure over realigned creek The creek should be built with the select crushed material in place and ready to accept the flow prior to diverting the stream. By completing the downstream connection before the upstream connection, minimal backflow will occur. When the upstream connection is made, the channel could be constructed in halves, finishing one side before opening to flow. The select crushed stone material shall be placed immediately after shaping the channel to minimize exposure to bare soil. Efforts should be made to schedule the upstream connection work during low flows if possible. | Mike Coleman | 1 | 2019-02-07 09:52 | 2019-02-11 06:21
20190212 | 20190212011 | 11 | Schedule | The contract states 45 working days to complete... Can WisDOT provide an anticipated schedule showing how the work can be completed in that time frame? | The department is comfortable with the 45 working days. The schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212011/ | Mike Coleman | 2 | 2019-02-07 09:55 | 2019-02-11 06:26
20190212 | 20190212011 | 11 | Riprap and Gravel Riffle | On page 21 erosion control plan shows Riprap lining the outside of the new stream bed. On page 5 stream typical shows no Riprap. Please clarify if riprap will be required and what size. Page 10 Gravel Riffle Detail seems to be conflicting itself on if the clay should be at the bottom or top of the select crushed. Also is the flow shown the correct way on the top right detail? | Sheet 21 - The Riprap along the realigned channel is not correct. The material for that area should be the Select Crushed Material to the limits as indicated on the Typical Section shown on Sheet 5. Sheet 10 â€“ The Gravel Riffle Detail Section A-A will be revised to correctly illustrate the Select Crushed Material running entire width of the channel with the 2-ft impervious subsoil/clay layer beneath the Select Crushed Material. The Flow direction in Section A-A is correct. Sheet 5 â€“ The Finished Typical Section Stream Relocation detail shown on Sheet 5 is correct. This detail is applicable to the non-Gravel Riffle areas. No changes. The quantities for Item No. 606.0200 RipRap Medium on Sheet 37 have been reviewed and are correct. The Location (Vincent Road North of Str. B-5-462) indicated on Sheet 37 Riprap Summary are for the new storm sewer and existing I-41 culvert outfalls at roughly Sta. 9+00 to 10+00 Lt. The quantities for Item No. 312.0110 Select Crushed Material on Sheet 35 have been reviewed and are correct. | Jill Fehrman | 3 | 2019-02-07 10:12 | 2019-02-08 15:37
20190212 | 20190212011 | 11 | Rail Road R/W | Is there any work that will take place within 25' from the rail road tracks? Will Rail Road Flagging be required for any work? | Yes. A minor amount of clearing and grubbing will take place within 25-ft of the railroad as noted on Sheet 13 â€“ Removal Plan of the plan set. The Special Provisions include Article 12 â€“ Railroad Insurance and Coordination to address the requirements for insurance and flagging. | Jill Fehrman | 4 | 2019-02-07 11:41 | 2019-02-08 14:47
20190212 | 20190212012 | 12 | Closure Schedule | On Stage 1, 1A, 2, and 2A, are we to assume the availability of night closures between 8PM-6AM? | The 8PM to 6AM restriction applies to Stage 2A only, when the westbound 29 to southbound US 51 ramp is closed. Other than the ramp closure, daytime lane closures are restricted to the hours of 8AM to 4PM. We will allow lane closures between 8PM and 6AM Monday thru Thursday. | Mike Coleman | 1 | 2019-01-10 17:02 | 2019-01-23 07:59
20190212 | 20190212012 | 12 | HFST cleaning and preparation | Will shot blasting be required on 100% of the HMA substrate? | Per the plan typical section, we are applying the High Friction Surface treatment to concrete only. | Mike Coleman | 2 | 2019-02-06 09:09 | 2019-02-08 07:36
20190212 | 20190212014 | 14 | Pipe elevations and intersections | Are there any elevations for the existing pipes? Are the new pipes going in at the same elevation as existing? Are there cross section's available for the intersection work as it is difficult to determine exactly what work is needed to be done. | The existing pipe elevations are not shown on the plans. The new pipes closely match the existing pipes because they need to match the existing ditch grades. Cross sections were not generated for the intersections. The scope of work is to remove the existing curb & gutter at the intersections because they are in poor condition and replace them in nearly the same location and elevation. The main line pavement will have 2â€ milled off and replaced with 2â€ of new asphalt pavement so the elevation of the roadway should change very little. | Mike Coleman | 1 | 2019-01-28 14:53 | 2019-01-30 06:39
20190212 | 20190212014 | 14 | 3/4'' BAD | Is 150 ton of 3/4" Base accurate for the project? | The only place we anticipated using the 3/4" BAD was on the finished shoulders of the beam guard areas. The quantity seems about right for those areas. | Mike Coleman | 2 | 2019-02-06 14:57 | 2019-02-07 14:14
20190212 | 20190212014 | 14 | Removing Asphaltic Surface Milling | Will the contractor be able to utilize any of the millings for HMA production? | No, the contractor will not be able to use any of the millings for HMA production, the County desires to retain the millings for their use. | Mike Coleman | 3 | 2019-02-07 08:26 | 2019-02-07 14:12
20190212 | 20190212015 | 15 | Boulder Placement | Boulders are intended to be placed at random locations as approved by the engineer in coordination with the DNR. Will any boulders need to be placed under the bridge? | Yes, as per the DNR, the intent is to place boulders to â€œrestore the in-channel habitatâ€. This would require placing some of the boulders underneath the bridge. | Mike Coleman | 1 | 2019-02-07 08:43 | 2019-02-08 07:34
20190212 | 20190212017 | 17 | Temporary Pavement Markings - Paint | In looking at this bid item, where do these markings come into play in terms of which part of the project and how many applications. It appears they will be placed after the chip seal with no incidental removal required? | For this project, Temporary Raised Pavement Markers, Type II are being used to provide temporary traffic delineation within the work zone. The General Notes on SDD 15C35 (Standard Application of Temporary Raised Pavement Markers, Type II), includes the following note: â€œSAME DAY TEMPORARY PAVEMENT MARKING MAY BE USED IN LIEU OF TEMPORARY RAISED PAVEMENT MARKERS, TYPE IIâ€ Therefore, the Temporary Pavement Markings â€“ Paint bid item was included as an alternate to using the raised pavement markers if deemed more appropriate by the Engineer and Contractor during construction operations. Temporary Pavement Markings would not need to be removed if covered by the fog seal. | Mike Coleman | 1 | 2019-01-28 11:27 | 2019-01-30 06:41
20190212 | 20190212019 | 19 | Detour Times | Bridge B-18-165 and B-18-182 call for a 24 hour detour. If there is any deck patching it will require a minimum 24 hour cure. Please advise what to do in the event there is deck patching on these structures. | B-18-165 does not allow for a detour. This structure is to be completed with single lane off-peak closures as defined in the Specials. Item SPV.0035.01 should be used to achieve strength in deck repair areas as needed. The 24-hour cure as mentioned in the question only applies to concrete overlays per the 2019 Standard Specification. Manufacturerâ€™s recommendations of the contractorâ€™s product of choice will need to be followed. Multiple manufactures detail fast setting patch materials compatible with their polymer overlay material. B-18-182 allows for the detour of NB USH 53 ramp to USH 12/Clairemont Ave. This closure location falls within the NB Hastings Split to Clairemont Avenue area and will be subject to the peak closures specified in the Specials. Weekend closures are allowed at this location if the contractor deems necessary. There is not a 24-hour limitation at this location per the Specials. | Jill Fehrman | 1 | 2019-02-07 11:06 | 2019-02-08 14:45
20190212 | 20190212019 | 19 | Lane closure times | for both NB and Sb there are no peak hours listed from IH 94 to Golf Rd. Will long term lane closures be allowed for str 37,38,35,36 as they are within those limits? | Yes. There are no peak hour restrictions between IH 94 and Golf Road which allows for long term closures. Please note the limitations to work on multiple structures in this area as noted in the Specials. | Jill Fehrman | 2 | 2019-02-07 11:09 | 2019-02-08 14:44
20190212 | 20190212020 | 20 | Line item 0176 Temporary Traffic Signals Bridges | Can solar traffic signals be an option? Traffic plans show hard wired signals. | Solar traffic signals can be used in place of hard wired signals as long as the two sets of signals are coordinated. | Mike Coleman | 1 | 2019-01-29 09:31 | 2019-01-31 09:03
20190212 | 20190212020 | 20 | Backfill Structure Type A | Where does the CY quantity of Structure Backfill in the roadway quantities get placed? | The new structure is shorter than the existing structure. The Backfill Structure Type A is being used in the â€œvoid areaâ€ where there was no previous roadway fill. | Mike Coleman | 2 | 2019-01-30 13:30 | 2019-01-31 09:05
20190212 | 20190212020 | 20 | 404 Permit | Can you post a copy of the 404 Permit? | The 404 permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212020/ | Mike Coleman | 3 | 2019-02-04 11:07 | 2019-02-04 11:11
20190212 | 20190212020 | 20 | Bridge inspection report | Can you post a copy of the bridge inspection report? | The Asbestos Inspection Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190212020/ | Mike Coleman | 4 | 2019-02-04 14:55 | 2019-02-04 14:55
20190212 | 20190212023 | 23 | Excavation | The cross sections at sta 26+00 show the cross hatched area that is to be excavated and backfilled behind the permanent steel sheet pile wall. The top of that excavation is approximately 8' below subgrade elevation. My question is how is the excavation paid above the cross hatched area from 12' LT to approximately 10' RT (if a 1:1 is continued) and what is it supposed to be backfilled with and how is that backfill paid? | The excavation and backfill above the cross hatched area are to be incidental to â€œExcavation for Structures Retaining Walls R-9-15â€. The backfill material can be common borrow material outside of the pay limits shown in the R-9-15 Retaining Wall Plans. The Cross Section for Station 26+00 states to â€˜Remove Loose Materials and Replace with Structural backfill as shown. (See Retaining Wall R-9-15 Plans for more Details.)â€™ Sheet 2 of 6 of the R-9-15 Retaining Wall Plans show the Structure Backfill Type A limits. The detail indicates that Backfill Beyond Backfill Pay Limits shall be incidental to â€œExcavation for Structures Retaining Walls R-9-15â€. Sheet 4 of 6 of the R-9-15 Retaining Wall Plans also show the Structure Backfill Limits and refer to sheet 2. The reason this was done this way is because the excavation areas for the bridge and retaining wall will overlap. It was difficult to determine exactly where the actual limits of the required excavation would be at. Therefore, it was decided to make the additional excavation and backfill incidental to the Retaining Wall pay item. | Mike Coleman | 1 | 2019-02-08 09:42 | 2019-02-11 11:15
20190212 | 20190212026 | 26 | STH 112 Question 1 | Was there a geotechnical investigation conducted along STH 112 and STH 118? If so can we get a copy of the boring logs? | There was a geotechnical investigation. The boring logs can be obtained by contacting Philip Keppers at philip.keppers@dot.wi.gov | Mike Coleman | 1 | 2019-01-16 14:38 | 2019-01-23 08:55
20190212 | 20190212026 | 26 | Safety Edge | Is the safety edge required on the CIR paver and on the HMA paver for the shoulder? | For the purposes of Safety Edge CIR is considered a pavement layer and any allowable alterative shown on the Safety Edge Standard Detail Drawing is acceptable. | Mike Coleman | 2 | 2019-01-23 09:00 | 2019-01-23 12:13
20190212 | 20190212026 | 26 | Existing Typical Section Cross Slope | Sheet 3 existing typical for STH 118 shows a cross slope of 2% in the eastbound and westbound lanes. We measured the actual cross slope along 4 locations of the eastbound and westbound lanes and it is approximately 5 to 5.5%. To correct this can we change this section to a pulverize instead of a 2â€ mill so we can reshape the grade prior to paving. Other option would be to wedge this section with HMA and then place a 2â€ overlay. Many areas of the pavement along STH 118 exhibit signs of severe fatigue cracking which indicates structural failure. We feel that existing pavement needs to retain the original thickness plus an additional overlay to sufficiently support existing traffic loads. | The intent is to match the existing slope. The existing typical section will be changed by addenda to show a variable slope and the finished typical section will be changed to say that the new slope should match the existing slope. No changes will be made in the pavement design. | Mike Coleman | 3 | 2019-01-23 09:17 | 2019-01-23 12:14
20190212 | 20190212026 | 26 | Loop Detectors | Are there loop detectors at the intersection of USH 2 and STH 112? If so how deep are they? | There are loops. The asbuilt shows that they are 4â€ deep. | Mike Coleman | 4 | 2019-01-23 09:20 | 2019-01-23 12:19
20190212 | 20190212026 | 26 | Full Depth Concrete Repair? | On sheet 11 STA 695+25 to 696+28 shows a 1.5â€ mill and overly of the existing concrete. There are 2â€ to 5â€ cracks that even after repaired per the proposal they will reflect through the pavement in a year or less. Full depth concrete pavement repair would be best fix for this. Crack repair and a HMA overlay will see reflective cracking in a year or less. | The proposal approach of using HMA to patch the concrete will not be changed. | Mike Coleman | 5 | 2019-01-23 09:25 | 2019-01-23 12:21
20190212 | 20190212026 | 26 | Milling Concrete to curb flag and 2-inch overlay | Sheet 10 from STA 674+53 to 695+25 shows 2â€ mill concrete to curb flag and then a 2â€ HMA overlay. The concrete curb along this section is cracked and distressed and milling may cause further damage to it. In addition to that if the curb and gutter has settled or has heaved along this stretch do we continue to mill 2â€ or do we follow the grade? Instead of milling the concrete curb and gutter can we mill along the curb and match into like the detail on Sheet 11? | Paving the gutter as shown in the plan will not be changed. The pavement surface will match the existing flow line. It is understood that in areas with short abrupt dips in the flow line due to curb settlement that the pavement surface will be higher than the existing flow line. | Mike Coleman | 6 | 2019-01-23 09:31 | 2019-01-23 12:21
20190212 | 20190212026 | 26 | CIR sta 674+53 - sta 690+75 | The CIR section from STA 674+53 to STA 690+75 will be very difficult to construct with all the utilities. The other issue is the CIR paver will have to make two passes through that section so there will be differing AC/moisture contents within the CIR along the second pass. Also, it is in our opinion the pavement structure is inadequate to support the type of traffic. Once we open the CIR to traffic it will have many tractor trailers stopping and turning at low speeds which we feel will cause distress to the CIR and lead to us removing and replacing it along the entire section. CIR with foamed asphalt has a significantly lower structural number than dense HMA and we feel the thickness of HMA in the section should be increased to support the slow speeds of the tractor trailer traffic. The typical section on sheet 9 from STA 666+66 to 673+11 shows a 4â€ mill and 4â€ of HMA overlay placed in two lifts. Can we extend this typical section from STA 674+53 to 695+25? We are proposing | This area will be changed to a mill and overlay pavement design by addenda. | Mike Coleman | 7 | 2019-01-23 09:42 | 2019-01-23 12:22
20190212 | 20190212026 | 26 | Temporary asphalt sidewalk instead of temporary pedestrian surface plywood | Can we pave a temporary asphalt sidewalk In lieu of the temporary pedestrian surface plywood? | The plywood temporary sidewalk is intended to allow reduced impact for restoration and the plan will not be changed. The contractor may propose alternatives after the contract is awarded. | Mike Coleman | 8 | 2019-01-23 09:44 | 2019-01-23 12:26