## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190514 | 20190514001 | 1 | Completion Date | Would the Department consider moving the completion date to May 22nd, 2020 for this project? With the standard process of having bases installed first in order to calculate post length to order, it pushes the installation and removal items into winter. With the majority of the work being post installation, sign installation, and the removal of existing signs, posts, and footings, the concern is that there aren't enough weather days over winter to finish the bid items by the required date. | The department is comfortable with the April 1, 2020 completion date. | Mike Coleman | 1 | 2019-04-19 10:23 | 2019-04-22 10:01
20190514 | 20190514004 | 4 | Stage 1 | Is the department anticipating night work during stage one to meet the 72 hour requirement? | No, the department is not anticipating night work during stage one to meet the 72 hour requirement. Please note the following: Stage 1 - STA 1201+00 to STA 1207+50, there is a 72 hour work requirement. Stage 1 - STA 1294+00 to STA 1303+00, there is a 72 hour work requirement. Stage 1 - STA 1201+00 to STA 1269+50, there is a 72 hour work requirement Stage 1 - STA 1269+50 to STA 1294+00, there is no 72 hour work requirement. | Mike Coleman | 1 | 2019-05-06 09:10 | 2019-05-09 08:06
20190514 | 20190514005 | 5 | Modular Expansion Joint Length | Looking for clarification on the termination of the Modular Expansion Joint in the sidewalk region of the expansion joint locations. Sheet 84 implies there might be a modular joint through the sidewalk as it shows the anchorage. Sheet 85 has details showing the joint ending at the upturn in multiple views and not going through the entire sidewalk area. Please confirm. | The existing modular joint on B-56-217 does extend from â€œedge of deckâ€ to â€œedge of deckâ€ (as itâ€™s shown/implied on sht. 84). However, current standards only require the 45â° bend 2â€ minimum from the gutter line. It will be the contractorâ€™s decision to determine the working limits of the modular joint, under the sidewalk. If the contractor decides to replace the modular joint in-kind, the deck thickness dimensions in the â€œsection thru joint @ abutmentâ€ (on sht. 83) will allow them to determine the size of the T-section needed on girder #7. | Fred Schunke | 1 | 2019-05-03 14:15 | 2019-05-07 14:53
20190514 | 20190514005 | 5 | Please Clarify Removal Quantities Sawing Asphalt and Sawing Concrete | Please refer to sheet 33. The individual quantities for Sawing Asphalt & Sawing Concrete listed in the Miscellaneous Quantities chart do not match the totals. The totals were used for the bid quantity. Please verify the bid quantity and location | The totals for the bid items Sawing Asphalt and Sawing Concrete on the Miscellaneous Quantities plan sheet 33 are incorrect. The correct Sawing Concrete total is 23 LF. The correct Sawing Asphalt total is 64 LF. Addenda will be issued to clarify quantities. | Mike Coleman | 2 | 2019-05-07 11:38 | 2019-05-09 08:01
20190514 | 20190514005 | 5 | Dynamic Late Merge | 1. Looking at #1 in the General Notes for this system it says that PCMS #1 should be placed 1 mile from the "expected queue" and then space FBS every 1 mile until until FBS #1. How long is the expected queue? | The expected queue length is 4 miles. See Miscellaneous Quantities table on plan sheet 36. | Fred Schunke | 3 | 2019-05-09 08:05 | 2019-05-09 13:58
20190514 | 20190514006 | 6 | Possible Guardrail Interference Locations | 1) Pages 23 and 24 of the plan show a WE Energies Gas Line crossing the guardrail in 4 separate locations. Specifically, STA 135+25 LT and 137+10 LT are at a shallow angle to the guardrail. The concern is that the guardrail will conflict at multiple consecutive post locations. The Special Provisions state "no adjustments are anticipated." Becase of the shallow angle causing multiple posts to be in conflict, would the Department consider moving this gas line? 2) Page 104 shows MGS 3K over an existing box culvert at Duck Creek. The cross sections don't show the box culvert. The plan doesn't state whether the existing posts are clipped to the box culvert, but the MGS 3K posts are even longer. Does the Department know if the existing box culvert will inhibit the MGS 3k posts over this box culvert? If it's possible, can a "clipped posts" item be added? | 1.) WE Energies was asked specifically about these locations in reference to the new beamguard proposed. WE Energies responded that â€œno conflicts are anticipated with the existing gas main and service crossings for the new beamguard.â€ 2.) The existing box culvert is shown in cross sections on page 147. The existing box is not labeled, but the two horizontal lines between the fore slopes on the cross sections represent the box culvert that was surveyed not in conflict with the proposed guardrail posts. | Fred Schunke | 1 | 2019-05-07 09:09 | 2019-05-07 14:52
20190514 | 20190514006 | 6 | Closure Length | Per section 4. Traffic of the special provisions, Limit the single lane restriction to a single continuous length not exceeding 1.5 miles. If traffic delays do not exceed 15 minutes, will the Department allow longer moving closures than 1.5 miles? | No. Please bid it as you see it. | Fred Schunke | 2 | 2019-05-09 10:42 | 2019-05-09 15:36
20190514 | 20190514009 | 9 | August 23rd Completion Date | Any chance that the completion date could be moved back? | We feel that we gave ample time based on conservative production rates to complete this project by August 23rd. | Mike Coleman | 1 | 2019-04-17 09:20 | 2019-04-22 09:20
20190514 | 20190514009 | 9 | 460.0105.S HMA PWL Test Strip Volumetrics | The quantity in the bid is 1 Each. Should this be 2 Each? (1 for each lift of HMA) | If the mix is the same for lower and upper layers(in this case they are), then just one volumetic test strip is required. | Mike Coleman | 2 | 2019-04-24 13:37 | 2019-04-29 13:50
20190514 | 20190514009 | 9 | HMA PAVEMENT NOTCH WEDGE | Can you explain how the qty of 32,470 lf is calculated between STA 263+00 TO 425+35? It would appear both lifts of HMA are to receive a notche wedge with this qty. Please advise. | HMA PAVEMENT NOTCH WEDGE should be 1,6235. An addendum will be issued to clarify. | Mike Coleman | 3 | 2019-04-26 15:51 | 2019-05-02 06:31
20190514 | 20190514009 | 9 | ASPHALTIC BASE | On plan sheet 113 for the Temporary Trench backfill detail it calls out 4.5'' of relaid asphaltic base. Is this what the asphaltic base pay item is for? I assume this material is the existing recycle asphalt base that is shown in the existing typicals? Will traffic be allowed to run over this material until asphalt overlay is constructed? Is the intent to patch all the culverts in with recycle and not HMA than mill off 2'' of the recycle material and install the 4'' HMA overlay? Please advise the sequence and allowable materials for traffic to cross these culvert patches. | The asphaltic base pay item refers to the 4.5â€ of asphaltic base called out on the Temporary Trench Backfill detail. Asphaltic Base can be the existing recycled asphaltic surface that is referred to on the typical sections or new asphalt millings, as long as it meets the criteria for Asphaltic Base in the 2019 Standard Specifications. Traffic will be allowed to run over this material temporarily until the mill and overlay operation goes through, if it is placed in such a way that traffic can cross over the temporary surface safely at the posted speed. The intent is to patch all the culverts with asphaltic base, then mill off 2â€ of the asphalt on STH 60 and overlay with 4â€ of HMA pavement. In the detail Temporary Trench Backfill Detail, we should have used the bid item Asphaltic Base instead of â€œRelaid asphalt baseâ€ An addendum will be issued to correct this. | Mike Coleman | 4 | 2019-04-26 16:33 | 2019-05-02 06:33
20190514 | 20190514009 | 9 | Spec Section 4 Traffic - Traffic delays | Specs say Hold traffic no more than 5 minutes per direction for lane closure. Is this a typo? Usually the requirement is 15 minutes. | We should have 15 minutes as the max. An addendum will be issued to correct this. | Mike Coleman | 5 | 2019-04-29 15:40 | 2019-05-02 06:34
20190514 | 20190514009 | 9 | Guardrail Conflict at C-11-1182 STA 121+80 | Page 110 shows the guardrail posts being deeper than the cattle pass structure. With the guardrail being MGS 3K (half-spacing), how is the area overtop of the cattle pass anticipated to be handled? |  |  | 6 | 2019-05-07 09:27
20190514 | 20190514009 | 9 | Completion time | I believe that there are enough days to complete the project, but most of the jobs bid already have the end of August for a completion time and many contractors are already filled up in this time frame. Why not put the reconstruct portion of the project as a Aug 23 deadline for school bus traffic if that's the concern and have the completion date after that because the road is going to be open to traffic anyway | At this time, the department is comfortable with the project as scheduled. | Mike Coleman | 7 | 2019-05-09 09:44 | 2019-05-13 08:27
20190514 | 20190514010 | 10 | Pavement Markings | The same day paint item needs to be placed, presumable, on the milled surface every night. What is your plan for marking the surface layer on a nightly basis? There is not same day epoxy item which would cover the requirement of marking the centerline daily. | This will be corrected in an upcoming addendum. | Mike Coleman | 1 | 2019-04-27 08:05 | 2019-05-02 06:41
20190514 | 20190514010 | 10 | Pavement Markings | Thank you for addressing the previous question with an addendum. In looking at the addendum, it has now included same day paint for the surface layer rather than a temporary epoxy or same day epoxy so that it would not need to be removed prior to placing permanent epoxy. Will an addendum be issued to change the same day paint to same day or temporary epoxy? Thank you. | Sheet 8 of the plan shows the paving for the first pass and second pass of asphalt. There is no binder layer on this project, only surface. Any pavement marking installed after the first pass will be removed during the milling operation for the second pass. Except for STA 430+50 to STA 487+13, the roadway is closed and detoured during construction. For this reason, Article 4 of the special provisions states the following: â€œDemark the centerline at the end of each working day utilizing temporary tabs or other marking. This work will be paid for as Marking Line Same Day Paint 4-Inch.â€ The addenda was issued to ensure there was enough quantity to mark the centerline per SDD 15C8-19a, Temporary Pavement Marking after each pass, if the engineer deemed it necessary until Marking Line Epoxy is installed. | Fred Schunke | 2 | 2019-05-07 08:03 | 2019-05-08 09:11
20190514 | 20190514010 | 10 | Anchor Assemblies for Steel Plate Beam Guard | The existing F-Railing on B-53-160 does not have the anchor assemblies for connecting the MGS Thrie Beam Transition to the railing. Would the Department consider adding 4 each of "614.0150, Anchor Assemblies for Steel Plate Beam Guard" for this bridges updates? | 614.0150 - Anchor Assemblies for Steel Plate Beam Guard will not be included in the contract. Per SDD 14b45-5g, general note #2, â€œDrilling holes through the parapet, bolts, nuts, washers, and repairing damaged concrete are incidental to the contract.â€ In addition, 614.0150 - Anchor Assemblies for Steel Plate Beam Guard, is not included in the associated bid items for MGS Thrie Beam Transition. | Mike Coleman | 3 | 2019-05-07 10:07 | 2019-05-09 07:59
20190514 | 20190514011 | 11 | WisDOT May 2019 Letting - Job #11 - Recycled Concrete base usage | For the 68 ton of 1 1/4" base material, will recycled concrete (meets WI DOT Spec) be allowed for use on this project? -Alan Olson | As long as the material meets the specs in 301.2.4 of the Standard Specifications, it will be allowed. | Mike Coleman | 1 | 2019-05-06 16:51 | 2019-05-09 08:02
20190514 | 20190514012 | 12 | Temporary Pavement Markings | What is your plan for temporary markings on the milled surface seeing as it is not required to mill and pave in the same day? I do not see a temporary pavement marking bid item that would cover this. Thank you. | The assumption is the contractor would mill one lane continuously with the requirement that the lane would need to be paved within 3 days (as stated in the Prosecution and Progress Article of the Special Provisions). Once Removing Asphaltic Surface Milling operations removes the existing centerline, we would have contractor place â€œNO CENTERLINE MARKINGâ€ and â€œPASS WITH CAREâ€ signs along with the existing No Passing Pennants to account for no pavement marking (as stated in the General Notes on the Traffic Control - Advanced Warning Signing Sheet). After the surface gets restored (within 3 days) the contractor would follow the specs (Section 646.3.1.2) to place either temporary pavement or temporary raised pavement markers since the roadway is open to traffic. Temporary raised pavement markers are anticipated to avoid removing temporary markings on the final HMA surface. These temporary raised pavement markers would remain until the adjacent lane has been brought up to final surface, completing the mainline paving. Once the adjacent lane is brought up to final surface, Marking Line Same Day Epoxy (double yellow) is installed (as shown on the Marking Line Application Phasing Detail). | Mike Coleman | 1 | 2019-04-27 09:36 | 2019-04-30 08:34
20190514 | 20190514012 | 12 | Anchor Assemblies for Steel Plate Beam Guard | The F-Railing at B-56-012, STA 71+19 to 71+81 doesn't have the plate for connecting the MGS Thrie Beam Transition to it. Will the Department consider adding bid item "614.0150, Anchor Assemblies for Steel Plate Beam Guard" to fabricate and install this item? | The F-Railing at B-56-012, STA 71+19 to 71+81 doesn't have the plate for connecting the MGS Thrie Beam Transition to it. Will the Department consider adding bid item "614.0150, Anchor Assemblies for Steel Plate Beam Guard" to fabricate and install this item? | Fred Schunke | 2 | 2019-05-07 10:32 | 2019-05-08 10:16
20190514 | 20190514015 | 15 | Porcelain ceramic tile repair | Are the quantities in line item 0108 " porcelain ceramic tile repair" reflective of removing and replacing the tile areas where a great deal of efflorescence is present leaching through the tile grout lines? | Porcelain ceramic tile repair is for removing and replacing damaged tile, tile that is loose, and tile that is severely delaminated and will fall off soon. The presence of efflorescence on or around a tile is not in itself a reason to replace that tile. The tile would also need to be severely delaminated to warrant replacement. Tap the tile with a hammer to determine if it is sound, or if it is loose and in need of replacement. Do not use aggressive tool or power tool cleaning on the tile. It is not required to remove all efflorescence with pressure washing. The pay item for pressure washing is to clean all the tile with a high pressure water blast. Itâ€™s intended to remove mainly dirt and grime off the tile surface and not necessarily remove efflorescence. The pay item for tile repair is intended to be limited areas where the tile is delaminated, physically damaged, or missing. This involves removing any remaining portions of the tile within the repair areas and prepare the substrate for application of new tile. Within the repair areas, the tile removal and substrate prep activities must be done in such a manner so as to not damage or weaken well adhered tile that will remain around the perimeter of the repair area. | Mike Coleman | 1 | 2019-04-18 09:56 | 2019-04-18 09:58
20190514 | 20190514015 | 15 | Pavement Markings | What is the departments expectation when it comes to placing the permanent markings on each section that has been treated with the polymer overlay? Will you require markings to be replaced after each stage of each bridge, after each bridge is fully overlaid, or combining one or more bridges that may or may not be completed at the same time? Thank you. | Erosion Control/Pavement Marking Notes and Legend sheet in the plans states that permanent marking lines shall be placed prior to opening to traffic as directed by the engineer, or place Temporary Marking when multiple nights are needed to complete the work and area will be opened to traffic between closures. The expectation is to maintain safe operation of traffic, and clear delineation of lanes. Quantities are included for placing one application of temporary markings. | Fred Schunke | 2 | 2019-05-01 07:57 | 2019-05-06 13:51
20190514 | 20190514017 | 17 | Monotube materials | Lead times for all monotube equipment has been 30 plus weeks after the materials drawings have been submitted and approved. How will the project handle to the project deadline? Materials will unlikely be here by the date. | Addendum #02 has been issued changing the completion date to August 1, 2020, with an interim completion date of October 31, 2019 to complete all work except for monotube materials associated with delayed deliveries (poles, arms, signals, wiring). | Mike Coleman | 1 | 2019-04-30 12:46 | 2019-05-01 07:38
20190514 | 20190514017 | 17 | Item 204.0120 Rem Asph Surf Milling | This item would normally be for only milling asphaltic pavement. It appears that in order to place the new 4" asphalt pavement cross section the concrete pavement would need to be milled as well. Can we get clarification on the milling item 204.0120, or will there be an addendum to add an item for milling of the concrete. Concrete milling is usually under item 204.0109.S Rem. Conc. Surf. Partial Depth. Thank you | We will add 204.0109.S in upcoming emergency addenda. | Fred Schunke | 2 | 2019-05-09 07:33 | 2019-05-10 12:19
20190514 | 20190514018 | 18 | monotube materials | Lead times for all monotube equipment has been 30 plus weeks after the materials drawings have been submitted and approved. How will the project handle this delayed delivery lead time with the working day contract? |  |  | 1 | 2019-04-30 12:50
20190514 | 20190514021 | 21 | Design CAD Files | Can we get a copy of the design CAD files? Per the earthwork summary in the miscellaneous quantities there is a line that says: Mitigation Site Grading Phase 3 & 1 (remaining grading sites) 90,312 CY of CUT. Where is the 90,312 CY of Cut, where can it be found in the plan? In the grading plan section of the plan it sure doesn't seem to show where the large amount of cut is? | 1. The existing and proposed surface models along with the contractor staking packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190514021/ 2. Total cut on the project equals 150,758 CY. Earthwork Summary details out specific divisions such as Culvert Pipe (Stage 1 & 2), Peshtigo Brook Wetland Enhancement Site(s), Peshtigo Brook Earth Spillway Grading Site(s), Peshtigo Brook Mitigation Berm(s). 150,758 CY minus the specific divisions equals 90,312 CY. All cut is hatched on sheet 7 â€“ 13 of the plan under the â€œgrading limitsâ€ hatch. This will likely be easier to see after looking at the C3D files. | Mike Coleman | 1 | 2019-04-10 11:20 | 2019-04-16 07:36
20190514 | 20190514021 | 21 | Restoration of Non-Grading Areas | In the plan it states that the contractor shall be responsible for reshaping and seeding any previously grass seeded areas disturbed by operations outside the normal construction limits at the contractors expense. What is DOT's intent on this statement? Anything outside the grading limits as shown in plan or within reason to build the project? There will be various haul roads / temporary stockpiles needed outside the grading areas, will the restoration costs be paid for by DOT? All borrow and waste site restoration costs for every other DOT project is paid for by DOT, which are outside the project limits, it would make sense that DOT would pay for restoration costs since all work would most likely be completed on DOT ROW. | Restoration of areas needed to construct the project, within reason, will be measured and paid for. However, there are various sites within the overall project that detail â€œNo Grading No Seedingâ€, see plan sheets 15-17. Those areas should be avoided and should not require restoration. In addition, there is work required on previously seeded areas that should not require restoration if care is taken, see Article 22 of the special provisions as well as plan sheets 14-17. If those areas are disturbed and require restoration, that would be at the contractorâ€™s expense, as noted in the plans and specials. | Mike Coleman | 2 | 2019-04-16 17:15 | 2019-04-22 08:10
20190514 | 20190514021 | 21 | Soil Borings | Can you provide soil borings for this project? | Response: Soil probes, not soil boring, were completed for proposal #21 by the NE Region soils engineer. Soil probes are not as accurate as soil borings, and provided estimated topsoil/marsh depths for the construction area, actual depths are not available. Soil probe information for the project site can be found here: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190514021/ | Mike Coleman | 3 | 2019-05-13 08:31 | 2019-05-13 08:34
20190514 | 20190514022 | 22 | 25 Working Days | For this project 25 Working Days seems inadequate. There is considerable concrete work that has to occur in multiple intersections and the Roundabout, A mill and pave that needs to occur at the shoulders prior to the mill and overlay of the mainline. Then shouldering, signs and rumbles. This seems like it should be somewhere around a 45 Working day contract. | The time for completion will be changed to a 30 working day contract in an upcoming addendum. | Mike Coleman | 1 | 2019-04-16 08:40 | 2019-04-23 08:15
20190514 | 20190514022 | 22 | PWL Tonnage | The tonnage placed on the binder lift of the shoulder will be placed prior to the test strip can be completed. Therefore, the shoulder tonnage placed on this lift cannot be considered PWL tonnage. Can this tonnage be switched to QMP tonnage? | We agree the binder lift for the shoulder should be added to QMP tonnage and excluded from PWL quantity. We will update this in an upcoming addendum. | Mike Coleman | 2 | 2019-04-16 08:56 | 2019-04-23 08:17
20190514 | 20190514023 | 23 | Temporary pavement marking paint | Can you break down where the 203,735 LFT of temporary paint markings are intended to be used? In looking at the paving, it appears you would need one application on the milled surface, one application on the lower layer, and possibly one application to place temporary paint on the upper layer in place of the edge lines which would, in essence, layout the edge lines for the wet reflective operation to follow. It appears there may be enough quantity to place center line markings on the surface as well which would not be needed as there is temporary epoxy that is to be placed prior to the rumble strips being installed. Thank you. | The temporary pavement marking paint quantities were estimated as follows: â€¢ Temporary Marking Line Paint 4-Inch (white) â€“ quantity is intended to mark the edge lines prior to the placement of the permanent grooved wet reflective edge lines. â€¢ Temporary Marking Line Paint 4-Inch (yellow) â€“ quantity is intended to temporarily mark the centerline for three applications (milled surface, lower layer and on the tapered joint portion of the upper layer) as shown in the construction detail. | Mike Coleman | 1 | 2019-04-29 07:34 | 2019-04-29 08:21
20190514 | 20190514023 | 23 | Contract Time for Completion | The timeline seems tight to finish this project in 40 working days. Can this be extended to a 55 working day contract? | The production rates used arenâ€™t excessive, therefore, we will be leaving the project at 40 working days. | Mike Coleman | 2 | 2019-05-02 06:45 | 2019-05-02 06:48
20190514 | 20190514023 | 23 | Density Testing | Will density testing be required on 3/4" lower layer of 5 LT 58-28S? | Density testing is will not be required on the lower ¾â€ layer. | Mike Coleman | 3 | 2019-05-02 06:47 | 2019-05-02 06:49
20190514 | 20190514023 | 23 | Manhole Depth | What is the depth for structure 611.2005 Manhole 5-Foot Diameter? | The structure depth is 6.50-ft. Additional information on this structure is included in the projectâ€™s addendum #1. | Fred Schunke | 4 | 2019-05-08 08:44 | 2019-05-08 09:13
20190514 | 20190514023 | 23 | 404 Permit | May I get a copy of the 404 permit? | The project is covered under a general permit and is found at the following link. ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190514023/ | Fred Schunke | 5 | 2019-05-09 13:17 | 2019-05-09 13:37
20190514 | 20190514023 | 23 | Box Culvert Access | Can we remove beamguard and posts in a section for access to a box culvert and then replace the beamguard and support it with concrete barrier? | You would have to place an asphalt or concrete pad and have the proper connections to the block and would be done at the contractorâ€™s expense. | Fred Schunke | 6 | 2019-05-09 13:27 | 2019-05-09 13:31
20190514 | 20190514023 | 23 | Gate Payment | How will the department would pay for the gate that needs to be salvaged and removed? | Item SPV.0090.01 states that gates will be deducted. The SPV will be modified to include gates as part of the measurement in an upcoming addenda. | Fred Schunke | 7 | 2019-05-09 13:35 | 2019-05-09 13:36
20190514 | 20190514024 | 24 | Asphalt Base Widening Material | Item #28 Asphaltic Base Widening References a 25 mm asphalt mix. Would a 19 mm or 12.5 mm mix be allowed do to the 2â€ asphalt section? | An addendum is being created to clarify the use of 12.5 mm aggregate. | Fred Schunke | 1 | 2019-05-01 15:39 | 2019-05-07 10:03
20190514 | 20190514024 | 24 | Culvert Asphalt Removal | The culvert pipe at STA 103+08-103+29 does not appear to have any common figured. How will the asphalt removal be paid for? | An addendum is being created to include the additional quantity in question. | Fred Schunke | 2 | 2019-05-01 15:42 | 2019-05-07 10:03
20190514 | 20190514024 | 24 | Culvert/ Frost Heave HMA | The culverts and frost heave areas are figured to be paved back in with 4 MT included in the PWL calculation. Would the department consider changing this to Asphaltic Surface as this work is likely to have to be placed prior to any test strips taking place? | An addendum is being created to clarify the departments direction. | Fred Schunke | 3 | 2019-05-01 15:45 | 2019-05-07 10:04
20190514 | 20190514024 | 24 | Granular Backfill Grade 2 | Could 1.25 or 3/4 Inch Base Course be substituted for the Granular Grade 2 item, as long as it is virgin material that meets the spec for Base Course? Granular material can be expensive in this area. | An addendum is being created to introduce the new item â€œFoundation Backfillâ€ for use instead of Granular Backfill Grade 2. | Fred Schunke | 4 | 2019-05-02 16:35 | 2019-05-07 10:04
20190514 | 20190514024 | 24 | Topsoil | Is there a reason why the topsoil item is not salvaged topsoil? Will new topsoil be required if we are able to salvage it? | The contractor should assume new Topsoil will be utilized. | Fred Schunke | 5 | 2019-05-08 14:10 | 2019-05-10 09:23
20190514 | 20190514025 | 25 | Milling of Temporay Asphalt | A note on sheet 170 in the miscellaneous quantities in the Removing Asphalt section states, " excludes excavation and storm sewer removal areas". This obviously mean that any milling of asphaltic base in incidental to the item, but dose this include areas temporarily surfaced to provide a uniform prior to the "Winter Shutdown"? | The intent of the comment on page 170 is to reduce overlapping work of milling pavement that is scheduled to be removed through common excavation and storm sewer installation. (An example would be in Stage 2, within the areas closed to traffic, paying for full roadway width milling and then paying for common excavation of ~5-FT of roadway on both sides for C&G installation) The assumed construction methods in areas closed to traffic, post winter shutdown, are in the following order: excavation, asphaltic base placement, milling existing/temporary pavement to match asphaltic base, and placing remaining asphaltic upper layers. The department intends to pay for milling existing and temporary asphalt in place after stage 1 that will not be excavated post winter shutdown. Milling is not incidental to the items of asphaltic base and temporary asphaltic surface. Quantities have been modified in addendum #1 to match proposal staging. | Fred Schunke | 1 | 2019-04-26 11:45 | 2019-05-03 09:53
20190514 | 20190514025 | 25 | Topsoil | There is no topsoil quantity for under the sod. I have never seen where there is not topsoil placed under sod. Please clarify. | An emergency addendum has been issued to add topsoil under the sod areas. | Mike Coleman | 2 | 2019-05-10 16:58 | 2019-05-13 12:30
20190514 | 20190514028 | 28 | Shaping Shoulders | This project contains Item 204.0120 Removing Asphaltic Surface Milling. It does not contain Item 305.0500 Shaping Shoulders. Can this Item be added to provide for shaping the shoulders after milling and after HMA Paving? Please review and advise. Thank you. Also, can Item 315.0100 Asphaltic Base be changed to Item 465.0110 Asphaltic Surface Patching? It looks like the Item is for patching the existing roadway at the 2 Concrete Curb and Gutter locations. It will be very costly to produce and provide 1.5 Tons of Asphaltic Base. Please review and advise. Thank you. | The shaping shoulders bid item is not needed. The spec for milling includes grading the shoulders at the end of each work day to provide positive drainage, and the spec for base aggregate includes preparing the foundation before placing. We agree the asphaltic patching appears to be a more appropriate bid item to use. This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2019-04-22 07:26 | 2019-04-24 08:42
20190514 | 20190514030 | 30 | Item 40 HMA Pavement 3 LT 58-34S | Item 40, HMA 3 LT 58-34 S, is being used for the first two lower lifts for the bridge tie-ins. Typically on a multiple lift project we see a 58-28 S asphalt cement utilized on the lower layers. Can the 3 LT 58-34 S be changed to 3 LT 58-28 S? | Contractor should bid HMA Pavement per plan. The design intent was to reduce excess/waste oil for a better HMA price. FDM 14-10-35.3.2 indicates a typical tanker holds approximately 22 tons of binder, which will produce about 420 tons of HMA mixture. Only 1/3 of a tanker would be utilized for the small quantity (138 tons) of upper layer HMA, so we felt it would be an efficiency to utilize the same oil with the lower two layers. The project total of 683 tons of HMA should require just under two tankers. Awarded contractor can request a no-cost change order if they desire to use the typical lower layer 58-28 binder. | Mike Coleman | 1 | 2019-04-25 11:23 | 2019-04-30 10:27
20190514 | 20190514035 | 35 | temporary pavement markings | Can you tell me where all of the quantities of temporary marking paint are to be placed please? It appears you have quantities for the surface layer edge lines which would provide layout for the wet reflective edge lines as well as quantities for centerline markings of some sort. Are you planning on double yellow center lines on the milled surface throughout the project as that would make sense based on the quantities. If the temporary paint is to go on the milled surface, is it to be all double yellow? It looks like you are using the same day epoxy item prior to rumble placement and the standard epoxy item to be placed on the center lines after the rumbles. | Temporary Marking Line Paint 4-Inch is included for centerline double yellow and white edge line on the milled surface. (The entire project will have double yellow center line on the milled surface.) Same Day Epoxy 4-Inch is included for center line after paving HMA surface. Epoxy 4-Inch is included for touch up after center line rumble strip milling per SDD 13a11 2-Lane Rural Center Line Rumble Strip, Milling Design Notes. | Mike Coleman | 1 | 2019-05-03 08:14 | 2019-05-06 06:22
20190514 | 20190514038 | 38 | Item Clarification | Where it says "Polymer Overlay" is that ppc (polyester polymer concrete) or mls (multi layer system)? | It is the mls (multi layer system) â€“ see Article 11 in the Special Provisions. | Mike Coleman | 1 | 2019-04-18 12:24 | 2019-04-22 08:08
20190514 | 20190514040 | 40 | Intersection Paving | In the Specials it states intersections will be paved within 72 hours of milling. Would the region consider removing this language, as it will be an added cost to get this done for some pretty remote intersections | In consultation with the NC Region, this requirement will be waived for every intersection except for the CTH J (N) intersection. Revised special provision language indicating these modified requirements will be included in an upcoming addendum. | Mike Coleman | 1 | 2019-04-26 09:54 | 2019-05-02 06:36
20190514 | 20190514040 | 40 | PWL | IN the plans it has 2 PWL Test strips. What is the reasoning for this? | The required quantity for HMA Percent Within Limits (PWL) Test Strip Density should be 1 EACH, and the quantity for HMA Percent Within Limits (PWL) Test Strip Volumetrics should be 1 EACH. Modifications to these quantities will be included in an upcoming addendum. | Mike Coleman | 2 | 2019-04-26 09:58 | 2019-05-02 06:37
20190514 | 20190514040 | 40 | Asphalt Butt Joint | Would the region consider adding bid Item#204.0115 Removing Asphaltic Surface Butt Joint to this project. Does the typical on sheet 8 in the plans (side road detail)indicate the need for a butt joint at the termini? | In consultation with the NC Region, the Removing Asphaltic Surface Butt Joint item will be added to this project. A construction detail documenting the pay limits (to replace the detail referenced in the question) and revisions to the miscellaneous quantities will be included in an upcoming addendum. | Mike Coleman | 3 | 2019-04-30 14:40 | 2019-05-02 06:39
20190514 | 20190514041 | 41 | Rumble Strips | In your SDD 15 C 12-6 it has temporary rumble strips; two arrays, however there is no bid item for them. Are they incidental to the traffic control or should there have been a bid item for the Rumble strips? | Yes, there should. Temporary Rumble Strip items are being added in an upcoming addenda to avoid confusion. | Fred Schunke | 1 | 2019-04-29 15:58 | 2019-05-03 10:34
20190514 | 20190514041 | 41 | Pavement Markings | If I am reading the proposal correctly, the bridge work will be completed in 2019 (stage 2) and the polymer overlay work will be completed in stage 3 during 2020. On project 9030-11-60, it appears there may be pavement marking center line quantities to cover both the 2019 work and the 2020 overlay. However, it does not appear the same has been done on the 9215-01-64 project. Can you confirm your intentions in terms of adding additional quantities for this work? Thank you. | While the quantity change in minor, we agree there could be some concern with pavement marking contractors not realizing a second mobilization may be required should the project winter over. An addendum will be issued to adjust the quantity. | Mike Coleman | 2 | 2019-05-04 06:52 | 2019-05-09 08:08
20190514 | 20190514043 | 43 | Milling / Paving | Is milling and paving allowed on a Saturday if all milled surfaces are covered the same day? | Yes, milling and paving will be allowed on a Saturday if the day does not fall under a Holiday Restriction and all milled surfaced are covered the same day. | Mike Coleman | 1 | 2019-04-30 07:16 | 2019-05-02 06:35
20190514 | 20190514043 | 43 | Soil Boring Information | Please provide any soil boring information available for the project area. | No soil borings or soils analysis was required or conducted as part of the roadway & culvert project. The best available soils information at this point for roadway and culverts would be NRCS web based soil survey data. The plan includes a culvert pipe backfill detail for culverts which calls for backfilling per specification 520. | Fred Schunke | 2 | 2019-05-09 13:55 | 2019-05-09 15:54
20190514 | 20190514047 | 47 | Culvert Pipe Liners | What would the "n" value be for the existing concrete pipe? It may not be possible to maintain 95% flow capacity when lining a concrete pipe as opposed to lining a CMP. | An â€œnâ€ value of 0.013 was used in the design H&H analysis for these concrete pipes. | Mike Coleman | 1 | 2019-05-07 17:44 | 2019-05-13 08:35
20190514 | 20190514049 | 49 | pavement markings | Good morning. Seeing as this project is open to through traffic for the duration of the project (page 2 of 11 in proposal), what is your plan for temporary markings on the milled and lower layer as well as temporary or same day epoxy on the upper layer? Thank you. | Temporary pavement marking is not included on this project. Work within the majority of the project limits includes pulverizing the existing asphaltic pavement and after this has occurred, temporary pavement marking is not overly feasible. In the area of milling within the Village of Curtiss this is a low speed area and "No Centerline" signs are anticipated to be installed information traffic of this condition. | Fred Schunke | 1 | 2019-05-06 11:22 | 2019-05-07 09:40
20190514 | 20190514049 | 49 | Pedestrian access | Why isn't there any bid items for temporary pedestrian access? | The prosecution and progress includes a section regarding Pedestrian Access during construction of this project. No temporary pedestrian ramps are required per discussions with Region and therefore the item is not included in the contract. Contractor shall maintain pedestrian access at a minimum of one location per block utilizing either existing or constructed curb ramps. | Mike Coleman | 2 | 2019-05-07 11:49 | 2019-05-09 08:00
20190514 | 20190514051 | 51 | Picking up and Installing State furnished Decorative Fencing | This project contains a bid item for picking up and installing state-furnished decorative fencing. Would be OK stop by the facility and take a look at the fencing, to better help prepare our bid? | The department furnished decorative fence and components are located at 935 S. 60th St., West Allis WI 53214-3362 Contact Mitzi Dobersek at (414) 266-1150 or (262) 875-1252 to coordinate viewing the fencing. | Mike Coleman | 1 | 2019-04-17 06:46 | 2019-04-17 06:49
20190514 | 20190514051 | 51 | Slurry Backfill | The special provisions detail information on Backfill Slurry to be used for removing and abandoning utility pipes and structures, installation of storm sewer, sanitary sewer and water pipes and structures, and exposing existing utility items as shown on the plans. Will construction details be provided to show the extent of slurry backfill required for those items? |  |  | 2 | 2019-04-24 09:07
20190514 | 20190514051 | 51 | Project Schedule | 1. Can the design schedule be provided for this project? 2. The completion date for this project is challenging, would the Department consider extending this deadline to be completed during this construction season? | 1. The design schedules can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190514051/ 2. The project time for completion cannot be extended based on coordination with the DNR. It must be open by mid-September. | Mike Coleman | 3 | 2019-04-29 10:02 | 2019-04-30 06:32
20190514 | 20190514051 | 51 | Lighting Pull Boxes | There are 6 pull boxes in Lighting Plan but not listed in proposal line. Are these quantities missing? | The plan and quantities will be updated in an upcoming addenda. | Fred Schunke | 4 | 2019-05-07 09:16 | 2019-05-07 09:18
20190514 | 20190514051 | 51 | Pedestrian Signs for RRFB Systems | Are the Pedestrian signs for the RRFB Systems (Line Items 0360, 0362, 0364, 0366, 0368, 0370, 0372)supposed to be included in these line items, or are they part of a separate bid/line item? The proposal spec they should be shall be supplied and installed under a separate bid item, but the Detailed Drawing of the RRFB system on the Plans states that they should be included in these line items. Also, what about the Poles/Bases/Anchor Bolts for these RRFB systems? | The pedestrian static signs are paid for under the miscellaneous quantities table for permanent signs attached. So, they are a separate bid item (637.2230) The poles, bases, bolts, solar, etc. are all part of the RRFB bid item as noted in the spec. Turnkey operation. Everything but the static warning signs. The RRFB drawing doesnâ€™t say that the sign is part of the RRFB, so not sure why that is being questioned. The RRFB drawing simply has to show the sign to make it clear that there is a sign. On the last page of the RRFB spec it says under â€œD Measurementâ€ that it is an RRFB system as a lump sum. On the second page of the spec it clearly says the sign is a separate bid item and the permanent signing miscellaneous quantities clearly show the sign numberâ€™s and pay item. | Fred Schunke | 5 | 2019-05-07 12:38 | 2019-05-09 14:26
20190514 | 20190514051 | 51 | Plan Holders List | Will a plan holders list be provided? | Plan Holders Lists is provided on the HCCI Site for all proposals, each letting. Here is the link for HCCI Page of the May 14, 2019: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2019/20190514.aspx The Plan Holders List for the May 14, 2019 Letting is found at the following location: https://wisconsindot.gov/hccidocs/bid-let/2019/20190514/planholders.pdf | Fred Schunke | 6 | 2019-05-10 08:06 | 2019-05-10 09:22