## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20190910 | 20190910002 | 2 | Line Item 0392 Traffic control close-open freeway enterance ramp | Under payment of this item you have a surveillance description. What is the intent?Daily reports with hourly metered tickets, sweeping and disposing of materials ETC. | An addendum will be issued to correct the language. | Mike Coleman | 1 | 2019-08-16 09:27 | 2019-08-27 07:46
20190910 | 20190910002 | 2 | Pipe Railing Baseplate Detail, R-40-694/695 | For the baseplates on the pipe railing for R-40-694/695 the detail shows a sleeved connection for the railing to the baseplate. This style of railing baseplate makes it difficult to install the rail plumb and level in the field, and usually results in a less than desired finished product. Can this railing be fabricated with the baseplates shop welded to the posts and do away with the sleeved field connection? | The railing can be fabricated with the baseplates welded to the posts. This option is actually listed in the plans. See sheets 265 and 272 of the plan set (Post Attachment detail). | Mike Coleman | 2 | 2019-08-19 15:03 | 2019-08-20 12:07
20190910 | 20190910002 | 2 | Gates Chain Link 6-Ft | The miscellaneous quantities show there is 1-6-ft chain link fence gate, but there are 2 callouts on plan sheet 17. Is there 1 or 2 gates? | There is 1 gate required. The callouts on the plan sheet are the station and offset of the beginning of the gate and end of the gate. | Mike Coleman | 3 | 2019-08-21 07:21 | 2019-08-21 07:22
20190910 | 20190910002 | 2 | Full Freeway Closure work windows | When you take into consideration traffic control setup and take down plus clean up the full closure windows seem pretty tight and inefficient. Is there any chance that the Sunday through Thursday window can be expanded to something similar to the Friday & Saturday full closure window? Specifically during the demo operation. | The contractor should bid per the closure hours in the proposal. These are the same full freeway closure hours that were used on other adjacent freeway projects within the last few years. Traffic capacity guidelines were used to determine the appropriate hours of the various types of closures. | Mike Coleman | 4 | 2019-08-29 10:14 | 2019-08-30 07:38
20190910 | 20190910002 | 2 | Intermediate Steel Diaphragms | Detail B on Sheet 18 of 33 of Structure B-40-1002 is not clear on the number of plate washers required for the bolts of the steel diaphragms. WisDOT Bridge Manual Standard Drawings state: "7/8" DIA. HIGH STRENGTH BOLT WITH HEX NUT. TWO WASHERS AND TWO 3 1/2" SQUARE X 5/16" PLATE WASHERS (TYP.). | Provide two standard washers and two 3 1/2" square x 5/16" plate washers at each bolt, per the latest WisDOT Bridge Manual Standard Drawings. | Mike Coleman | 5 | 2019-08-30 09:06 | 2019-09-03 14:55
20190910 | 20190910002 | 2 | CAD Files - WDOT #2 68th St Overpass | Are CAD Files available? | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190910002/ | Mike Coleman | 6 | 2019-09-03 07:17 | 2019-09-06 13:31
20190910 | 20190910003 | 3 | Soil Borings C-67-86 | Are there any soil borings available associated with Structure C-67-86? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190910003/ | Mike Coleman | 1 | 2019-08-28 08:26 | 2019-09-03 11:08
20190910 | 20190910003 | 3 | Please confirm Quantity Concrete Surface Repair 300 sf | Item 0058 # 509.1500 Concrete Surface Repair. Bid quantity shows 300 SF. Misc Quantity sheet (sht 70) shows 19 sf @ Sta 1322+70, Structure plans C-67-86 shows 150 SF. Total 169 sf I cannot find any additional quantity. Please confirm quantity or supply input as to the location of the additional quantity. (131 sf)? | The correct quantity is 169 SF. An addendum will be issued to correct this. | Mike Coleman | 2 | 2019-08-29 14:19 | 2019-09-03 11:01
20190910 | 20190910003 | 3 | Lane Closures for work at Box Culvert | The Special Provision for Maintaining Traffic indicates that flagging operations will be required for Milling, Paving, Base Patching and Guardrail work but does not include work at the box culverts. Please confirm that lane closures during non-peak hours are acceptable to complete box culvert work and that all work is not required to be completed in the one weekend closure period. | Correct, any Box Culvert work that needs to be done outside of the full-closure shall follow the Traffic Special Provision during work hours. | Mike Coleman | 3 | 2019-08-30 09:10 | 2019-09-03 11:02
20190910 | 20190910003 | 3 | Bid Item 210 - Special Box Culvert WIngwall, STA 1342+65 | Is there a special provision for this item? This is the stationing for C-67-86, but the item is not listed in the Estimated Quantities sheet for the structure. | The estimated quantities for C-67-86 are on the structure plans. There is no specific Special Provision for this Item, however, items are detailed under the Scope of Work, Prosecution and Progress, and Traffic Sections. | Mike Coleman | 4 | 2019-08-30 09:16 | 2019-09-03 11:03
20190910 | 20190910003 | 3 | Concrete surface repairs Sta 1322+70, Offset LT, 19 SF | Please confirm that the concrete surface repair required at this location is on the exposed wings. Anything inside the box culvert is virtually inaccessible. | No work is anticipated inside the box culvert. Most of work is on the outside of the box header on the west end. Additional repair is on the bottom at the immediate west end within armâ€™s reach from outside of box. | Mike Coleman | 5 | 2019-08-30 10:52 | 2019-09-03 10:37
20190910 | 20190910003 | 3 | Bid Item #210 - What is this for? | Still do not understand this bid item. Stationing indicates it is work at Structure C-67-86, but standard bid items are included to cover all work on the box culvert wings. What work is included in this lump sum item? It seems as though this is a duplicate item and should be removed since there is no mention of the item in the structure plans. | An addendum is being issued to remove this bid item. The item was included in error as a previous placeholder for the structure items. The other structure items encompass required bid items for box culvert work. | Mike Coleman | 6 | 2019-09-05 06:43 | 2019-09-05 12:27
20190910 | 20190910004 | 4 | Weighing of Base Materials | Please confirm if weighing of Base Materials will be allowed by in place measurement, conveyor scale, loader scale, platform truck scale or any other means. Please also confirm if onsite processing of existing onsite materials will be allowed. Please confirm which of these forms of measurement will be accepted and if they will be accepted for both quality control requirements and payment. Please also confirm if milling of the existing asphalt on site will be allowed or if the milled existing asphalt material must be screened or crushed to a size below maximum spec top size. | 1. Please confirm if weighing of Base Materials will be allowed by in place measurement, conveyor scale, loader scale, platform truck scale or any other means? Bid accordingly so that measurement of aggregates confirms to sub-section 109.1.4 of the Standard Specifications. 2. Please also confirm if onsite processing of existing onsite materials will be allowed? An addendum will be forthcoming. 3. Please confirm which of these forms of measurement will be accepted and if they will be accepted for both quality control requirements and payment? See answer to question 1. 4. Please also confirm if milling of the existing asphalt on site will be allowed or if the milled existing asphalt material must be screened or crushed to a size below maximum spec top size. Reclaimed Asphalt shall meet the requirement specified in subsection 305.2.2.2 of the Standard Specifications. | Mike Coleman | 1 | 2019-08-11 10:42 | 2019-08-13 09:53
20190910 | 20190910004 | 4 | Design Schedule | Can the design schedule be provided? | The time chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190910004/ | Mike Coleman | 2 | 2019-08-13 06:02 | 2019-08-13 10:30
20190910 | 20190910004 | 4 | Design Files and Control Request | Are the CAD and Control Files available? | The design files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20190910004/ Please note that there were 2 engineering firms working on the design and that is the reason for the two separate folders. | Mike Coleman | 3 | 2019-08-20 15:00 | 2019-08-28 10:45
20190910 | 20190910004 | 4 | Type SR GEOTEXTILE | Has an addendum been issued regarding the specification for this item? | An addendum has been issued to correct the requirements of the Geotextile Type SR. TEST METHOD VALUE[1] Minimum grab tensile strength ASTM D4632 170 lb Minimum puncture strength ASTM D6241 350 lb Maximum apparent opening size ASTM D4751 No. 70 Minimum permittivity ASTM D4491 0.35 s-1 | Mike Coleman | 4 | 2019-09-05 06:37 | 2019-09-06 11:39
20190910 | 20190910004 | 4 | Optimized Gradation | Our understanding is that optimized gradation will be a requirement on this project for the concrete pavement. Can you confirm that this is the case (er no?)? | Optimized Gradation will be required for the Concrete Pavement. | Mike Coleman | 5 | 2019-09-06 11:28 | 2019-09-06 13:40
20190910 | 20190910005 | 5 | STH 22 Closure | The contract is 35 working days, but special provisions detail 35 calendar days for the closure of STH 22 with $7,500/day in LDs for calendar days beyond 35. Please verify the departments intent and provide the designer's schedule. | This project is a 35 working day contract. There is an interim completion time of 35 calendar days that the department has allowed for the detour. Complete all work associated with Structure C-58-024 construction and open STH 22 to traffic on a HMA lower layer within 35 calendar days from the time the detour is implemented. The contractor has the remaining working days to complete the rest of the work. | Mike Coleman | 1 | 2019-08-21 08:37 | 2019-08-22 07:35
20190910 | 20190910005 | 5 | Temporary Water Diversion | The item Temporary Water Diversion details that it is for a "culvert pipe" at Shawano Lake in the special provisions, but there is no pipe at the rigid frame box at shawano lake and the culver pipe is not at shawano lake. Was this item intended for the culvert pipe on another area of the project, or was it intended for use at the rigid frame box culvert at shawano lake? | The Temporary Water Diversion pay item is intended for use at the existing STH 22 structure that is being replaced as part of this project. Regarding the TWD pay item for project 9180-17-60, the TWD application is for use at the existing STH 22 open-bottomed structure (not some other culvert within the project limits; not some other upstream/downstream conduit outside the project limits), and the purpose of the TWD is to give the contractor a means of conveying stream flow during construction with payment for stream conveyance provided by the TWD pay item. In the TWD special provision (Article 22: section A Materials, first sentence; section C Construction, first sentence) the words â€œculvert pipeâ€ are misleading and should have been replaced with something like â€œdrainage conduitâ€ or â€œdrainage structureâ€. The STH 22 drainage structure is located over 2000â€™ away from Shawano Lake and the language of the contract is not meant to imply that the proposed drainage structure for the project is on or abutting Shawano Lake. | Mike Coleman | 2 | 2019-08-28 13:21 | 2019-08-29 06:43
20190910 | 20190910005 | 5 | Sheet Membrane Waterproofing | Does the concrete deck surface need to be sand or shot blasted prior to installing the sheet waterproofing? If so, is this incidental to the item? | The preparation method does not have to be sand/shot blasting, but the surface must be prepared using an acceptable method as described in article 17 of the special provisions and/or section 516 of the standard specifications. The method of preparation is incidental to the pay item of Sheet Membrane Waterproofing for Top Slab C-58-024 | Mike Coleman | 3 | 2019-08-30 06:21 | 2019-09-03 08:02
20190910 | 20190910005 | 5 | Overhead Utilities at STH 22 Bridge | There are existing overhead lines on the north side of STH 22 that will fall directly above the new structure when it is widened out. SPV #6 indicates that no conflicts are anticipated, but these will interfere with pile driving operations. | The department and the utility company have reviewed the sited and have determined the project is constructible as shown in the plans. If your means and methods will encroach on the utility, coordination with the utility will be the contractor's responsibility. | Mike Coleman | 4 | 2019-09-05 06:35 | 2019-09-05 13:45