## qandasearchletting_results
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20191210 | 20191210001 | 1 | Cad files | Can you please release the cad files for this project? Thank you. | The files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210001/ | Mike Coleman | 1 | 2019-11-13 06:43 | 2019-11-18 09:08
20191210 | 20191210001 | 1 | HMA - Temp Pavement | Line item 90 has 55 TN of Asphaltic surface Temporary. I do not see it in the Misc. Qty's. Can you identify where this is being used on the project? | The bid item of â€œAsphaltic Surface Temporaryâ€ is used on the project for the installation of culvert pipes in three locations. There is not enough time in one nighttime work period to install a culvert pipe under the existing roadway and then open it up to traffic the next day as a concrete surface. The temporary asphalt allows the contractor to install the temporary asphalt at the end of the allowable closure time and then come back the next night to remove the asphalt and replace it with permanent concrete. See sheet 26 of the plans, note 6. See sheet 186 of the plans, Culvert Pavement Items, lower left area of the sheet. | Mike Coleman | 2 | 2019-11-19 12:20 | 2019-11-20 08:55
20191210 | 20191210001 | 1 | Bar Steel Reinforcement-Galvanized tie wire | The spec states to provide a "polymer coated wire" for the tie wire on this rebar installation. Is this in reference to the same plastic coated wire that is currently used for installation of the epoxy coated rebar? If not, is there a list of approved tie wire that meets the "polymer coated wire" requirement. | The same plastic coated wire used for the epoxy coated bars should be used for the whole bridge. Same tire wire for all bars. | Mike Coleman | 3 | 2019-11-19 12:34 | 2019-11-20 10:22
20191210 | 20191210001 | 1 | Gates for Railing Tubular Screening on R-13-348/349/350/351/352 | In reference to the gate design for the tubular screening railing for R-13-348/349/350/351/352, page 505 is the detail for R-13-348. The way these gates are designed with the hinge on the post that is to be set in the slope paving area has been a problem for constructability. We have done railing on several projects on the I39 corridor in the past with similar gates and have had an issue on each one in getting the hinge post set correctly. The issue lies in the fact that the slope paving is poured before the railing gets installed, so being able to get the post set in the correct location to align with the railing is impossible. It always needs to be set after the coping and paving is poured, typically off to the side of the abutment and never ends up with a good finished product. Would the department consider a different design on these gates where the hinge is located on one of the railing posts on top of the coping instead? A clip could be then anchored into the front face of the abutment with the latch and lock for the gate. Some railing was installed on project 1030-24-72 on R-51-83 with this design that was much easier to install, and left a much better finished product. | This design has been used on the entire I 39 corridor. Tor remain consistent, this detail will remain in the plans. | Mike Coleman | 4 | 2019-11-25 09:05 | 2019-11-26 12:34
20191210 | 20191210001 | 1 | textured epoxy coating & galvanizing rebar | Structure B-13-729 calls out two bars to be textured epoxy coated for three beams and galvanized for another three beams. The special provision calls for bending after coating - is it possible to bend and then coat to avoid issues with cracking the coating and having to cut the straight bar and recoat the exposed ends? Also the testing calls for 60 inch #4 bar samples but the bar required is #3. Could we send #3 bar samples? | 1. is it possible to bend and then coat to avoid issues with cracking the coating and having to cut the straight bar and recoat the exposed ends? â€“ Yes 2. The testing calls for 60 inch #4 bar samples but the bar required is #3. Could we send #3 bar samples? -- Yes | Mike Coleman | 5 | 2019-12-03 14:08 | 2019-12-04 08:23
20191210 | 20191210001 | 1 | Tribal Contact | Tracy Thundercloud is no longer the Executive Director of Labor for the Ho-Chunk Nation. Who is the new contact from the Department of Labor for the Ho-Chunk Nation? | The new contact for the Ho-Chunk Nation is: Angela K. Ward Executive Director Department of Labor W9814 Airport Road/PO Box 667 Black River Falls, WI 54615 Office: 715-284-5877 ext: 1139 Fax: 715-284-1520 angela.ward@ho-chunk.com | Mike Coleman | 6 | 2019-12-03 16:10 | 2019-12-04 07:05
20191210 | 20191210001 | 1 | Design Schedule | Could the Department provide the Design Schedule for this project? | The Preliminary Construction Schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210001/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 7 | 2019-12-05 14:31 | 2019-12-09 11:27
20191210 | 20191210005 | 5 | Are soil borings available? |  | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210005/ | Mike Coleman | 1 | 2019-11-11 08:32 | 2019-11-11 09:19
20191210 | 20191210005 | 5 | WisDOT Permit for water main directional bore in IH 39 R/W | Is there a permit to construct the watermain directional bore in IH 39/90 right-of-way? | The permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210005/ | Mike Coleman | 2 | 2019-11-11 09:41 | 2019-11-11 09:46
20191210 | 20191210005 | 5 | CAD Files | Could you please provide the following: 1. Existing Conditions Survey Surface CAD files (Format: LandXML, .DWG or .DGN) 2. Existing Condition Survey Mapping CAD files (Format: LandXML, .DWG or .DGN) 3. Proposed Finish and Subgrade Surface CAD files (Format: LandXML, .DWG or .DGN) 4. Proposed Alignments CAD files (Format: LandXML, .DWG or .DGN) 5. Proposed Linework CAD files (i.e. Curbs, Road Lines, etc) (Format: LandXML, .DWG or .DGN) | The Cad Files and surfaces can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210005/ | Mike Coleman | 3 | 2019-11-22 07:30 | 2019-11-27 06:53
20191210 | 20191210005 | 5 | Excel Earthwork Tables | Could you please provide the earthwork tables in excel format | The Excel Earthwork spreadsheet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210005/ | Mike Coleman | 4 | 2019-11-22 07:32 | 2019-11-27 06:52
20191210 | 20191210005 | 5 | December 10 letting, #05, 2019 | I see no bid item 652.0800 for Conduit Loop detector, Cottage Grove Rd, North Star to Sprecher Rd. Thanks Mike | An addendum will be issued to add the item 652.0800 Conduit Loop Detector and corresponding quantities. | Jill Fehrman | 5 | 2019-11-26 13:49 | 2019-12-02 13:13
20191210 | 20191210006 | 6 | Railing - Square Sleeve Detail | All railing drawings in the structure plans describe a "square sleeve fabricated from 1/2-inch cold drawn steel alloy square conforming to ASTM A331". ASTM A331 is an obsolete specification. Additionally, could the sleeves simply be made from A36 steel. It's also not practical to fabricate a 1-inch square sleeve from 1/2-inch plate as shown in Section C. Type C railing is typically fabricated from 3/16-inch thick A36 steel. | Square sleeve fabricated from 3/16â€ plates conforming to ASTM designation A709 Grade 36 x 2â€™-4â€ long at expansion joints and 1â€™-10â€ long at field joints. Provide ½â€ dia. surface welds on all sides as shown. Grind welds to fit free into I.D. of No. 3. Provide 3/8â€ dia. x ½â€ welding studs on top and bottom surfaces at centerline. An addendum will be issued to clarify. | Mike Coleman | 1 | 2019-11-05 16:59 | 2019-11-07 09:39
20191210 | 20191210006 | 6 | Railing - Post Configuration | All railing drawings show what appears to be a sleeved or stepped post detail in the section thru railing steel. It also shows a 3/16" fillet weld all-around, but it doesn't clarify what this component is to be fabricated from. The same is not shown in the part elevation of railing steel detail. | The â€˜Section Thru Railing Steelâ€™ section should show the rail post down to the Railing Base Plate on the 7 sets of structure plans. It should match the â€˜Part Elevation of Railing Steelâ€™ section. An addendum will be issued to clarify. | Mike Coleman | 2 | 2019-11-05 17:00 | 2019-11-07 09:40
20191210 | 20191210006 | 6 | Railing - Top Rail Material | All railing drawings state the top rail as a 2 1/2-inch standard pipe which would have an actual O.D. of 2.875-inches but the section thru railing steel shows 2 1/2-inch dimension. 2-inch standard pipe has an actual O.D. of 2.375-inch. | The â€˜Section Thru Railing Steelâ€™ section should show the top rail depth as 2 7/8â€, NOT 2 ½â€ on the 7 sets of structure plans. The length of member 4 should also be 2â€™-1 5/8â€, NOT 2â€™-2â€ in this section. An addendum will be issued to clarify. | Mike Coleman | 3 | 2019-11-05 17:01 | 2019-11-07 09:41
20191210 | 20191210006 | 6 | Railing - Base Plate Slotted Holes | Can railings be provided with slotted holes in base plates for anchor to allow ease of installation similar to Type-C railing? | The Railing Base Plate can be provided with slotted holes. Note #5 in the Legend on the 7 sets of structure plans should read as follows: Base plate ½â€ x 7â€ x 7â€ conforming to ASTM designation A709 Grade 36 with ¾â€ dia. x 1 ½â€ slotted holes for anchor bolts No. 6. Weld to No. 2 as shown. The â€˜Railing Base Plateâ€™ detail can be modified to call out the centerline of the railing and call out the ¾â€ dia. x 1 ½â€ slotted holes for 5/8â€ dia. anchors. An addendum will be issued to clarify. | Mike Coleman | 4 | 2019-11-05 17:02 | 2019-11-07 09:42
20191210 | 20191210006 | 6 | Railing - Retaining Wall Plan Orientation | On the retaining walls with horizontal curves on the plan, will the railing be required to be curved or can they have tangent rail sections along horizontal curves? | The railings on the retaining walls with horizontal curves on the plans should be curved. | Mike Coleman | 5 | 2019-11-05 17:10 | 2019-11-07 09:43
20191210 | 20191210006 | 6 | Colored Bike Box | It is my understanding that the City of Madison does not use an Epoxy for the Bike Lane Green, but use MMA(Methyl-Methacrylate) as their preferred material for the bike boxes as this is a more durable material than an epoxy. Can you verify what material we are to use, and a vendor that sells the Green Modified Exothermic Epoxy binder, and its components, if the Department does not switch to the MMA generally used in Madison? | A revised special provision has been prepared for article #95 for Colored Crosswalk Green which will be included in an addendum that will include an MMA resin product. | Mike Coleman | 6 | 2019-11-19 10:08 | 2019-11-20 12:05
20191210 | 20191210006 | 6 | Reheating HMA longitudinal Joints | Are HMA joints being reheated on all 3 lifts of HMA for the project? Which joints are being reheated; I.E. between two driving lanes, shoulders, turn lanes etc... | The reheating of longitudinal joints should be completed as described in Special Provision Article #28, applied between driving lanes, shoulders, and turn lanes, for all longitudinal joints, in all HMA layers. The table in the miscellaneous quantities should be revised to better identify these areas. An addendum is currently being prepared for several other items and this change can also be incorporated by addendum. | Mike Coleman | 7 | 2019-11-19 12:26 | 2019-11-25 06:21
20191210 | 20191210006 | 6 | HMA notched wedge | Plan sheet 365 Shows a notched wedge detail for two lifts of HMA. This project has 3 lifts. Do all three lifts get a notched wedge installed? Does the notched wedge get installed only between the drive lanes? Please also confirm that the notched wedge is to stay in place and not be removed prior to paving the adjacent lane. | Per the requirements of SDD 15D39, the notched wedge should be installed at HMA pavement joints whenever the elevation difference between abutting layers is 2â€ or more, and open to traffic. The notched wedge will primarily be required near the end of the construction under Stage 4, when the upper 2â€ of HMA pavement is placed, and all traffic lanes in both directions are open during daytime hours in their permanent location. This Stage 4 upper layer HMA paving is limited to overnight under lane closures when the West Towne Mall is closed to the public. The notched wedge will also be required for turning and cross traffic movements at intersections during Stage 1 and Stage 2, when the lower and middle layers of HMA pavement are installed. Wherever used, the notched wedge will be temporary, and should be removed prior to paving the adjacent lane. Because the notched wedge wonâ€™t remain in the permanent pavement, SDD 13C19 â€œHMA Longitudinal Jointsâ€ (advertised plan sheet 365) will be removed from the plan. Newly-created STSP 204-045 (Removing Asphaltic Longitudinal Notched Wedge Joint Milling, Item 204.0126.S) can be included as an article in the special provisions, and quantities identifying locations for the new bid item can be added to the Miscellaneous Quantities sheets. An addendum is currently being prepared for a few other items, and this information can be included with that addendum. | Mike Coleman | 8 | 2019-11-19 12:29 | 2019-11-25 06:22
20191210 | 20191210006 | 6 | HMA lift thickness | The plan calls for 2.25'' lower(3MT), 2.5''(3MT) middle and a 2'' Upper(4MT) lift. Please explain why the middle lift is thicker than the lower. | The City of Madison prefers these layer thicknesses which allow for more mill and overlay resurfacing cycles of the street without causing the middle layer to become too thin. With those layer thicknesses, they feel they can get 2 to 3 mill and overlay cycles without having to remove the entire middle layer. | Mike Coleman | 9 | 2019-11-19 12:31 | 2019-11-20 14:25
20191210 | 20191210006 | 6 | Architectural surface treatment details | In regards to the Architectural surface treatment details on page 518 of the plans it calls out specifically the colors to be used, with a grout line color stained in, however in the special provisions and page 35 of 112 there are references to using a multi color effect. Is the more traditional multi color replicating stones as it states in the special provisions required on this project or are we to follow the single colors dictated in the plans with the grout line color stained in? | The staining should be completed as called out on Sheet 518 in the plans. The referenced special provision for â€˜Concrete Staining Multi-Color B-13-870â€™ is a Standardized Special Provision and Section A states to provide a concrete stain as the plan details show. | Mike Coleman | 10 | 2019-11-20 14:04 | 2019-11-21 12:02
20191210 | 20191210006 | 6 | Cad File | Can you please release the cad files for this project. Thank you. | The Cad files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210006/ | Mike Coleman | 11 | 2019-11-22 08:46 | 2019-11-26 06:28
20191210 | 20191210006 | 6 | Sign Bridges | Line items 276-288 have a bid item ID and description of "641.1200 Sign Bridge Cantilevered..." as opposed to "641.8100 Overhead Sign Supports" like line items 290-296. The Structures Details sheets, pgs. 504-508' consistently reference how to design the Overhead Sign Supports. Are these line items cantilevered sign bridges or overhead sign supports? Please provide the shop drawings for bidding these structures if they fall under "641.1200 Sign Bridge Cantilevered" bid items. | The items 7 structures listed under the bid item â€˜Sign Bridge Cantileveredâ€™ should be under the bid item â€˜Overhead Sign Supportâ€™ instead. The estimated unit prices for those should also be adjusted since the original estimate only included the cantilevered arm extending from the pole. An addendum will be issued to correct. | Mike Coleman | 12 | 2019-11-26 09:59 | 2019-11-27 15:23
20191210 | 20191210006 | 6 | Geotech | Do you have a geotech report available for this project?? | The Geotechnical Reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210006/ | Mike Coleman | 13 | 2019-12-03 08:39 | 2019-12-04 08:20
20191210 | 20191210006 | 6 | Cad files | Can you please post the link for the cad files? Thank you. | The Cad files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210006/ | Mike Coleman | 14 | 2019-12-04 07:33 | 2019-12-04 08:20
20191210 | 20191210006 | 6 | Fluid Thermal Backfill | Please provide clarification on the limits of the fluid thermal backfill for the ATC line. | The fluid thermal backfill is called out for ULO areas identified in the plans and a special provision is provided. If excavation is required down to the ATC conduit, then fluid thermal backfill that is removed should be replaced. The area of the backfill is approximately 2 ft wide x 2 ft deep along the excavated area over the conduit. | Jill Fehrman | 15 | 2019-12-04 13:37 | 2019-12-06 12:50
20191210 | 20191210006 | 6 | Retaining Wall Block Height | The specification for the MSE Block and Gravity Block Retaining walls specifies a block height of 9". The WISDOT approved supplies blocks exceed 9". Please confirm it is acceptable to utilize blocks from approved suppliers that exceed 9" in height. | WisDOT approved suppliers blocks exceeding 9â€ block height will be acceptable, with the following exception: The block height at the coping should be limited to 9â€ to maintain the 1â€™-3â€ coping depth at the front face of the wall with the 6â€ minimum depth of the concrete coping over the block as shown in the plan details. | Jill Fehrman | 16 | 2019-12-06 09:34 | 2019-12-09 09:30
20191210 | 20191210007 | 7 | HMA Overlay of Concrete Pavement | The lower lift HMA in the Overlay Concrete Base Patching sta 9+12 to 18+95 is variable thickness for crown correction. This HMA should be QMP instead of PWL. | After consultation with the WisDOT Design Team and the WisDOT SW Region Pavement Design Engineer, the lower lift of HMA Pavement 4 MT 58-28 S (variable thickness) between Station 9+12 and Station 18+95 should not be included in the PWL. An addendum will be issued to address this update. | Mike Coleman | 1 | 2019-11-15 15:01 | 2019-11-20 08:39
20191210 | 20191210007 | 7 | schedule | Can the construction schedule that was developed with the design be uploaded to the ftp site? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210007/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2019-11-19 09:21 | 2019-11-19 12:51
20191210 | 20191210007 | 7 | Pavement Markings | Can you please take a look at the temporary paint for the milled and lower layers as outlined in the proposal as well as the same day epoxy item quantities. At first glance, it appears the temporary paint item will be used on the milled surface and lower layer in sections 9+12-25+00, 43+92-164+30, and 225+50-586+40 and just on the lower layer in sections 25+00-43+92 and 164+30-225+50. The bid quantities, if you are looking for double yellow the entire way as noted under the temporary paint item on sheet 139, seem to be off. Per page 4 of 56 in the proposal, it calls out temporary epoxy on the surface layer before center line rumble strips are installed yet there is no temporary epoxy item included in the proposal. The same day epoxy item might be a better fit for this application as not all sections get rumbles, is that your intent? Thank you. | In the station ranges of 9+12-25+00, 43+92-164+30, and 225+50-586+40 (rural typical section locations) the Temporary Marking Line Paint 4-inch (double yellow) was quantified following the sequence shown on pages 14 and 15 of the plan. The intent is to not place the double yellow on the milled surface, rather, install it on the lower lift (labeled in the first pass detail) and these markings will remain until the Marking Line Same Day Epoxy 4-Inch (double yellow) is placed after the fourth pass. In the station ranges of 25+00-43+92 and 164+30-225+50 (urban typical section locations) the Temporary Marking Line Paint 4-inch (double yellow) was quantified following the sequence shown on pages 16 and 17 of the plan. The intent is to place the Temporary Marking Line Paint 4-inch (double yellow) on the existing surface to remain (labeled in the first pass detail). The double yellow is then reestablished on the new lower layer shown in the third pass detail and will remain until the top lift is placed. The Pavement Marking and Centerline Rumble Strips paragraph under the Prosecution and Progress Article will be updated via an Addendum to reflect the Marking Line bid items shown in the fourth pass detail on page 15 of the plan. | Mike Coleman | 3 | 2019-11-20 09:25 | 2019-12-03 06:57
20191210 | 20191210007 | 7 | ASP 6 - Pilot Car | ASP 6; 104.6.1.2.2 Flagging - reads that a Pilot Car is incidental to Flagging if required. Does that mean if required as needed? - or - Does that mean if required per the proposal specifications? | According to SDD 15C12 â€œTraffic Control for Lane Closure With Flagging Operationâ€, A pilot car will be required if the distance between flaggers exceeds 2 miles and/or when curves reduce sight distance below 400 feet. | Jill Fehrman | 4 | 2019-11-26 09:34 | 2019-12-02 16:26
20191210 | 20191210007 | 7 | Base Patching | Can the 390 spec be amended to allow for 19mm HMA instead of the 1" nominal (25 mm) as per 315.2? | For item 390.0203 Base Patching Asphaltic, a 19 mm HMA pavement gradation may be used as an alternative to the 1-inch nominal (25 mm) size specified in Standard Specification 315.2. If a 19 mm HMA pavement gradation is used, the maximum allowable compacted layer thickness is 5 inches or less (1-inch less that the allowable 6 inches or less as specified in Section 390.3.3 (3) of the Standard Specification). | Mike Coleman | 5 | 2019-12-02 08:36 | 2019-12-04 06:40
20191210 | 20191210007 | 7 | Special Provisions Under Milling & Paving Operations | The special provisions references a lower layer HMA Pavement of 4 LT 58-28 S and an upper layer HMA Pavement of 4 LT 58-28 S (see page 4), should these be changed to 4 MT to match the plan? | The HMA pavement types referenced in paragraph two under the â€œMilling and Paving Operationsâ€ header within Article 3. Prosecution and Progress should be HMA Pavement 4 MT 58-28 S for the lower layer (not 4 LT 58-28 S) and 4 MT 58-28 S for the HMA Pavement upper layer (not 4 LT 58-28 S). In addition, the following HMA Pavement references on Page 6 and Page 148 of the Let plan should be HMA Pavement 4 MT 58-28 S (not 4 LT 58-28 S): 1. Page 6: Match Line A Typical Section - Station 220+25 to Station 225+50. 2. Page 148: â€œPave 0â€ - 4â€ HMA 4 LT MT 58-28 S Wedge Layer from 226+77.11â€BRâ€ - 227+80â€BRâ€ between 4â€™ LT and 24â€™ RT. An addendum will be issued to correct this. | Mike Coleman | 6 | 2019-12-02 08:38 | 2019-12-03 10:30
20191210 | 20191210007 | 7 | Earthwork Breakdown | Earthwork Summary Table only shows two areas for Common Excavation 9+12 - 46+50 and 147+25 - 227+80. Is there a breakdown by station Earthwork Data available or how this quantities had been arrived at? Cross Section for Mainline LT and RT in a beam guard areas showing grading in the roadway, but there is no typical sections that show any kind of excavation in these areas. Can it be clarified on what is the work in these areas besides filling for beam guard? | The excavation common quantities listed in the miscellaneous quantities Earthwork Summary table on Plan Sheet 132 between Station 9+12 - Station 46+50 is associated with spot curb ramp and curb and gutter replacement areas within the station range. The excavation common listed in the miscellaneous quantities Earthwork Summary table on Plan Sheet 132 between Station 147+25 - Station 227+80 is associated with spot curb ramp and curb and gutter replacement areas within the station range, along with the pavement reconstruction areas adjacent to the bridge replacement near the STH 22 and Haskin Drive intersection (Plan Sheet 91). The excavation common quantities (For Information Only; included in bid item 614.0010 Barrier System Grading Shaping Finishing) listed in the miscellaneous quantities MGS Guardrail Summary table on Plan Sheet 135 between Station 76+14.4 - Station 84+33.1 LT (3 CY) and Station 307+83.9 - Station 313+52.6 RT (1 CY) is associated with minor excavation common anticipated near the cross section between Station 83+83.1 - Station 84+08.1 LT and cross section Station 313+77.7 RT. | Jill Fehrman | 7 | 2019-12-04 16:08 | 2019-12-06 14:43
20191210 | 20191210009 | 9 | Fill material under south abutment, channel realignment | Good morning, Under which item is the channel re-alignment to be paid under? It also appears that the south abutment may require fill to be placed under the abutment in order to be raised to proper grade. Can excess materials from excavation/removal of existing structure be used from the project to fill this void, or is this a pay item under "backfill, structure" or "borrow?" | Under which item is the channel re-alignment to be paid under? The re-alignment of the channel will be paid for under Excavation Common. Potential fill under the south abutment: Outside the limits of Structure Backfill Type A, excavated material meeting Standard Specification 207 may be used to backfill the void under the abutment. | Jill Fehrman | 1 | 2019-12-06 09:47 | 2019-12-09 09:46
20191210 | 20191210009 | 9 | Fill material under south abutment, channel realignment | Good morning, Under which item is the channel re-alignment to be paid under? It also appears that the south abutment may require fill to be placed under the abutment in order to be raised to proper grade. Can excess materials from excavation/removal of existing structure be used from the project to fill this void, or is this a pay item under "backfill, structure" or "borrow?" | See answer to Question #1 | Jill Fehrman | 2 | 2019-12-06 09:47 | 2019-12-09 09:46
20191210 | 20191210009 | 9 | Fill material under south abutment, channel realignment | Good morning, Under which item is the channel re-alignment to be paid under? It also appears that the south abutment may require fill to be placed under the abutment in order to be raised to proper grade. Can excess materials from excavation/removal of existing structure be used from the project to fill this void, or is this a pay item under "backfill, structure" or "borrow?" | See answer to Question #1 | Jill Fehrman | 3 | 2019-12-06 09:47 | 2019-12-09 09:47
20191210 | 20191210009 | 9 | Fill material under south abutment, channel realignment | Good morning, Under which item is the channel re-alignment to be paid under? It also appears that the south abutment may require fill to be placed under the abutment in order to be raised to proper grade. Can excess materials from excavation/removal of existing structure be used from the project to fill this void, or is this a pay item under "backfill, structure" or "borrow?" | See answer to Question #1 | Jill Fehrman | 4 | 2019-12-06 09:47 | 2019-12-09 09:46
20191210 | 20191210010 | 10 | Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210010/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2019-11-12 09:42 | 2019-11-14 12:42
20191210 | 20191210010 | 10 | Design CAD Files, Excel Earthwork Sheets and Soils Reports? | Can you provide the Design CAD Files, Excel Earthwork Sheets and Soils Reports? | The Cad Files, Earthwork Sheets, and Soils Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210010/ | Mike Coleman | 2 | 2019-11-19 15:07 | 2019-11-26 08:17
20191210 | 20191210010 | 10 | CAD Files | Can CAD files be made available with existing and proposed surfaces | The Cad Files, Earthwork Sheets, and Soils Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210010/ | Mike Coleman | 3 | 2019-11-20 05:39 | 2019-11-26 08:17
20191210 | 20191210010 | 10 | Staging | Can WisDOT be more specific on what changes to the Staging it will allow? Will WisDOT allow various Stage 2 stages that match up with the various Stage 3 stages? Further clarification would help bidders and sub-bidders be more competitive in their pricing. | Per the contract Special Provisions, any proposed stage changes must be approved by the Engineer. Bid the project per the staging as shown in the contract | Mike Coleman | 4 | 2019-11-26 08:17 | 2019-11-26 09:12
20191210 | 20191210010 | 10 | Staging | Can WisDOT be more specific on what changes to the Staging it will allow? Will WisDOT allow various Stage 2 stages that match up with the various Stage 3 stages? Further clarification would help bidders and sub-bidders be more competitive in their pricing. | Per the contract Special Provisions, any proposed stage changes must be approved by the Engineer. Bid the project per the staging as shown in the contract | Mike Coleman | 5 | 2019-11-26 08:17 | 2019-11-26 09:12
20191210 | 20191210010 | 10 | CAD Files | Can you provide the Subgrade Surface, Select Crushed Surface and Base Course Surface? The information provided currently is only 2D Linework, not surface information. | The subgrade surfaces can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210010/ CTH-H_Prop-Datum: CTH H and STH 11 STH_11_Sidewalk_Prop-Datum: STH 11 and Willow Rd Sidewalk STHE_Stage_1A_Temp-Datum: Stage 1A temp widening STHE_Stage_1C_Temp-Datum: Stage 1C temp widening | Mike Coleman | 6 | 2019-11-26 13:58 | 2019-12-04 06:39
20191210 | 20191210010 | 10 | Design Schedule | The Design Schedule provided only includes stages 1 and 2. Can the Design Schedule with all the stages be provided? | A revised time chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210010/ | Mike Coleman | 7 | 2019-11-29 16:05 | 2019-12-03 10:24
20191210 | 20191210010 | 10 | Cold weather work items. | Can WisDOT add items for cold weather work like there is for asphalt pavement? Historically WisDOT has on occasion included various cold weather protection items for concrete pavement work. Concrete work has been bid with cold weather covering on a number of projects in the past. Given the extremely cold springs and falls we continue to experience, can WisDOT add cold weather work items? This will minimize bid costs in the long run an prevent Contractors from bidding in cold weather costs when they likely will not be needed in future springs and falls. It will also set market driven rates for this work. | Cold weather bid items are not going to be added to the contract. The cost of cold weather concrete work, if required, is incidental to the contract. | Jill Fehrman | 8 | 2019-11-29 16:12 | 2019-12-05 15:57
20191210 | 20191210010 | 10 | Article 3 Wisconsin Inclusion Plan | "All Bidders should submit a Wisconsin Utilization Plan at the time of bid demonstrating how s/he will achieve the inclusion objectives for targeted businesses and workforce participants. The submission should comply with the Wisconsin Utilization Plan." - If this in not submitted at the time of Bid, will your bid be rejected? - What if you don't make the goals, will your bid be rejected? | WisDOT strongly encourages bidders to submit an Inclusion Plan at the time of bid. Submittal of an Inclusion plan is not a condition of award, but will provide desired documentation of the bidderâ€™s outreach to targeted businesses and work force participants. | Mike Coleman | 9 | 2019-12-03 16:56 | 2019-12-04 07:00
20191210 | 20191210010 | 10 | Dowel Basket Assembly locations. | There are an exceptional number of inlets and other features on the project. Is there a jointing plan that can be provided and if not what is the spacing requirement for the joints that will be enforced on this project. |  |  | 10 | 2019-12-08 04:53
20191210 | 20191210011 | 11 | As-built drawings | Can as-built drawings be made available? | Project files, including reports and survey files, can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210011/ | Mike Coleman | 1 | 2019-11-14 14:50 | 2019-11-18 09:13
20191210 | 20191210011 | 11 | As-built drawings | Thank you for the previous response to the submitted question. However, when I go to the provided link and review all the files (regarding bridges that are to be painted on Item #011), structural as-builts are only provided for B-45-32 & 33. There are no structural as-builts for B-45-27, 30, 31, 55, & 56. Can these be provided? | The additional as-built drawings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210011/ | Mike Coleman | 2 | 2019-11-18 12:19 | 2019-11-19 06:14
20191210 | 20191210011 | 11 | Preparation and coating of top flanges | Steel structure B-45-32 is specified to have the deck replaced. Typically when this occurs on a steel structure, preparation and coating of top flanges is required. Is this required for structure B-45-32? Steel structures B-45-27/30/31/55 and 56 are specified to have joint repairs. Is the typical bid item preparation and coating of top flanges required on the steel structures requiring joint repairs? Thank you. | An addendum will be issued to clarify. | Mike Coleman | 3 | 2019-11-20 14:16 | 2019-11-25 09:33
20191210 | 20191210011 | 11 | Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210011/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2019-12-05 05:18 | 2019-12-05 11:30
20191210 | 20191210011 | 11 | Vertical Clearance of Roadways | What is the required vertical clearance of the roadway(s) to remain open during construction for each bridge? | Vertical clearance should match existing and not be reduced on any structure over lanes carrying traffic. | Jill Fehrman | 5 | 2019-12-05 12:34 | 2019-12-06 13:34
20191210 | 20191210011 | 11 | Vertical Clearance for Platform Use | In the past, we have been allowed to install a working solid platform under several structures on several different projects for the state of Wisconsin, as long as a vertical clearance of 14'5' remained. Would the state allow a platform to be installed on this project? | Most of these bridges are over the interstate. Vertical clearance should match existing and not be reduced on any structure over lanes carrying traffic. | Jill Fehrman | 6 | 2019-12-09 10:21 | 2019-12-09 11:59
20191210 | 20191210012 | 12 | Pavement Markings | In looking at pages 77 and 78 of the proposal under the special epoxy SPV items, sealant and grooving is referenced. Can you elaborate on what you are looking for on these markings and the need for sealant and/or grooving to install them? Thank you. | The intent is the same as the standard grooved epoxy bid items per section 646 of the Standard Specifications. | Mike Coleman | 1 | 2019-11-22 09:10 | 2019-11-27 06:57
20191210 | 20191210012 | 12 | Catch basins type 45A | Detail shows 36" diameter, miscellaneous quantities states 4 FT diameter. Which is the correct size catch basin? | The correct size of the Catch Basins Type 45A is 36â€ (3-FT) Diameter. | Mike Coleman | 2 | 2019-11-26 11:08 | 2019-11-26 13:18
20191210 | 20191210013 | 13 | #5 Anchors - Incidental to Removal | Per note 'A26' on sheet 3 of the structure plan, any severely corroded or damaged deck steel that is to be incorporated into the new work is to e replaced with #5 epoxy anchors. This work is incidental to the removal. Why not pay for these with the standard bid item to protect contractor and owner when the quantity required is not known. | Based on current information available to us, there isnâ€™t any indication of severe corrosion of the abutment bars to be preserved. Based on this, we donâ€™t anticipate replacement bars being needed and will leave the notes as stated in the plans. | Mike Coleman | 1 | 2019-12-02 10:18 | 2019-12-03 11:02
20191210 | 20191210013 | 13 | PWL Testing | Is PWL density and mix testing required for project 2310-14-70, the CTH Y improvements? | For ID 2310-14-70, PWL mix testing applies to all tonnage and PWL density applies to the upper layer only. The applicable bid items will be added via an addendum. | Jill Fehrman | 2 | 2019-12-03 09:26 | 2019-12-05 10:48
20191210 | 20191210013 | 13 | Erosion control/ signs | Can you please update the erosion control and signing quantities so that the bid quantities match the misc quantities Silt fence Erosion mat urban 1B 18' wood posts 2x2x14' posts sign supports structural steel HS sign supports conc masonary sign supports steel reinforcement type 2 sign quantities | The designers find no discrepancies between the bid quantities and miscellaneous quantities for the items referenced in the question. Please be sure to reference the Proposal Schedule of Items from Addendum #1, which includes items listed for both project IDs 2310-14-70 and 2310-17-70. | Jill Fehrman | 3 | 2019-12-04 09:49 | 2019-12-04 17:05
20191210 | 20191210013 | 13 | Traffic Control | The special provision for Traffic Control states "Do not park or store equipment, contactor's and personal vehicles or construction materials within the clear zone or on any roadway carrying traffic during working and non-working hours except at locations and periods of time approved by the engineer'. Please clarify the Departments intent of the previous statement. Please define "clear zone". Will equipment and materials be allowed to be stored and parked within the project limits or will the engineer arbitrarily determine the acceptable locations by referring to this special provision and then directing the contractor to remove the equipment and materials? | Standard Specification 104.6 applies. The language will be removed by addendum. | Jill Fehrman | 4 | 2019-12-04 15:10 | 2019-12-05 10:43
20191210 | 20191210014 | 14 | Temporary Structure | I did not see any info regarding the temporary structure relating to: 1)required waterway opening 2)low steel (superstructure) elevation |  |  | 1 | 2019-12-06 09:40
20191210 | 20191210015 | 15 | SP-13 Pier Construction - No Pouring Under Water | SP-13 Pier Construction states "Concrete poured under water will not be allowed." Please either eliminate this wording from the special provisions or provide a design/information on a concrete seal (502.1100 Concrete Masonry Seal) within the cofferdam that would be necessary to construct this project. Not addressing this issue makes the project non-constructable and puts unnecessary risk on the contractor. SP-14 Abutment Construction states something similar. | The existing soils at the bottom of proposed excavations are predominantly clay based on the subsurface investigation. The existing clay soils should adequately seal the bottom of the cofferdams and not require a concrete seal to dewater. Concrete poured under water is not allowed. The Subsurface investigation can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210015/ | Mike Coleman | 1 | 2019-12-02 10:47 | 2019-12-03 12:23
20191210 | 20191210015 | 15 | SP-3 Prosection and Progress - Interim LD's | SP-3 states that installing/removing a cofferdam & removing existing piers needs to be complete by 3/30/2020. This is a lot of work to be completed in this timeframe (knowing the likely start date of a project like this that bids in December), especially considering that it would make sense from a cost & time standpoint to also construct the new piers which includes driving piling, a cofferdam seal and construction of 2 large wall piers. Please address this issue by either eliminating the interim LD's, allowing for more than a 65 WD contract and/or allowing the cofferdam and work within to continue after 3/30/2020 with the cofferdams not removed until after the 6/1/2020 no in-stream period. Not addressing this issue puts unnecessary risk on the contractor and adds significant costs to the project/department. | Please see Addenda No.1 posted on 12/5/2019. | Jill Fehrman | 2 | 2019-12-02 11:10 | 2019-12-06 13:05
20191210 | 20191210015 | 15 | 404 Permit | Please provide a copy of the 404 permit for this project for contractor review. | This project falls under Category 2: Modification â€“ Linear Transportation of the Transportation Regional General Permit. | Jill Fehrman | 3 | 2019-12-05 13:22 | 2019-12-06 11:28
20191210 | 20191210017 | 17 | Soils Report | Can you post a copy of the soils report and borings for this proposal? | The soil report and borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210017/ | Mike Coleman | 1 | 2019-11-11 12:55 | 2019-11-11 13:55
20191210 | 20191210017 | 17 | SPV 0060.47 Conect to existing Water Main | Under measurement it say " including all fittings required" where under Special provision item 12 says that all ductile iron fittings are to be provided by MPU. Which statement is correct? | An addendum will be issued stating that MPU will provide all ductile iron fittings. | Mike Coleman | 2 | 2019-11-20 08:40 | 2019-11-26 11:08
20191210 | 20191210017 | 17 | SPV 0060.53 reconnect Sanitary Lateral | Under materials it says that the contractor is to supply Schedule 40, PVC pipe conforming to ASTM D3034. I believe that being schedule 40 and ASTM D 3034 are two different specifications and that it is impossible to satisfy both at the same time. Please advise. | An addendum will be issued to address the correct ASTM specification. | Mike Coleman | 3 | 2019-11-20 08:45 | 2019-11-20 13:23
20191210 | 20191210017 | 17 | water main ( general) article 116 of the specifications | B.2 says Provide bedding and Backfill conforming to standard spec 209.2. My question why is this statement here? There is an item for watermain backfill if the existing trench excavation is unacceptable. Payment further says for " for furnishing ALL materials not provided by MPU". Trying to clarify what this is all telling us. Please advise. | This will be clarified in an upcoming addendum. | Mike Coleman | 4 | 2019-11-20 08:51 | 2019-11-20 15:41
20191210 | 20191210017 | 17 | Imported Water Main and Sanitary Backfill | Since both of these items are being paid by the Cubic Yard how is this going to be measured? Truck measure or some other means, there is nothing in the special provisions to offer nay insite and we can find no detail in the plans. Please advise. | An upcoming addendum will clarify the means of measurement. | Mike Coleman | 5 | 2019-11-20 08:59 | 2019-11-20 15:45
20191210 | 20191210017 | 17 | Imported Backfill for Water Main and Sanitary Sewer | Can the use of materials meeting 608.2.2.3 be added as a permissible material? | An addendum will be issued to clarify the acceptable backfill material. We are planning to submit the addendum for this question and the others on December 2. | Mike Coleman | 6 | 2019-11-21 07:25 | 2019-11-26 11:09
20191210 | 20191210017 | 17 | SPV 0060.51 Remove Sanitary Manhole | Special provisions under materials list granular backfill. The measurement section says per each completed. I would assume any granular backfill required would be paid under the imported trench backfill item. Would this assumption be correct? | Granular backfill is part of the item of Remove Sanitary Manhole and is not paid separately. In the Payment section of the specification it lists â€œfurnishing and placing granular backfillâ€. | Mike Coleman | 7 | 2019-11-21 07:41 | 2019-11-21 12:05
20191210 | 20191210017 | 17 | Utility Clarifications | Please confirm that the existing power lines and fiber optic over B-36-232 are to remain in their current location through the entire project. Also, there are no utility notes regarding the existing overhead lines underneath B-36-29. Are these lines active and will they remain in their current location through the entire project? | The existing overhead lines over B-36-232 will remain. MPU will be making temporary accommodations to relocate the power pole at station 70+35 lt. This will be addressed in a future addendum. The existing overhead lines along the railroad are not active. Contractors are to follow standard spec 107.17. This will be added in a future addendum. | Jill Fehrman | 8 | 2019-11-25 14:48 | 2019-12-04 14:36
20191210 | 20191210017 | 17 | Water & Sanitary backfill placed in 2019 | How much imported backfill was used for water & Sanitary construction during the 2019 construction of Waldo Blvd? | Approximately 15,000 tons was used during 2019 construction. | Jill Fehrman | 9 | 2019-12-02 12:47 | 2019-12-02 12:50
20191210 | 20191210017 | 17 | Traffic Control / Pedestrian Accomodations | What are some of the new changes to traffic control/pedestrian accommodations? | In addition to other changes: Temporary Curb ramp units have gone from EACH to DAY, Prefabricated curb ramps need to be from WisDOT's APL, Temporary Pedestrian Barricades need to be from WisDOT's APL. Please check Standard Detail Drawings and Standard Specifications 2020 edition. | Jill Fehrman | 10 | 2019-12-02 12:49 | 2019-12-02 12:54
20191210 | 20191210017 | 17 | Steel Casings | The specifications for the casing call for a 0.625 " wall thickness. Per CN (website)it appears that is the minimum wall thickness for a 42" Dai. Casing that is not coated. The minimum thickness listed for a 20" Dia. Steel casing that is uncoated is 0.344 inches Please advise. | Casing thickness was designed to carry load at a shallow depth of bury. Please bid as shown. | Jill Fehrman | 11 | 2019-12-05 09:33 | 2019-12-05 11:11
20191210 | 20191210017 | 17 | Imported trench backfill | Per the Sewer and water specifications it says the trench width for payment is defined as the OD of the Pipe plus 24". There does not appear to be any allowance for wall thickness of any trench boxes used. Also because of the type of soils present on this project there will be slumping of trench sidewalls that will occur even with the use of a trench box. Will this additional trench width backfill be measured and paid for, or is all of this overage beyond the defined OD + 24" going to be considered incidental to the theoretical Cubic yards. We need to know this because this overage would greatly affect the bid price. | Bid as shown for the method of measurement in the addendum for imported trench backfill. | Jill Fehrman | 12 | 2019-12-05 09:54 | 2019-12-05 17:50
20191210 | 20191210017 | 17 | Imported trench backfill | When constructing the Sanitary sewer and the water laterals, some locations will have both pipes in the same trench. How would the trench width be computed under this scenario since there would be two pipes and a minimum separation between pipes required? | Trench width will be computed in the same manner as listed in the special provisions (addendum) for imported trench backfill. If two utilities are located within the same lateral limits any overlap of trench backfill area will only be paid for once. | Jill Fehrman | 13 | 2019-12-05 10:02 | 2019-12-05 16:08
20191210 | 20191210018 | 18 | 404 Permit | Can we get a copy of the 404 permit? | A determination was made late in the design that this project falls under the no-PCN (no preconstruction notification) criteria for the transportation general permit so no project specific permit was required or obtained but the language in the specials was not updated to reflect this. | Mike Coleman | 1 | 2019-11-25 06:19 | 2019-11-25 06:20
20191210 | 20191210018 | 18 | Typical Finished Section HMA Surface Note | The typical finished sections include a note calling for 2" upper layer with 19 mm nominal aggregate size. I am assuming this note is a mistake and that it should say 12.5 mm aggregate size? | It should say 12.5 mm for the surface layer. An addendum will be issued to correct this. | Mike Coleman | 2 | 2019-11-27 09:53 | 2019-12-03 10:48
20191210 | 20191210019 | 19 | Soils Report | Is there a soils report available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210019/ | Mike Coleman | 1 | 2019-12-05 09:34 | 2019-12-06 06:17
20191210 | 20191210019 | 19 | EBS | Typical Sections for Stations 24+12.88-31+50 has a note stating 0-10" existing base aggregate dense to remain. How can existing base remain, if these areas are designated for EBS. Does this mean that base is to be salvaged? Another note for the same stations states "EBS area to be backfilled with material acceptable to the Engineer. Backfill must be homogeneous with adjoining fill material. There is also item 208.1100 Select Borrow for backfilling the EBS. Which one is to be used? | Most of the existing base aggregate dense in the EBS area will be pulverized with the asphalt and salvaged as stated in Article 12 - Pulverize and Relay of the special provision. â€œPulverize the existing asphalt and base prior to completing culvert replacements and excavation below subgrade. Salvage the pulverized material and install above backfill material. Salvaging and relaying the pulverized material will be incidental to Pulverize and Relay.â€ Additional virgin base aggregate dense is included in the miscellaneous quantities for the few remaining inches of base aggregate dense that is not pulverized and will be lost as part of the EBS operation. Select borrow will be used to backfill the EBS area. | Jill Fehrman | 2 | 2019-12-06 08:26 | 2019-12-06 15:23
20191210 | 20191210019 | 19 | Select Borrow | What are the quality requirements for Select Borrow? Don't see them specified in a contract? |  |  | 3 | 2019-12-09 08:33
20191210 | 20191210020 | 20 | Temporary Bypass | Plan calls for constructing a Temporary Bypass road to the west of North 5th Street. Currently area of the bypass is under water. Will any additional Bid Items be provided to address dewatering needs for bypass construction? | The water elevation varies quite a bit at this site and in checking with the town chairman, the water levels are currently high. No additional bid items will be added for dewatering for the temporary bypass construction. | Mike Coleman | 1 | 2019-11-25 17:05 | 2019-12-03 10:50
20191210 | 20191210020 | 20 | High Water / Differing Site Condistion | Regarding the question about the current high water levels, WisDOT provided the answer below. Our question now is, "If the high water levels remain during construction, will that be considered a differing site condition as defined in the standard specs?" The water elevation varies quite a bit at this site and in checking with the town chairman, the water levels are currently high. No additional bid items will be added for dewatering for the temporary bypass construction. Original Question: Temporary Bypass Plan calls for constructing a Temporary Bypass road to the west of North 5th Street. Currently area of the bypass is under water. Will any additional Bid Items be provided to address dewatering needs for bypass construction? | Addenda No. 1 was issued providing breaker run material to be utilized for the construction of the bypass road under the current high water condition. | Jill Fehrman | 2 | 2019-12-03 11:18 | 2019-12-09 09:41
20191210 | 20191210021 | 21 | Earthwork Summary Footnotes Missing | Can you provide the footnotes for the earthwork chart on sheet no. 8? | An addendum will be posted updating sheet 8 of the plan to include the footnotes for the earthwork summary table. | Mike Coleman | 1 | 2019-11-26 07:46 | 2019-11-27 15:20
20191210 | 20191210021 | 21 | Geotechnical Report | Can you post a copy of the Geotechnical Report for this project? | The Geotechnical Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210021/ | Mike Coleman | 2 | 2019-12-02 08:43 | 2019-12-02 08:47
20191210 | 20191210022 | 22 | Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210022/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2019-12-05 06:36 | 2019-12-05 11:21
20191210 | 20191210022 | 22 | Project Staging | Can Stage II be performed prior to Stage I? | Because of the condition of the existing median shoulder, Stage 2 cannot occur first. The existing median shoulder has settled, and constructing Stage 1 first improves the existing median shoulder condition for traffic use in Stage 2. | Jill Fehrman | 2 | 2019-12-06 10:47 | 2019-12-06 15:20
20191210 | 20191210023 | 23 | Pipe Transition Cut Backfill | For the pipe transition backfill it states to be backfilled with Foundation or Trench backfill. Will the backfill be a pay item? | The construction detail for the Culvert Pipe Transition indicates "Backfill the transition cut areas with foundation and trench backfill as specified in standard Spec 520." Per Specification 520 everything that is inside the trench width is incidental to the culvert pipe. | Jill Fehrman | 1 | 2019-12-04 11:06 | 2019-12-05 10:36
20191210 | 20191210023 | 23 | Transition cut | The question IS will the backfill in the TRANSITION CUT AREA BE A PAY ITEM? NOT THE PIPE TRENCH AREA! | Backfilling of the Transition Cut will not be a separate pay item. The contractor may backfill the Transition Cut with excavated material that meets Standard Specification 520.2.5.3. | Jill Fehrman | 2 | 2019-12-06 07:14 | 2019-12-09 09:17
20191210 | 20191210024 | 24 | Geotech Report | Is there a geotech report that the Department can provide? | The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210024/ | Mike Coleman | 1 | 2019-11-25 13:22 | 2019-11-25 16:39
20191210 | 20191210024 | 24 | Temporary Bridge Restrictions | The only information that I see for the temporary bridge parameters is that it is to provide 16' clear roadway width and a minimum hydraulic area of 525 sf. Are there any restrictions to placing piers in the stream to make a multiple span structure? Do the abutments need to be outside the streambanks? An estimated clear span length of 112' is shown, is this required or does the minimum hydraulic area control the length? | The 112â€™ foot clear length was set based on the width of Pine River at the temporary bridge location. Based on the DNRâ€™s final review of the project during the 401 Water Quality Certification process, this clear length between the abutments is required. There are no restrictions (besides timing of construction due to instream work restrictions) regarding temporary piers in the stream. For the hydraulic analysis of the temporary structure, a 3-span structure was assumed. | Mike Coleman | 2 | 2019-12-03 09:42 | 2019-12-04 06:41
20191210 | 20191210024 | 24 | Structural Approach Concrete Quantity | Please verify concrete plan quantities for structural approaches: - Footings: 40'x5'x1'6"= 11.11 cy - Approach: 42'7-1/2"x1'4"x20'= 42.10 cy - Total per side: 11.11 cy + 42.10 cy = 53.21 cy - Plan qty: 60 cy, difference is 6.8 cy per side, 13.6 cy for project. | The quantity for the approach slab concrete was calculated as follows: Footings: [(42.625â€™ x 5â€™ x 1.5â€™)-(1.5â€™ x 1.3125â€™ x 1.5â€™ x 2)] /27 = 11.62 CY Approach Slab: (42.625â€™ x 20â€™ x 1.33â€™) / 27 = 41.99 CY 42SS Parapet on Approach Slab: (2 x 20â€™ x 3.75 SF) / 27 = 5.56 CY Total Per Side: 11.62 CY + 41.99 CY + 5.56 CY = 59.17 CY (~60 CY) | Mike Coleman | 3 | 2019-12-03 10:26 | 2019-12-04 06:46
20191210 | 20191210024 | 24 | Question Bid Item #0172 Geotextile Fabric Type SR | I sent the spec to Mirafi and they are having trouble matching the spec. Would the Mirafi HP370 work? Is there a particular brand name and fabric number you were thinking? This would let me find an equal. |  |  | 4 | 2019-12-05 15:37
20191210 | 20191210025 | 25 | Soil Borings | Are soil borings available for this project? | Soil borings were not completed for this project. No soil borings are available for this project. | Mike Coleman | 1 | 2019-11-18 09:13 | 2019-11-18 12:07
20191210 | 20191210026 | 26 | Sealing Asphaltic Pavement Cracks | What is the minimum size of crack that will need to be filled? | Any crack 1/4-inch or less does not need to be filled due to the scrub or chip seal being placed after crack filling. All cracks over 1/4-inch will need to be filled according SPV.0125.01 Sealing Asphaltic Pavement Cracks specification. | Mike Coleman | 1 | 2019-12-03 06:50 | 2019-12-03 06:50
20191210 | 20191210027 | 27 | HTCB Post Spacing | With moving to a 10 ft offset at the locations of existing bullnose guardrails, it appears there will be a minimum of 10 ft separation between the two rail systems. Will reduced post spacing for the HTCB be needed at any bullnose locations or will the HTCB manufacturer's working width govern that requirement? | The Special Provisions for Cable Barrier Type 1, Item 613.1100.S; Cable Barrier End Terminal Type 1 Item 613.1200.S under Construction state, â€œCertify that the installation was done according to manufacturerâ€™s recommendations and the plan requirements.â€ Construction Detail â€œCable Barrier at Existing Bullnose Median Piersâ€ shows that there is a maximum of 10-ft post spacing required in such an occurrence. | Mike Coleman | 1 | 2019-11-19 07:45 | 2019-11-25 06:18
20191210 | 20191210027 | 27 | Plate Beam Guardrail | Will MGS rail be required for the installation or Class A? It appears Class A is what is currently at this location. Also, who gets the salvaged materials? | Class A will be added to the contract. Clark County will get the salvaged materials. An addendum will be issued to add. | Mike Coleman | 2 | 2019-11-19 08:21 | 2019-11-25 06:14
20191210 | 20191210027 | 27 | USH 53 HTCB | A small portion of this run of HTCB extends into Eau Claire County. Given that the majority of the stretch is in Chippewa County, should this run be installed based on Chippewa Counties Approved HTCB systems? | Due to the majority of this segment of median cable barrier being installed within Chippewa County, Chippewa County has agreed to maintain this entire run on USH 53 near Melby Street; including the short stretch extending into Eau Claire County. Therefore, this specific run of cable barrier on USH 53 may be installed based on the approved HTCB systems for Chippewa County as listed in the County Specific System table on the General Notes sheet. With that being said, it is worth noting that the County Specific System table does show a HTCB system approved for both Chippewa & Eau Claire Counties (Nucor/Marion TL-4 [4 cables]). | Mike Coleman | 3 | 2019-12-02 07:54 | 2019-12-03 10:52
20191210 | 20191210028 | 28 | Soil Borings | Are soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210028/ | Mike Coleman | 1 | 2019-11-18 09:13 | 2019-11-18 12:16
20191210 | 20191210028 | 28 | Monotube Traffic Signals | If the contractor orders the Monotubes immediately after the bid is awarded and the Monotubes still do not arrive in time will the DOT work with the contractor even though the spec says no additional time is granted? This is an ongoing issue with every project and with limited suppliers that ship when they want, it seems that maybe the DOT should pre-order the Monotubes. | WisDOT will not allow additional contract time for delays in the delivery of monotubes. | Mike Coleman | 2 | 2019-12-03 09:12 | 2019-12-03 13:51
20191210 | 20191210028 | 28 | MS specification | Will an addendum be issued with the specs for the MS fabric? | The addendum was issued today 12/5/2019. | Jill Fehrman | 3 | 2019-12-05 16:39 | 2019-12-05 17:32
20191210 | 20191210029 | 29 | As-built darwings | Can as-built drawings be made available? | The as-builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210029/ | Mike Coleman | 1 | 2019-11-14 14:52 | 2019-11-18 10:55
20191210 | 20191210029 | 29 | Removing Old Structure Station 185+14.20 | Is this bid item for the removal of the existing expansion joints? | The â€˜Removal of Old Structureâ€™ item is intended to cover all the miscellaneous removals required. The â€˜Joint Repairâ€™ item covers the removal of the existing joint. The â€˜Removing Bearingsâ€™ item covers removal of the existing bearings. However, there may be some other miscellaneous removals that may be required, so the item was added as a â€˜catch allâ€™ of all remaining removals required. | Mike Coleman | 2 | 2019-11-25 11:15 | 2019-11-25 16:33
20191210 | 20191210029 | 29 | Epoxy Sealer for bridge deck Overhang | Is there a specific product you had in mind for the epoxy sealer used on the underside of the bridge over hang? I have contacted both Sika and TK products and both say they have something close but cannot meet the requirements of the special provisions. There is nothing on the pre-approved products list that matches. Any suggestions would be helpful. | The product needs to needs to meet requirements of the special provisions. Sherwin Williams Protective & Marine Coatings, Macropoxy ® 646 Fast Cure Epoxy was used on one of the past projects. | Jill Fehrman | 3 | 2019-11-26 15:22 | 2019-12-05 16:39
20191210 | 20191210029 | 29 | Manhole Adjustment | Special provisions state the adjustment to happen when the contract milling and paving operation permits setting the frame to grade. Since both layers of pavement are to be installed before traffic is placed on the lane. Is the intent to raise the manhole after the final surface? If after, what material shall be used for patching? With SMA as the upper layer, it is not feasible to patch manholes with SMA. Therefore if the manholes are not be adjusted after surface, which is desirable, the patching should be concrete. | An addendum will be issued that will revise article # 47 â€œAdjusting Manhole Coversâ€ to patch with concrete. | Mike Coleman | 4 | 2019-12-02 08:49 | 2019-12-04 06:43
20191210 | 20191210029 | 29 | QMP HMA Density | Confirming DOT will be performing QMP HMA Density testing as there is no QMP HMA special provision. | An addendum will be issued to add QMP HMA Pavement Nuclear Density. | Mike Coleman | 5 | 2019-12-02 08:52 | 2019-12-04 06:44
20191210 | 20191210029 | 29 | IRI Ride | There is no item for IRI Ride incentive. Per specifications contractor is required to perform IRI. | An addendum will be issued to add Incentive IRI Ride, Item 740.0440 | Mike Coleman | 6 | 2019-12-02 08:53 | 2019-12-04 06:45
20191210 | 20191210029 | 29 | Polymer Overlay | With the Polymer Overlay specified as Brown in color, we find there is not a Brown Colored aggregate available with the required WISDOT testing as in the specs. Being this is a sidewalk, can the aggregate spec be modified, or can the brown color be omitted? | The color will be removed by Addenda 2. | Jill Fehrman | 7 | 2019-12-02 11:20 | 2019-12-05 16:47
20191210 | 20191210029 | 29 | Railroad Flagger | Will a Railroad Flagger be required during the painting operation? or just during the erecting of the staging? | Flagging requirements are dependent on the contractor means and methods. Please review Article 10 of the Contract Proposal. | Mike Coleman | 8 | 2019-12-05 14:20 | 2019-12-06 06:33
20191210 | 20191210029 | 29 | Centerline joint repair | The plans show a detail for centerline repair but the bidding documents do not have an item for them. Are there going to be any centerline joint repairs? | We do not anticipate centerline joint repairs. They centerline joints should be adequately addressed with the adjacent planned concrete panel repairs. | Jill Fehrman | 9 | 2019-12-05 14:25 | 2019-12-06 15:09
20191210 | 20191210029 | 29 | Preparation and Coating of Top Flanges | Pay Line Number 110 Preparation and Coating of Top Flanges. Usually this item is needed to coat the top flanges of beams on bridge deck replacement jobs. On this contract the deck remains and gets an overlay. Please identify the quantity and location this work item will be needed, if any. |  |  | 10 | 2019-12-07 14:59
20191210 | 20191210029 | 29 | Blasting, Cleaning and Painting when winds exceed 15 MPH. | Proposal Page 47, Section 37 C.1 States "Do Not Perform Blasting, Cleaning and Painting on days of high Winds. Prevailing Winds in excess of 15 MPH shall be considered High Winds." In this part of Wisconsin, we experienced conflict with one consultant that directed us to shut down production when wind speeds peaked at 15 MPH. Specifically between 4:00 pm and 5:00 pm weekdays and always on weekends. Our required Negative Pressure containment is designed to work in wind speeds in excess of 15 MPH. In all other parts of Wisconsin and with all other consultants and state inspectors, we have been allowed to blast, clean and paint when winds speed are in excess of 15 MPH as long as our negative pressure containment was working properly with zero emissions. This job is located in Superior and the average wind speed are at or over 15 MPH. With that said, can the blasting, cleaning and painting operations continue when wind speeds exceed 15 MPH within the Negative Pressure Containment? |  |  | 11 | 2019-12-07 16:16
20191210 | 20191210030 | 30 | Soil Borings | Are soil borings available for this project? | The soils report with marsh probes can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210030/ | Mike Coleman | 1 | 2019-11-18 09:14 | 2019-11-19 12:55
20191210 | 20191210031 | 31 | SP 19 Culvert Pipe | Will pipe ties be required on culvert pipe in marsh areas (as in ALL Joints Tied) or will the standard 3 joints tied suffice? Also, does SP19 infer that the contractor is to saw cut joint ties that protrude? On small culvert pipe that may be difficult. | Pipe ties will be required on every RCCP pipe at every joint. (This is the Mellen hill country. Very flashy streams, with steep gradients that can develop low and high pressures in conduits.) Article 19 of the special provisions is clear that joint ties will not be allowed to protrude past the nut inside the pipe and the nut must be tight to the pipe wall. | Mike Coleman | 1 | 2019-11-15 08:55 | 2019-11-18 12:05
20191210 | 20191210031 | 31 | Soil Borings | Are soil borings available for this project? | The soil borings and logs can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210031/ Additional pavement core information has been added - 11/20/2019 | Mike Coleman | 2 | 2019-11-18 09:14 | 2019-11-19 12:46
20191210 | 20191210031 | 31 | Select Borrow | What are the specifications for the select borrow item? | The item of Select Borrow shall conform to the Grade 2 specifications of Section 209 for Granular Backfill. | Mike Coleman | 3 | 2019-12-02 09:33 | 2019-12-03 10:35
20191210 | 20191210031 | 31 | Slope Paving Repair Crushed Aggregate | The unit of measure for the item Slope Paving Repair Crushed Aggregate is shown as CY in the proposal but is shown as SY in the Estimate of Quantities in the structure plans. Which is correct? | The units should have shown CY and the quantity 5 CY. An addendum will be issued to clarify. | Mike Coleman | 4 | 2019-12-02 14:50 | 2019-12-03 11:17
20191210 | 20191210032 | 32 | Soil Borings | Are soil borings available for this project? | Soil borings are not available for this project. | Mike Coleman | 1 | 2019-11-18 09:15 | 2019-11-19 06:18
20191210 | 20191210033 | 33 | Soil Borings | Are soil borings available for this project? | Soil borings are not available for this project. | Mike Coleman | 1 | 2019-11-18 09:15 | 2019-11-19 06:19
20191210 | 20191210034 | 34 | Soil Borings | Are soil borings available for this project? | Soil boring information is provided on sheet 91 of the plans (sheet 3 of 18 in the structure plans). | Mike Coleman | 1 | 2019-11-18 09:15 | 2019-11-19 06:15
20191210 | 20191210034 | 34 | 4MT 58-34S | There are 330 ton on this project. Bid item is 4MT 58-34S which implies the QMP HMA and Density are required per section 460. Was the intent to have QMP on such a small quantity? If so there is no QMP Density in the special provisions which would require the department to complete the density testing. Would an Asphaltic Surface Special item fit this project better? | Per FDM 19-21-2.1.2 QMP HMA Mixture, the QMP provision is included in standard spec 460. Bid item 460.2000 Incentive Density HMA Pavement is already included in the contract and covered under standard spec 460. (Per the STSP Index, QMP HMA Pavement Nuclear Density is only used on project with 10,000 tons or greater.) | Mike Coleman | 2 | 2019-11-27 15:09 | 2019-12-03 10:26
20191210 | 20191210037 | 37 | Soil Boings | Are soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210037/ | Mike Coleman | 1 | 2019-11-18 09:16 | 2019-11-18 12:19
20191210 | 20191210037 | 37 | EBS for wall R-27-01 | Sheet 95 includes the following note, "Soil to be completely removed and replaced, incidental to bid item wall concrete panel mechanically stabilized earth". We need elevations and a plan view of the removal area in order to calculate this quantity. What kind of material is required to replace the material that is removed? | The extents of the removal area are anticipated to be as follows: â€¢ Lower limits: Top of rock elevation (assumed to be 762â€™ +/-). â€¢ Upper limits: Bottom of wall elevations as shown on the plans. â€¢ Front of wall: Excavation at 3:1 in front of Segment B. â€¢ Front of wall: Excavation at 1:1 in front of Segments A & C. â€¢ Back of wall: Extent of MSE reinforced zone as defined by wall designer. The material removed below the MSE soil material shown on sheet 95 of the plans shall be replaced by material meeting structure backfill (standard spec bid item 210.1500). | Jill Fehrman | 2 | 2019-12-05 08:33 | 2019-12-05 16:10
20191210 | 20191210037 | 37 | CAD Files | Can you please release the cad files for this project? Thank you. | The Cad files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210037/ | Jill Fehrman | 3 | 2019-12-05 11:58 | 2019-12-06 14:30
20191210 | 20191210037 | 37 | B-27-0170 | Would WIDOT consider a reinforced concrete box culvert as an alternate to the proposed bridge structure B-27-0170? It seems that it would be more cost effective and would impact traffic for a reduced amount of time in comparison to the bridge structure. | Please bid the project as detailed. | Jill Fehrman | 4 | 2019-12-05 12:02 | 2019-12-06 11:22
20191210 | 20191210037 | 37 | Fixed Ladder, B-27-170, Item SPV.0060.01 | Is there an approved fabricator list for ladders? | No, there is not an approved fabricator list for ladders. Any of the fabricators listed on the WisDOT â€œFabricated Bridge Component- Railingâ€ list would be allowed to fabricate the ladder for this project. | Mike Coleman | 5 | 2019-12-06 06:37 | 2019-12-06 06:38
20191210 | 20191210040 | 40 | Tack Coat | From our take-off it appears the tack coat quantity is understated, you may want to take a look at that item. | An addendum will be issued to increase the quantity of tack. | Mike Coleman | 1 | 2019-11-20 16:35 | 2019-11-21 11:55
20191210 | 20191210040 | 40 | Adjusting Manhole Covers | The plan calls for temporary cover plates and adjusting manholes. Confirming the intention is to remove the existing manhole casting and place a cover plate, temporary patch with hot mix, mill and overlay the road then raise the manhole to match existing surface grade. With that process does the department want hot mix asphalt or concrete to finish the pavement around the adjusted manhole casting? | HMA. | Mike Coleman | 2 | 2019-11-20 16:41 | 2019-11-21 12:00
20191210 | 20191210041 | 41 | Soil Borings | Are soil borings available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20191210041/ | Mike Coleman | 1 | 2019-11-18 09:16 | 2019-11-18 12:16
20191210 | 20191210041 | 41 | Temporary Bypass | For the temporary bypass, the asphalt pavement is specified to be 3MT, which would include full QMP HMA and Density. Would the department consider changing this pavement to Asphaltic Surface Temporary. | The pavement will be changed to Asphaltic Surface. See Addenda No. 1 posted 12/5/2019. | Jill Fehrman | 2 | 2019-12-02 08:58 | 2019-12-06 12:59
20191210 | 20191210042 | 42 | Pavement Type | In the general notes it is stated: 4.5" Asphaltic Surface shall be constructed in two 2.25" Layers using 19.0 mm Nominal Aggregate Size. Is this correct? | Yes, both layers are 19.0 mm nominal aggregate size. | Mike Coleman | 1 | 2019-11-27 15:05 | 2019-12-03 11:00