## qandasearchletting_results
Date: | 2020-05-11
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200512 | 20200512005 | 5 | Turbidity Barrier | Due to the depth of the water, Q2 EL and flow rate will Floating Alternate barrier be allowed? Length of posts required could be in excess of 20 ft |  |  | 1 | 2020-05-08 09:25
20200512 | 20200512007 | 7 | Common Excavation - page 62 on plans | In column 3, salvaged/unusable pavement material, the quantities for STH 60 of 2609 CY (stage 1) and 2767 CY (stage 2) most closely match our calculations of both pavement and base aggregate layers and not just pavement, which we are most used to seeing. Please clarify if column 3 numbers display pavement or pavement + base aggregate layers and double check quantities. | An addendum is being issued to clarify. | Mike Coleman | 1 | 2020-04-17 14:09 | 2020-04-21 08:19
20200512 | 20200512008 | 8 | Wind Load Provisions in special provisions | According to bid item 531.0300.S.0001, the design shall conform to the current edition of AASHTO LRFD (which is edition 8). The wind load provisions in AASHTO LRFD edition 8 do not correspond to the wind pressure shown within the STSP language. Please clarify what wind pressure should be used in the design of noise wall N-40-93. | The minimum design wind pressure shall be 35 psf (Strength III) for ground mounted noise barriers and 40 psf (Strength III) for structure mounted noise barriers. For ground and structure mounted noise barriers, the minimum Service I design wind pressure shall be 15 psf. All wind loads shall be applied perpendicular to the barrier, alternately in each direction. An addendum will be issued to correct the special provision. | Mike Coleman | 1 | 2020-04-30 06:36 | 2020-04-30 06:36
20200512 | 20200512008 | 8 | Noisewall Post Concrete Aggregate Concrete | In the past we have encountered difficulty getting concrete mix designs approved that consist of coarse aggregate of size no. 1 only instead of size no. 1 & 2. In standard spec section 501.2.5.4.5: (4) The contractor may provide coarse aggregate consisting entirely of size No. 1 as follows: 6. For concrete in foundations for soldier pile walls and noise walls. Based on this excerpt from the standard specifications can it be assumed that the use of a concrete with coarse aggregate consisting of size no. 1 only would be acceptable for this project? | The contractor may use the option of providing coarse aggregate consisting entirely of size No. 1 as long as all other requirements of the spec are met. | Mike Coleman | 2 | 2020-05-06 12:45 | 2020-05-07 12:10
20200512 | 20200512009 | 9 | Bearing Replacements B-40-46 and B-40-47 | In review of the plans and an onsite inspection the area of the superstructure above the bearings is in terrible shape. The area was sounded and in review the plans and the existing structure the area over the abutments should not be jacked because it would put the integrity of the structure in danger as well as potential impact to the travelling public. There is not discussion in the plans on the structural integrity of the bridge. How did the DOT plan on the bridge being raised to replace bearings. Keep in mind that at each abutment the bridge would have to be jacked and left high for several days if not longer. | There was some spalling evident but it did not appear to be extensive at the bearings. Please note, this is a voided slab bridge but it is solid over the abutments. If the bridge was sounded away from the abutment, then I believe the voided areas would give off the sound of delaminated concrete. In our opinion, since the bridge is able to sufficiently carry loads to the existing bearings it should be able to carry loads to be jacked. The design, maintenance and construction team met in the field to discuss this issue further. The consensus is, that although there are areas of spalled or delaminated concrete under the deck at the abutment, the deck itself is still structurally sound and there are methods available (distributing the load the jack puts on the deck. . .) to safely lift the deck. There was also some confusion as to why the deck would need to be raised for several days. The assumptions the design team made were that the deck would not be jacked all at once and instead be done in stages, overnight with lane closures above. It was also assumed the deck would only need to be raised just enough to take the load off the bearing. To account for staging restrictions and to reduce the time the structure needs to be raised, the design calls for replacing the bearings with precast bearing blocks and elastomeric bearings. | Mike Coleman | 1 | 2020-04-27 13:23 | 2020-04-28 11:27
20200512 | 20200512010 | 10 | Soil Borings | Please provide soil borings for the project. These are especially needed for the trenchless pipe installation. | The geotechnical reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512010/ The boring logs for the both the retaining wall and the bridge are included, with northing/easting coordinates for location. We would recommend contractors to review the boring logs associated with R-40-622. (There are some maps/diagrams in the report, but they are more bridge focused.) | Mike Coleman | 1 | 2020-04-28 07:09 | 2020-05-07 14:31
20200512 | 20200512010 | 10 | Trench Backfill Material | Trench backfill material does not appear to be clearly defined in the plans and special provisions, along with numerous references to slurry backfill in the special provisions. Is it the Department's intent to use slurry backfill for all trenches? | For Article 32. Steel Casing w/ Sanitary Sewer 20-Inch PVC Carrier, Item SPV.0090.5010, since both of the bore bit excavations fall under existing pavement, the backfill shall be granular backfill material meeting the standards in the SSSW (Standard Specification for Sewer and Water Construction in Wisconsin, latest edition). For Article 33. Sanitary Sewer 15-Inch PVC, Item SPV.0090.5011, Sanitary Sewer 20-Inch PVC, Item SPV.0090.5012, Sanitary Sewer 21-Inch PVC, Item SPV.0090.5013, the trench backfill under existing pavement areas shall be granular backfill material meeting the standards in the SSSW, and the trench backfill under non-pavement areas can be spoil backfill material meeting the standards in the SSSW. | Mike Coleman | 2 | 2020-04-28 08:42 | 2020-05-04 07:12
20200512 | 20200512010 | 10 | Bypass Pumping | Sanitary sewer bypass pumping is incidental to the respective pipe/manhole items. Please provide the sewage flow rate in the existing sewers so appropriate systems can be designed and priced. | The flow rates can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512010/ The capacity of the 21-Inch MIS from manhole 08715 to 08712 is 14.5 cfs. | Mike Coleman | 3 | 2020-04-28 08:55 | 2020-05-04 08:04
20200512 | 20200512011 | 11 | Temporary Pavement Markings | Good morning. In looking at the temporary pavement marking bid item, this project has temporary marking line-paint that is, per page 4 of 20 in the proposal, to be placed same day in the exact configuration as permanent markings are placed. This project does not have any grooved in permanent markings so, with that being said, should the temporary markings be changed to same day epoxy rather than temporary paint seeing as epoxy cannot be placed over temporary paint or should the permanent markings be switched to grooved in markings either wet reflective, tape, etc.? Will an addendum be issued to address this issue? | Epoxy can be placed over temporary paint as long as the temporary paint is not old or pealing which of course it would not be. Since this was a joint repair project we did not go with grooved in tape or grooved in epoxy since it is not an entirely new surface | Mike Coleman | 1 | 2020-04-21 09:34 | 2020-04-30 09:11
20200512 | 20200512011 | 11 | Material testing for pay item 26. HMA Longitudinal Joint Repair, Item SPV.0195.01 | what are the material testing requirement for item SPV.0195.01, HMA Longitudinal Joint Repair? | The article states under section B Materials, â€œFurnish asphaltic mixture as specified for type 3 HT 58-28 H under standard spec 460.2.â€ QMP Material testing is required for this item as specified under standard specification 460.2. | Mike Coleman | 2 | 2020-05-11 13:31 | 2020-05-11 13:32
20200512 | 20200512012 | 12 | Crack Sealant on Bridge Deck | There's a significant amount of crack sealant on the deck of bridge B-40-377. Will this need to be removed prior to placing polymer overlay? | Yes, crack sealant will need to be removed prior to placing the thin polymer overlay and incidental. As a follow-up, shot blasting for surface prep prior to TPO should take care of crack sealant per Julie Brooksâ€¦ | Mike Coleman | 1 | 2020-05-07 13:37 | 2020-05-07 15:04
20200512 | 20200512014 | 14 | Asphaltic Surface 465.0105 | Good afternoon, The way we understand the asphalt specification, it calls for any LT or MT mix to be used for the shared use paths. This could be a binder such as 19MM. Would the state like to specify a 9.5 or 12.5MM mix to be used on these paths? It could be clarified through a special provision. Thank you, Payne & Dolan Inc | An addendum will be issued to correct this. An article will be added to the special provisions. | Mike Coleman | 1 | 2020-05-05 13:30 | 2020-05-06 13:40
20200512 | 20200512015 | 15 | Prosecution & Progress - Fish Spawning Season Dates | Please review the dates listed for fish spawning restrictions. Per Prosecution and Progress, project is to be completed during 2020 construction season (60 calendar days). Per the Fish Spawning spec, "no instream disturbance of the Rubicon River..., from June 15 to March 1". If these dates are correct, there is no window to construct the project in 2020. Perhaps it should read no instream March 1 to June 15? | There can be no in stream disturbance prior to June 15. An addendum has been issued to clarify the language. | Mike Coleman | 1 | 2020-04-23 09:35 | 2020-04-23 12:24
20200512 | 20200512015 | 15 | Prosecution & Progress - Fish Spawning Season Dates | Please review the dates listed for fish spawning restrictions. Per Prosecution and Progress, project is to be completed during 2020 construction season (60 calendar days). Per the Fish Spawning spec, "no instream disturbance of the Rubicon River..., from June 15 to March 1". If these dates are correct, there is no window to construct the project in 2020. Perhaps it should read no instream March 1 to June 15? | An addendum was issued to clarify the dates. | Mike Coleman | 2 | 2020-04-23 09:35 | 2020-04-29 12:25
20200512 | 20200512015 | 15 | Overhead Utility Issues | In the special provisions it does not state that the overhead lines will be relocated. It just states that the poles will be held during construction. If the overhead lines are not relocated and/or removed the bridge will be unsafe and dangerous to build. Will the overhead lines be relocated? | The overhead line is not a high voltage line. OSHA allows work up to within 10â€™ for voltages up to 50 kV. West edge of bridge is right around that 10â€™ distance, so it will be more difficult to construct if they canâ€™t use a crane, but not impossible. They could still use an excavator and stay below the lines. We have reached out to the utility to see if they can â€œtipâ€ the poles out away from the bridge to give them an extra few feet. When I hear back from the utility I will let you know. If the utility can shift the line, I will update the special language and prepare an addendum. After discussions with the utility company, they have a agreed to de-energize during construction. In addition, this line will be shifted west from the road centerline onto longer bracket arms. An addendum will be issued to update the utilities section for City of Harland (Electrictiy and Lighting). | Mike Coleman | 3 | 2020-04-24 11:00 | 2020-04-27 09:13
20200512 | 20200512015 | 15 | Contaminated Soil Disposal Fees | Please clarify whether the tipping fees at the landfill are the responsibility of the contractor or WDOT. Measurement & Payment indicates excavating, stockpiling, loading and hauling but does not specify on the fess from the landfill. | Tipping fees are the responsibility of the contractor. An addendum will be issued to clarify the Payment section. | Mike Coleman | 4 | 2020-04-30 15:09 | 2020-05-04 08:39
20200512 | 20200512016 | 16 | Backfill Structure Type B | Line Item #34 Backfill Structure Type B 3790 CY. Plan Sht. 85 Miscellaneous Quantities - Revetment Backfill items lists Backfill Structure Type B as 3790 Ton. Please clarify correct unit of measure. | An addendum will be issued to clarify the bid item. | Mike Coleman | 1 | 2020-04-30 13:47 | 2020-05-04 08:44
20200512 | 20200512016 | 16 | Soil Borings | Are there any soil borings other than the ones at Outfall 1&3 shown in the plans? | The geotechnical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512016/ The borings shown in the plan are the only borings taken at outfall #1 and #3. | Mike Coleman | 2 | 2020-05-08 15:15 | 2020-05-11 13:22
20200512 | 20200512017 | 17 | banded joint sealer | For the bridges with existing joint sealer with over banded sealer that is on the edge of the bridge deck, does the over banding need to be removed prior to placing the polymer overlay? | Yes, all over banding material shall be removed from the bridge deck prior to placing the polymer overlay. | Mike Coleman | 1 | 2020-05-07 10:59 | 2020-05-07 10:59
20200512 | 20200512018 | 18 | 643.1200.S Queue Warning System | For the Queue Warning System, what is the intended overall length of the system? Also, for the Northbound traffic queue, will the system only need to be placed on I-43 or was there any intention to place part of the warning system on WI-172? Thank you. | The intended length for NB is 8 miles and SB is 7 miles from the lane closure taper locations. For NB it was always anticipated that 172 and 43 would need to have coverage with boards placed on it. For SB it is anticipated that QWS will go back onto I-41 for 2021 work. Depending on contractor work schedule, the QWS may have to be moved closer to lane closures. It is anticipated that NB will have to moved once for the period when Mason St is complete, unless all NB is complete. We will have an addendum coming to adjust days to account for NB and SB setups separately. | Mike Coleman | 1 | 2020-04-20 15:57 | 2020-04-22 09:46
20200512 | 20200512018 | 18 | Beam Ends Cleaning and exposed steel from bridge deck overlay | Can the beam ends and the exposed steel be cleaned using sand being that the surface areas are minimal? | The assumption here is that you are questioning Item 38 of the table of contents for the special provisions Cleaning Concrete Girder Ends, the intent of the special is to remove the loose concrete from the existing girder ends and then sand blast the existing exposed bar steel and prestressing strands. This is not to be confused with Item 23 Containment and Collection of Waste Materials- this item is for metal girder ends that are to be painted and existing rust and scale is to be removed be power tool cleaning. | Mike Coleman | 2 | 2020-05-04 11:39 | 2020-05-06 08:40
20200512 | 20200512018 | 18 | Item Traffic Control Lump Sum Missing | Item 643.0500 Traffic Control Lump Sum is missing | Item will be added with upcoming addendum. | Mike Coleman | 3 | 2020-05-06 15:24 | 2020-05-07 08:09
20200512 | 20200512018 | 18 | Concrete Overlay adjacent pour | On concrete overlays can the contractor pour adjacent concrete overlay within the 3 days of curing as specified, with Overlay machine rail resting on newly placed concrete? | The contractor can pour adjacent concrete overlays with Engineer Approval- Only placement of overlay machine support railing on newly poured overlay will be allowed, all curing will only be pulled back far enough for placement of support rail and will be replaced immediately on completion of pour. Also provide Engineer the calculations of the weight of the overlay machine as PSI onto the newly placed overlay. The weight of overlay machine will need to be less than the PSI of the concrete breaks for new placed concrete. Psi concrete breaks will be provided to the engineer prior to placement. | Mike Coleman | 4 | 2020-05-07 06:07 | 2020-05-07 06:08
20200512 | 20200512018 | 18 | Removal of existing asphalt and existing concrete deck | In the general notes of structure plans for removal of existing Asphalt overlay and existing concrete deck it states that â€œup to 1/2-inch of concrete shall be removed from the original bridge deck â€œ, does this mean anything less than 1/2-inhch is ok? | The intent of this note is to remove a minimum of 1/2-inch of existing original bridge deck, between 1/2-inch to 3/4-inch of original deck removal will be ok. | Mike Coleman | 5 | 2020-05-07 06:09 | 2020-05-07 06:11
20200512 | 20200512018 | 18 | Item Bridge Painting | Can we get a copy of the original bridge plans for the structures that need full repainting as part of proposal 18? | The original bridge plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512018/ | Mike Coleman | 6 | 2020-05-07 08:58 | 2020-05-07 09:11
20200512 | 20200512018 | 18 | Interim Liquidated Damages | The Prosecution and Progress section conflicts the Interim Liquidated Damages section of the Special Provisions, which section is right. | An addendum has been issued to correct this. | Mike Coleman | 7 | 2020-05-07 15:57 | 2020-05-07 15:58
20200512 | 20200512018 | 18 | Item Traffic Control for Bridge Painting |  | Yes, at Irwin Ave and Danz St. traffic can shifted to one half of the structure, at University Ave over 54/57 there can be single lane closures on 54/57, and at Biard Creek structures a lane may be closed and stop signs erect to control traffic. | Mike Coleman | 8 | 2020-05-07 16:00 | 2020-05-07 16:00
20200512 | 20200512018 | 18 | Item Holiday Work Restrictions | Under the Special events for Lambeau Field Events, is the intent of this to remove lane closures for the construction of bridge overlay? | No, lanes closures will be allowed for bridge overlays only during these events, no lane closures for other work will be allowed. | Mike Coleman | 9 | 2020-05-07 16:02 | 2020-05-07 16:03
20200512 | 20200512019 | 19 | B-31-112 Geotechnical Report | Can the geotechnical report and/or boring logs for B-31-112 be provided? | The geotechnical report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512019/ | Mike Coleman | 1 | 2020-04-20 14:04 | 2020-04-21 08:45
20200512 | 20200512019 | 19 | Staging | Under Article 4 Traffic. Construction Operations it states that Stage 1 is Duvall Street to CTH D, and Stage 2 is CTH O to CTH D. Is it a typo and Stage 1 should be Duvall Street to CTH O (not CTH D)? | There was a typo in the special provisions. Stage 1 is Duvall St to CTH O. An addendum will be issued to correct this. | Mike Coleman | 2 | 2020-04-27 11:13 | 2020-04-27 14:17
20200512 | 20200512019 | 19 | Grading and shaping culverts | Can cross sections be provided to provide information on the expectations of these items? | Cross sections were not developed in these areas. Please refer to the plan details for pipe information and the miscellaneous quantities, sheet 45, for the "information only" quantities for each pipe location. | Mike Coleman | 3 | 2020-04-28 22:09 | 2020-04-29 12:22
20200512 | 20200512019 | 19 | Grading & Shaping Cilverts | Coming back to question # 3. We still would like to see cross sections or better breakdown of earthwork quantities for the grading by the pipe ends. Plan just shows Common Excavation at each location; what does it mean - is it all excess dirt, is there fills there? To come up with earthwork quantities designer must have cut cross sections. Same question would be for Common Excavation in transition cuts - how much is pavement, fill, excess. | Question #3 clearly answered this question. No cross sections were created for the pipe outfalls and no cross sections will be provided for these outfalls. Between the construction detail, the plan details of each pipe location and the â€œinformational onlyâ€ quantities provided in the Miscellaneous Quantities sheet, the department is comfortable there is plenty of information on how to grade and shape culverts. | Mike Coleman | 4 | 2020-05-04 13:35 | 2020-05-05 13:36
20200512 | 20200512019 | 19 | Grading and Shaping and fininshing cross culverts | If there are no cross sections how were they quantities calculated. In the chart on page 45 there is a common CY quantity of 8370 CY. Is this common waste? In the spv item page 13 0f 15 in the Spec it states payment is for "borrow". What is the finished section of these areas supposed to be? The existing and finished typicals both show existing and finished to be a 4:1. Please clarify. | The intention was to replace in kind and match the existing cross section. The design assumed that the common excavation would be used as backfill for the areas outside of the shoulder points, however the contractor may elect to use borrow as backfill outside the shoulder points instead of using the common excavation, but would be covered under the â€˜grading and shaping culvertsâ€™ item, and not paid for separately as borrow. | Mike Coleman | 5 | 2020-05-04 21:31 | 2020-05-05 13:37
20200512 | 20200512019 | 19 | Foundation Backfill item SPV 0035.01 | Will the all the Foundation Backfill as shown on the detail on plan sheet 12 be paid for using the above listed bid item? We understand the excavation in trench area will not be paid as transition cut but the way we interpret the detail all of the foundation backfill will be paid for separately and not incidental to the culverts. | Foundation backfill is paid for in the culvert pipe transition and within the shoulder points under SPV.0035.01. Foundation backfill placed for the culvert trench is not paid for, per Special Provision #24. Any backfill placed outside of the shoulder points is paid for under Item #SPV.0060.01 Grading, Shaping and Finishing Culvert Pipes & Endwalls. | Mike Coleman | 6 | 2020-05-08 13:52 | 2020-05-11 09:41
20200512 | 20200512020 | 20 | Earthwork | Can you explain / confirm stage 1 earthwork quantities. Cannot get quantities shown for stage 1 on page 67 to match what is show on page 208. Can the excel sheets of the earthwork quantities be provided. | The earthwork spreadsheet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512020/ All cross-sectional areas shown on pg. 208 under the â€œAREA (SF)â€ heading were measured in AutoCAD based on the procedures detailed on page 13 of the plans. In the Earthwork Summary (pg. 67) column A is for excavation common. In stage 1, this value is 375 CY which comes from the cumulative volume of CUT in the earthwork table (pg. 208). In the earthwork table the areas, incremental volumes, and cumulative volumes for excavation common do not include the excavation and benching for the existing clay and fly ash. For example, at STA 120+00 the excavation common cross-sectional areas represents the necessary cut for the flat bottom ditch (30.36 SF) and for placement of the 3â€™ base of the new clay cover (51.7 SF). The excavation for the existing clay and fly ash was calculated separately from excavation common. The total volume for the excavation of the clay and fly ash is shown in column M of the earthwork summary and is 3,225 CY. This value comes from the earthwork table and is the sum of the incremental volumes of the clay and fly ash cut. The general procedure for benching and removing the existing clay and fly ash is shown in the construction detail on pg. 13 of the plans â€œFly Ash Removal â€“ Stepped Embankment Benching Stageâ€. The existing clay cover was estimated as 2â€™ thick measured from existing ground. At STA 120+00 the cross-sectional area for fly ash benching is 169.62 SF and the clay cover removal area is 259.79 SF. These combine for a Clay & Fly Ash Cut of 429.41 SF. The new clay cover is shown in column L of the earthwork summary and is 3,090 CY. This value comes from the cumulative volume of expanded clay cover as shown in the earthwork table (pg. 208). The cross-sectional areas on pg. 208 represent the 3â€™ base underneath the relocated excavated fly ash, the 2â€™ cap surrounding the relocated fly ash, and the minimum 2â€™ cap of the remaining exposed fly ash. The placement of the 3â€™ base and the 2â€™ cap surrounding the relocated fly ash is shown on pg. 13 â€œFly Ash Removal â€“ Stepped Embankment Benching Stageâ€. The capping of the remaining exposed fly ash is shown on pg. 13 â€œFly Ash Removal â€“ Stepped Embankment Recovering/Widening Stageâ€. The unexpanded fill is shown in column G of the earthwork summary and is 6,468 CY. This value was estimated as follows: in the earthwork tables (pg. 208) under the â€œAREA (SF)â€ heading, the cross-sectional areas were measured for Clay & Fly Ash Cut, Clay Cover Fill, and Fill. The Fill column represents the total overall fill area that is needed for each station. The overall fill includes the excavated Clay & Fly Ash that needs to be relocated to the bottom of the slope, the new Clay Cover that needs to encapsulate the relocated fly ash and the remaining exposed fly ash that was benched, and Borrow material. The incremental areas for all of these were converted to volumes with the average end area method. The volumes for the excavated Clay & Fly Ash and the new Clay Cover are not included in the mass ordinate so they need to be removed from the overall Fill volume. Therefore, the unexpanded total Fill volume shown in column G of the earthwork summary is the sum of the incremental Fill volumes from the earthwork table (12,380 CY, which is the sum of the 10th column of the earthwork table) minus the sum of the incremental volumes of excavated Clay & Fly Ash (3,225 CY) minus the sum of the incremental volumes of new Clay Cover fill (2,687 CY). The resulting unexpanded fill (6,468 CY) was expanded by the expansion factor (1.15) to achieve the expanded fill volume in column H (7,438 CY). The available material in stage 1 is the excavation common value in Column A (375 CY). This was subtracted from the expanded fill to achieve the stage 1 mass ordinate in column I and the stage 1 Borrow in column K (7,063 CY). | Mike Coleman | 1 | 2020-04-28 07:25 | 2020-04-30 06:26
20200512 | 20200512020 | 20 | Contractor Data Packet | Can you post the contractor data packet for this project? | The contractor data packet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512020/ | Mike Coleman | 2 | 2020-04-28 14:58 | 2020-04-28 15:02
20200512 | 20200512020 | 20 | Stage 1 Grading | For Stage 1B grading work (2020) on the slope along CTH EE SB would require the existing guardrail to be removed to be able to access the work efficiently with the called out work zone restrictions. Per the plan guardrail is not shown to be removed until 2021 work. What would be put in place of guardrail for 2020 winter shutdown. | The existing beam guard may be removed along CTH EE to better accommodate the 2020 construction. After the CTH EE widening is constructed in 2020, beam guard will no longer be needed to protect the slopes along CTH EE, but the beam guard around the intersection radius and along STH 28 will need to remain in place. An addendum will be issued clarifying this and to specify placement of a temporary Energy Absorbing Terminal at the end of the existing beam guard that will remain over winter. | Mike Coleman | 3 | 2020-04-30 09:15 | 2020-05-01 05:54
20200512 | 20200512020 | 20 | Clay Cover | Under the special provision, the contractor will do the "screening" portion of the testing frequency while DOT will preform the QA/QC portion of the testing frequency, correct? Please clarify as in under payment section it then states "and for performing all tests", contradicts. Also, under QA/QC Testing, provide the following: Machinery required to collect undisturbed clay samples with shelby tubes. The contractor is responsible to provide the drill rig with shelby tubes to take these samples? Isn't that part of the QA/QC testing? | The contractor will perform the Screening tests shown in Table 1, and the department will perform the QA/QC tests. An addendum will be issued to clarify this in the Payment section of the article. | Mike Coleman | 4 | 2020-05-04 11:59 | 2020-05-05 12:55
20200512 | 20200512020 | 20 | Storm Sewer Stage 1A | During placement of storm sewer between 122A and 122B are we digging through flyash to do this work? The detail on sheet shows Trench Backfill above the pipe, is it the departments plan to replace all this flyash into the trench? what about the clay cap will this also be an area that is tested? This work will generate waste, where will this be disposed if its flyash? are any of the other storm sewer pipes being placed in flyash? | As shown on page 3 of the plans, the existing fly ash cell is expected to be northwest of the pipe from 122A to 122B. The southeastern end of the existing fly ash cell is estimated to be around STA 121+50â€™SBâ€™, and the storm sewer pipe from 122A to 122B is at STA 122+40â€™SBâ€™. Additionally, the southeastern end of the existing fly ash cell is presumed to be deeper than the proposed storm sewer pipe. Removal of the existing culvert pipe had some potential to require excavation into the fly ash cell, which is why it is proposed to abandon the existing pipe. The new storm sewer pipe is proposed higher and further southeast than the existing pipe to provide further separation from the existing fly ash cell. Backfill the pipe from 122A to 122B in accordance with the construction detail on page 14. Fly ash should not be used to backfill that pipe, and thus, clay cover is not required. The remaining storm sewer pipes on the project are expected to be beyond the fly ash cell, or installed above the existing fly ash cell and its clay cap. If existing clay cover or fly ash are encountered during any other parts of the project, coordinate with the engineer in accordance with Article 10 in the special provisions. | Mike Coleman | 5 | 2020-05-06 06:29 | 2020-05-06 13:27
20200512 | 20200512020 | 20 | Satge 1A Storm Sewer | Addendum to first question: When encountering flyash on other pojects the material was saturated and not suitable for backfill. Is there an contingency for disposing of flyash that will be waste from this portion of the work? | The existing fly ash is not expected to be saturated. It is likely to get mixed with existing clay cover when the benching is graded, which should aid in its workability. If the fly ash to be excavated is found to be unsuitable for fill, the contingency would be to haul it to a landfill. Since that is not anticipated, bid items for hauling it to a landfill have not been included. If required, work associated with hauling it to a landfill will be paid for as extra work. | Mike Coleman | 6 | 2020-05-06 06:48 | 2020-05-06 13:29
20200512 | 20200512021 | 21 | job 21 | Can this job be poured 30'-0" or 34'-0" Wide. | Yes, the concrete can be paved at 30â€™ or 34â€™ wide, as long as access to local traffic is maintained. An addendum will be issued to further outline requirements related to paving and providing access. | Mike Coleman | 1 | 2020-04-14 11:45 | 2020-04-20 06:18
20200512 | 20200512021 | 21 | Removing Pavement | Has the department witnessed a clean separation of the existing (5"-7") thick concrete from the underlying (2" average) milled asphalt pavement without the two materials either bonding together or breaking up the asphalt so badly that it will not be feasible to salvage the existing asphalt as a pulverized base? It seems very unlikely that after breaking and removing the existing concrete that the existing thin asphalt will be as the department intended. | We expect a relatively clean separation of the concrete layer from the underlying asphalt layer. We also expect very little breaking of the concrete necessary prior to removal. Adams County crews have done a significant amount of repair work on this portion of STH 82 and have not experienced issues with bonding of the layers. Contractor operations may need to be adjusted at the start of concrete removal to determine the amount of breaking of the concrete necessary, and to develop a method that will minimize effects to the asphalt layer. | Mike Coleman | 2 | 2020-04-20 15:49 | 2020-04-21 14:23
20200512 | 20200512021 | 21 | SPV 17 - Pulverized and Re-Laid Material | The SPV states that "removing waste material" is incidental and "hauling material from one location on the project to another, the department will pay for hauling as extra work". There is no indication in the plan quantifying a quantity of waste material. There has been an item of wasting excess material by the CY used on other projects before and would like to see an item added instead of incidental for bidding purposes. | An addendum will be developed to include an estimated volume of waste material, that can be used for informational purposes during bidding. Removal of waste material will remain incidental to the item of Pulverized and Re-laid Material. It is not anticipated that there will be material that will need to be relocated within the project. | Mike Coleman | 3 | 2020-04-20 16:01 | 2020-04-22 06:54
20200512 | 20200512021 | 21 | QMP Pulverize and Relay Compaction | We feel this is not a typical relay project where a NEW vertical profile has been proposed in the plan. The intent also with this project is to pulverize on average 2" of the existing asphalt and move that material throughout other locations to establish the NEW proposed vertical profile. This could lead to un-uniform thickness of the pulverized base or possibly none depending on the new profile which will make uniform density testing very difficult. | An addendum will be developed to remove the item of QMP Pulverize and Relay Compaction. | Mike Coleman | 4 | 2020-04-20 16:15 | 2020-04-22 06:55
20200512 | 20200512021 | 21 | SPV Removing Aggregate Shoulder | Can you explain in more detail the intent of this item. It states to "Remove existing, unsuitable shoulder material to the depth the plans show. Do not see a detail or a volume of material anticipated? This item is bid by the station? We feel that a typical detail must show what is to be removed and/or pay by the CY with a quantity included in the plan. It also states to dispose of this material, not to incorporate back into the project and must be removed prior to any other construction activities. What is in this shoulder and why does it have to be removed separately? | The proposed typical section indicates that 3 inches of shoulder material is required to be removed and replaced with new base aggregate. This is the material that is designated to be removed and disposed of under the Removing Aggregate Shoulder item. This upper layer of existing shoulder material is required to be removed separately due to significant contamination of fine and organic materials. The intent is to allow lower aggregate shoulder materials to remain in place, such that they can be temporarily relocated prior to concrete paving, without being contaminated by the organics in the upper layer. | Mike Coleman | 5 | 2020-04-20 16:40 | 2020-04-22 06:57
20200512 | 20200512021 | 21 | Removing Pavement | What is the department prepared to do if the asphalt pavement is connected to the bottom of the concrete and does not separate during the removal process? | Past maintenance and repair projects did not experience any issues with bonding of the asphalt and concrete layers. Therefore, clean separation of the layers is expected. Should separation issues be encountered during construction, changes to the contract will be considered. Any contract adjustments will be determined in accordance with Standard Specification 104.2.2.4 Change Orders for significant Changes in the Character of the Work. | Mike Coleman | 6 | 2020-05-04 10:38 | 2020-05-05 08:58
20200512 | 20200512021 | 21 | Asphaltic Surface Detours | Is it the intention to do this paving prior to starting the detour or will this be used as maintenance of the detour route as needed? | It was intended that this item be used as needed for maintenance of the detour route. | Mike Coleman | 7 | 2020-05-05 09:49 | 2020-05-05 12:54
20200512 | 20200512021 | 21 | Note #3 on the Proposed Typical Sections | Industry is concerned with this work being incidental to the concrete pavement. Is the assumption being made that there is more than enough material here that it can be salvaged and moved to accommodate paving operations? If this material were to run short is the Department open to providing dense graded base to properly construct a track line for paving? And pay for the base material needed? | This note is to direct that this material be salvaged and reused in the lower layer of the base aggregate shoulder. We anticipate that a good method might be to relocate/windrow this material to outside the track-line of the paver, and then pull it back in once paving is completed. Preparing the foundation for concrete pavement and payment for any extra work will be done in accordance with Standard Specification 415.3.3 Preparing the Foundation. | Mike Coleman | 8 | 2020-05-06 10:23 | 2020-05-07 08:55
20200512 | 20200512022 | 22 | Special Material Requirements for Mitigation of Alkali-Silica Reactivity for Cast-in-Place Concrete | Item 17 of the Special Provisions indicate if the contractor elects to us a coarse aggregate from sources containing significant amounts of felspa-volcannics, they shall provide test results of an ASTM C1260 Test. What is considered significant? Further it states to run ASTM C1567 mortar bar tests. The specials also state ASTM C1260/ASTM C1567 testing every 3 years or more frequent if the aggregate changes. What is the intent of this spec if the completion date is listed as 9-30-2020. Will the contract be left open? What is the total duration required for testing? | This special provision is not applicable to this project. An addendum will be issued to remove it from the contract. | Mike Coleman | 1 | 2020-05-05 07:39 | 2020-05-05 08:44
20200512 | 20200512023 | 23 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512023/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-04-22 13:59 | 2020-04-23 06:00
20200512 | 20200512023 | 23 | Aerial Enforcement Bars | Good afternoon. The bid item for the aerial enforcement bars is per each while plan sheet 36 lists this item as (LF) which makes sense based on the area they are to be installed. Can you please clarify if this should be a per each item or a per (LF) item and if there will be an addendum issued to modify the bid item if in fact it is warranted? Thank you. | The bid item Marking Aerial Enforcement Bar Epoxy should be EACH rather than LF. An addendum will be forthcoming to modify the bid item. | Mike Coleman | 2 | 2020-04-28 14:18 | 2020-04-30 09:12
20200512 | 20200512024 | 24 | Beam Guard and Milling Requirements | 1. The advertisement showed 5817 LF of beam guard, but there is no beam guard in the quantities. Is there beam guard on this project? 2. Does the milling requirements shown in the special provisions also apply to the side road work? | 1. No, there is no beam guard in this contract. The advertisement was incorrect. 2. Yes, the milling requirements also apply to side road work. | Mike Coleman | 1 | 2020-04-30 06:32 | 2020-04-30 06:34
20200512 | 20200512025 | 25 | Design Schedule | Could the schedule developed in design be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512025/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-04-20 14:48 | 2020-04-22 07:26
20200512 | 20200512025 | 25 | Centerline Joint Milling | Page 12 shows that the centerline joint is to be milled out, however page 26 shows that the proper joint is a tapered joint. Is it the departments intention to mill out the tapered joint prior to the second pass? If it is their intention would a SPV for Removing HMA Pavement Notched Wedge Longitudinal Joint Milling be added to better define the work required? | The longitudinal joint will need to be constructed per SDD 13C19 and the standard specifications (including ASP-6). | Mike Coleman | 2 | 2020-04-27 08:21 | 2020-04-29 07:25
20200512 | 20200512025 | 25 | Removing Distressed Pavement Milling | Is The Minimum 4-Foot By 8-Foot Area To Encompass Distressed Pavement Expected To Be 4-Feet Wide By 8-Feet Long Or 8-Feet Wide By 4-Feet Long? This Would Determine The Size Of The Milling Machine To Be Utilized. Thank You. | The dimensions would be minimum 4â€™ wide by 8â€™ long. | Mike Coleman | 3 | 2020-04-28 08:51 | 2020-04-29 07:19
20200512 | 20200512025 | 25 | Center Line Milling and Paving | On sheet 12, the miscellaneous quantities show items for center line joint milling and center line joint paving for the length of the project. What is the intent for these two quantities? Please provide a specific answer and construction detail if necessary. Thank you. | The centerline joint should be constructed per SDD 13C19. The quantity for milling the centerline joint was removed with addendum 1. | Jill Fehrman | 4 | 2020-04-30 07:11 | 2020-05-01 16:03
20200512 | 20200512025 | 25 | Center Line Milling and Paving | Thank you for your response to question no. 4. The reason for asking for further clarification was that Addendum No. 1 removed only the center line joint milling of STH 22/110 (97 SY). The center line joint milling of STH 22 (1456 SY) between station 331+00 and station 462+07 remains in the Miscellaneous Quantities shown on sheet 12. Thank you. | That quantity should have been removed as well. An addendum will be issued to correct this. | Mike Coleman | 5 | 2020-05-02 09:35 | 2020-05-06 06:18
20200512 | 20200512026 | 26 | Construction Schedule | Could the schedule developed in design be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512026/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-04-20 14:49 | 2020-04-21 09:14
20200512 | 20200512028 | 28 | Base Aggregate Dense 1.25" | On sheet 9 there is a quantity of 174 TN for Base Aggregate Dense 1.25â€ I cannot find a reference to where this would be placed. Could you please clarify or provide a detail? | The bid item will be eliminated in an upcoming addendum. | Mike Coleman | 1 | 2020-04-22 12:15 | 2020-04-28 15:08
20200512 | 20200512030 | 30 | design work schedule | Northeast Asphalt is requesting a copy of the design schedule of work. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512030/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-04-20 11:24 | 2020-04-20 13:39
20200512 | 20200512030 | 30 | Asphalt CE's and PE's | There are at least 42 asphalt CE's and PE's along the length of this project. Shouldn't there be a asphaltic surface driveway item to account for asphalt going in these areas? | The profile elevation of the road isnâ€™t changing so driveways are not impacted. It is proposed to mill and overlaying the mainline through the driveway locations. | Mike Coleman | 2 | 2020-04-27 12:11 | 2020-04-27 15:19
20200512 | 20200512030 | 30 | intersections | The plan does not show a detail or does not denote any quantity of HMA in the Miscellaneous Quantities for intersections. Could the department supply both a detail and a quantity? | The profile elevation of the road isnâ€™t changing so side roads are not impacted. It is proposed to mill and overlaying the mainline through the side road locations. | Mike Coleman | 3 | 2020-04-28 12:42 | 2020-04-28 15:06
20200512 | 20200512031 | 31 | Winter shutdown | If all work can't be completed in the 2020 construction season because of temps can it be finished in spring of 2021? | The Contract Completion Time for this Project is 49 Working Days. The intent of this Contract is to complete all of the Project work in the 2020 construction season. | Mike Coleman | 1 | 2020-05-07 12:35 | 2020-05-07 13:52
20200512 | 20200512031 | 31 | Chippewa County Bridges B-09-0052 & 0053 | The two bridges in Chippewa county B-09-0052 & 0053 Pages 58-63 show structure painting and no polymer overlays. There are no line items for painting, and total quantities for polymer overlays is short without these two bridges. | The plans for B-09-52 & B-09-53 shown are incorrect plans from a previous project. An addendum is being issued to put the proper plans in. | Mike Coleman | 2 | 2020-05-07 12:40 | 2020-05-07 13:53
20200512 | 20200512031 | 31 | Abatement of Asbestos Containing Material B-55-0065 | The proposal contains Special Provision for Abatement of Asbestos Containing Material B-55-0065, Item 203.0210.S. which refers to bid item 203.0210.S Asbestos Containing Material B-55-0065 - LS. This item is not included in the bid file. Please advise. |  |  | 3 | 2020-05-08 12:01
20200512 | 20200512033 | 33 | Shaping Shoulders Quantity | It appears the shaping shoulder quantity is half of what we may be required to complete? Shaping shoulders will be needed on both sides of the roadway in each direction. | See the typical sections. The outside shoulder calls for Shaping Shoulders. The inside shoulder is anticipated to be low and the plan calls for new BAD. Per 305.5(2), payment for the Base Aggregate Dense bid items is full compensation for preparing the foundation; and for placing, shaping, compacting, and maintaining the base. Separate payment is not made for shaping shoulders in areas needing new BAD. | Mike Coleman | 1 | 2020-05-06 18:46 | 2020-05-07 08:07
20200512 | 20200512033 | 33 | Removing Asphaltic Surface Milling - Units | The Removing Asphaltic Surface Milling item is currently bid/paid by the ton (204.0125). Milling by the ton is beneficial when there are variable or unknown milling thicknesses on a project. Weighing the material requires additional cost for moving a scale, labor for operating the scale and additional paperwork. The milling thickness on this project appears to be consistent. We suggest changing the item unit to the SY (204.0120). | See the typical sections. The mainline and inside shoulder require a 4â€ mill. The outside shoulder requires a 2â€ mill. The TON item was used since this better reflects the project work and was coordinated during the design process and during estimate review. It also offers the field staff to address any additional milling is identified. We would propose that the contractor bid the project by TON as currently proposed. | Mike Coleman | 2 | 2020-05-06 19:18 | 2020-05-07 08:08
20200512 | 20200512037 | 37 | Soil Borings | Were any soil borings done in the reconstruct area? | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512037/ | Mike Coleman | 1 | 2020-04-21 09:26 | 2020-04-21 10:09
20200512 | 20200512037 | 37 | Removing Asphaltic Surface MIlling / Salvage Asphaltic Pavment MIlling | It appears that the item of Removing Asphaltic Pavement Milling covers the entire project. Where will the tonnage for the Salvage Asphaltic Pavement come from? Will the quantity of Removing Pavement Milling be reduced and paid as Salvage Asphaltic Pavement Milling? | Yes, the Removing Asphaltic Surface Milling quantity is intended to be reduced by the amount of material needed for the Salvaged Asphaltic Pavement Milling item, which also matches the needed Salvaged Asphaltic Pavement Base item. This is factored into the Miscellaneous Quantities calculations. It is the contractor's discretion for which locations within the project they would use the Salvaged Asphaltic Pavement Milling item in order to produce the material needed for Salvaged Asphaltic Pavement Base. | Mike Coleman | 2 | 2020-04-27 16:02 | 2020-04-30 06:17
20200512 | 20200512037 | 37 | Removal of existing shoulder material to widen the asphaltic pavment | There are a few questions pertaining to the widening of the asphaltic pavement. What item will be used to pay for the removal of the existing shoulder material to accommodate the widened pavement? Is the width of the salvaged asphaltic pavement base two feet or three feet? If it is three feet, is the intent to remove one foot of the existing asphaltic pavement? Finally, is the typical section correct in showing the existing shoulder removal as 6" below the milled surface starting at the edge of the existing asphaltic pavement and extending to the slope intercept? | 1. The Shaping Shoulder item was intended to be used for movement of existing shoulder material to accommodate shoulder paving. 2. Salvaged Asphaltic Pavement Base layer should be 2-ft wide. When looking into this we agree that the plans incorrectly list 3'. 3. No removal of existing pavement, 3' incorrectly listed. 4. Yes, 6-in is intended to be removed but is only required under the additional shoulder paving area. An addendum will be issued to correct the plan sheets | Mike Coleman | 3 | 2020-04-27 16:40 | 2020-04-30 06:27
20200512 | 20200512037 | 37 | Salvage and Reinstall Guardrail | The plan has notes to "salvage and reinstall guardrail during culvert replacement." Does this need to be done each day? Is this incidental to the culvert replacement? | There is a bid item in the plans to address the guardrail (SPV.0090.01 Salvage and Reinstall Guardrail). Guardrail is not required to be replaced each day. The intent is to salvage the guardrail, replace the culvert, and then replace the guard rail in-kind. The guardrail work should be performed as efficiently as possible but is not required to be the same day. | Mike Coleman | 4 | 2020-05-05 06:40 | 2020-05-05 10:03
20200512 | 20200512041 | 41 | Asphaltic Surface | Due to the small quantity and a lot of ancillary beam guard widening paving, will the department consider changing the HMA to Asphaltic Surface, with a SPV spelling out the 4MT mix with 58-34S oil | Asphaltic Surface item will be added by addendum. The asphaltic surface shall meet the requirements of 4MT 58-34S and will be added to the special provisions with the addendum. | Mike Coleman | 1 | 2020-04-25 09:00 | 2020-04-28 07:17
20200512 | 20200512043 | 43 | 3 Prosecution and Progress - Migratory Birds | With a letting date of May 12. Will the department have bird netting installed prior to May 1? There are old bird nests currently under the structure. If netting is not installed, can the Department supply contact information for the US Fish & Wildlife representative that will handle the depredation permit application for this project. | The Department is unable to install the netting prior to May 1st and the Contractor will need to apply for the depredation permit. The online permit application is on the USFWS website at: : https://www.fws.gov/birds/policies-and-regulations/permits/need-a-permit.php The contact for the USFWS Region 3 is: U.S. Fish and Wildlife Service Migratory Bird Permit Office 5600 American Blvd. West Suite 900 Bloomington, MN 55437-1458 Tel. (612) 713-5436 Fax (612) 713-5393 Email: permitsR3MB@fws.gov | Mike Coleman | 1 | 2020-04-13 08:15 | 2020-04-16 06:43
20200512 | 20200512043 | 43 | B-17-226 | Can the geotechnical report for the borings at B-17-226 be provided? Specifically looking for more information on the rock core(s) taken. | The geotechnical reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200512043/ | Mike Coleman | 2 | 2020-04-20 14:03 | 2020-04-22 07:22
20200512 | 20200512043 | 43 | Lowering the upstream pool | The existing penstock appears to be handling all the water that it can take, and the upstream pool is maintaining its current level approx. EL 835 ±. Is there a stoplog system or slide gate associated with the penstock (inside the diesel building?) that can be opened fully to lower the upstream pool. | There is no known functional stoplog or slide gate for the penstock. The diesel building is relatively empty and it looks as if any gate system may have been removed. | Mike Coleman | 3 | 2020-04-22 09:08 | 2020-04-22 13:44
20200512 | 20200512043 | 43 | Bid Item 0212 SPV.0035 Sediment Removal - Clarification | Page 32 Miscellaneous Quantities sheet shows "Sediment Removal" location as "Dam Removal" 450 CY. Plans Sheets 22 & 23 both show a significant section of sediment removal on the upstream side of the existing crest/spillway. The special provisions read: Sediment Removal, Item SPV.0035.02 This special provision describes removal of sediment at turbidity barrier locations as shown on the plans and as hereinafter provided. Work includes, but may not be limited to: - Removal of sediment accumulated behind turbidity barriers. - Hauling and disposal of sediment. - Providing temporary traffic control as required for sediment removal at 150th Avenue location. What is paid for under this item? | The sediment upstream of the dam as shown on plan sheets 22 and 23 to be removed is estimated to be 450 CY of material and will be paid for under item Sediment Removal, Item SPV.0035.02. This special provision should have identified this as the main location. If any of this material is washed downstream, then it would be removed at the two turbidity barrier locations as described in the associated special provision. An addendum has been issued to clarify the special provisions. | Mike Coleman | 4 | 2020-04-22 12:44 | 2020-04-22 14:15
20200512 | 20200512043 | 43 | turbidity barrier | According to the plans it appears as though turbidity barriers are to be installed directly across Rock Creek at two different locations. Turbidity barrier is an impermeable fabric and essentially is creating a dam. If Rock Creek has any flow at all it is inevitable that the turbidity barrier will fail if it can even be installed at all. Please advise. | An addenda is being prepared to address the turbidity barrier. | Mike Coleman | 5 | 2020-04-24 07:11 | 2020-04-27 09:14
20200512 | 20200512043 | 43 | Please clarify the upstream pool draw down procedure. | B.1 Design Requirements Lower impoundment at a rate of no more than 6 inches per 24-hour period. Intent is to drawdown to remove the impoundment prior to dam removal. Approximate drawdown elevation is 825+/-. Dam removal cannot proceed until drawdown is completed and approved by the engineer. If the penstock cannot effectively lower the upstream pool and the dam (or portion thereof) cannot be removed until drawdown is complete. How is it intended that the pool be drawn down to approx EL 825 | The intent is to not remove the entire dam at once until the drawdown is complete. This will aid in slowing the sediment transport. It is assumed that a notch will be cut into or a portion of the dam removed to facilitate drawdown. This is being addressed in a forthcoming addenda. | Mike Coleman | 6 | 2020-04-24 11:32 | 2020-04-27 11:04
20200512 | 20200512043 | 43 | Grinding Mill Turbine Tower Removal Limits | On sheet 17 of the Dam Removal Plans, Photos A and B do not show the tower backwall being removed while Photo C has this area highlighted for removal. Please clarify what the limits are for this. If this is being taken out, can WisDOT verify that this element does not provide support for the retaining wall that is to stay in place? | The intent is to NOT remove the tower backwall. Photo C was not intended to depict the back wall. As shown in Photo A and B the mill tower / posts are to be removed. | Mike Coleman | 7 | 2020-05-04 14:23 | 2020-05-05 12:56
20200512 | 20200512043 | 43 | Beveled Anchor Plate Structure B-17-226 | A beveled anchor plate is referenced on page 93 (sheet 8 of structure B-17-226 details) and points to the Superstructure details sheet for more information; however, there is no additional information regarding the beveled anchor plate on that page. Please provide the beveled anchor plate details or confirm the correct details at the end of the girder. | The anchor plate on sheet 8 of structure B-17-226 was incorrect. An addendum will be issued to correct this. | Mike Coleman | 8 | 2020-05-05 12:08 | 2020-05-06 06:16
20200512 | 20200512043 | 43 | Schedule Allowance: Contractor-Furnished Cofferdam Permit / Dewatering Permit | The permits required for the cofferdam and dewatering can take up to 90+ days for approval according to the special provisions. If a contract is awarded in May/ June, dewatering potentially would not begin until September and with no instream work taking place after 9/15 there will not be sufficient time to complete this project. Will the department consider a time extension or modify the instream dates to allow sufficient time to complete the work if the permits take 90+ days to receive approval. | Addendum 1 removed reference to the Chapter 30 WDNR/COE cofferdam permit. The cofferdam will be permitted as part of the ECIP process. | Mike Coleman | 9 | 2020-05-05 15:46 | 2020-05-06 06:49
20200512 | 20200512043 | 43 | Follow up to Question 1 - Migratory Birds | USFWS has indicated that the DOT must apply for the permit as they are the owner - Can the Department tell us the timing it takes to achieve a Depredation Permit and will this impact the completion date? | WisDOT will net the bridge in lieu of a depredation permit. | Mike Coleman | 10 | 2020-05-05 15:48 | 2020-05-07 06:16
20200512 | 20200512043 | 43 | Haunch Height | The Haunch Height seems extremely high on the Bridge and will prove difficult in forming - has the Department considered raising the beam seat height and thereby reducing the haunch? | BOS did consider raising the beam seat height, however with numerous other project design constraints and the need to maintain the minimum required haunch on the girders, we were left with a high haunch value. | Mike Coleman | 11 | 2020-05-06 12:29 | 2020-05-06 14:01
20200512 | 20200512044 | 44 | WN Ramp closure for HFST | Will the WN Ramp have a full nightime closure for the HFST? Not defined in the plans. Thanks | The WN Ramp will have a full closure for the install of the HFST as stated in the Traffic article and will adhere to the Full Freeway and System Ramp Closure Hours defined in the Prosecution and Progress article. The plans show the full closure for the WN Ramp in IH 43 NB Stage 1B. | Mike Coleman | 1 | 2020-05-06 10:20 | 2020-05-07 08:54