## qandasearchletting_results
Date: | 2020-07-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200714 | 20200714001 | 1 | Cold Weather Epoxy | Good morning. Can you please elaborate on what the anticipated use of the cold weather epoxy item? The quantities included don't necessarily make sense as to where this item will be used as the quantities do not match the edge line quantities. Thank you. | The Cold Weather Epoxy bid item will be removed from the plans and will not be part of this project. An addendum to the plans will be sent out next week. | Mike Coleman | 1 | 2020-06-24 07:35 | 2020-06-26 06:17
20200714 | 20200714001 | 1 | Cross Section Information | Is there an earthwork data sheet available for the cross sections or can we get an electronic file for the earthwork cross sections? This information is needed to determine the haul distances of cut to fill within each segment. | The earthwork data sheet can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714001/ | Mike Coleman | 2 | 2020-06-24 13:59 | 2020-06-26 06:21
20200714 | 20200714001 | 1 | SPV Hauling Excess Shoulder Material and 3/4" BAD |  |  |  | 3 | 2020-06-29 09:21
20200714 | 20200714001 | 1 | Hauling Excess Shld Matl and 3/4" BAD | Can you explain intent and verify quantities of both items. Excess item indicates to place in areas of deficiencies as directed by engineer which makes it difficult to bid if there is no room along the shoulders and excess has to wasted off R/W. Quantity seems high along with 3/4" BAD. | The Hauling Excess Shoulder Material item was added to give the contractor flexibility to either haul the excess shoulder material to a section with lower amounts of aggregate, or to beamguard locations as fill material. The quantity for these items considered many factors including the paved shoulder being widened, additional aggregate being used at the beamguard end terminals, and the observation that the existing aggregate shoulder is about one to two inches low when compared to the driving surface for the length of the project. Taking into account these factors, we believe that these quantities are accurate. | Mike Coleman | 4 | 2020-07-01 10:12 | 2020-07-02 09:14
20200714 | 20200714001 | 1 | IRI Ride | This project has IRI Ride Incentive and the existing road is in very poor condition. The plan calls for a 1.75â€ mill and a single (1) lift 2â€ thick HMA overlay. It is likely that defects will reflect through the new HMA. Will additional consideration be made to reduce IRI ride disincentive? | The standard spec for IRI Ride has been used on many other projects consisting of 2-inch mill and overlays without issue. This item is intended to ensure quality between the milling and paving operations. In addition, this plan includes the Removing Distressed Pavement Milling and the Extra Depth HMA Pavement items to remove and replace the worst locations of pavement on this project. Incentive IRI Ride will follow the incentive and disincentive pay as outlined in Spec Book. | Mike Coleman | 5 | 2020-07-08 14:55 | 2020-07-10 11:04
20200714 | 20200714002 | 2 | As Built Plans Available | Can the as-built plans for this project be posted? | The as-builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714002/ | Mike Coleman | 1 | 2020-06-18 15:04 | 2020-06-22 11:55
20200714 | 20200714002 | 2 | Stage 2 Traffic Control - clarification | Stage 2 traffic control single lane closures shown on sheet 19 & 20 is shown as closing the northbound only. Can the southbound lane be closed if we have the northbound lane open? | Due to potential sight distance concerns at the CTH C intersection the southbound lane north of the intersection cannot be closed. Any proposed changes to the contract will be addressed during the project per Section 104 of the Standard Specifications. | Mike Coleman | 2 | 2020-06-25 14:03 | 2020-07-01 10:18
20200714 | 20200714002 | 2 | Extend Project Limits | Would WisDOT consider extending the project limits beyond 100 ft of the bridge approaches? | WisDOT will review and discuss this suggestion. If we determine that it would benefit the project, we will add it through an addendum. | Mike Coleman | 3 | 2020-06-26 06:25 | 2020-06-26 06:26
20200714 | 20200714002 | 2 | 661.0300 Generators | What is the intent of item 661.0300 Generators? As it is listed on a Misc QTY table with the Temporary Traffic Signals, are they meant to be a supplemental power source for the solar powered signal trailers? Thanks | Yes, the generators are supplemental power sources for the 3 temporary traffic signals in Stage 2 phase 1 and the 2 temporary traffic signals in Stage 2 Phase 2. | Mike Coleman | 4 | 2020-06-26 11:38 | 2020-06-30 05:45
20200714 | 20200714002 | 2 | DNR Contact Information | Can you provide Andy Barta's contact information for the DNR? | Andy Bartaâ€™s email is andrew.barta@wisconsin.gov, his office phone is 608-275-3308 and his cell phone is 608-235-2955. | Mike Coleman | 5 | 2020-06-30 05:49 | 2020-06-30 05:50
20200714 | 20200714002 | 2 | Steel beam guard, Line 0164/0166 | In regards to line item 0164/0166; On page 4 of the plans reference is made to station 418+40 to 419+40 (remove,refurbish and replace beamguard) Are line items 0164 and 0166 referring to only one (the same) 180 LF section from station 418+40 to 419+40 at the south end of the structure or is one line item for the northend of the structure? Or are these two separate 180 LF beamguards? Thank you. | Line item 0166 refers to the NORTH end of the bridge, STA 429+09 â€“ 429+98 as shown in the Miscellaneous Quantities sheet page 27. Line item 0166 is the required coating of the beam guard. Line items 0010, 0078 & 0080 are also items for the NORTH end of the bridge. Item 0164 refers to remove and resetting the existing brown beam guard on the SOUTH end of the bridge. They are no duplicate items in the plan. | Mike Coleman | 6 | 2020-07-06 09:41 | 2020-07-07 06:14
20200714 | 20200714002 | 2 | In Stream Disturbance Dates | Are there any restrictions for in-stream disturbance on this project for fish spawning seasons? | There are no restrictions for in-stream disturbances as part of this project. Standard best management practices (BMP) shall be followed to minimize erosion and sedimentation. | Mike Coleman | 7 | 2020-07-07 10:39 | 2020-07-08 05:41
20200714 | 20200714002 | 2 | Navigation Season | Can navigational season dates be provided for when waterway markers will be required. Portions of this contract will likely occur during winter weather conditions where ice will dictate removal of buoys or prevent installation of buoys. | Per articles 9 and 33 of the special provisions, the contractor shall comply with the requirements of the Wisconsin Department of Natural Resources Waterway Marker Application and Permit process. Markers should remain in place when bridge work over the Wisconsin River is occurring with open water present. | Mike Coleman | 8 | 2020-07-07 10:45 | 2020-07-08 05:42
20200714 | 20200714002 | 2 | Cold Weather Painting | The June 12th opening date will drive the coating of beam tops into winter weather conditions. Will alternate low temperature paint products be considered to maintain schedule and provide contractors with a reasonable means to complete the work? | The Department believes the schedule provides sufficient time to perform the painting operations within the requirements of the painting specifications. Bids should be based on using the Departmentâ€™s approved products list and the requirements of the specifications. | Mike Coleman | 9 | 2020-07-07 10:48 | 2020-07-10 07:57
20200714 | 20200714002 | 2 | Project Schedule | Please provide the Department's schedule for this project? If there is not a specific item for painting beam tops, and when does the Department feel this work is going to happen? |  |  | 10 | 2020-07-10 08:19
20200714 | 20200714004 | 4 | Intersection Milling / Butt Joints | 1. Does the total milling quantity for the project include the square yardage of the 24 intersections which are identified to receive butt joints? 2. Are the intersections in the wedge and overlay section (169+50 to 395+00) to also receive milling? or only a 2â€™ butt joint? 3. Would the DOT be willing to consider revising the butt joint detail on this project to reflect the large amount of side road milling required? Paying for only a 2â€™ cross cut does not accurately capture what is required at the side roads on this project, if field adjustments are made to these intersections then there is at least a unit price available to compensate fairly for the work. Thanks for your consideration. | 1. There is a milling quantity for each side road on the project included in the total milling quantity. The limits are based on the butt joint detail, construction detail in the plans. 2. All sideroads are included in the milling quantity. Adjustments to milling limits and depth of milling will be directed by the engineer. 3. The milling limits and butt joint limits are defined in the construction detail and plan details, the construction detail will not be changed. | Mike Coleman | 1 | 2020-06-22 08:25 | 2020-06-23 09:11
20200714 | 20200714005 | 5 | Wing Strapping - Steel Shims | The plan details for steel strapping show (3) layers of steel shims but don't note the number of layers. Is there a minimum or maximum number of shims that are allowed? Could a Contractor provide one thick shim that meets the required thickness or a multitude of smaller shims to allow flexibility? | Multiple shim layers or a single shim layer are allowed. The minimum allowable shim plate thickness shall be 1/8â€ and there should be no more than two shim plate layers of any given plate thickness less than 1â€ thick. Per the plans, the contractor will need to field verify the total thickness required prior to fabrication, and all elements should be galvanized as directed in the plans. | Mike Coleman | 1 | 2020-06-16 09:19 | 2020-06-22 12:50
20200714 | 20200714006 | 6 | Electronic Data Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement and Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The files requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-06-12 09:22 | 2020-06-18 07:12
20200714 | 20200714006 | 6 | Mandatory Pre-Bid Meeting | A copy of the presentation. | A copy of the presentation can be viewed using the following links: https://wisconsindot.gov/Pages/doing-bus/contractors/hcci/bid-let/2020/20200714.aspx or ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/ | Jill Fehrman | 2 | 2020-06-12 14:19 | 2020-06-12 14:21
20200714 | 20200714006 | 6 | Preliminary boring info - Mt. Pleasant Potential Borrow Material | In the prebid presentation, Potential Borrow Material Section, it states that WisDot will provide info from preliminary Borings. Where is this information available at? Thank you | The soil borings for the potential borrow site can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/ | Mike Coleman | 3 | 2020-06-23 11:55 | 2020-06-24 15:01
20200714 | 20200714006 | 6 | Excavation RSC Restoration | Special Provisions RSC Restoration, Item SPV.0180.002 states that the department will pay separately for Excavation, Geotextile, Manholes, Underdrain and Storm Sewer furnishing and materials under other bids items in this contract. This leaves one to believe that the excavation required for the RSC Pond should be part of the common excavation. The earthwork Summary Table (plan sheet 413) does not include the RSC excavation quantity. Should it be included? Please calrify. | All information related to RSC including Excavation Common is shown on sheet 501. | Mike Coleman | 4 | 2020-06-23 13:16 | 2020-06-23 14:07
20200714 | 20200714006 | 6 | Existing Ground Surface in xml | Can we get the Existing ground surface file, in LandXML format vs the dtm format? | The existing surface in xml can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/Metadata/2_Existing Surface/ | Mike Coleman | 5 | 2020-06-23 13:52 | 2020-06-23 14:04
20200714 | 20200714006 | 6 | CAD Files Provided | When attempting to import the landXML file titled â€œCTH-KR-EASTâ€ into Civil 3d, an error message appears â€œNot a LandXML file. Please select another.â€ Can we have another copy of that file? Also is there a LandXML for CTH-KR-WEST? | The requested file can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/Metadata/11_Proposed Surfaces/ There isnâ€™t a LandXML file for the as-built finished surface for CTH KR-West (I-94 East Frontage Rd to CTH H). | Mike Coleman | 6 | 2020-06-24 08:39 | 2020-06-24 12:27
20200714 | 20200714006 | 6 | Connect Drain Tile - Miscellaneous Quantities | On page 497 of the misc. qtys, under the connect drain tile the three items listed (connect drain tile, storm sewer RCCP 12" & pipe underdrain unperforated 12") are all large quantities of undistributed. Can these items be eliminated or greatly reduced since there is no called out locations in the plan. | The designer will review and revise the quantities in an upcoming addendum. | Mike Coleman | 7 | 2020-06-24 10:39 | 2020-06-25 08:03
20200714 | 20200714006 | 6 | Temporary Construction Access Road | Can the temporary construction access road be made wider than 24 feet the detail on plan sheet 47 shows? If so, what is the maximum allowed (say due to TLE's)? Does Breaker Run have to be utilized? Can any or no material be used? | The â€œTemporary Construction Access Roadâ€ needs to be 24 feet wide. The Department has made commitments to stakeholders, property owners, TLE/FEE regarding haul road location and width, and obtained ACOE/WDNR permit for wetland impacts based on 24â€™ wide access road. The specs note in the material section, â€œObtain approval of the engineer for all materials and conform to the pertinent requirements of the standard specifications.â€ This will allow the contractor flexibility in what material they can utilize. Since maintenance is their responsibility it would be acceptable to use other types of materials for the access road. We will update the call out of â€œbreaker runâ€ to â€œmaterialâ€ shown on plan sheet 47 in the upcoming addendum. | Mike Coleman | 8 | 2020-06-24 11:55 | 2020-06-25 08:17
20200714 | 20200714006 | 6 | Temporary Railroad Crossing | Will relocated utilities be clear of the temporary railroad crossings? | Utility coordination with We Energies is ongoing, anticipated to be clear by the start of construction. | Mike Coleman | 9 | 2020-06-26 06:28 | 2020-06-26 06:29
20200714 | 20200714006 | 6 | Conditional Use Permits for batching | Do conditional use permits from the local municipality or County need to be obtained for concrete batching? Is that the â€œcoordination with localsâ€ that was referred to in the presentation? | Yes, a permit will need to be obtained for concrete batching. One possible location for batching would be the site along 90th Street. Batching will not be allowed on the Mt Pleasant site on the north side of CTH KR across from 56th Avenue. | Mike Coleman | 10 | 2020-06-26 06:31 | 2020-06-26 06:32
20200714 | 20200714006 | 6 | Trucking Restrictions | Are there any trucking restrictions anticipated in this contract, such as special reporting, permitting, badging or marking for trucks? | There are trucking restrictions in the neighborhood from Sta. 540+00 to the Pike River. All hauling restrictions are noted in the Special Provisions, article 10. Trucks are not required to use the placards that were implemented in previous projects as part of the Wisconn Valley Development Roads projects. | Mike Coleman | 11 | 2020-06-26 06:32 | 2020-06-26 06:33
20200714 | 20200714006 | 6 | Subgrade Stabilization | Is there a bid item to stabilize the subgrade with lime / fly-ash? | No there is not. | Mike Coleman | 12 | 2020-06-26 06:34 | 2020-06-26 06:35
20200714 | 20200714006 | 6 | Inclusion Plan | Where does the Inclusion Plan get submitted? Is it due prior to bid? | Submittal of an Inclusion Plan is not required for this contract. | Mike Coleman | 13 | 2020-06-26 06:36 | 2020-06-26 06:37
20200714 | 20200714006 | 6 | Prestressed Wall Panel Aesthetics | There were no aesthetic details in the plans for the prestressed wall panels. Is there something that is missing? | The precast panels will be plain with no aesthetics. | Mike Coleman | 14 | 2020-06-26 06:39 | 2020-06-26 06:39
20200714 | 20200714006 | 6 | Union Pacific Railroad temporary crossing | Per the specials for the UPRR railroad "the DOT has made no arrangements for a temporary grade crossing". And the "approval is subject to the discretion of the railroad". Therefore we reached out to the construction contact in the specials and were told to ask questions through the DOT. But they added a single sentence that makes this temporary crossing quite questionable. They said "We do not install xings for convenience or construction efficiency". If this cannot get done, then this dramatically effects the Mt. Pleasant borrow and basically eliminates the Temporary Construction Access Road bid item. Is there any reason why the DOT was unable to secure a temporary grade crossing with this particular railroad prior to bid to hep eliminate the risk to the contractor in getting a temporary crossing approved? What are the costs the contractors are to incorporate into their bid for accounting for either temporary railroad crossing? Assuming we can get them. | 1. The DOT has formally requested approval from the Union Pacific Railroad (UPRR) for this temporary construction crossing. UPRR denied the request because it occurred during the design process. They stated they would only consider it when itâ€™s requested by the contractor. They did not want to authorize the construction crossing unless the winning bidder determined that they would need it to complete their work. 2. See the â€œConstruction Detail â€“ Temporary Railroad Crossing (UPRR)â€ and â€œConstruction Detail â€“ Temporary Railroad Crossing (UPRR)â€ sheets in the plan for details. The construction crossings will be paid by the Department using the â€œTemporary Access Gates at CPRR, Item SPV.0060.007â€, â€œTemporary Access Gates at UPRR, Item SPV.0060.008â€ and the â€œTemporary Construction Access Road, Item SPV.0090.005â€ bid items. Both railroads will complete the work within the railroad track areas themselves, as shown on the Construction Detail sheets. The Department has reached an agreement with Canadian Pacific Railroad (CPRR) for this work at their crossing, and the Department will pay them separately outside of the contract. Because the Department has not reached an agreement with UPRR, it is the Contractorâ€™s responsibility to reach an agreement with UPRR. If that does occur, UPRR will submit invoices to the Contractor as they complete their work, which the Contractor will pay. The Department will then reimburse the Contractor through the â€œConstruction Crossing with UPRR, Item SPV.0055.002â€ bid item that will be added to the contract via Addendum #1. | Mike Coleman | 15 | 2020-06-26 10:01 | 2020-07-01 13:41
20200714 | 20200714006 | 6 | R.S.C. Items | -Sand/Woodchip Bed: for the double-shredded hardwood chips/mulch, what is the maximum size of the chips? -Compost: compost that is certified as wdnr S100 will not meet the ph spec stated. Talking with a local expert they stated it will be hard to find anything lower than 8.0 ph even if they would add sand (more like spec s1004), also I'm guessing that would defeat the purpose since there is a sand/woodchip bed directly below the compost layer. If the compost is certified as wdnr s100 but does not make ph spec will it still be allowed? -Construction: statement about tracked equipment less than 2000 lbs can drive on the gravel bed to more easily distribute media and place boulders as necessary. Is the 2000 lbs weight restriction of equipment correct? If so, this is a unrealistic to be able to build this pond since the boulders that will be needed to be placed in the boulder weir cascade will most likely be greater than the 2000 lbs weight restriction of the equipment. | - Sand/Woodchip bed â€“ shredded woodchips should be less than 6 inches long. - Compost â€“ The DNR S100 specifications do not include pH. We will revise the article subsection B.1.4 as follows in the upcoming addendum) B.1.4 Compost Place a 4-inch layer of compost on top of the sand layer within the pools of the RSC. Ensure that the compost is WDNR S100 certified or equivalent. - Construction â€“ Heavier equipment is allowed on the gravel bed provided contractor uses a timber or hardwood mat to distribute the weight of the equipment. | Mike Coleman | 16 | 2020-06-29 13:49 | 2020-07-01 06:08
20200714 | 20200714006 | 6 | Storm Sewer Excel Files | Please provide Storm Sewer/Structure data in excel format. | The storm sewer/structure data in excel format can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714006/ | Mike Coleman | 17 | 2020-06-30 16:22 | 2020-07-02 12:03
20200714 | 20200714006 | 6 | R-36-66 Bid item 0776 | Looking at bid item 0776 - it is noted as R-36-66 on the bid item, but the plan pages starting at page 938 has this as R-30-66. Which one is correct? R-36-66 or R-30-66? | R-30-66 | Mike Coleman | 18 | 2020-07-02 09:18 | 2020-07-02 10:00
20200714 | 20200714006 | 6 | EBS Backfill | Is there a reason the EBS must be filled with select crushed material? Could it just be filled with breaker run like the rest of the pavement structure? | Grade 1 Granular is consistent with the recommendations presented in the geotechnical report. Grade 1 Granular is utilized to facilitate pile installation and avoid pile drivability issues that breaker run may present. | Jill Fehrman | 19 | 2020-07-06 10:26 | 2020-07-06 14:24
20200714 | 20200714006 | 6 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch and Breaker Run? | The CY to Ton conversion factor used is as follows: 2 for Base Aggregate Dense 3/4 Inch 2 for Base Aggregate Dense 1-1/4 Inch 1.8 for Breaker Run | Jill Fehrman | 20 | 2020-07-06 11:37 | 2020-07-06 12:29
20200714 | 20200714006 | 6 | Stage 3 Storm Sewer Old Green Bay Rd to End of Project | To get the deep storm sewer installed in stage 3 from +/- sta. 590+00 (old green bay rd) to 595+50 (43rd ave) would DOT consider shutting this entire section of road down vs. having 2 sub-stages? It would basically consist of combining traffic control stages 3A & 3C together and then 3B would be from +/- 595+50 to end of project. This would greatly reduce the cost of any potential shoring that may or may not be needed to complete the storm sewer install and simplify the work area. | The existing CTH KR between Old Green Bay Rd to end of the project must accommodate local traffic at all times. 43rd Street is the only entrance to the subdivision on the southside. There has been a commitment made to the stakeholders, the general public, elected officials, municipalities, and county government to keep CTH KR open in this area to local traffic at all times. The contractor needs to bid as shown on the plan. | Mike Coleman | 23 | 2020-07-06 14:52 | 2020-07-07 08:53
20200714 | 20200714006 | 6 | Existing Pedestrian Bridge Abutment Removal | Sheet 46 shows a removal sequence for the existing box culvert at the Pike River, the details also have call outs for removal of the pedestrian bridge abutments and riprap. Is the abutment removal required as part of the removing old structure bid items (items 12 & 14)? It is not noted anywhere in the special provisions - these only refer to the culvert. | An addendum will be issued to include pedestrian bridge structure abutment removal as a pay item 203.0600.S.202, Removing old structure with minimal debris Station 565+95. | Mike Coleman | 24 | 2020-07-06 15:05 | 2020-07-07 08:54
20200714 | 20200714006 | 6 | SANITARY MANHOLE SURFACE TREATMENT | PLEASE CLARIFY THE COATING FOR THE SANITARY MANHOLES ITEM SPV.0060.601. SPECIFICATIONS CALL OUT A WATER BASED ACRYLIC COATING. OUR COATING SUPPLIERS DO NOT HAVE ACRYLIC COATINGS FOR THIS APPLICATION. MOUNT PLEASANT USES COAL TAR EPOXY. WOULD THAT BE AN ACCEPTABLE TREATMENT? | The following is the product we normally see: ConSeal CS-55, Water Based Acrylic Coating. Yes, coal tar epoxy is acceptable as well | Mike Coleman | 25 | 2020-07-06 17:29 | 2020-07-07 12:30
20200714 | 20200714006 | 6 | EBS Backfill Item | Is there a reason the EBS Backfill item must be select crushed material? Since the rest of the pavement structure is breaker run, could we just use breaker run for the EBS Backfill item as well? | This question was asked and answered as Question 19. No, Grade 1 Granular is consistent with the recommendations presented in the geotechnical report. Grade 1 Granular is utilized to facilitate pile installation and avoid pile driveability issues that breaker run may present. | Mike Coleman | 26 | 2020-07-07 08:59 | 2020-07-07 09:52
20200714 | 20200714006 | 6 | Structures B-30-143 and B-30-144 Reinforcing Quantites | Can you confirm that the Exterior Strip Bar(Top and Bottom) quantities match up with the bill of bars? In first review it looks like they don't match. | Quantities are correct, but there was an error on the bill of bars for a few rebar locations. These will be updated by addendum. | Mike Coleman | 27 | 2020-07-07 10:10 | 2020-07-09 07:46
20200714 | 20200714006 | 6 | Settlement during construction | According to the Geotech, it recommends that the embankment fill be placed to an elevation 4 inches above finished grade for approach embankments built within 500 feet of each abutment and 2 inches from 500 feet to 800 feet. Is this a requirement of the contract? If so how will it be paid? It appears in the contract now, Breaker run gets placed on the embankment at the end of 2021, then base course and concrete placed in the 2022. If the embankment and the breaker run settles, will the department pay for the additional base course to account for the settlement? Or will the contractor have to remove the already placed breaker run to place more embankment? According to the Geotech, it states 98% compaction is required within 800 feet of abutments. Is this a requirement? For all materials, embankment, breaker run and base course? | Place embankment fills as per the Geotech recommendation. If the settlement does not exceed the amount of overbuild fill, the fill should be removed down to finished subgrade elevation before placing the breaker run. We will update the embankment fill and excavation common quantities in the upcoming addendum. Place breaker run, base course and, concrete pavement after the settlement is complete. The Prosecution & Progress article, subsection Work Restriction, the ninth paragraph will be updated to include breaker run in the upcoming addendum Perform compaction according to article 52 and for all other items follow pertinent standard specification or special provisions | Mike Coleman | 28 | 2020-07-07 10:37 | 2020-07-08 08:08
20200714 | 20200714006 | 6 | RR Flagging at temp crossings | Will railroad flagging be required when using the access road temporary construction crossings where it crosses over the CPRR and UPRR? The spec is not clear if it is required here. | Flagging is necessary at RR crossings including temporary construction crossings and a pay item is included for that purpose. It is inherently included in articles 4, 8 and 9. However, to be more specific we will add a sentence to Article 4, M Temporary Railroad Crossings and Flagging in the upcoming addenda. | Mike Coleman | 29 | 2020-07-08 12:33 | 2020-07-08 13:28
20200714 | 20200714006 | 6 | Anchor Slab Construction | Please confirm if anchor slabs and structure approach slabs can be placed in 2021 before settlement period is completed. The provided schedule of operations shows all structure work being completed by end of stage 3 Nov 2021. |  |  | 30 | 2020-07-08 12:53
20200714 | 20200714006 | 6 | SPV.0035.02 EBS BACKFILL Line Item 658 | The item of EBS Backfill states the following: EBS Backfill, Item SPV.0035.002. A Description This special provision describes backfilling EBS Excavation with select crushed material. Can we use breaker run for this item due to the fact that the rest of the pavement structure shows breaker run? | An addendum was issued to change the EBS Backfill material to be breaker run or backfill granular grade 1. | Mike Coleman | 31 | 2020-07-08 16:28 | 2020-07-10 08:17
20200714 | 20200714006 | 6 | Bearing Details Sheet | B-30-145 calls out details for a beveled anchor plate on the "Bearing Details" sheet; however, there is not a bearing details sheet. Please provide the bearing details sheet or confirm that there are no beveled anchor plates required in these prestressed beams. | An addendum was issued to remove the beveled anchor plate. | Mike Coleman | 32 | 2020-07-08 16:38 | 2020-07-10 08:18
20200714 | 20200714006 | 6 | B-30-146 bearing details | B-30-146 calls out details for a beveled anchor plate on the "Bearing Details" sheet; however, there is not a bearing details sheet. Please provide the bearing details sheet or confirm that there are no beveled anchor plates required in these prestressed beams. | An addendum was issued to remove the beveled anchor plate. | Mike Coleman | 33 | 2020-07-08 17:26 | 2020-07-10 08:18
20200714 | 20200714006 | 6 | B-30-147 bearing details | B-30-147 calls out details for a beveled anchor plate on the "Bearing Details" sheet; however, there is not a bearing details sheet. Please provide the bearing details sheet or confirm that there are no beveled anchor plates required in these prestressed beams. | An addendum was issued to remove the beveled anchor plate. | Mike Coleman | 34 | 2020-07-08 17:39 | 2020-07-10 08:18
20200714 | 20200714006 | 6 | B-30-148 | B-30-148 calls out details for a beveled anchor plate on the "Bearing Details" sheet; however, there is not a bearing details sheet. Please provide the bearing details sheet or confirm that there are no beveled anchor plates required in these prestressed beams. | An addendum was issued to remove the beveled anchor plate. | Mike Coleman | 35 | 2020-07-09 11:25 | 2020-07-10 08:18
20200714 | 20200714006 | 6 | Rip Rap at Outlet Structures | "Rip Rap Medium to Elevation 727.50" is noted at all three outlet structures. This elevation is above the top of the ponds. Please clarify the appropriate amount of rip rap required at each outlet structure. | The riprap medium should be placed up to the rim of the outlet structure. For Pond L, that is an elevation of 719.30; for Pond M, that is an elevation of 693.00; for Pond N, that is an elevation of 660.00. | Mike Coleman | 36 | 2020-07-09 13:10 | 2020-07-10 08:20
20200714 | 20200714006 | 6 | Maintain, Remove and Dispose Field Office Left in Place Special Project 3763-00-74 | Please provide a list of current monthly expenses for this Field Office? Are the 6 modular office building units owned by the DOT or are they leased? If owned what was the purchase price? If lease, what is the monthly fee? Looks like Phone & Electric charges are paid off of invoice. Does this include internet, or is that incidental? | 1. Average monthly expense for electric and phone service which includes internet is currently $2,372. Electric and phone service including internet is included in the contract under SPV.0055.001 Maintain Field Office Left in Place Special Utility Fees Project 3763-00-74. All other monthly expenses for maintaining the field office are included in SPV.0135.001 Maintain, Remove and Dispose Field Office Left in Place Special Project 3763-00-74. 2. Modular office building units are owned by the DOT. Purchase price is unavailable as the purchase was incidental to the bid item SPV.0105 Field Office Left In Place Special as part of Contract ID 20180612005. The unit price of SPV.0105 Field Office Left In Place Special was $351,000.00. 3. Internet is included in the paid invoice under the SPV.0055.001 Maintain Field Office Left in Place Special Utility Fees Project 3763-00-74. | Mike Coleman | 37 | 2020-07-10 10:46 | 2020-07-13 10:41
20200714 | 20200714006 | 6 | Boulder Weir Cascade | Can the material used for the Boulder Weir Cascade Item be limestone boulders? |  |  | 38 | 2020-07-11 21:17
20200714 | 20200714008 | 8 | As built Plans | Are there any as built drawings available for the above-mentioned project? We need to identify the structural members, the layout of the diaphragms and any pertinent information affecting the work in order to perform an accurate take off. | The as builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714008/ | Mike Coleman | 1 | 2020-06-19 07:45 | 2020-06-19 07:50
20200714 | 20200714008 | 8 | Qualification Requirements | Does this project require SSPC-QP1 & SSPC-QP2 Certifications to perform the painting scope of work? | It is not required. | Mike Coleman | 2 | 2020-07-06 09:00 | 2020-07-08 07:50
20200714 | 20200714008 | 8 | completion date | Would you consider pushing a completion date out until the spring? Thank you. | No. The region needs the project to be completed this year. | Mike Coleman | 3 | 2020-07-07 11:47 | 2020-07-09 09:33
20200714 | 20200714009 | 9 | Progress Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200714009/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-06-23 11:40 | 2020-06-23 14:17
20200714 | 20200714009 | 9 | Asphaltic Surface | would the department consider pulling the special provision for Asphaltic Surface stating the mix needs to be a 5LT. If the contractor can make a larger stone it would be a lot better for the patches | Special provision 12 is being revised by addendum to a 5MT mix rather than a 5LT mix. Additionally, The Department will allow the use of a 3MT mix for the asphalt patching that needs to be done during the culvert replacements. Typical sections and Construction details in the plan are being revised by addendum to reflect the 3MT 58 28 S mix being used for asphaltic patching during the culvert replacements. | Mike Coleman | 2 | 2020-06-29 07:55 | 2020-07-07 14:33
20200714 | 20200714009 | 9 | Temporary markings on milled surface | Good morning. In looking at page 2 of 25 in the special provisions, it states that no milled surfaces are permitted over the weekend. If milled surfaces are left during the week, will the department add a temporary paint bid item for temporary pavement markings on the milled surface to accommodate the safe movement of the traveling public? It appears that the temporary epoxy bid item will be used only on the upper layer as the quantities would not support 2 applications. Can you please clarify your intentions as well as if an addendum will be issued to address this question? Thank you. | Match up pavement surface heights at centerline by the end of the work day is being removed via addendum from special provisions article 4. Additionally, item number 649.0105 Temporary Marking Line Paint is being added via addendum to allow temporary pavement markings during the week on milled surfaces. | Mike Coleman | 3 | 2020-06-29 09:44 | 2020-07-07 14:34
20200714 | 20200714009 | 9 | Culvert Replacement | Good morning, in looking at the pavement marking quantities on plan sheet 40, there are separate pavement marking quantities for each culvert location. Is it the departments thought process to have each culvert marked as it is completed, all of them marked when they are all complete, or some other combination? The quantities are not same day so that is where the question is coming from. Will an addendum be issued to address this question? Thank you. | Culvert locations can have pavement markings applied after all culvert patches have been completed. | Mike Coleman | 4 | 2020-06-29 09:57 | 2020-06-30 13:27
20200714 | 20200714009 | 9 | Driveways | Is it assumed being there is no Driveway quantity or detail, there is no intention on going into them | That is correct. No driveway work on this project. | Mike Coleman | 5 | 2020-07-08 08:34 | 2020-07-08 09:58
20200714 | 20200714009 | 9 | Traffic Control Signs | It does not appear that side road signing is included in the Misc. Quantities for Traffic Control Signs. Are side roads not to have advance warning signs on them? | An emergency addendum is being issued to include the side roads | Mike Coleman | 6 | 2020-07-08 10:45 | 2020-07-10 09:46
20200714 | 20200714009 | 9 | Schedule | The schedule provided by the DOT shows 2021 work in June and July, however, the special provisions state no work in 2021 until September 7th. Could you please clarify. | Addendum No. 01 was issued on Tuesday that changed the contract time for completion from a completion date of November 9, 2021 to a 70 working day contract. The addendum also modified the prosecution and progress article removing the September 7, 2021 start date. | Mike Coleman | 7 | 2020-07-09 10:55 | 2020-07-09 11:03
20200714 | 20200714009 | 9 | Asphaltic Surface Clarification | Addendum No. 1 changed Article 12 to require that a 5MT 58-28S HMA mix be used for the Asphlatic Surface bid item. However, the Typical Section for the Culvert Replacement Locations (revised sheet 6), and the Construction Details for the Culvert Pipe Transitions (revised sheet 9), shows that the mix type is to be a 3MT 58-28S for the Asphaltic Surface in these pipe patches. The revised special provision article and the revised plan sheets contradict one another. Can you please verify which mix is to be used for the Asphaltic Surface bid item? Also, will the Asphaltic Surface Patching bid item be restricted to a specific mix type, based on article 12, either 3MT or 5MT? | The asphaltic surface for full depth at the culvert replacements shall be 3MT. | Mike Coleman | 8 | 2020-07-10 11:40 | 2020-07-10 14:09
20200714 | 20200714011 | 11 | Removing Asphaltic Surface Butt Joints | There are up to 20 locations that could need a butt joint. Shouldn't an item be added? | The item will be added via addendum. | Mike Coleman | 1 | 2020-06-23 12:01 | 2020-06-25 11:34
20200714 | 20200714011 | 11 | Misc Quantities Tables | Could Miscellaneous Quantities Tables (storm sewer, culvert pipes and earthwork)be provided in EXCEL format? Thank you | The Miscellaneous Quantities Tables are not available for this project. | Mike Coleman | 2 | 2020-07-08 14:28 | 2020-07-09 08:41
20200714 | 20200714011 | 11 | Article #33 - Fence Chain Link Salvage 5-ft | Number of questions regarding this spec. #1 - Work scope is at the discretion of the engineer which pushes high risk to contractor. Can additional details be provided on anticipated work scope? #2 - If cast-in pipe sleeves are deteriorated will the concrete removal and replacement be paid as Concrete Surface Repair or is it incidental to this item? #3 - Bid quantity includes the entire length of fence. Will this be the pay quantity regardless of amount of repair required, or will payment be for only those areas directed for replacement by the engineer and those necessary for removal to access concrete repair areas? #4 - Has DOT considered simply removing existing fence system and replacing with new fence with base plates epoxy anchored to the deck to avoid future problems? | 1. There are no additional details, but we did modify the spec with Addendum 3. 2. Removal of the concrete inside the sleeve is incidental to the item, if removal of the metal pipe sleeve is necessary, removal of the deck will also be necessary, removal of the deck concrete will be paid for as concrete surface repair. 3. The special provision has been modified with Addendum 3 to require the entire fence to be removed. 4. AECOM is not aware of any considerations. | Mike Coleman | 3 | 2020-07-08 16:59 | 2020-07-10 07:55
20200714 | 20200714012 | 12 | HMA Density | On sheet 5 it shows the different thicknesses to be paved. We wanted to confirm that due to the variable thicknesses as well as thicknesses less than specified under 460.3.2 that the lower layer would be considered a leveling layer and fall under ordinary compaction? Technically we could take densities on the TWLTL and from Sta 448+54 to 450+41, but did not know if testing those areas on the lower layer is worth the additional costs. We also want to confirm ordinary compaction will apply to the surface layer on the 6ft paved shoulder and 2ft paved curb & gutter due to the variable thicknesses and thicknesses less than the minimums on 460.3.2. | The Lower Layer of the HMA will be considered a leveling layer and fall under the ordinary compaction. Ordinary compaction will also apply to the surface layer on the 6â€™ paved shoulder and 2â€™ curb & gutter. An Addenda will be issued to correct the items, plan and special provisions for this project. | Mike Coleman | 1 | 2020-07-07 17:51 | 2020-07-08 12:42
20200714 | 20200714012 | 12 | Shaping Shoulders | Should there be a Shaping Shoulders item and/or a prep item for the south end of the project (Sta 448+50 - 450+41) to push out the shoulders and pull them up during milling and to shape the areas to be paved with asphaltic surface for Stage 1 and Stage 2? | Yes, the Shaping Shoulders item should be a part of the contract and will be added by Addenda. | Mike Coleman | 2 | 2020-07-07 17:56 | 2020-07-08 12:43
20200714 | 20200714013 | 13 | Schedule | Due to the fact that this project was previously let in May with a Sept 1 completion date and now with a later Let date and the completion date being Oct. 30 would the department consider allowing the last phase of paving to be done in the spring if the weather in October turns cold as this is a tight schedule to complete and paving will be done towards the end of the month | It is our intent the work is completed by October 30 and should be bid as such. Should unusual weather prevent the work from being completed to the quality expected by WisDOT, then weâ€™ll address the issue at that time. | Jill Fehrman | 1 | 2020-07-02 11:43 | 2020-07-06 07:41
20200714 | 20200714013 | 13 | PCC Milling quantity change | Item #204.0109.S has changed from 448,437 sf to 396,593 sf. It appears all of the change is from Sta 47+24 to 67+09 (WB)/67+78 (EB) changed from 166,734 sf to 114,890 sf (almost a 30% decrease), with no changes in any other sections. I cannot find any change to the plans or typical section that show this change. Can you please let us know what changes to this quantity have occurred since the original May letting? | The quantity in the May letting was miscalculated and the area from this bid item was used to calculate 455.0605 and 460.6224. The quantity was corrected for the re-let in July. | Mike Coleman | 2 | 2020-07-06 15:29 | 2020-07-08 09:51