## qandasearchletting_results
Date: | 2020-08-10
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200811 | 20200811001 | 1 | Permanent Pavement Markings | Good morning. What is the expectation for placing the permanent pavement markings on this project? There is no same day item so daily would not appear to be the expectation even though the edge and/or center lines may be removed during the paving operation. The pavement markings are separated by stage so per stage would appear to be the expectation. Please advise as to what the departments expectations are as you are able. Also, on plan sheet #45 it is showing the typical detail with contrast markings that are also grooved in and there is not a bid item to place such markings. Could you please confirm you are not looking to have the center line markings contrast markings as shown on this typical? Thank you! | 1. It is the departments expectation that permanent pavement markings be completed within each stage. The special provision state that â€œThe contract time for completion is based on an expedited work schedule and may require extraordinary forces and equipmentâ€ bid accordingly. 2. The departments expectation would be to apply the permanent markings without contrast. | Mike Coleman | 1 | 2020-07-28 10:29 | 2020-07-29 08:04
20200811 | 20200811001 | 1 | Follow up on Pavement Markings | Thank you for your timely reply to the previous question, it is appreciated. Do you anticipated "within each stage" as a one time per stage mobilization or an "as needed", sometimes daily trip into the project? If it is one time per stage, I would think the current bid item would satisfy that requirement. If it is as needed daily, I would think the bid item should be a "same day" item and an addendum would need to be issued. Could you please clarify this, thank you. | The departments intent is to mobilize one time per stage. | Mike Coleman | 2 | 2020-07-29 13:12 | 2020-07-30 06:18
20200811 | 20200811003 | 3 | Seal Coat Aggregate | What size chip seal aggregate is the agency looking for on this project? | Standard specifications section 475 gives the aggregate gradation. | Mike Coleman | 1 | 2020-08-10 10:04 | 2020-08-10 11:02
20200811 | 20200811006 | 6 | Sediment control around existing pier | There is no erosion control detailed for the removal of the existing pier. There is a cofferdam bid item. Is it the Department's intent to use the cofferdam as a erosion control device during pier removal, or was there a different sediment control technique contemplated for pier removal? If so, does that mean the cofferdam is intended to encompass the piers? | It is the departmentâ€™s intent to use the cofferdam bid item for placement of the new piers as required in the pier details but not to use the cofferdam bid item as erosion control for removal of the existing pier. It is up to the contractorâ€™s means and methods to meet the intent of the Removing old Structure over Waterway with Minimal Debris bid item. Updates to the erosion control plan detail and quantities to clarify this intent are being considered and will be included in an addendum. | Jill Fehrman | 1 | 2020-07-14 16:18 | 2020-07-23 12:04
20200811 | 20200811007 | 7 | Waterproofing SPV.0105.01 Question | In reading the "Waterproofing Bascule Pier and Bascule Abutment, Item SPV.0105.01" specification section, the section appears to be a performance-based spec. Is there a qualified products list category that addresses this section, and if not, what is the process to submit a product to be utilized for this application? CIM Scrim is mentioned in one of the line items, and that combined with the performance specs, I would like to submit CIM 1000 for consideration on this project. Thank You, Graham Wilson | No, there is no qualified products list. See section B.2 of the specification for submittal requirements. If CIM 1000 meets the requirement of section B.2 of the special provision SPV.0105.01, it would be an acceptable product for the waterproofing bid item. | Mike Coleman | 1 | 2020-07-14 10:01 | 2020-07-15 10:10
20200811 | 20200811007 | 7 | Bridge Electrical Work | 1 - Specification page 43 of 452 states â€˜a new pad-mount cabinet will be installed at Broad Street and Racine Street to provide access to a redundant electric service for the bridgeâ€™. Specification page 224 of 452 under Incoming Bridge Power states we are to intercept existing conduits from MU that are installed within 10â€™ of the new utility transformers. Drawing 571 shows 4-4â€ underground conduits for power to MU along with a 2â€ underground conduit for fiber. Drawing 572, entry level appears to show disconnecting means and a junction box on the north side. No service disconnecting means are shown on the one line diagram (the ATS is shown inside). I assume the junction box is for the fiber. Please show the location of MUâ€™s cabinet or transformers and the location of the bridge power CT/meter cabinets. Also show a location for MUâ€™s fiber pullbox or vault. | The junction box is for fiber optic. The disconnect and meter cabinets are to be installed on outside building near entrance. The single line drawing will be updated and included in an addendum. | Jill Fehrman | 2 | 2020-07-14 18:39 | 2020-07-21 16:02
20200811 | 20200811007 | 7 | Bridge Electrical Work | Looking at the conduit schedule on plan sheet 622 for circuits 1 through 4, one 4â€ conduit is required from each transformer to each meter and then one 4â€ from each meter to the ATS. Drawing 571 shows 4 â€“ 4â€ underground conduit â€“ power â€“ (to Menasha Utilities). Please confirm if we are to install 1 or 2 â€“ 4â€ conduits to each meter and transformer. | 4 â€“ 4â€ conduits are required 2 will be spares | Jill Fehrman | 3 | 2020-07-14 18:40 | 2020-07-21 16:12
20200811 | 20200811007 | 7 | Bridge Electrical Work | Note 2 on plan sheet 574 states provide a generator plug but it is not shown on the one line nor mentioned in the specifications. Is one required and if so, provide size, location and how to integrate it into the electrical system. | Generator plug is not required. | Jill Fehrman | 4 | 2020-07-14 18:41 | 2020-07-21 16:15
20200811 | 20200811007 | 7 | Span Drives & Motors | Sheet 568 task E4 states 40hp motors and the 1 line diagram, sheet 574 shows 50hp. Confirm 50hp for the main motors please. | 50 HP for the main motors. | Jill Fehrman | 5 | 2020-07-14 18:41 | 2020-07-21 16:17
20200811 | 20200811007 | 7 | Bridge Electrical Work | Reference drawing 575 - Is there a disconnecting means required ahead of transformer T2 and is that arrangement a Mini Power Center NEMA 3R? | A local disconnect will be added to single line in addendum. Yes, Mini Power center NEMA 3R. | Jill Fehrman | 6 | 2020-07-14 18:42 | 2020-07-21 16:19
20200811 | 20200811007 | 7 | Traffic Gates & Signals | Where are the flashers located for the Advance Warning Signals, in a junction box at the pole or in the control cabinet? | The flashers for the Advance Warning Signals should be located in a junction box at the pole. | Jill Fehrman | 7 | 2020-07-14 18:43 | 2020-07-23 10:27
20200811 | 20200811007 | 7 | Bridge Electrical Work | Please indicate the fixture type shown on drawings 612 through 617. If they are type A fixtures, there does not seem to be any type C fixtures shown on any of the drawings. | They are Type A fixtures. No Type C fixtures are required. | Jill Fehrman | 8 | 2020-07-14 18:44 | 2020-07-21 16:21
20200811 | 20200811007 | 7 | Thickness of Fiberglass Sidewalk Plates | Plan sheet 393, 'Fiberglass Sidewalk floor Plate..' detail indicates that the sidewalk plate thickness is 1/2". Plan sheet 394 details in Section C-C and Connection Detail show 5/8" thickness. Which is correct? | 5/8â€ is the correct plate thickness. | Mike Coleman | 9 | 2020-07-22 09:06 | 2020-07-28 05:51
20200811 | 20200811007 | 7 | Lightning and Surge Protection | Lightning and Surge Protection - By not fully bonding rebar, the UL master label for lightning protection is not possible. Letter of Finding may be possible for the operator house. There are no UL listed stainless steel ground rods - note 5, plan sheet 594. Is the contractor responsible for re-designing the system to meet UL or bid according to what is shown on plan sheets 594 and 595? | The U.L. listed installer shall install the lightning protection system such that the a master label or U.L. letter of Finding can be achieved. This is for the Tender house only. Follow the ground rod spec in SPV.0105.13 section B.1. Plan will be updated with addendum. | Mike Coleman | 10 | 2020-07-22 10:37 | 2020-07-28 13:00
20200811 | 20200811007 | 7 | Brake Position | SPV.0105.06.B.3 page 166, paragraph 6 states that â€œWhen the bridge is in the closed position the brake will be horizontal. When the bridge is in the full open position the brake will be a 70 ï¿½ angle with actuator above the brake wheel.â€. Sheet 550 & 552 depict the brake being set at 45 degrees. Please verify which statement is correct. | The brakes are mounted at 45 degree angle per Sheets 550 & 552. SPV will be updated with addendum | Mike Coleman | 11 | 2020-07-22 11:38 | 2020-07-28 13:01
20200811 | 20200811007 | 7 | Brake Wheel Material | SPV.0105.06.B.3 page 167, paragraph 6 states the brake wheel shall be ASTM A276 Type 316 Stainless Steel. Per the brake vendor, this will result in an approximately 17% reduction in torque due to friction. Was this reduction considered in the required torque values specified on sheet 549, note 5? Would a cast iron material be acceptable for brake wheels? The cost of a stainless steel wheel would be 2-5 times the cost of cast. If a cast wheel is not acceptable, could Type 304 Stainless Steel be utilized. | Cast iron material is acceptable. SPV will be updated with addendum. | Mike Coleman | 12 | 2020-07-22 11:39 | 2020-07-28 13:05
20200811 | 20200811007 | 7 | Brake Torque | Sheet 549, machinery note 5 states the rated torque for the machinery brake is to be 2650 ft-lbs and sheet 550 states the brake is 16â€™â€™. Per manufacture, to achieve the rated torque a 19â€™â€™ drum brake would be required. Please clarify. | The rated torque given was for the pair of machinery brakes, not each. Plan will be updated with addendum. | Mike Coleman | 13 | 2020-07-22 11:40 | 2020-07-28 13:09
20200811 | 20200811007 | 7 | Brake Wheel | If 19â€™â€™ brake wheels are to be used, would the weldment need to be revised for the larger base plate and elevation to the center of the drum? | The machinery brakes wheels shall be 16â€ diameter. | Mike Coleman | 14 | 2020-07-22 11:40 | 2020-07-28 13:10
20200811 | 20200811007 | 7 | Materials | A majority of the brake fabrication/assembly is complete overseas (Germany, Italy, etc.). Please verify if the â€œBuy Americaâ€ clause is applicable to the machinery and motor brakes. | Buy America clause is applicable to the machinery and motor brakes. | Mike Coleman | 15 | 2020-07-22 11:41 | 2020-07-28 13:11
20200811 | 20200811007 | 7 | Couplings | SPV.0105.06.B.3 page 167, paragraph 6 states " do not use brake wheel couplings. Sheet 551 states "10'' drum type motor brake with double engagement gear type motor brake coupling(typ.)". Please clarify. | Do not use brake wheel couplings. Plan will be updated with addendum. | Mike Coleman | 16 | 2020-07-22 11:41 | 2020-07-28 13:11
20200811 | 20200811007 | 7 | Brake Operation Limits | Pre the brake manufacturer, due to an air chamber in the brake thrusters, the maximum operational limits for the brakes would be 15 degrees below horizontal. With the current 45 degree preset, the brakes would not release. If the brakes were installed horizontally, the thruster could be rotated 180 degrees for proper operation, otherwise the brakes could be preset to a minimum of 56 degrees. Please clarify. | Multiple manufacturers have provided brakes for various past projects with an angled installation as depicted. See Section A.6.7. Substitutions for substitution requirements due to arrangement of parts. If the contractorâ€™s selection of brake manufacturer requires mounting at an alternate angle then any associated costs with modifying the reducer weldment for proper fit shall be at contractorsâ€™ expense and no additional cost to the department. | Mike Coleman | 17 | 2020-07-22 11:42 | 2020-07-28 13:14
20200811 | 20200811007 | 7 | Bolt Size | Sheet 553 Section A-A states the turned bolts are to be 1 ï¿½â€™â€™ dia. while the elevation and trimetric drawings state the turned bolts to be 1 ï¿½â€™â€™ dia. Please clarify which diameter governs. | Turned bolt size for the bearing â€˜Aâ€™ hub is 1-3/4â€ as correctly shown on front view on same sheet. Plan will be updated with addendum. | Mike Coleman | 18 | 2020-07-22 11:42 | 2020-07-28 13:16
20200811 | 20200811007 | 7 | Bolt Material | SPV.0105.06.B.11.3 calls for high strength bolts to be ASTM F3125 Gr. A449. ASTM F3125 only covers A325, A490 F1852 and F2280. Please clarify. | Provide bolts, nuts, and hardened washers that conform to the requirements of ASTM Specifications F3125 Gr. A325. SPV will be updated with addendum. | Mike Coleman | 19 | 2020-07-22 11:43 | 2020-07-28 13:17
20200811 | 20200811007 | 7 | Section 410 WQC and Section 404 Permit | The Section 410 WQC and Section 404 Permit have been posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811007/ | The Section 410 WQC and Section 404 Permit have been posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811007/ | Jill Fehrman | 20 | 2020-07-23 11:55 | 2020-07-23 11:56
20200811 | 20200811007 | 7 | Concrete | Does the structural concrete and the concrete for seals need to be High Performance Concrete? | There is no high performance concrete required for this project. | Mike Coleman | 21 | 2020-07-23 13:00 | 2020-07-28 13:18
20200811 | 20200811007 | 7 | Structural Lightweight Concrete | With regards to the target unit weight of the lightweight concrete, is the 115+/-1 PCF the unit weight at 28 days or at Equilibrium? | The target unit weight of the lightweight concrete given in the bid documents is at equilibrium. | Mike Coleman | 22 | 2020-07-23 13:06 | 2020-07-28 13:20
20200811 | 20200811007 | 7 | Lightweight Concrete | How will testing of the air content in the lightweight concrete be performed as no Engineers or Testing Companies are HTCP certified using the roll-a-meter (Volumetric air content method)? A type B air meter cannot be used to measure the air content due to the type of aggregate used to make the concrete be lightweight. | The tester should have ACI basic Field Testing Technician certification sponsored by the Wisconsin Ready-Mix Concrete Association for the volumetric air test. | Mike Coleman | 23 | 2020-07-23 13:09 | 2020-07-28 13:24
20200811 | 20200811007 | 7 | Counter Weight Concrete | What is the acceptable range for the unit weight of the counter weight concrete? If the target unit weight is 149.0 PCF, what are the maximum and minimum acceptable unit weights? | There are no predefined maximum and minimum acceptable unit weights for the counterweight concrete. However, the design is based on 149.0 PCF and the contractor will be required to adjust the counterweight as necessary to achieve a balanced leaf condition as defined in the bid documents. | Mike Coleman | 24 | 2020-07-23 13:13 | 2020-07-28 13:25
20200811 | 20200811007 | 7 | Pier Demolition | Will cofferdams be required during demolition of the existing water piers to meet the Minimal Debris Removal Spec? | Cofferdams are not required for removal of the existing water piers. | Mike Coleman | 25 | 2020-07-24 08:49 | 2020-07-28 13:26
20200811 | 20200811007 | 7 | Schedule | Please provide preliminary DOT schedule for the project. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811007/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 26 | 2020-07-24 08:50 | 2020-07-28 13:42
20200811 | 20200811007 | 7 | Maintaining River Navigation | There will be a time period during the project that neither the existing bridge or the new bridge will be operational for opening/closing to overheight boat traffic. Per the Staging Specification, contractor is to 'Maintain river navigation during the navigation season'. Does this mean that at least one leaf of each structure must be able to be opened at all times during the navigation season to allow overhieght boat traffic to pass? Can DOT provide further details on the anticipated dates of the Navigation Season. | At least one leaf of each structure should remain open to maintain navigation during navigation season. Additionally, the contractor must maintain a navigation channel clear of equipment and barges during the navigation season. The USCG permit does not specify specific dates for a â€œnavigation seasonâ€. Per Special Provisions, Section 4d, USCG Permit â€“ Contractor needs to coordinate with the USCG 30 days prior to any work that impacts navigation. | Mike Coleman | 27 | 2020-07-24 08:59 | 2020-07-28 13:46
20200811 | 20200811007 | 7 | Contractor Operation of Existing Bridge | When does the contractor take over operation of the existing bridge? | The contractor takes over operation of the existing bridge when the Racine Street Bridge is closed to traffic in stage 2 of construction. | Mike Coleman | 28 | 2020-07-24 09:01 | 2020-07-28 13:47
20200811 | 20200811007 | 7 | Stabilization of Dredge/Excavated Materials | Landfills have indicated that the excavated material from the river may need to be stabilized with Portland cement or flyash prior to acceptance into their facilities to ensure stability of their slopes. If required by the landfill, would this be considered extra work? Would the added weight from the stabilization material be included in the pay quantity? | Soil borings show granular material and on-site dewatering is required, so stabilization treatment is not anticipated to be needed. If additional stabilization is required and documentation from the landfill is provided, staff could consider extra work. | Mike Coleman | 29 | 2020-07-24 12:51 | 2020-07-28 13:48
20200811 | 20200811007 | 7 | South Abutment Seal Layout | Please provide anticipated footprint of concrete seal for south abutment. Section C-C of sheet R02 of R43 scales to roughly 2'0" outside of new footing, however at 3'9" thickness this only calculates to 50% of plan quantity for seal concrete. | There is a note on sheet R01 of R43 (South Abutment) that refers the contractor to the â€œRip Rap Detailsâ€ sheet (drawing R43 of R43) for assumed cofferdam layout. | Mike Coleman | 30 | 2020-07-24 13:31 | 2020-07-28 13:49
20200811 | 20200811007 | 7 | Mandatory Pre-Bid Meeting | Could you post a roster of the people that attended the Pre-Bid Meeting? | The attendance list has been posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811007/ | Jill Fehrman | 31 | 2020-07-24 13:31 | 2020-07-24 13:34
20200811 | 20200811007 | 7 | Structure Excavation | Will all material excavated for Piers #1, #3, #4, and the Bascule substructure units be paid under the SPV. Exc., Haul, & Disposal of River Material pay item or only the portion that is determined to be contaminated? | Please refer to drawing G05 of G15 in the plan which includes general notes regarding pay limits for the excavation of river material. The assumption is that all excavated river material is contaminated and will be disposed of as such. | Mike Coleman | 32 | 2020-07-24 14:26 | 2020-07-28 13:50
20200811 | 20200811007 | 7 | Asphalt Questions | 1. On sheet 15 the detail showing the side road tie ins show a 4 MT with H oil. With the side roads being low volume would an LT mix be a better application. 2. For the Dam Access can a 12.5 mm mix be used with 1-3" Lift. | 1. Use asphaltic surface as shown in the miscellaneous quantities. A revised detail will be included in an addendum. 2. We will allow a single 3â€ lift with 12.5 mm nominal size for the Dam Access Road. | Mike Coleman | 33 | 2020-07-28 08:03 | 2020-07-31 07:32
20200811 | 20200811007 | 7 | North Bascule Abutment Concrete Quantity | Was an allowance included in the concrete quantities for the bascule abutment for additional footing thickness or was the 2'6" thickness used in the calculations? Can a breakdown of concrete quantities of both bascule substructure units be provided to help clarify discrepancies? | Yes, the expected variation in footing thickness was accounted for in the calculation of the footing concrete quantity. The estimated concrete quantities are broken down by substructure unit on plan sheet 313. | Mike Coleman | 34 | 2020-07-28 11:54 | 2020-07-29 13:43
20200811 | 20200811007 | 7 | Motor and Machinery Brake Mounting Arrangement | Drawing M4 shows the brakes mounted at a 45 degree angle with the bridge in the closed position. Section B.3 of specification (page 166 of 293) states that the brakes will be in a horizontal position when the bridge is closed. The brake manufacturer states the brakes will not function properly after the bridge is opened if mounted at the 45 degree angle with the bridge closed. Brakes must be mounted at a horizontal position when the bridge is closed. The brake manufacturer needs to be advised to the actual mounting position of the brake when the bridge is closed as this is a contradiction between the plans and the specification and affects the orientation of the thruster. | See responses to questions 11 and 17. The specification is updated in Addendum #1. | Mike Coleman | 35 | 2020-07-29 09:19 | 2020-07-31 06:57
20200811 | 20200811007 | 7 | Sidewalk Panel Attachment | Are sidewalk panels fastened to the underlying structural steel only at the splice locations as detailed on sheet 394 or are there additional fasteners required along the longitudinal edges as well? | Use the â€œCountersunk Bolt Connection Detailsâ€ on sheet 394 to fasten sidewalk panels to all supporting steel including sidewalk stringers with typical spacing of 5 ï¿½â€ as noted. | Mike Coleman | 36 | 2020-07-29 11:26 | 2020-07-31 06:58
20200811 | 20200811007 | 7 | Peninsula Parking Lot Use | What are the expectations and/or requirements for contractor use of the parking lot? Are there any size limitations or use restrictions? What kind of restoration work would be required? | Parking lot must be restored to pre-construction condition. Public access to the peninsula must be maintained during construction, but not within the contractor area. Refer to the traffic control plans. Contractor area must stay within the TLE as shown in the plat. Equipment size and limitations shall be determined by the contractor. No hauling across the Curtis Reed Plaza bridge is allowed. Addendum #2 will include asphalt quantity for restoration of the parking lot within the TLE. | Mike Coleman | 37 | 2020-07-29 12:03 | 2020-07-31 06:59
20200811 | 20200811007 | 7 | Concrete for the Bascule Pier and Abutment at Track | The plan states the required compressive strength for the concrete for the bascule piers and the abutment at track is 6,000 p.s.i. Does this concrete need to have 1.5" (#2 Stone) coarse aggregate or would 3/4" coarse aggregate (#1) Stone be acceptable? The reason for the question is with the larger aggregate, it will take more cementitious material to get the desired strength results; however, this will also lead to a higher potential for plastic shrinkage cracking!! Does it need to have 6% +/- 1.5% for an air content? How many yards of this concrete is on the project? | 1.5â€ aggregate is not required. Air content per Section 501. Limits of the 6,000 psi concrete are for those pours that encapsulate the track girders. Those are pour M for the bascule abutment (drawing P41) and pour K for the bascule pier (drawing P65). | Mike Coleman | 38 | 2020-07-29 12:37 | 2020-07-31 07:00
20200811 | 20200811007 | 7 | Lightweight Concrete to fill the open grid deck | Is corrosion inhibitor required as an admixture in the lightweight concrete mix? | No. | Mike Coleman | 39 | 2020-07-29 12:39 | 2020-07-31 07:01
20200811 | 20200811007 | 7 | Failure Critical Material | The structural set notes parts that are Fracture Critical Material (FCM). This requirement is not noted for any parts in the mechanical set. Are there any mechanical parts to be FCM? Possibly the bearing housing or rear lock components? | No. | Mike Coleman | 40 | 2020-07-29 13:19 | 2020-07-31 07:02
20200811 | 20200811007 | 7 | Bearing B | Plan PDF page 550 shows Bearing B, including a shaft, adapter, bearing, seal, and housing. These parts as specified in the plan set do not match. Please clarify. | This is not a question. Please clarify the what the question is. | Mike Coleman | 41 | 2020-07-29 13:20 | 2020-07-31 07:04
20200811 | 20200811007 | 7 | Secondary Reducer Fasteners | Plan PDF page 551 shows the secondary reducer connection to its support, which does not allow access to the threaded end of the bolt. Access is required for hydraulic tensioning. Are these fasteners to be hydraulically tensioned? | These fasteners are not required to be tensioned hydraulically. | Mike Coleman | 42 | 2020-07-29 13:22 | 2020-07-31 07:04
20200811 | 20200811007 | 7 | Center Lock Castings | Plan PDF page 383 shows the center lock castings. Can a forging be substituted for the casting material requirement of this part? | No. | Mike Coleman | 43 | 2020-07-29 13:23 | 2020-07-31 07:05
20200811 | 20200811007 | 7 | North Abutment Concrete Quantity - Follow Up Question | What is the expected variation in footing thickness and how much additional concrete does this add above the 2'6" nominal thickness. Our takeoffs are coming up significantly low for this substructure unit but were based on a 2'6" footing. Is there a further breakdown of the total concrete quantity for the two bascule substructure units (footings, exterior wall, floors, interior walls/supports) so we can try to find where our calculations differ? | No further breakdown will be provided. Footing thickness varies due to variation in the elevation of sound rock as evidenced by the soil borings. See plan sheet 426 for sketch of approximate variation. | Mike Coleman | 44 | 2020-07-29 13:57 | 2020-07-31 07:06
20200811 | 20200811007 | 7 | Navigation Season | In the special provisions it states that the water wary needed to maintain river navigation during navigation season. When will the area be allowed to not have navigation area open? | See response to question 27. The area may be allowed to not have navigation from mid-October to mid-April pending approval and after coordinating with the USCG 30 days prior, per Special Provisions, Section 4d, USCG Permit. | Mike Coleman | 45 | 2020-07-29 14:47 | 2020-07-31 07:07
20200811 | 20200811007 | 7 | Item SPV.0085.02, Steel Treads, Tracks & Centerblocks: E, Payment Unit LB? | These very labor and machining intensive items are typically bid as a lump sum and not by the pound, can payment be changed from "LB" to "LS"? | The department is comfortable with leaving the item as a unit of LB. | Mike Coleman | 46 | 2020-07-30 08:16 | 2020-07-30 12:59
20200811 | 20200811007 | 7 | Mechanization Bearing B | The specified Bearing â€œBâ€ bearing (23160 CCK/W33, SH M01 - Design Loads For Bearings) does not fit in the specified Bearing â€œBâ€ housing (23068 KA/12.5, SH M14 - Note 6). If bearing (23160 CCK/W33) is required, what is the required SKF housing part number? If the bearing housing (23068 KA/12.5) is required, what is the required SKF bearing part number? | Bearing 23160 CCK/W33 + OH 3160 H as listed on Sheet M14 Note 6 is the correct bearing. | Mike Coleman | 47 | 2020-07-31 15:42 | 2020-08-04 14:09
20200811 | 20200811007 | 7 | Mechanization Bearing B | What is the required Bearing â€œBâ€ housing material: Cast Steel (per pg 171 of 293, SPV 0150.06 B13) or SPHEROIDAL GRAPHITE CAST IRON (per Plan Set Pg 549, SH M01)? | Cast steel is preferred but if not available, SG cast iron is allowed. | Mike Coleman | 48 | 2020-07-31 15:43 | 2020-08-04 14:10
20200811 | 20200811007 | 7 | RPL Insurance Requirement | Can the Department explain the intent of RR Protective Insurance when the closest spur is more than 5 blocks away from the construction zone? | The project utilizes STH 114 as part of the detour route. There is a RR crossing at the intersection of 3rd Street and Tayco Street (STH 114). | Mike Coleman | 49 | 2020-08-03 13:37 | 2020-08-04 05:47
20200811 | 20200811007 | 7 | Geotechnical Report | Please provide a copy of the geotechnical report. | The geotechnical reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811007/ | Mike Coleman | 50 | 2020-08-04 10:55 | 2020-08-06 12:55
20200811 | 20200811007 | 7 | Aluminum Railing Material Issues | 1.) The sections specified have availability issues with the requirement of ASTM 6061, T6. The tubing 4x2 with round corners is not readily available, the 6x6 beam weighing 8.30lbs/ft is not available - what substitutions are acceptable for these materials? 2.)The assembly and welding of a wider variety of sections will result in welds that will be clearly visible and after anodizing will detract from appearance. Anodizing will be an issue as Grade 6061-T6 will not offer an acceptable cosmetic appearance and the welds will not be the same shade of color as the main structural sections. ASTM 6063 is a favorite allow for cosmetic work - will ASTM 6063 be an acceptable substitution. 3.) Anodizers in the Midwest region can't process material of this size and will be cost prohibitive over alternate materials. Has this been considered? | 1. Per question 60, the 4x2 with round corners is available. A 6 x 6 x 7.61 lb/ft is an acceptable substitution for the 6x6 beam. 2. ASTM 6061 is the required material because this is a for a structural application. 3. Yes, it was considered. There are no members longer than 9â€™ â€“ there are anodizers in Wisconsin that can process much larger sizes than this. Parts should be individually anodized as needed before bolting together. Past projects have been constructed with similar details. | Mike Coleman | 51 | 2020-08-04 11:18 | 2020-08-06 13:03
20200811 | 20200811007 | 7 | Aluminum Rail Fabrication Issues | The fabrication of this railing in accordance with plan sheet 421 and standard specification 513.3 will present problems for the manufacturer. The requirement that all joined corners shall be rounded to 1/8" radius when the item being joined is only 1/8" thick presents a problem. The requirements to cut the bottom of the post to make handrail posts vertical in both the transverse and longitudinal directions is not reasonably constructible to the standards that are required by the DOT. Can these details be modified to something more constructible? | Similar fabrication requirements have been used on past projects. Do your best to round the joined corners so they are not sharp. Shims at the bottom of posts may be used to correct minor misalignments. Details are constructible as-is and will not be modified. | Mike Coleman | 52 | 2020-08-04 11:24 | 2020-08-06 13:12
20200811 | 20200811007 | 7 | Pressure Grouting of Rock Allowance | Would the WI DOT consider providing a bid item allowance for potential pressure grouting rock at the north abutment and the south bascule pier? There may be existing rock fissures inside the cofferdams that will not allow the cofferdams to be dewatered at these locations. This unknown cost would be better determined during construction as to whether it is needed or not. | If existing fissures inside the cofferdam are discovered during construction, this would constitute differing site conditions and would warrant consideration of a CCO to resolve this issue. Based on geotechnical investigation completed to date, we donâ€™t expect rock fissures to be present. | Mike Coleman | 53 | 2020-08-04 11:26 | 2020-08-06 13:13
20200811 | 20200811007 | 7 | B.20 Spare Parts and B.21 Tools | B.20 specifies two drop forged steel wrenches for each sized fastener as well as two 36"x24"x78" permanent storage cabinets, and B.21 specifies one set of wrenches to fit all nuts and bolt heads in the machinery installation (as well as assorted screwdrivers, punches, etc.) and an additional cabinet. Is this a duplication and are three sets of wrenches and three cabinets required? | Yes, the intent is for three sets: B.20 describes two larger stationary storage cabinets to be located in each machinery room in order to store spare parts and tools in. B.21 describes a smaller cabinet or toolbox that is big enough to fit the wrenches and hand tools in, but that may be carried around onsite. | Mike Coleman | 54 | 2020-08-04 13:37 | 2020-08-06 13:20
20200811 | 20200811007 | 7 | 2" Rigid Conduit Quantity | Line item 0398 shows 244â€™ of 652.0125 Conduit Rigid Metallic 2â€, 240â€™ on the approach span. I cannot see where more than 100â€™ is shown on sheets 362 Conduit Plan and 364 Electrical Details at joints. There is only 3â€™ on either side of the joints except by 4 junction boxes where there is 10â€™ each on one side. Is there more quantity some where else on the approach? | The 240â€™ is correct. Drawings R40 of R43 & R42 of R43 show the correct limits of rigid metallic conduit. Rigid metallic conduit extends through approach span 5. | Mike Coleman | 55 | 2020-08-04 16:04 | 2020-08-06 13:25
20200811 | 20200811007 | 7 | Submarine Cable Excavation | How will the disposal of material being displaced by riprap in the submarine cable trench be paid? Will it be considered direct landfill material? | The material displaced by riprap will be paid with the item Hauling and Disposal of Dredging Material, item SPV.0195.04. | Mike Coleman | 56 | 2020-08-04 16:49 | 2020-08-06 13:26
20200811 | 20200811007 | 7 | cofferdam excavation | The limits of the cofferdams will be controlled by the fender systems bump outs(pg 431) and/or the retaining wall attachments as shown on page 461. This will require additional excavation beyond the pay limits of 3ft past the footing. Will the Department be paying for the additional excavation and disposal as required to ensure the cofferdams are large enough to accommodate the fender bump outs and the Retaining wall attachments? | No, the pay limits will remain as stated in the plans and specs. The cost of additional excavation and disposal due to larger cofferdams is incidental to the project. | Mike Coleman | 57 | 2020-08-04 17:06 | 2020-08-06 13:28
20200811 | 20200811007 | 7 | Warranty period clarification | Do all purchased components need to have a 5 year warranty based on Section C.4 of Mechanical Work Bascule Span Specification even though in the component sections state 12 month? | Yes, as stated in SPV.0105.06 Section C.4, mechanical systems require 5-year warranty. | Mike Coleman | 58 | 2020-08-05 08:45 | 2020-08-06 13:29
20200811 | 20200811007 | 7 | North bascule Abut. East Service Platform | Sheet 504 does not state the width of the stair treads for the East Service Platform similar to other sheets. | The stair width (between the channels) is 2â€™-6â€. | Mike Coleman | 59 | 2020-08-05 11:02 | 2020-08-06 13:29
20200811 | 20200811007 | 7 | Aluminum Railing Material | 4" x 2" x .125" tubing is not available in square corner. It is available in round corner. WF 6 x 6 x 8.3 is not available at all. | Provide round corner 4x2 per plan. For the WF, 6 x 6 x 7.61 lb/ft is an acceptable substitution. | Mike Coleman | 60 | 2020-08-05 11:23 | 2020-08-06 13:30
20200811 | 20200811007 | 7 | Seismographs & Vibration Monitoring | Has DOT considered adding items for seismographs, crack & damage surveys, and vibration monitoring due to the proximity of buildings to the new construction and demolition? | There is a Blasting section in the specs that covers crack/damage survey and seismograph use. See section 11c of the special provisions. | Mike Coleman | 61 | 2020-08-06 10:47 | 2020-08-06 13:32
20200811 | 20200811007 | 7 | Item #126 - Underwater Substructure Inspect, B-70-324 | Is the intent of this item to inspect the top of the seal concrete prior to dewatering the cofferdams? If so, what is to be gained through this inspection? The only surface that will be able to be inspected is the top since the top of seal elevation is below streambed elevation. | The intent of the bid item is to inspect to ensure the quality of Concrete Masonry Seal placed under water. The spread footing bears directly on the concrete seal, requiring the seal to be sound. | Mike Coleman | 62 | 2020-08-06 11:04 | 2020-08-06 13:32
20200811 | 20200811007 | 7 | Longitudinal Break Extruded neoprene seal | Reference Sheet 385 details 2 & 3: Does the department have a manufacturer and pattern/part number for the neoprene extrusion show in these details? | No | Mike Coleman | 63 | 2020-08-06 20:09 | 2020-08-07 08:18
20200811 | 20200811007 | 7 | Seismographs & Vibration Monitoring - Follow-up question | Section 11c refers to surveys and vibration monitoring for blasting but the costs are incidental to the rock excavation item, however no blasting is allowed for rock excavation. Please advise if the blasting and any necessary surveys and vibration monitoring should be incidental to the structure removal? | Yes, consider all costs associated with blasting, surveys and vibration monitoring as included in the structure removal costs. | Mike Coleman | 64 | 2020-08-07 06:50 | 2020-08-07 08:24
20200811 | 20200811007 | 7 | Aluminum Material | In regards to question 60, I had a mistake. 4 x 2 is NOT available in round corner, but is available in square corner. The channel rail is going to have square corners and would match a square corner top rail. |  |  | 65 | 2020-08-07 11:00
20200811 | 20200811007 | 7 | 6,000 PSI Concrete Bascule Pier and Abutment @ Track | Page 311 calls for 6,000psi concrete at the Bascule Pier and Abutment track; however, there is not a pay item for 6,000 psi concrete or qty for this indicated in the plan - Can a bid item be added or clarification to the qty required be provided? |  |  | 66 | 2020-08-07 12:58
20200811 | 20200811007 | 7 | Aluminum Beam WF 6x6 8.3 or 7.6 Pedestrian Rail | American Standard Aluminum Wide Flange Beams lists only 4 sections produced All are 6061-T6B WF 4x4x 0.313 4.758#/LF WF 6x6x 0.240 5.401#/LF WF 8x6.5x 0.245 8.321#/LF WF 8x8x 0.288 10.725#/LF Have not been able to find either of the sections that are listed as acceptable. Please Advise |  |  | 67 | 2020-08-10 12:50
20200811 | 20200811008 | 8 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The preliminary project schedule for the project has been posted at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200811008/ | Jill Fehrman | 1 | 2020-07-23 08:40 | 2020-07-24 12:28
20200811 | 20200811009 | 9 | Asphalt Pay Items | Due to the small quantities on this project and the type of paving, should the 3 MT and 4 MT pay items be combined and changed to Asphaltic Surface? | The Region reconsidered our approach on this and we will make a change to Asphaltic Surface. An addendum will be issued shortly for this updating plans and special provisions. | Jill Fehrman | 1 | 2020-07-22 17:38 | 2020-07-24 12:33
20200811 | 20200811009 | 9 | Anchor assemblies for Steel Plate Beam Guard | 58 614.0150 4.00 EACH Anchor Assemblies for Steel Plate Beam Guard is included in the bid items, but this is an item that typically refers to embedded anchors in a bridge parapet. this project has an M-rail, not a parapet. Is this bid item intended to cover the back up plate (note 7 on sheet 12 of the structure) that is noramlly incidental to the railing, or is this an error? |  |  | 2 | 2020-08-08 07:39
20200811 | 20200811010 | 10 | SIGNAL MOUNTING HARDWARE | PROPOSAL LINE NUMBER 0196 & 0198 ARE FOR SIGNALS, BUT THERE DOES NOT APPEAR TO BE A LINE FOR SIGNAL MOUNTING HARDWARE. IS SIGNAL MOUNTING HARDWARE NOT REQUIRED FOR THIS PROJECT, OR WILL THERE BE AN ADDENDUM TO ADD THIS LINE? | There will be an addenda submitted to address the missing bid item. | Jill Fehrman | 1 | 2020-07-20 11:13 | 2020-07-24 12:40
20200811 | 20200811010 | 10 | Traffic Signal Cabinet | Does the contractor need to supply the traffic signal cabinet, or is it being state furnished? If being state furnished, should there be a proposal line number for transport and install state furnished traffic signal cabinet? | The region will transport and install the cabinet. We do not need a bid item for this. | Mike Coleman | 2 | 2020-07-24 12:50 | 2020-07-27 10:48
20200811 | 20200811010 | 10 | 0220 SPV.0170 52.000 STA Special 01. Concrete Joint and Crack Cleaning and Repair | Is the intent to clean and fill all cracks and joints in the 52 station project? Or will the joints and cracks be selective? If so, what will be the determination of what crack/joint gets repaired and what does not? |  |  | 3 | 2020-08-04 09:37
20200811 | 20200811010 | 10 | Guardrail bid items | Is the plan missing MGS Guardrail Terminal Type 2's at the exit end of both stretches of guardrail? |  |  | 4 | 2020-08-07 10:26
20200811 | 20200811011 | 11 | Pavement Markings | Good morning. Can you elaborate more on when and how the permanent markings are to be placed? There is no temporary or same day item to cover operating on the milled surface and/or placing markings on the same day as the surface is applied. Thank you. | Permanent markings will be installed during Stage 2 during a lane closure. Permanent or temporary lane line markings will be required when two lanes in one direction of travel are open to traffic. An addendum will be issued to add temporary markings. | Mike Coleman | 1 | 2020-08-04 10:40 | 2020-08-04 14:09
20200811 | 20200811012 | 12 | Pipe Culverts | With the inclusion of ASP 6; Will thermoplastic pipe 24" and greater require 100% mandrel testing with this let? | Yes, please follow ASP 6 for current requirements. | Mike Coleman | 1 | 2020-07-16 08:23 | 2020-07-16 10:00
20200811 | 20200811012 | 12 | Protective Thermoplastic Coating at Snowmobile Trail Crossing - Material provider | Looking at bid item 0164 for the protective snowmobile crossing, the spec calls out PK Contracting as the manufacturer. I called them, and was told that they do not sell that material in this area, or provide installation instructions. Who will provide us as a contractor this information? Is the spec accurate? | The designer called the supplier. Recently, Geveko bought out Cleanosol for the thermoplastic coating at snowmobile crossings used by WisDOT. The special provision article needs to be updated to allow the new manufacturer name. Same material just a new company. At this time, we will leave the old item in since some contractors may carry a supply of this under the old name or they may obtain new material under the new name. An addendum is being issued to update the product in the special provisions. | Mike Coleman | 2 | 2020-07-28 13:52 | 2020-07-29 08:02
20200811 | 20200811012 | 12 | 48 hour milling requirement | Contractor is requesting that the Department consider allowing the exposed milled surface to remain open to traffic for a period not greater than 72 hours instead of 48 hours as per the special. In part this has to do with the job being PWL and requiring a test strip, and the unknown of the Prepare Foundation for Asphaltic Paving item could require additional time for repair per the special provisions. | The region has agreed to change the special provision to the following: â€¢ Do not allow the exposed milled surface to remain open to traffic for a period greater than 96 hours or during weekend non-working hours. This will be changed by addendum. | Mike Coleman | 3 | 2020-08-03 15:36 | 2020-08-04 09:52
20200811 | 20200811012 | 12 | Pavement Markings | Good morning. Can you elaborate more on when and how the permanent markings are to be placed? There is no temporary or same day item to cover operating on the milled surface and/or placing markings on the same day as the surface is applied. Thank you. | Please see the qtys on page 68 for ID 9110-10-70â€¦. â€¢ 649.0105 TEMPORARY MARKING LINE PAINT 4-INCH item covers the temporary centerline on the milled surface â€¢ 649.0120 TEMPORARY MARKING LINE EPOXY 4-INCH item covers placement of the centerline on the surface before the centerline rumble strips are placed â€¢ 646.1020 MARKING LINE EPOXY 4-INCH item covers the centerline placement after the centerline rumble strips are placed as well as edgelines | Mike Coleman | 4 | 2020-08-04 10:15 | 2020-08-04 10:35