## qandasearchletting_results
Date: | 2020-09-14
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20200915 | 20200915001 | 1 | approach milling for B-22-0059 | Are the approaches to be milled for this location to be milled to base course or will areas of existing HMA greater than 3" remain? Are butt joints to be removed to base course or tapered? | The existing typical section shows 3â€ HMA and the proposed typical calls for milling to a depth of 3â€ so it is expected to be to base course. Butt joints to be milled to 3â€ depth also. | Mike Coleman | 1 | 2020-08-24 11:32 | 2020-08-25 06:08
20200915 | 20200915001 | 1 | Finishing around wings | The wall Drain detail on Sheet 3 of 8 of the B-22-59 structure plan indicates that restoration behind the new wings is incidental to the Excavation for Structures item however quantities are listed in the Miscellaneous Quantities tables for these areas. Should the note in the structure plan be removed? | An addendum has been issued to remove the note on the structure plan. | Mike Coleman | 2 | 2020-09-08 12:18 | 2020-09-10 15:00
20200915 | 20200915001 | 1 | B-12-29 East Abutment Joint Repair | Can the concrete repair at the face of East Abutment diaphragm for B-12-29 be measured and paid as a separate item rather than included in the joint repair item since the quantity is unknown? This is very similar to Concrete Surface Repair which is paid by SF which protects both owner and contractor. | The quantity of joint repair will be measured by the SY of plan view area, no matter the depth. The depth at the east abutment diaphragm is dependent on the extent of delamination which is determined in the field. If the delamination does not meet the criteria for joint repair it will be measured and paid as concrete surface repair. | Mike Coleman | 3 | 2020-09-09 14:39 | 2020-09-10 13:48
20200915 | 20200915002 | 2 | Temporary Pavement Markings | Good morning. I am wondering if there should be a temporary paint item added to this project in case the milled surface is left for 24 hours (proposal states that is allowed, plan states pave same day)? Thank you. | The General Notes in the Plan and the Traffic Article in the Special Provisions state that HMA pavement is to be placed on the same day (within 24 hours) of milling to minimize damage to the remaining pavement. 70000LF for both Marking Line Same Day and Temporary Marking Line are included as items in the Miscellaneous Quantities on page 27 of the plan. | Mike Coleman | 1 | 2020-08-31 08:51 | 2020-09-01 05:44
20200915 | 20200915002 | 2 | Temporary Markings | Good morning and thank you for your prompt rely to our previous question. I do see the temporary epoxy and the same day epoxy items on plan sheet 27 which would appear to account for temporary markings on the surface daily after paving and prior to the rumbles being placed and same day epoxy on the same day after the rumbles are applied. I do not see any temporary markings included in the quantities that may be needed for the milled surface should the contractor choose to pave within 24 hours (page 3 of 28) rather than pave the same day (plan sheet 2). Will the department issue an addendum to include these temporary quantities that may or may not be needed? Thank you. | After further review we are going to be creating an addendum to change the language in the general notes to pave within 24hrs to match the special provisions and also add temp paint to the quantities. | Mike Coleman | 2 | 2020-09-01 07:20 | 2020-09-02 10:31
20200915 | 20200915002 | 2 | 418 Ton Asphaltic Surface for Distressed Pavement Milling | Please verify the quantity for this item. Based on 2135 S.Y. of Distressed Pavement Milling @ 2" = 240 ton. Am I missing something? | The 418 ton of asphaltic surface is comprised of 240 ton for the distressed milling, surface for the pipe replacement and also the shoulder widening. We are modifying page 3 to show adding a 2â€™ wide layer of 3â€ of asphaltic material for the shoulder widening and will update via addendum. | Mike Coleman | 3 | 2020-09-01 13:13 | 2020-09-02 10:34
20200915 | 20200915002 | 2 | 418 ton Asphaltic Surface for Distressed Pavement Milling Response | So if the 418 ton of Asphaltic Surface includes the culvert patches, then what is the tonnages of Asphaltic Surface at stations 210+07, 218+52, 306+90, and 333+63 used for? | An addendum is being issued that breaks down asphaltic surface by location. | Mike Coleman | 4 | 2020-09-03 07:35 | 2020-09-03 09:55
20200915 | 20200915002 | 2 | Time between Milling and Paving | Can the time between milling and paving be changed to 48 hours to allow time to prep and pave the 3" Asphaltic Surface in the 2' shoulder widenings? This will also give more time to mill and pave distressed patches and create separation between the milling work zone and paving work zone to help move traffic through the job. | I misspoke in my previous response. We are staying with the language below from the special provisions in reference to the single lane restriction to a single continuous length not exceeding 1.5 miles. Maintain traffic on STH 60 and intersecting roads during construction. Traffic may be restricted to a single 12 foot wide lane and 4 foot shoulder during working hours. Limit the single lane restriction to a single continuous length not exceeding 1.5 miles. Hold traffic for no more than 15 consecutive minutes per direction with the work zone lane closure. If traffic delays become longer than 15 minutes, coordinate with the engineer to limit or alter construction operations to prevent undue inconvenience to the traveling public as specified under standard spec 108.5. | Mike Coleman | 5 | 2020-09-08 13:35 | 2020-09-09 13:38
20200915 | 20200915003 | 3 | drilled tie bar length | Sheet 6 shows drilled tie bar length being 2"-0' long is that correct or should the length be 1'-0"per SDD 08D16-11 | The length in the detail is incorrect. The length should be 1â€™0â€ per SDD 08D16-11. An addendum will be issued to clarify. | Mike Coleman | 1 | 2020-08-28 11:41 | 2020-09-01 05:45
20200915 | 20200915004 | 4 | Temporary Pavement Marking | Special Provisions - Section 3 Prosecution and Progress, the last paragraph in this section references Temporary Pavement Markings. "Temporary pavement markings shall be placed same day and shall be placed in the exact configuration where permanent pavement markings will be placed" ; however there isn't any quantities listed in the MQ's for this project. Page 43 of the plan also calls out 4" Temporary Tape to be placed across the exit ramp at the Kilbourn tunnel. Please review any required Temporary Pavement Markings. Thank you | This will be addressed via addendum. | Mike Coleman | 1 | 2020-08-18 10:28 | 2020-09-02 09:09
20200915 | 20200915004 | 4 | Special Provisions - Section 33 Traffic Control Signs Removal | In the Special Provisions - Section 33 "Traffic Control Signs Removal", can the following wording be clarified: "Remove all signs on temporary mounts and other potential associated hazards to the traveling public from the right-of-way when not in use" 1. Please define "when not in use". Is the intent of this to remove temporary signs every day when not in use, or is it when not in use for a specific duration - IE 7 days? 2. Please define "other potential associated hazards to the traveling public". Is this strictly for traffic control signs, or does this encompass any hazard to the traveling public such as broken down vehicles, garbage, tires, etc? Thank you |  |  | 2 | 2020-08-18 10:39
20200915 | 20200915004 | 4 | Kilbourn Tunnel Area Interim LD's Requirements | The Interim Liquidated Damages section doesn't list the restoration work or signing as required inside the 120 calendar day restriction. Will nightly ramp closures be allowed after the long term closure to complete this work? Also, bid item 631.0300 Sod Water is not included in the bid items. Can it be added, is it incidental to the sod, or are others maintaining the sod after the ramps are open? | Nightly lane and ramp closures will be allowed after the Interim completion date noted to perform restoration work or signing in compliance to the timeframes allowed in the special provision and with the approval of the engineer in the field. This will be addressed via addendum. | Mike Coleman | 3 | 2020-08-26 09:32 | 2020-09-02 10:47
20200915 | 20200915004 | 4 | Item 509.0500 Cleaning Decks for Structure B-40-292 | This bid item is usually for the removal of the deck overlay. For this structure it appears that this quantity matches the quantity for Item 509.9010.S. Is there additional material to be removed under the existing asphaltic overlay? No other mention of what this work is. The Cleaning Decks for Structure B-40-429 is clearly spelled out as a removal item. | General note on plan sheet 258 states the following: Remove existing membrane waterproofing below existing asphaltic overlay completely before cleaning the deck for placing new concrete overlay. Cost included in the bid item â€œRemoving Asphaltic Concrete Deck Overlay B-40-292â€. Standard spec 509.3.3 (2) 1. Clean the entire surface of the bridge deck or approach pavement receiving the new concrete by using a suitable mechanical scarifyer. Accomplish this in a way that prevents hooking or tearing the reinforcing steel and that removes at least one inch of concrete from the deck or pavement surface but not more than the maximum depth the plans show. | Mike Coleman | 4 | 2020-08-28 10:18 | 2020-09-01 05:42
20200915 | 20200915004 | 4 | hydro demo | In the spec 56 A.1 it states that hydro demo â€œequipment shall be capable of operating at 35,000 psi and 32 gallons per minuteâ€. 95%+ hydro demo contractors utilize 20,000 psi pumps to perform robotic hydro demo. 20,000 psi is the industry standard so I am not sure how they came up with this specification. Can you please verify that this is acceptable. I can direct you to several hydro demo equipment OEMs if more support of this information is needed. | If the contractor believes they can perform the required work with lower PSI equipment, they will be allowed to do so. | Mike Coleman | 5 | 2020-09-02 11:03 | 2020-09-08 06:17
20200915 | 20200915004 | 4 | Hydro- Demolition SPV.0180.4302 | Prior to the hydro-demolition process would it be permissible to use a conventional mill to remove the top 1.5" of material? |  |  | 6 | 2020-09-09 14:26
20200915 | 20200915004 | 4 | Traffic Control for Bridge Painting | Is the intent to have all painting work on Structure B-40-429 completed during nighttime closures only, or will long term lane closures be allowed? All painting is listed under Phase 2 construction which only allows for nighttime closures and would require removal of containment system at the end of every shift. |  |  | 7 | 2020-09-10 15:24
20200915 | 20200915004 | 4 | Design Schedule | Can the design schedule please be provided? |  |  | 8 | 2020-09-10 15:33
20200915 | 20200915005 | 5 | Marking Removal Line 4-Inch | In regards to Pavement Marking removals, there is a bid item for 8" removal, however there isn't an item for 4" removal. It appears that 4" removal will be needed at the cross-overs, the lane shifts at Sherman Road, and the lane shifts at the Pleasant Valley ramp reconstruction areas. Please review estimated quantities for this item, if needed. Thank you | We will add a 4â€ removal quantity to the plan. In addition, we will be increasing temporary marking quantities to account for interim conditions. Updated plan sheets and quantities will be included in an upcoming addenda. | Mike Coleman | 1 | 2020-08-20 14:24 | 2020-08-25 12:25
20200915 | 20200915005 | 5 | Lane Closure time clarification | Hello, we are requesting a clarification on the allowed lane closure times. First, on the sections north of STH 33 - the Special Provisions state that there aren't any restrictions to lane closure times. If the contractor is working daytime hours Monday - Friday, will the closures be allowed to stay up all week? Or will the closures need to be removed nightly when work is not actively occurring? We would like a similar clarification for the work south of STH 33 as well; can the closures be left in place with the exception of the peak hours listed in the Special Provisions? For example on Southbound if the contractor works from 9am to 10pm, does the lane closure need to be opened immediately or does it just need to be opened up by 6am the next day? Thank you | Due to the lower traffic volumes, there are no restrictions for lane closures north of STH 33. Lane closures in this section could remain multiple days. | Mike Coleman | 2 | 2020-08-20 14:37 | 2020-08-24 06:13
20200915 | 20200915005 | 5 | Concrete Patching | When the concrete patching work is ongoing, can the holes from the removals be left open for several days and be filled in at the convenience of the contractor, or will they need to be filled in during that same shift? | During concrete patching work, the plan intent is to remove and replace concrete pavement during the same work shift. | Mike Coleman | 3 | 2020-08-26 13:19 | 2020-09-01 09:25
20200915 | 20200915005 | 5 | Existing Concrete Pavement | In the areas in the typical sections that state there is reinforced concrete pavement, what type of reinforcement is there in these sections? Continuously, mesh, dowel bars, etc? | Concrete pavement constructed in 1989/1990 â€“ sections with 14â€™ wide outside lanes â€“ was reinforced with dowel bars during construction. The dowel bars were change ordered in during construction and the notation is not included in as-built plans. | Mike Coleman | 4 | 2020-08-28 09:05 | 2020-09-01 09:28
20200915 | 20200915005 | 5 | Existing Concrete Pavement Non Reinforced | Does the existing concrete pavement that is listed as non-reinforced have any dowel bars or any steel in the concrete? | The non-reinforced concrete pavement constructed in 1985/1986 â€“ sections with 12â€™ wide outside lanes â€“ does not have any known reinforcement. However, if found, the removal of reinforcement is incidental to the Removing Pavement bid item. | Mike Coleman | 5 | 2020-08-28 09:10 | 2020-09-01 09:30
20200915 | 20200915005 | 5 | As Builts | Could you provide as-builts for the the NB and SB lanes throughout the limits of this project? | The as-builts can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915005/ Deanna, please create a link in the SE Region Preliminary Plans Page for proposal #05. | Mike Coleman | 6 | 2020-08-28 09:10 | 2020-09-02 08:50
20200915 | 20200915005 | 5 | Diamond Grinding | Are we able to place the slurry discharge from the Diamond Grind onto the shoulder slopes throughout the project? | Plan intent and coordination with WDNR is to haul slurry offsite due to proximity to wetlands and lowlands. Contractor needs to work with WDNR to identify locations where slurry may be disposed of. | Mike Coleman | 7 | 2020-08-31 13:38 | 2020-09-01 09:32
20200915 | 20200915005 | 5 | Cold Weather Pavement Marking | With a completion date of 11/30/21 can there be consideration given to add Cold Weather Epoxy to this project? Depending on weather, there may not be warm enough temperatures to install final pavement markings within manufacture specifications, especially the contrast tape. Thanks | Cold weather Epoxy will be added to the project via addendum 2. | Mike Coleman | 8 | 2020-09-04 16:05 | 2020-09-09 14:30
20200915 | 20200915005 | 5 | Temp shoring B-66-64 | Is there no temporary shoring required for wing wall removal and replacement for B-66-64? | The roadway work associated with the mainline pavement and concrete approach slab replacement requires a full freeway closure in this segment of NB USH 45. Sheet 4 of 6 on the B-66-64 structure plans shows the removal and replacement of the existing wingwall and backfill behind the new wingwall utilizing this USH 45 closure. Temporary shoring is not required if utilizing the traffic control and structural details provided. | Mike Coleman | 9 | 2020-09-10 07:19 | 2020-09-10 09:42
20200915 | 20200915005 | 5 | Permanent Markings | What is the expectation for installing the permanent pavement markings on this project. Tape cannot be installed the same day as diamond grinding due to manufacturers recommendations and the fact that water will be used in the diamond grinding process as well as the 5 day wait period for grooving on asphalt. Also, can you elaborate on where and when the same day epoxy item will be used? Thank you. | Expectation is that permanent pavement marking will be placed as soon as possible following WisDOT and manufactureâ€™s recommendations. The exception is in areas where future traffic control is needed. Same day marking is expected for the dashed lane line between lanes 1 & 2 each day after diamond grinding or mill and overlay operations are completed. | Jill Fehrman | 10 | 2020-09-10 09:44 | 2020-09-11 14:06
20200915 | 20200915005 | 5 | Traffic Staging | The staging plan shows the barrels being placed inside the work area during the short term non peak work time. Can the barrel be placed over the centerline and traffic run on the shoulder | The new 4â€ HMA shoulders do not fix existing base or subgrade issues and have not been designed to support traffic during construction. The shoulders are only shown as being fully reconstructed in segments where the current traffic control plans show traffic shifted to the shoulders. | Mike Coleman | 11 | 2020-09-10 10:41 | 2020-09-10 13:39
20200915 | 20200915005 | 5 | B-66-54 Hwy NN Traffic control | I don't see on the plans where the traffic control on Hwy NN for the work on B-66-54 will be handled. | Single lane operations are proposed for the traffic control on B-66-0054 using Item 661.0100, Temporary Traffic Signals for Bridges B-66-0054. SDDs are included in the plan for the Bridge Temporary Traffic Signal Installation and Traffic Control, One Lane Road with Temporary Signals. | Jill Fehrman | 12 | 2020-09-10 11:38 | 2020-09-11 10:17
20200915 | 20200915005 | 5 | Beam Guard Grading Earthwork Summary | I'm wondering if there is a detailed earthwork summary available that breaks down the beam guard grading items on sheet 237. | The spread sheet containing earthwork detail in the areas where beam guard grading is required can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915005/ | Jill Fehrman | 14 | 2020-09-10 12:18 | 2020-09-11 10:34
20200915 | 20200915005 | 5 | Concrete Patching | Will the contractor be allowed to patch prior to or extend after the allowed times for full closures with single lane closures? | Work related to patching could be done with single lane closures as long as the lane closure restrictions given in the special provisions are followed and it conforms to section 104.6.1.2.3 of the standard specifications. | Jill Fehrman | 15 | 2020-09-11 07:16 | 2020-09-11 14:05
20200915 | 20200915005 | 5 | Reconstruct Section | What grades are we supposed to go off of for the reconstruct section in NB? How do we know how much material to add or remove in this section? How will this section be staked? | The proposed pavement will be replaced in the same vertical location. All survey is covered under bid item SPV.0105.01 Survey Project 2220-02-70. Contractor is responsible for surveying existing pavement profile and then staking proposed pavement. | Jill Fehrman | 16 | 2020-09-11 09:24 | 2020-09-11 14:07
20200915 | 20200915005 | 5 | Concrete Patching | With your response to the question about extended patching times does this allow us to remove and replace patches up to the crown point/center line or do we have to maintain the four foot clear zone of center line? If we don't have to maintain the four foot clear zone would this allow us to remove and replace patches, under a single lane closure, during the day outside of the restricted hours? | The project should be constructed as indicated in the plans and specifications where concrete repair and replacement and base patching will be completed during nighttime full mainline USH 45 closures. | Mike Coleman | 17 | 2020-09-12 09:00 | 2020-09-14 13:15
20200915 | 20200915005 | 5 | Can the Design Schedule be provided? | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915005/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 18 | 2020-09-13 22:11 | 2020-09-14 08:20
20200915 | 20200915005 | 5 | Concrete Patching Clarification. | Please clarify that all Concrete SHES Base Patching, Concrete Repairs and Replacements will be required to be performed during the full closure period from 9:00pm to 5:00am and none of this work will be allowed to be performed during single lane closures. The prior questions and responses have made this less than clear. On USH 41 near this project with heavier traffic all the Base Patching was performed during the day time hours even when it was specified south of STH 60 to be done at night. It is very expensive to perform this work in the extremely limited time frame above at night. |  |  | 19 | 2020-09-14 14:48
20200915 | 20200915006 | 6 | Wisc Dot September letting job #6 | Will the PCC Base Patch bid item require drilled dowels and pavement ties.The exisiting pavement in the base patch concrete locations isnt identified as doweled existing pavement. | The existing underlying concrete pavement is doweled. The Base Patching Concrete item will require Drilled Tie Bars and Drilled Dowel Bars. An addendum will be issued to revise the Drilled Tie Bar item quantity and add the Drilled Dowel Bar item. | Mike Coleman | 1 | 2020-08-26 09:37 | 2020-08-27 12:49
20200915 | 20200915006 | 6 | Patching | 1) For the Base Patching Asphaltic item, is there a minimum size and depth? 2) For the Asphaltic Surface Patching item, what is the intended use and scope of the item? | 1. Minimum is the full pavement depth of 7 inches before milling or 4 inches after milling. Base patching is for areas of pavement distress on the asphalt pavement, just like concrete base patching is used on concrete pavement, and follow the same dimensional sizing. Also Base patching is for the signal loop replacement. 2. Asphaltic Surface Patching is for filling potholes or patching the surface in an emergency. | Mike Coleman | 2 | 2020-09-08 12:20 | 2020-09-10 13:37
20200915 | 20200915006 | 6 | Base Patches | Typically asphaltic base patching is done prior to milling to provide for a better ride. Will patching be done prior to milling on this project? Also, will the concrete base patches be completed to top of existing pavement? | The milling will be first to verify if patching is needed on the lower layers. The concrete pavement should be placed to match the existing concrete. This will allow for a leveling layer prior to the final surface overlay. | Jill Fehrman | 3 | 2020-09-10 17:21 | 2020-09-11 14:03
20200915 | 20200915008 | 8 | Temporary Markings | Good afternoon. Would it be prudent to add a temporary epoxy item to be installed on the paved surface daily prior to the rumble strips being installed so as to provide a better layout for the rumble machine? We have seen other projects that are designed in similar fashion (using TRPM's) that ultimately want to have a more formal layout than using the TRPM's in advance of the rumbles. Thank you. | After review and discussions with teams on previous projects, the rumble strips have been successfully installed using the pavement joint as the guide, while using the TRPMâ€™s to maintain traffic. Temporary same day stripping of the centerline is a significant cost increase over using the TRPMâ€™s. The design team did evaluate the advantages of placing temporary pavement markings in lieu of the TRPMâ€™s on the centerline, but the benefits did not justify the increase in cost. No changes in quantities or items will be made in regards to this inquiry. | Mike Coleman | 1 | 2020-08-31 14:01 | 2020-09-01 10:15
20200915 | 20200915010 | 10 | Design Schedule | Can a copy of the depart's anticipated schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915010/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-08-26 13:01 | 2020-08-27 10:08
20200915 | 20200915010 | 10 | B-5-260 overlay limits | Overlay limits on B-5-260 plan sheet extend to the front face of the type W railing. This doesnâ€™t leave room for overlay machine screed pipe. Can overlay limits be reduced 6â€-9â€ in order to accommodate? This would make overlay limits 42.5â€™ â€“ 43â€™ vs the 44â€™ in the plan. | The entire width of the 3â€ existing asphaltic overlay must be removed as shown on the plans. The removing 1â€ minimum of existing deck and concrete overlay limits may be reduced by up to 6â€ from the face of the rail, provided that the new concrete overlay matches the elevation of the existing deck outside of the overlay limits. Any areas of deck preparation identified by the engineer in the field outside the overlay area, shall be completed with a neat saw cut parallel and perpendicular to the deck centerline at a minimum of 1â€ deep and will be paid for under the contract items for deck preparation and masonry. | Mike Coleman | 2 | 2020-08-27 09:49 | 2020-09-02 10:45
20200915 | 20200915010 | 10 | 9190-20-71 Crown Location in Reconstruct Area | The typical sections and x-sections appear to show the crown (reference line) offset 6' from center line in the reconstruct area from approximately station 261+25 to station 282+02. Did the designer intend to do this? The plan sheets do not appear to show the reference line moving away from the center line. | The crown reference line was intentionally left off the plan sheets. See the intersection detail sheets for the crown reference line through the reconstruct area. The intent is to move the crown point 6â€™ from the former center of the road to the edge of southbound through lane and new left turn lane. | Mike Coleman | 3 | 2020-09-08 13:41 | 2020-09-09 13:26
20200915 | 20200915010 | 10 | Removing Asphaltic Surface Milling Prior to CIR | After the 3" of asphalt surface milling is it the intent to leave the 2' of gravel shoulder on the NB lane and incorporate all the existing shoulder material in the CIR or will this area be milled 3" flush with the milled surface and included in the milling quantity? | The intent is to leave the 2â€™ gravel shoulder on the NB lane and incorporate the existing shoulder material into the CIR. | Mike Coleman | 4 | 2020-09-08 14:32 | 2020-09-09 13:25
20200915 | 20200915010 | 10 | Milling and Paving Round-A-Bout CTH B/ Crest Drive | The specials allow for 1 day to mill and pave the RAB at CTH B & Crest Drive. It is unlikely that this work could be completed in 1 day. Would the department consider allowing 1 day for milling and 1 day for paving? | The department would consider allowing closing one day for milling and one day for paving if the roundabout could be open to traffic overnight between operations. An addendum will be issued to revise the roundabout closure language. | Mike Coleman | 5 | 2020-09-08 14:41 | 2020-09-10 09:45
20200915 | 20200915010 | 10 | Pipe Transitions | The Construction Detail on page 17 of 9190-23-71 shows Base Agg Dense over the foundation backfill. There is no depth shown. There is also no quantity bid for these areas. This is not shown to be incidental to anything. The special provisions say to fill the trenches flush with aggregate each night. This will be a 9" thick area that will be removed once the asphalt is paved. Will this 9" of gravel be paid for? Please clarify. | The depth of the base aggregate dense over the foundation backfill can be determined from the typical sections. Pipes in the STA 43+84.53 to STA 95+23.46 range will have a depth of 1.5 feet. Pipes in the STA 95+23.46 to STA237+79.9 range will have a depth of 1.25 feet. The base aggregate dense over the foundation backfill in the pipe transitions and the base used to make the transition flush at night will be paid for under item 305.0120 Base Aggregate Dense 1 ï¿½-Inch. | Mike Coleman | 6 | 2020-09-12 13:29 | 2020-09-14 13:54
20200915 | 20200915011 | 11 | Test Digging | All areas on project where there is cut (ponds, etc.) is currently cropped. Are contractors able to dig these areas, run down any crops? | Access to parcels that are WisDOT owned may be allowed if a work on highway right of way permit is approved by the NE Region office. Work on highway right of way permits and guidance can be found at the following link: https://wisconsindot.gov/Pages/doing-bus/real-estate/permits/work-on-hwy.aspx | Mike Coleman | 1 | 2020-08-12 16:01 | 2020-08-17 06:41
20200915 | 20200915011 | 11 | Misc Quantities | Are the misc quantity sheets available in excel? | The MQ Excel files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915011/ | Mike Coleman | 2 | 2020-08-13 15:04 | 2020-08-18 09:02
20200915 | 20200915011 | 11 | Electronic Date Request | Please provide these files below: 1. Existing ground surface file, in LandXML format. 2. Reference line alignments and proposed profiles, in LandXML format. 3. Superelevation transition information, .csv format. 4. Proposed roadway features, 2D DWG file. 5. Proposed structure horizontal features, 2D DWG file. 6. Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format 7. Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files 8. Slope stake report, .csv format. 9. Earthwork data, Excel spreadsheet xlsx file(s). 10. Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. 11. Design Schedule 12. Soils Report | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915011/ | Mike Coleman | 3 | 2020-08-13 16:50 | 2020-08-19 09:31
20200915 | 20200915011 | 11 | Borrow Material from DOT property | Is there any DOT Property near or adjacent to this project that will be available to be used to excavate borrow material from? | There are WisDOT owned parcels in the vicinity of the project, however, it is not anticipated the parcels will be available for borrow excavation. | Mike Coleman | 4 | 2020-08-13 16:56 | 2020-08-18 09:04
20200915 | 20200915011 | 11 | Soil Borings | Were soil borings completed for the project? If so, can the logs/reports be posted? | The Soils Reports files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915011/ | Mike Coleman | 5 | 2020-08-18 08:54 | 2020-08-18 11:08
20200915 | 20200915011 | 11 | Native American Hiring | The contact for the Oneida Nation is not correct. Who should be contacted? | Oneida Nation tribal labor office contact information: The correct contacts are listed below: Troy Parr, Community Development Email: tparr@oneidanation.org David Jordan, Community Development Email: DJORDAN1@oneidanation.org N7332 Water Circle Place, PO Box 365, Oneida, WI 54155 Office: (920) 869-4574 Cell: (920) 606-8909 The Native American Hiring provision will be updated in an upcoming addendum. | Mike Coleman | 6 | 2020-08-25 14:27 | 2020-08-25 14:29
20200915 | 20200915011 | 11 | Article #31 - Topsoil Stockpile - 5,000 CY | Can a separate special item be created for this Article? Incidental to a bid item that is measured by the SY is difficult cover the cost if the item under runs and the DOT pays more if the quantity over runs. The cleanest way is to create a special item for this 5,000 CY stockpile of Topsoil. | The stockpiling of topsoil will be addressed in an upcoming addendum. | Mike Coleman | 7 | 2020-08-25 16:49 | 2020-08-27 13:28
20200915 | 20200915011 | 11 | Temporary Asphalt | On sheet 514 there is 3LT and 4LT Quantity for the Temporary Connection Road of 195 Ton in stage 2. On sheet 516 there is 200 tons of Temporary asphalt on Stage 2 for the same stationing on Temporary Connection Road. Is this quantity doubled up inadvertently or is there another reason for the the tonnage to be to be in two different items? | The asphalt quantity shown on sheet 514 under the bid items of 460.5523 and 460.5524 for the Temporary Connection Road is not correct and will be removed via addendum. The Temporary Connection Road asphalt will be paid under 465.0125 as shown on sheet 516. | Mike Coleman | 8 | 2020-09-01 14:33 | 2020-09-03 10:50
20200915 | 20200915011 | 11 | Typical Finished Section for CTH TS | Typical Finished Section for CTH TS page 23, doesn't align with the cross sections and miscellaneous quantity sheets. 24" Select Crushed is only shown on the Cross Sections from STA 110+00 to 119+75, not from STA 110+00 to 119+76. Which is correct? | Cross sections are correct. A new typical section for CTH TS will be provided for STA 100+00 â€“ 110+00 and an updated typical section will be provided for 110+00 â€“ 119+76.20. Updated typical sections will be provided via addendum. | Mike Coleman | 9 | 2020-09-01 18:07 | 2020-09-08 06:14
20200915 | 20200915011 | 11 | Aggregate Items - CY to Ton design Conversion Factors | What is the CY to Ton conversion factor used on these items: Base Aggregate Dense 3/4 Inch, Base Aggregate Dense 1-1/4 Inch, Base Aggregate Dense 3 Inch and Select Crushed? | Conversion factors used during design for the purpose of calculating estimated quantities are as follows: â€¢ Base Aggregate Dense 3/4" â€“ 2 Ton/CY â€¢ Base Aggregate Dense 1 1/4" â€“ 2 Ton/CY â€¢ Base Aggregate Dense 3â€ â€“ 2 Ton/CY â€¢ Select Crushed Material â€“ 1.8 Ton/CY | Mike Coleman | 10 | 2020-09-01 19:19 | 2020-09-08 06:16
20200915 | 20200915011 | 11 | 643.1205.S Basic Traffic Queue Warning System | Hello, in regard to the Measurement & Payment of this item, the addendum states the item will be measured "as each complete system per roadway". Is the "complete roadway" defined as both directions of WI-29, or is each direction of travel measured separately? Past projects have had the total number of days broken down by direction and stage in the Misc Qty tables; and this project does not. Thanks | Per standard specification 101.3 and the measurement section of 643.1205.S, the item will be paid per direction of travel. The miscellaneous quantity table will be updated via addendum to reflect direction of travel for the estimated quantity. | Mike Coleman | 11 | 2020-09-02 13:32 | 2020-09-08 08:28
20200915 | 20200915011 | 11 | Hauling Restricions | In the proposal there are hauling restrictions for local roads. Do local roads include county highways? | Article #11 â€“ Hauling Restrictions, will be deleted from the special provisions via addendum. | Mike Coleman | 12 | 2020-09-08 08:05 | 2020-09-08 09:39
20200915 | 20200915011 | 11 | sidewalk | What is the intent under the sidewalk area, can this be filled with topsoil? Or does this area need to be stripped and borrow be placed under the sidewalk? | Embankment construction should follow standard spec 207.3. In addition follow standard spec 625.3 to make sure enough topsoil is stripped to cover proposed slopes. | Mike Coleman | 13 | 2020-09-08 16:09 | 2020-09-10 10:32
20200915 | 20200915011 | 11 | Addendum | Is addendum 011b-soi dated Aug 31 the same as the one dated Sep 8? | The website has been updated. Sorry for the confusion. | Mike Coleman | 14 | 2020-09-09 08:12 | 2020-09-09 09:31
20200915 | 20200915011 | 11 | Clearing & Grubbing | In the MQ table for clearing and grubbing on sheet 505 in the plan, there is an undistributed amount of clearing and grubbing. With the variability in cost for clearing a heavily wooded area vs a lightly wooded area, the undistributed amount is difficult to bid. Please review if this undistributed amount is needed. | The undistributed quantity of clearing and grubbing will be removed via addendum. | Mike Coleman | 15 | 2020-09-09 15:46 | 2020-09-10 10:51
20200915 | 20200915013 | 13 | Asphalt Quantities | Can you please verify the asphalt quantities for this project? Based on the typical sections and the asphalt quantity tabulations, the quantities seem to be overstated by a substantial amount. | An addendum was issued to correct the quantities. | Mike Coleman | 1 | 2020-08-24 10:17 | 2020-09-08 08:38
20200915 | 20200915013 | 13 | B-37-100 Painting Operations | When does the Department anticipate the painting of structure B-37-100 to take place? |  |  | 2 | 2020-09-11 08:58
20200915 | 20200915014 | 14 | Schedule | Please provide the DOT's preliminary schedule. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915014/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-08-25 15:24 | 2020-08-26 07:28
20200915 | 20200915015 | 15 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915015/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-09-03 07:20 | 2020-09-03 08:24
20200915 | 20200915015 | 15 | HMA Mix Type for Lower Layer Pavment | In the reconstruct section between sta 207+50 and 215+50, the lower layer pavements are shown as a 3LT 58-28S mix type. Should this be changed to a 3MT 58-28S to match the MT designation for the surface layer pavement? | An addendum is being issued to correct this. | Mike Coleman | 2 | 2020-09-03 07:25 | 2020-09-09 14:28
20200915 | 20200915015 | 15 | Project Staging | The traffic control staging for project 9140-12-70 doesnâ€™t allow for access to the pavement between the start of the project at STA 207+50, and the end of the work zones shown on Sheets 13 & 14, beginning at approx. STA 209+00. Would the department consider revising the staging to allow for space to build the full depth pavement and base course section between 207+50 and 209+00? Or would the department consider extending the 2â€ mill and overlay section through the Hafemeister Lane intersection, up to approx. 209+00 to resolve the conflict with the position of temporary barrier wall for the staged bridge construction? | Weâ€™ve reviewed the question below with our construction staff and feel that construction is possible with a flagging operation after stages 1 & 2 as called out in the T.C. notes. The contractor might have to put up a bump sign at 209+00 and place a temporary paper joint/taper in to account for the 3 inches of profile change after stage 1. | Mike Coleman | 3 | 2020-09-08 16:51 | 2020-09-09 14:29
20200915 | 20200915016 | 16 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915016/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-09-03 07:21 | 2020-09-03 09:59
20200915 | 20200915016 | 16 | Overlay Stage Width Constructibilty Issue | For B-34-838 the allowable construction width is 12'-8" per stage - the low slump overlay machine's physical dimensions cannot be configured that small to pave the overlay, as such the job is not biddable with the current specifications. The only way to complete this work is to have a full closure of the roadway. Please Advise. | The previous overlay on the bridge was successfully completed using the same traffic control configuration shown in the plans. The overlay must be constructed with plan staging. | Mike Coleman | 2 | 2020-09-08 16:53 | 2020-09-14 08:22
20200915 | 20200915017 | 17 | Schedule | Can you post the anticipated schedule for this project? Thank You | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20200915017/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-08-17 11:15 | 2020-08-17 12:35
20200915 | 20200915017 | 17 | 649.0150 4" Temp Tape | Hello, in the Misc. Qty tables on page 63 of the plan the 4" Temporary Removable tape is listed as "Contrast"; but in the bid items this is listed as regular 4" Temporary Removable Tape. Can this be clarified which type of 4" tape is intended for this project, standard or contrast? Thanks | The temporary removable tape should be standard not contrast. An addendum will be issued to clarify. | Mike Coleman | 2 | 2020-09-01 14:28 | 2020-09-08 08:34
20200915 | 20200915017 | 17 | Temporary Regulatory Speed Limit Reduction | Hello, on page 3 of the Special Provisions, "Temporary Regulatory Speed Limit Reduction", we are requesting a clarification of the language used. The second paragraph of this section states: "Post temporary regulatory speed limit signs in work zone only during continuous worker activity. During periods of no work activity or when the traffic controls are removed from the roadway, cover or remove the temporary speed limit signs." This could be interpreted as changing the 55/65 MPH signs daily when work is actively occurring. However in the next paragraph the language states: "Establish a statutory 55 mph speed limit zone for USH 53 only when a lane is closed to traffic." Since the lane closures will remain in place long term, is the intent to leave the 55 MPH signs up at all times that a lane closure is in place, or is the intent to switch the signs out daily during continuous worker activity? Thanks | An addenda will be issued to address this. | Mike Coleman | 3 | 2020-09-02 08:47 | 2020-09-08 06:13
20200915 | 20200915017 | 17 | PWL for lower lift | With the milling going all the way to the rubblized Concrete the lower lift will have varying thickness as you build the cross slope back with the lower lift. I believe the old PCC profile was a 1.5% cross slope and it will be difficult to meet PWL consistent densities paving a varying thickness mat. I Feel PWL specification should not apply in this situation. | This project has been withdrawn and is being moved to the November 10, 2020 letting. | Mike Coleman | 4 | 2020-09-10 08:38 | 2020-09-10 14:54
20200915 | 20200915017 | 17 | Clarification of Item 460.0100S HMA Pavement Test strip | I am wondering if this item is intended to cover all aspects of the SMA test strip? In prior projects there were two items to cover volumetrics and density (compaction acceptance). | This project has been withdrawn and is being moved to the November 10, 2020 letting. | Mike Coleman | 5 | 2020-09-10 08:42 | 2020-09-10 14:55