## qandasearchletting_results
Date: | 2020-11-09 15:56
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20201110 | 20201110001 | 1 | HMA 3 HT 58-28 H | Would the DOT want to consider changing the temporary asphalt on the job from HMA bid item to asphaltic surface bid item to save the added cost of QMP testing? | No, the Department wants to control the mix type because of the amount of truck traffic and the duration of using the temporary road for two years. | Mike Coleman | 1 | 2020-10-17 09:03 | 2020-10-22 06:21
20201110 | 20201110001 | 1 | 614.0800 Crash Cushions Permanent | Hello, after reviewing the placement of the Crash Cushions Permanent and seeing that they are attached to Temporary Barrier Wall, is the intent of these Crash Cushions a true permanent installation or are these meant to be Temporary Left In Place and left in for the next project? Thanks | The permanent crash cushions are to be left in place with the Temporary Barrier Left In Place. The next project will remove them. | Mike Coleman | 2 | 2020-10-21 09:33 | 2020-10-22 06:19
20201110 | 20201110001 | 1 | SPV.0090.04 Traffic Control Gawk Screen Furnished/Installed | Hello, after reviewing the placement of the Traffic Control Gawk Screen, is this item intended to be Left In Place along with the temporary barrier wall that is left in place for use on the next project? The special provisions for the Gawk Screen items include furnishing, installing, and removing upon completion of the project. Thanks | The Gawk Screen is not intended to be left in place. It can be removed prior to winter. | Mike Coleman | 3 | 2020-10-21 09:40 | 2020-10-22 06:22
20201110 | 20201110001 | 1 | 643.0920 Traffic Control Covering Signs Type II | Hello, reviewing the Misc Qty tables for Traffic Control it appears that the Type II Covers may have been tabulated as "days" not as "each". For example in Stage 1B the plan sheets show one 70 MPH sign getting covered, but the quantities for this stage is 166 covers. Please review and update if needed. Thanks | The quantity for covering signs will be updated in an upcoming addendum. | Mike Coleman | 4 | 2020-10-21 17:27 | 2020-10-26 07:08
20201110 | 20201110001 | 1 | Temporary Bridge Details | Are there additional details for the temporary bridges other than Special Provision #20 and the stationing listed is the SPV and on plan sheet #9? Does the stationing represent the minimum length of the structure? Can DOT provide minimum span lengths to clear the stream and underlying roadways as well as minimum low chord elevations at all structures so that all bidders are looking at the same thing? Will piers be allowed to meet overall bridge length requirements and are there any restrictions for placing them in or near the Lemonweir River? | 1. Are there additional details for the temporary bridges other than Special Provision #20 and the stationing listed is the SPV and on plan sheet #9? No. 2. Does the stationing represent the minimum length of the structure? No, they are just approximate limits. 3. Can DOT provide minimum span lengths to clear the stream and underlying roadways as well as minimum low chord elevations at all structures so that all bidders are looking at the same thing? For the Lemonweir River temporary bridge, there are some hydraulic design parameters listed in the Temporary Bridge special provision. This special provision also states lateral and vertical clearance requirements for the grade crossing structures. 4. Will piers be allowed to meet overall bridge length requirements and are there any restrictions for placing them in or near the Lemonweir River? Yes, piers will be allowed. Placing them in the river will be allowed, per DNR, with methods included in the ECIP. The ECIP should include detailed information on installation and stabilization methods to protect the waterway for full duration of this project. ECIP should include pier locations (if utilized), type of material, use of sheeting or turbidity barrier for sediment control, etc. | Mike Coleman | 5 | 2020-10-27 15:21 | 2020-10-29 06:32
20201110 | 20201110001 | 1 | DOT #1 Pavement Thickness | Looking at the Typical Cross Sections on Sheet #7 the pavement thickness for the guardrail extensions and outside shoulders is stated at to be a thickness of 5" HMA Pavement. In the Prosecution and Progress under the description of Stage 1A it states that the guardrail extensions and the outside shoulders will be constructed with 6" of HMA Pavement. is the plan to do 5" of HMA or with 6" of HMA in those areas? | The plan typical section is correct with 5â€ HMA pavement for the guardrail sections and outside shoulders. | Jill Fehrman | 6 | 2020-11-02 10:36 | 2020-11-02 16:10
20201110 | 20201110001 | 1 | Temporary Bridge Structure Maintenance and Recovery | Typical temporary bridges are constructed from steel girders with a timber deck and asphalt overlay. From past experiences, we have found that temporary bridges in place constructed in this manner sometime require maintenance after one year of use (asphalt overlay mill and repave, check/tightening deck tie downs, pavement markings, etc). If this contract is to be completed 5/01/22, who will be responsible for maintenance costs after year 1 of use? Will a temporary bridge design that may require maintenance, such as one with a timber deck and asphalt driving surface, be considered if maintenance maybe necessary after 1 year of use? Upon completion of the project(s) that requires the temporary bridges to be in service, can the components of the temporary bridges be returned to the installation contractor if requested by installation contractor? | The next contractor from the 1016-05-70 project. That separate let is planned to have a special item for maintenance of the temporary bridges. Yes. As previously stated, that future separate let is planned to have a special item for maintenance of the temporary bridges. No. The components of the temporary bridges will not be returned to the installation contractor if requested by installation contractor? | Mike Coleman | 7 | 2020-11-03 09:08 | 2020-11-05 05:59
20201110 | 20201110001 | 1 | Traffic Control During Construction of the Temp Bridges and Associated Grading | It appears that there is no traffic control for STH 82 and CTH G during construction of the temporary bridges and associated grading activities. Will lane closures and/or shoulder closures be allowed on STH 82 and CTH G and will the traffic control items be paid through the items on the project or would the contractor need to figure something into the temporary structures to cover these costs? |  |  | 8 | 2020-11-05 13:20
20201110 | 20201110001 | 1 | SPV.0090 Alternative Materials in Lieu of Cast Iron Castings | Item SPV.0090 Drain Slotted Vane Longitudinal, would the Department entertain alternative materials verses the cast iron castings as indicated in the construction details? | Bid the item as it is shown in the plans. Per 104.10 of the Standard Specification a contractor may submit a Cost Reduction Incentive (CRI) for the departments consideration post execution of an awarded contract. | Jill Fehrman | 9 | 2020-11-05 14:44 | 2020-11-06 08:28
20201110 | 20201110004 | 4 | Questions | 1.) Should some of the guardrail areas be short radius rail and terminals instead of MGS 3 and Type II's? 2.) Restoration Quantity - 312+47 is listed in misc quantities but nothing for restoring curb and gutter removal areas or 310+17. 3.) Concrete Mowstrip - What are the pay limits for this item? Typically it is a minimum 3'6" wide x the length but this is different. 4.) Mowstrip Backfill - Backfill with low strength grout or emulsified asphalt? 5.) Guardrail connection at bridge on Bloomer Mill Road - WIll this just be the W-Beam panel with a bridge shoe as it currently is? 6.) Curb and Gutter removals - Removals at CR YY or at Breidel Coulee Road as shown in the plans? 7.) Salvage and Reinstall EAT - The plan detail for the EAT is a MASH style anchor. The existing EAT is not MASH compliant. Should a new anchor be installed? Thanks | 1.) Limitations in available right-of-way required that MGS 3 and Type II ends need to be used. 2.) Restoration quantity will be required in all areas that require restoring curb and gutter, and removal areas. 3.) Pay limit is the area outside of the existing surface drain. 4.) Emulsified asphalt (see detail for guard rail mow strip). 5.) Yes. 6.) MQ table should include a line for removal and installation of concrete curb and gutter 6-inch sloped 36-inch type D at Breidel Coulee Rd., and the plan should have a note at CTH YY indicating removal and replacement of curb and gutter. 7.) We will investigate whether the anchor meets standard. If not we, will replace it with one that does. | Mike Coleman | 1 | 2020-10-19 15:34 | 2020-10-26 07:29
20201110 | 20201110004 | 4 | Borings | Were any borings taken in the guardrail locations? | No borings were taken at the guardrail locations. | Jill Fehrman | 2 | 2020-10-21 08:55 | 2020-10-23 07:09
20201110 | 20201110004 | 4 | Plans | On page 2 of the plans there is a note saying the 3.5 inch area will have 2 1.75" lifts and that the lower layer is a 4LT 58-28 S. First, there is no bid item for 4LT in the proposal and, secondly, if is a 1.75" lift, that won't leave 2 inches for the surface lift to match the adjoining lane. Can you address these issues please. | On page two of the plans, the note referencing the 1.75" lower layer (4LT 58-28 S) should be changed to reference 4 MT 58-28 S. In regards to matching the surface between the 2" mill and overlay section, and the 3" mill and overlay with 3.5" section, the 0.5" profile change can be made using the butt joint detail on page 5. An addendum will be issued to clarify. | Mike Coleman | 3 | 2020-10-22 16:00 | 2020-10-26 07:18
20201110 | 20201110004 | 4 | Specifications | In the proposal there is one line that significantly impacts how this project will be built and that is the one that states lane closures will not be allowed from 3:00 PM to 6:00 PM. Can you shed some light on the rationale behind this? | Peak afternoon traffic volumes would result in long delays, therefore lane closures / flagging is to be avoided during the hours listed. | Mike Coleman | 4 | 2020-10-22 16:06 | 2020-10-26 13:05
20201110 | 20201110005 | 5 | Temporary Pavement Markings | Good morning. It appears the project has temporary markings included for the surface layer but does not have any temporary markings included for the milled surface or the lower layer. Will there be an addendum to address this? Thank you. | An addendum was issued to correct this. | Mike Coleman | 1 | 2020-10-24 07:05 | 2020-11-05 16:32
20201110 | 20201110005 | 5 | Removing Asphaltic Surface Milling | It appears that the widening quantities were included in the milling quantity. Is it the departments intent to mill the widening? | The intent is to mill the full width of one lane of the proposed roadway and paved shoulder, including widening, at the same time. The shoulder widening is not needed in advance of the roadway milling. | Mike Coleman | 2 | 2020-10-27 10:49 | 2020-10-28 10:56
20201110 | 20201110005 | 5 | PWL Items | It appears that the â€˜Incentive Density HMA Pavementâ€™ item has been listed/calculated in error. It appears that the â€˜Incentive Density PWL HMA Pavementâ€™ item has been calculated in error. It appears that the â€˜Incentive Air Void HMA Pavementâ€™ and â€˜Incentive Density HMA Pavement Longitudinal Jointâ€™ items are missing from the contract. Can WisDOT please revise and/or update the contract with these items or clarify the intent for these items in regards to the SPVâ€™s. | These are administrative items that will be addressed during construction. | Mike Coleman | 3 | 2020-11-04 16:04 | 2020-11-09 13:36
20201110 | 20201110007 | 7 | Concrete Masonry Structures | Will an addenda be issued to update the structures items to the new spec? Also, will CMP's be allowed as casing to remain in place for the footings? The casings cannot be pulled due to the wings on the Ancillary Structure or on any Type 13's. | Currently, there are no plans to issue an addenda for this. The Department is using the old items that have updated names and numbers as the Dept is in a transition period to the new sign structure designs. Both steel & CMP casings are acceptable stay-in-place forms for drilled shafts, experiencing soil stability issues. Intimate soil contact between the base (or its form) is desired. Any backfilling around the stay-in-place form shall be well compacted in layers of 1 foot or less. Cardboard sono-tubes are not acceptable as a stay-in-place forms. | Mike Coleman | 1 | 2020-10-20 08:43 | 2020-10-22 13:55
20201110 | 20201110007 | 7 | Clarification - S-32-45 | There are distinct differences between the old 636/641 Standard Specifications and the new 531/532 Standard Specifications. Under which Standard Specifications does the S-32-45 sign structure fall? It is not clear to me which set the Contractor will be held to with the previous answer. | S-32-45 will fall under the new 531/532 standard specification. An addendum will be issued to revise the associated bid items and plan sheets. | Mike Coleman | 2 | 2020-10-23 15:39 | 2020-10-28 09:26
20201110 | 20201110007 | 7 | Reflective Backplate | Proposal line numbers 0308 & 0310 call for reflective backplates for the signal heads. What reflective tape width is required, 1", 2" or 3"? | 2â€ retroreflective tape should be used. | Jill Fehrman | 3 | 2020-10-29 08:31 | 2020-10-30 09:44
20201110 | 20201110008 | 8 | Borings | Were any borings taken in the guardrail locations? | No soil borings were taken specifically at guardrail locations. Soil borings were taken throughout the project and the results are shown within the â€˜Soil Boring Summaryâ€™ in the plan. | Mike Coleman | 1 | 2020-10-21 08:15 | 2020-10-21 09:00
20201110 | 20201110008 | 8 | Cad Files | Can you please provide the cad file for this project? Thank you. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110008/ | Mike Coleman | 2 | 2020-10-21 12:21 | 2020-10-22 08:28
20201110 | 20201110008 | 8 | Center line rumble strips | Good morning, What is your expectation for laying out the center line rumble strips? Will that be incidental to the item or will an addendum be issued to include a temporary epoxy item as is typical with a project that includes center line rumble strips? Thank you. | Layout of the center line rumble strips will be incidental to the item. There will not be an addendum issued to add temporary epoxy as the road is closed during construction. | Mike Coleman | 3 | 2020-10-26 06:39 | 2020-10-26 08:32
20201110 | 20201110008 | 8 | Existing Rubblized Concrete Pavement | Please confirm that the existing rubblized concrete pavement can or cannot be used as recycled crushed concrete for base aggregates for this project? |  |  | 4 | 2020-10-29 10:38
20201110 | 20201110009 | 9 | Type 1/Type 2 Lead Water Service Replacement | In the specials under Section 9, it states that the property owner is responsible to replace existing water service from end of new curb box to inside of their building, house or structure. However, in the details, it is shown that the contractor is supposed to core the foundation wall and take the service inside which contradicts the specials. Looking for clarification to see if the GC stops at the exterior of the building and the private contractor takes over or if the GC is supposed to take the service inside the building. | Paragraph four of article 9 will be revised in an upcoming addendum to the following: Lead and galvanized water services must be replaced to inside buildings, houses, and structures within the Project area. The contractor is responsible to replace existing water service from end of new curb stop to inside their building, house, or structure to the existing water meter. Contractor must coordinate water service replacement with property owner. The following property addresses have, or potentially have, existing lead or galvanized water services: | Mike Coleman | 1 | 2020-10-16 16:11 | 2020-10-20 05:58
20201110 | 20201110009 | 9 | NY4 Railing - Wall Thickness | In order to curve the 6" x 6" tubing to the sharp radius's required it is recommended to increase the wall thickness to 1/4" to minimize distortion of the tube cross section. Is this acceptable? It will require the erection sleeves to be modified to a reduced profile. | Increasing the wall thickness of the 6" x 6" tubing of the NY4 railing to ï¿½â€ to minimize distortion during bending would be acceptable for this bridge. This would include the superstructure as well as the wing railing. | Mike Coleman | 2 | 2020-10-26 15:53 | 2020-11-02 13:24
20201110 | 20201110009 | 9 | Retaining Walls | We do not see any details or anything in the plans regarding the retaining walls. They are only mentioned in the Estimated Quantities. Can you please provide more details on these? | The retaining wall details begin on pg. 51 and end on pg. 67 of the plan set in the Construction Details section. Each wall has itâ€™s own detail showing a plan view, elevation view, concrete steps geometry table and alignment table. Typical sections for the walls are on pg. 66. Wall railing details are on pg. 67. | Mike Coleman | 3 | 2020-10-27 12:14 | 2020-10-27 14:23
20201110 | 20201110009 | 9 | NY4 Railing - Post | On Sheet 19 of 22 for Structure B-33-7, the Legend states the W6 x 25 posts shall be placed vertical and normal to grade. Those would be contradicting statements, placing the post vertical would make it plumb whereas placing normal to grade the posts would be perpendicular to the grade of the bridge. Please clarify which is correct. | The intent of the note is referring to two different things: 1. The posts are vertical (plumb) when looking at the section view (see angle provided on â€œSection Thru Railing on Sidewalkâ€ on page 19 of 22 to make the railing vertical (plumb) in that direction) 2. The posts are normal to grade when looking at the elevation view (the rail posts are not plumb in elevation view). | Jill Fehrman | 4 | 2020-10-28 13:16 | 2020-11-02 11:34
20201110 | 20201110009 | 9 | Specifications | The specifications for the project state that the contractor is to obtain a railroad protective liability insurance policy for the project. There is not a railroad on this project. Will this specification be removed? | The specification will not be removed. Protective liability insurance is required to cover the Pecatonica Rail Transit Commission and Tri-County Trail Commission on this project as specified in special provision article 11. The Cheese Country Trail, which follows an old railroad corridor that passes through Darlington, crosses STH 23 at the Ann Street intersection. Since work is proposed in the area where the trail crosses STH 23, the commissions need to be covered by the protective liability insurance obtained by the contractor. As a further reminder per section A.4 of article 11, a temporary authorization permit must also be approved by the Pecatonica Rail Transit Commission before any work can proceed within the trailâ€™s right-of-way. The completed permit and evidence of insurance must be coordinated with the commission at least 15 days prior to the meeting dates specified in the special provision in order to obtain authorization to work in this area. | Jill Fehrman | 5 | 2020-10-29 11:56 | 2020-10-30 09:52
20201110 | 20201110009 | 9 | Retaining Walls #2 | The engineering requirements for the "modular block gravity landscape" walls is not allowing for a "small block" gravity wall. Either grid is needed in these walls, which would make them "MSE walls" or the much larger "Recon"-style walls will be needed. These Recon walls will not look similar to the MSE walls on the project. Would the Department consider changing the "modular block gravity landscape" walls to MSE wall bid items or will the larger style blocks need to be used for these walls? | The Department will not change the modular block gravity landscape walls to MSE walls. Right-of-way limitations and the presence of existing nearby retaining walls make it difficult to use MSE walls at all locations. The products available on the Departmentâ€™s approved product list should meet the requirements for the modular block gravity landscape wall bid items. If â€œReconâ€-style walls are referring to the manufacturer Recon Wall Systems â€“ Series 50, that would be acceptable as those products are on the approved products list. | Mike Coleman | 6 | 2020-11-03 09:58 | 2020-11-04 09:17
20201110 | 20201110009 | 9 | Excavation Waste | Is this item for the trenches for the utilities? | The Excavation Waste item is a â€œpilot itemâ€ on this project. This item is meant for roadway waste material that would be hauled off the project that is not needed (from roadway excavation). The item is meant to identify the costs associated with hauling material off the project and separating it from the common excavation costs. Article 50 in the special provisions provides more detail on this item. The earthwork summary tables in the miscellaneous quantities also highlight this. | Mike Coleman | 7 | 2020-11-03 11:16 | 2020-11-03 15:59
20201110 | 20201110009 | 9 | Seismograph/Crack and Damage Survey Limits | There are bid items for Seismograph and Crack and Damage for this project with the Crack and Damage Survey specifically for residences and business between Alice and Cornelia Street. There are 10 different locations that require Temporary Shoring from Sta 21+25 to Sta 40+83 that are in close proximity to residences that are not located between Alice and Cornelia Street. Can the Crack and Damage Survey/Seismograph limits be extended to include the temporary shoring locations? | The main intention of the bid item was to ensure appropriate monitoring within the historical district downtown between Alice and Cornelia Street. | Mike Coleman | 8 | 2020-11-05 10:15 | 2020-11-05 16:34
20201110 | 20201110010 | 10 | 1/2" between adjacent traveled lanes | Special Provision - 3. Prosecution and Progress - Paving Operations states "Differing height great than 1/2 inch between adjacent traveled lanes will not be permitted overnight." Question: Since a notch wedge joint is required for the centerline joint and the maximum height of the notch in a notch wedge joint is 1/2 inch does this meet the requirement for 1/2 inch between adjacent lanes? From a quality and cost stand point it will be better if the paving operation can even up paving lanes every 2nd day to minimize stop and start joints for better ride in the driving lane and not having to cover the cost of lost production resulting from backing up and starting again in the middle of the day. | The use of the notched wedge is acceptable and is permitted overnight. | Mike Coleman | 1 | 2020-10-19 08:36 | 2020-10-21 05:56
20201110 | 20201110010 | 10 | Borings | We're any borings taken in the guardrail locations? | There were no soil borings taken as part of this project. | Mike Coleman | 2 | 2020-10-21 08:14 | 2020-10-21 08:55
20201110 | 20201110011 | 11 | Prosecution & Progress: Fish Spawning | Proposal states that "There shall be no instream disturbance of Mill Creek as a result of construction activity under or for this contact from September 15 to August 15 both dates inclusive, in order to avoid adverse impacts upon the spawning of trout and Blanchard Cricket Frogs". Please verify the dates given, because as written the specification provides only thirty days for instream work on a triple span structure. | Per WDNR coordination, instream disturbance is allowed between August 15 and September 15. The new structure clear spans Mill Creek and therefore the construction of it is not impacted by these restrictions. Instream work is limited to removal of the old structure. | Mike Coleman | 1 | 2020-10-12 10:12 | 2020-10-14 09:06
20201110 | 20201110011 | 11 | Relocated Power Lines | We have guys onsite right now and it looks like the power lines were moved in the last couple days, but they were not moved nearly far enough out. The new poles are in just 6' off the existing structure, but the new structure is 6' wider than the existing and the angled wing wall has a pile in it which is located directly below the power lines now. We have some pictures if you would like them. Is the intent to use specialized equipment under these lines, or was the intent to move the lines so traditional pile driving equipment could be used? | Alliant Energy will de-energize the OH utility and drop the line as needed during construction. Alliant Energy requires a two week notice in order to de-energize and temporarily drop the line. The Alliant Energy contact for this work is: Matthew Hosler, (608) 963-3655, MatthewHosler@alliantenergy.com | Mike Coleman | 2 | 2020-10-27 13:16 | 2020-10-28 10:43
20201110 | 20201110012 | 12 | Removing Reprocessed Concrete Base Material | The reprocessed concrete layer from the Badger ammo plant that is under the existing roadway that is to be wasted I would assume contains no contaminates? Is there anything that bidders should be worried about with this material as far as contamination? | Testing was conducted prior to the materials use in the 2009. No contaminants were found at that time. The files are too large to email, so if a contractor wants to look at testing, we would need to set up a file share on BOX. | Mike Coleman | 1 | 2020-10-19 10:37 | 2020-10-26 07:06
20201110 | 20201110012 | 12 | Earthwork tables | Would the dept please provide the earthwork tables in xcel format. | The earthwork tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110012/ | Mike Coleman | 2 | 2020-10-19 15:51 | 2020-10-21 05:53
20201110 | 20201110012 | 12 | Special Provisions - Interim Completion for STH 113 | Completion of segment between STH 113 N and Weynand Road is stated to be complete by June 11, 2020. Transportation of aggregates for this project will likely need to traverse local roads. Local Roads will have limitations posted due to spring breakup weight restrictions preventing transportation during the affected 6 to 8 week period. The period of time between the lifting of restrictions and the interim completion date do not allow enough time to complete this section. Would the state extend this interim completion by 30 days due to the expected road restrictions? | No, the interim completion date will not be extended. | Mike Coleman | 3 | 2020-10-21 08:03 | 2020-10-27 09:54
20201110 | 20201110012 | 12 | Cad File | Can you please provide a cad file for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110012/ | Mike Coleman | 4 | 2020-10-21 12:22 | 2020-11-03 06:04
20201110 | 20201110012 | 12 | Pre-existing Recycled Concrete Under Roadway | Is there any documentation declaring that the recycled concrete under the road way is not contaminated? If not, how and what will be done to verify that it is not contaminated to reassure offsite dumping locations? | The documentation for testing of the concrete material from the Badger Ammunition plant can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110012/ | Mike Coleman | 5 | 2020-10-23 13:39 | 2020-10-27 14:28
20201110 | 20201110012 | 12 | Reprocessed Contrete Base Material | Special provision items 8 and 9 indicate the reprocessed concrete base material is from the Badger Ammunition plant. Please confirm the contractor is to assume this material is clean and can be disposed of with out restriction. Please confirm the Department will pay the contractor additional to remove contaminated or hazardous material. Thank you. | The department is assuming the material to be removed is not contaminated. The documentation for testing of the concrete material from the Badger Ammunition plant can be found in the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110012/ Should hazardous substances be encountered, the department would follow section 107.24 of the standard specifications. | Mike Coleman | 6 | 2020-10-26 11:59 | 2020-10-27 14:30
20201110 | 20201110012 | 12 | Temporary Epoxy Pavement Markings | Good morning, Can you please clarify the department's intentions for the temporary epoxy pavement markings? The quantities listed on sheet 79 appear to be the length of each section rather than a combination of skips and pass/no pass zones. Thank you. | The temporary epoxy markings are typically used prior to rumble strip placement on projects constructed under traffic. After further discussion, with the road being closed to through traffic, the quantity for temporary epoxy should not be needed for this project and will be removed from the plan via addendum. | Mike Coleman | 7 | 2020-10-27 07:21 | 2020-10-28 10:52
20201110 | 20201110012 | 12 | Electronic Data Request | Please provide these files below: - Existing ground surface file, in LandXML format. - Reference line alignments and proposed profiles, in LandXML format. - Proposed roadway features, 2D DWG file. - Proposed structure horizontal features, 2D DWG file. - Surface models, Proposed Top of Pavement, Top of Aggregate, Top of Select Crushed and Subgrade/Datum, in LandXML format - Proposed surface model longitudinal breaklines, 3D AutoCAD DWG files - Right of Way and easement data, LandXML and/or 2D AutoCAD DWG file. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110012/ | Mike Coleman | 8 | 2020-10-28 10:30 | 2020-11-03 06:05
20201110 | 20201110012 | 12 | Detour for STH 78 | The detour for STH 78, Proposal #12 in the November letting utilizes STH 60. There is a project scheduled for 2021 on STH 60 from Sauk City to Lodi that was let in September. How will this be addressed so STH 78 traffic isnâ€™t being directed to another project being completed under traffic? | The detour for STH 78 will be revised to utilize US 12 to STH 33 to IH 90 and back to STH 78. There will still be a detour for STH 113. The revised detour plans will be provided prior to the start of construction. | Mike Coleman | 9 | 2020-11-03 12:00 | 2020-11-03 12:04
20201110 | 20201110013 | 13 | Storm Sewer Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | The bid items will remain as shown. The city requested this material based on cost participation and local preference. | Mike Coleman | 1 | 2020-10-12 11:14 | 2020-10-29 15:28
20201110 | 20201110013 | 13 | Curb Boxes and Water Service | 1. Would Mueller Curb boxes be acceptable? They are from Canada but are speced on all Janesville jobs. 2. Is the 1-1/4â€ water service required? Is there any way we could upsize the line to 1-1/2â€ or 2â€? Mueller does not make that size anymore. | 1. Buy America provisions apply and should be followed 2. Please bid as shown in the plans. | Mike Coleman | 2 | 2020-11-05 14:29 | 2020-11-05 14:29
20201110 | 20201110014 | 14 | Design Schedule | Can the Design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110014/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-10-19 09:57 | 2020-10-20 10:05
20201110 | 20201110014 | 14 | Butt Joints | There is no butt joint item, will one be added? | Since the mill thickness and overlay thicknesses are the same the butt joint item will not be needed. Match points will require saw cuts as shown in the plan. | Jill Fehrman | 2 | 2020-10-28 15:15 | 2020-10-30 09:43
20201110 | 20201110014 | 14 | Wedge Layer | The lower layer from Sta 10+00 to 13+60 and from STA 484+-0 to 499+54 is 1.25". This material is below the minimum allowable thickness per the spec. Will ordinary compaction per section 450.3.2.6.2 be the basis of acceptance for these areas? | All wedging and leveling layers are accepted by ordinary compaction due to the variable thicknesses, however the mix is still subject to testing per 460.2.8.2.1.3.1. | Mike Coleman | 3 | 2020-10-28 15:17 | 2020-10-29 15:14
20201110 | 20201110014 | 14 | Cold Joint | There is language in the special provisions about cold joints only being allowed at centerline. Will a cold joint be allowed between the 12' driving lane and 8' parking lane from STA 484+02 to STA 499+55? | Yes | Mike Coleman | 4 | 2020-10-28 15:18 | 2020-10-29 15:21
20201110 | 20201110015 | 15 | Milling and C.I.R. Depths | According to the borings 26 of the 50 cores taken have less than 7" of existing asphalt pavement. The plan shows milling off 3.5" of existing asphalt surface then Cold In Place Recycling 3.5" deep. That means that approximately half of the job will be incorporating pulverized & relayed millings from below the existing asphalt pavement into the C.I.R. I believe this will result in inconsistent millings for the C.I.R. pavement as well as possible subgrade issues. Perhaps the Department should consider milling off less asphalt prior to the C.I.R. like maybe 1.5" or 2" depth. | The pavement design and soil borings were reconfirmed. Incorporating pulverized material should be properly addressed in the mix design to limit potential issues in the field and to determine the correct AC. Please bid as let. | Mike Coleman | 1 | 2020-10-13 13:48 | 2020-10-20 07:26
20201110 | 20201110015 | 15 | Culvert Pipe Replacement | Details of pipe replacement on sheet 8 of the plan has a note stating "Mill area of culvert pipe replacement prior to placing 3.5" asphaltic surface". Does this mean that the patch for the pipe replacement will be filled flush with gravel base and reamain gravel base until after the milling in that area or is it the intention to do the culvert replacement after the milling is done? | The intent was for pipe replacements to be completed prior to milling. As shown on the detail on page 8, this patch should be repaved with new pavement flush to the existing surface. After repaving the patches, milling and CIR operations will commence for the entire corridor including the new asphalt in these patched areas. | Mike Coleman | 2 | 2020-10-15 10:43 | 2020-10-20 07:27
20201110 | 20201110015 | 15 | Match Adjacent Lanes | On page 2 of the Special Provisions under 3. Prosecution and Progress states "Match adjacent lanes and shoulders to the same elevation at the end of each working day". Is this for milling only or does it apply to the HMA paving as well? I can understand milling because we don't want a 3.5" uneven centerline. The HMA is 1.75" per lift and will have a Notch Wedge Joint at centerline. Evening up lanes each day while paving slows production and results in more stop and start joints which affects the IRI Ride. It will be better for the job if the HMA paving could be evened up every 2nd day of paving. | The concern with matching adjacent lanes and shoulders applies to the milling operations. Avoid creating drop offs greater than 2-inches during all work operations. | Mike Coleman | 3 | 2020-10-15 10:51 | 2020-10-20 07:27
20201110 | 20201110015 | 15 | SPV Item - Remove Excess Shoulder Material | Can you more specifically show how you came up with 4985 CY. Plan typicals show locations of extra width paved shoulder 171+07-521+06 and 526+66 - 705+75. Looks like 2 feet wide on both shoulders at the depth matching the 3.5" milling. Or is it removing to the CIR depth for a total of 7"? | This quantity was calculated to match the 3.5" milling depth on both shoulders. | Mike Coleman | 4 | 2020-11-03 13:35 | 2020-11-04 08:27
20201110 | 20201110015 | 15 | SPV Item - Remove Excess Shoulder Material | Can you more specifically show how you came up with 4985 CY. Plan typicals show locations of extra width paved shoulder 171+07-521+06 and 526+66 - 705+75. Looks like 2 feet wide on both shoulders at the depth matching the 3.5" milling. Or is it removing to the CIR depth for a total of 7"? | This quantity was calculated to match the 3.5" milling depth on both shoulders. | Mike Coleman | 5 | 2020-11-03 13:35 | 2020-11-04 08:28
20201110 | 20201110017 | 17 | Dowel baskets | Will the concrete pavement replacement and base patch concrete have transverse dowel baskets ? | The SDD sheets (SDD 13c9-b and SDD 13c14-b) note that existing non-doweled pavements do not need to be doweled. However, for this project the dowels are required to maximize the lifespan of the pavement structure. Below outlines when dowel baskets are required whether in the Concrete Pavement Replacement section or Concrete Base Patching section: Concrete Pavement Replacement Per Spec 416.5.1 (8), â€œThe department will pay for individual repairs at least one lane wide and greater than 15 feet to less than 300 feet long as Concrete Pavement Replacement. Payment includes jointing and providing tie bars and dowel bars in unhardened concrete.â€ Transverse dowel baskets will be included in the concrete pavement replacement bid item as detailed in SDD 13c9-b/c and the spec. Concrete Base Patching Per Spec 390.5 (2), â€œPayment includes providing tie bars and dowel bars in unhardened concrete and steel within the patch.â€ SDD 13c14-b/c details that a single base patch has a minimum 6-foot length and a maximum 15-foot length. Base patches greater than 15 feet require dowel bars as shown in the SDD, they are paid for as Concrete Pavement Replacement if the patch is one lane wide. If there are base patches that are less than a full lane width and greater than 15 feet (such as a turn lane taper), dowel bars may be placed within a base patch at adjacent transverse joint locations or cracks. The plan detail sheets note that final base patch locations are to be determined by engineer in field. This will determine final dimensions and pay items. | Mike Coleman | 1 | 2020-10-16 10:02 | 2020-10-20 06:02
20201110 | 20201110017 | 17 | Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110017/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. - Most important item, Stage 2A (full closure) cannot start prior to August 1, 2021, as indicated in the lower right corner of the page, in the note section. This is also called out in the Special Provisions. - Stage 2A and 2B are designed to lined up in the time chart to minimize the number of traffic control mobilizations. However, if the contractor can stage it where they can start Stage 2B prior to August 1, that should not be an issue. | Mike Coleman | 2 | 2020-10-28 14:58 | 2020-10-29 15:19
20201110 | 20201110017 | 17 | Sign Bridge | After searching the plans I found a drawing of Structure S-51-257. I was unable to find an item number for this structure in the plans or proposals. Am I missing something or were the item numbers left out? Thanks | The sign structure plan sheets are located under the Tab 8 section of the plan, sheets 346 â€“ 347. All the items listed on the plan sheets are included in the proposal. Note: The two signs (#29 & #35) were installed last year. The existing signs are to be salvaged, stored and re-installed on this new sign structure. | Jill Fehrman | 3 | 2020-10-29 13:25 | 2020-11-02 12:05
20201110 | 20201110017 | 17 | Removing Pavement | Is the Removing Pavement Shown in Sheet 29 of the plans Concrete Pavement or some other type of pavement. | The Removing Pavement is for removing the full depth asphalt pavement and shall be paid for under and part of the Item Excavation Common for the widening area. | Jill Fehrman | 4 | 2020-11-02 00:14 | 2020-11-02 16:09
20201110 | 20201110017 | 17 | Traffic | The Traffic Section of the Special Provisions states, "...base patching work that encroaches on the travel lane will require flagging operations." Can this language be explained and further developed? Isn't all "base patching work" performed in closed lanes and does not encroach into live travel lanes not needing flagging? | Regarding base patching, this is for the contractorâ€™s information only. Base patching work will be within the lane closure, but in the narrow cross sections (10.5 ft travel lane), there is not sufficient buffer next to the longitudinal joint. Therefore, if the contractorâ€™s operations encroach onto the live lane, they would need to utilize flagging operations as needed. This is for the safety of the travelling public and the construction staff. As for intersection areas, flagging operations shall be required for base patching, milling and paving as the intersection remains open to traffic. Again, this is a safety concerns for roadway users and workers. | Jill Fehrman | 5 | 2020-11-02 00:43 | 2020-11-02 16:46
20201110 | 20201110017 | 17 | Removing Pavement | Will The area shown as 2 Pavement Removal on Sheet 22 going to be paid as Pavement Removal or Asphalt Pavement Removal? | This is a turn lane widening area and excavation is required. Therefore, the pavement removal as indicated on the plan sheet shall be paid for and part of Excavation Common item for the widening of the area. There will be no additional pay for Pavement Removal itself (as it is not an item.) | Jill Fehrman | 6 | 2020-11-02 12:19 | 2020-11-02 16:47
20201110 | 20201110017 | 17 | Moving Signs Type I | In the Specials, #18 for removing the sign structure, it states that the existing signs shall be moved under the move signs type 1 bid item. In the answer to question #3 for this project, it was noted that signs 29 and 35 are to be moved to the new sign structure. I can't find the bid item for moving type 1 signs. Is there an addendum in the works or am I missing it? | Yes, an addendum will be submitted to add the item â€œMoving signs type 1â€ to the contract. | Mike Coleman | 7 | 2020-11-02 15:49 | 2020-11-05 08:44
20201110 | 20201110017 | 17 | Rapid Set Deck Repair - Need Bid Item? | If bridges 54 & 74 are required to be opened to traffic after each night of Deck Prep should a Bid Item for Rapid Set Deck Repair be added to this contract? If not, how can this requirement be met? | Yes, an addendum will be submitted to add this item â€œRapid Set Deck Repairâ€ to the contract. | Mike Coleman | 8 | 2020-11-02 21:20 | 2020-11-05 08:54
20201110 | 20201110017 | 17 | Road closure | Will STH 38 be closed at STH 31 in stage 1, on page 137 there is FMS signing saying the road is closed and follow DETOUR and on page 140 it shows the road closed. The detour and road closure are both called out for stage 2A | STH 38 from STH 31 to the east project limit will remain open to traffic during stage 1. The full roadway closure and detour traffic for this section shall not begin earlier than August 1, 2021 under stage 2A, as indicated in the special provisions. The FMS signs with the date required to be in place at least 14 days prior to the full roadway closure or August 1, 2021 date. | Mike Coleman | 9 | 2020-11-04 09:01 | 2020-11-04 11:49
20201110 | 20201110017 | 17 | Night Work | The Traffic Control Plans call for night work from Shamrock to STH 31. This is a residential area and typically WisDOT does not call for night work in residential areas unless it is absolutely necessary. Can it be confirmed night work is required and this will not be changed? | Due to narrow lane width and heavy traffic volume, some of the operations will require night time work, especially at STH 38 & STH 31 intersection. As outlined in the SPV Article 12, Public Convenience and Safety, the contractor shall notify Tom Lazcano, Village of Caledonia Engineer, and Tony Beyer, Village of Mount Pleasant Engineer, a minimum of 14 days before any overnight closure. | Mike Coleman | 10 | 2020-11-08 11:01 | 2020-11-09 09:28
20201110 | 20201110017 | 17 | SHES Base Patching | Is the SHES Base Patching on STH 31 between STA. 651+03 and 654+13 included in the Plan Quantities? What time of day is this work to be performed? Are there any special restrictions in performing this work? | Yes, the SHES Base Patching quantities is included in the plan. There is restriction associated with this item as this work cannot be done during peak hours. Night time intersection closures for this work are permitted with proper notification and coordination with the local authorities as outlined in the special provisions for the project. | Mike Coleman | 12 | 2020-11-08 13:09 | 2020-11-09 10:20
20201110 | 20201110018 | 18 | Storm Sewer Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Additionally, breaker run can be counted towards sub-grade cover when used for stabilization (FDM 13.15.9). Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2020-10-12 11:22 | 2020-10-22 05:26
20201110 | 20201110018 | 18 | Soils Report | Please provide the soils report. | The soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110018/ | Mike Coleman | 2 | 2020-10-16 21:13 | 2020-10-19 10:19
20201110 | 20201110018 | 18 | Stage 1 Stage Line | The Stage line in the cross sections runs directly down the center of STH 20. The concrete paver will need 4 feet of the centerline in Stage 1. Can the Pavement Removal and Common Excavation be performed over the Stage line 4 feet? | Yes, Pavement removal and common excavation can be performed over the stage line 4 feet in stage 1. If the contractor decides to remove pavement up to four (4) feet left from the reference line, sawcut should be along the limit of pavement removal, not along the center-line. Contractor will not get paid for sawcut along centerline and four (4) left from the centerline. | Mike Coleman | 3 | 2020-10-17 22:38 | 2020-10-19 11:19
20201110 | 20201110018 | 18 | Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2020-10-22 06:25 | 2020-10-22 09:40
20201110 | 20201110018 | 18 | CAD Files | Could the CAD files please be provided. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110018/ | Mike Coleman | 5 | 2020-10-26 12:01 | 2020-10-29 15:07
20201110 | 20201110018 | 18 | Crushed Aggregate Base | Can milled asphalt be used as crushed aggregate base course? | Section 301 (Table 301-1) of the Standard Specs allows for Reclaimed Asphalt to be used as 1 ï¿½ inch base course. Section 305.2.2.2 lists the gradation requirements for reclaimed asphalt. | Jill Fehrman | 6 | 2020-10-28 20:14 | 2020-11-02 10:33
20201110 | 20201110018 | 18 | Crushed Aggregate Base | Can milled asphalt be used as crushed aggregate base course? |  |  | 7 | 2020-10-28 20:14
20201110 | 20201110018 | 18 | Sidewalk Staking. | Can a sidewalk staking item be added? | No. Sidewalk staking will not be added. | Mike Coleman | 8 | 2020-10-28 23:12 | 2020-10-29 15:12
20201110 | 20201110018 | 18 | Temporary Crushed Aggregate Base Course Item. | Would WisDOT consider adding a temporary crushed aggregate base course item. | No. | Mike Coleman | 9 | 2020-10-28 23:29 | 2020-10-29 15:33
20201110 | 20201110018 | 18 | 5' MH #8 | Is reducing Manhole #8 5' Diameter to a 48" Manhole above the pipe allowed on this project? | MH# 8 is an existing MH; this MH needs to be reconstructed. MH diameter should be same as existing for the entire depth. | Jill Fehrman | 10 | 2020-10-29 14:13 | 2020-10-30 09:28
20201110 | 20201110018 | 18 | 8-1/2" PCC pavement quantites | Per sheet 374 the plan quantites total of 49,883 sy for 8-1/2"pavement needs to remove 4,639 sy to reflect a total of 45,224 sy. Sheets 107-110 identify 8-1/2" HES area thats within the 8-1/2" pavement location.the hEs pavement was already identified in the pan quantities. | Concrete Pavement Removal and new pavement (both standard and HES) quantities shown on plan and miscellaneous quantity tables are correct. | Jill Fehrman | 11 | 2020-10-30 15:55 | 2020-11-02 10:30
20201110 | 20201110018 | 18 | Temporary Crushed Aggregate Base | Will Temporary Crushed Aggregate Base be needed for pedestrian traffic and vehicle traffic that will also need to be removed or can we plan on placing all Crushed Aggregate Base to plan elevations or elevations taken from the cross sections? | Access to business and residences needs to be maintained during construction. Base aggregate dense needed to maintain access during construction will not be paid separately, it should be incidental to construction. | Jill Fehrman | 12 | 2020-10-31 06:09 | 2020-11-02 10:31
20201110 | 20201110018 | 18 | Asphalt Surface Temporary | Can you clarify where the Asphalt Surface Temporary will be used? Assuming it is used for walk ramps and pedestrian traffic, how is the removal of the Asphalt Surface Temporary paid? | Location for asphaltic surface temporary (Temporary pavement) is shown on the staging plans. It is not for maintaining pedestrian access, it is for providing smooth transition between new and existing pavement for cross traffic. Removal is included in the common excavation. | Jill Fehrman | 13 | 2020-10-31 06:19 | 2020-11-02 10:33
20201110 | 20201110018 | 18 | Petroleum Contaminated Soil | Has the Petroleum Contaminated soil been removed from the Common Excavation volumes in plans or will both the Common Excavation and Petroleum Contaminated excavation be paid in the areas that have Petroleum contamination. | The quantity of contaminated soil was inadvertently included in the Common Excavation quantity shown in earthwork miscellaneous quantity table. The volume of contaminated soil within the limits of pavement structure is approximately 2,500 CY and will not be paid for as common excavation. This quantity should be deducted from total quantity of common excavation (69,668 CY) included in the contract. Quantity of common excavation currently shown in proposal = 69,668 CY Volume of contaminated soil = 2,500 CY Net quantity of common excavation = 67,168 CY. Excavation and removal for contaminated soil is included in pay item 205.0501.S. | Jill Fehrman | 14 | 2020-10-31 21:57 | 2020-11-02 10:35
20201110 | 20201110018 | 18 | Contract execution | Will there be any issues executing the contract prior March 1st, 2021 to give the contractor an opportunity to begin work at this time if weather and conditions permits? | We do not have issues with work starting earlier as requested. At this time, all utilities are proposed to be moved by that time. | Mike Coleman | 15 | 2020-11-03 09:25 | 2020-11-05 09:24
20201110 | 20201110018 | 18 | Sawing | Will sawing of the concrete sidewalk be paid where sidewalk abuts existing sidewalk or other structures and there isn't an expansion joint? | Sidewalk abutting existing sidewalk should be replaced to the nearest joint, therefore sawcut for sidewalk replacement abutting existing sidewalk is not anticipated. Sawcut for sidewalk replacement abutting other structures, if needed, will be paid and those locations are shown on the plan. | Mike Coleman | 16 | 2020-11-04 07:49 | 2020-11-04 08:52
20201110 | 20201110018 | 18 | Sawing sidewalk | Will sawing sidewalk be paid where there is not an expansion joint at building fronts? Some areas the existing sidewalk appears to go under the building front. Will sawing of sidewalk be performed at building fronts where needed to avoid damage to the buildings? | Sidewalk should be replaced up to the nearest joint. If they need to be replaced at non-joint location because of the fieled condition, sawing sidewalk will be paid as approved by the engineer. | Mike Coleman | 17 | 2020-11-07 05:46 | 2020-11-09 08:00
20201110 | 20201110019 | 19 | Steel Crack Repair, Special 06 B-64-019 | There are no special provisions or a bid item provided for work involving the "Special 06. Steel Crack Repair(B-64-019) SPV.0060" detailed under B-64-019 on page 369 of the plans. | The wrong structure plans were inadvertently inserted in the plans. The correct sheets have been added by addendum. | Mike Coleman | 1 | 2020-10-22 10:40 | 2020-10-22 13:37
20201110 | 20201110019 | 19 | Bearing and joint repair details B-64-19 | There are quantities listed for bearing removals and what must be laminated bearing pads on B-64-19 but there are no plan details for this. Judging by the quantities listed under "Expansion Device" there looks to be a joint repair on this structure as well but no details for that are listed either. | The wrong structure plans were inadvertently inserted in the plans. The correct sheets have been added by addendum. | Mike Coleman | 2 | 2020-10-22 11:28 | 2020-10-22 13:38
20201110 | 20201110019 | 19 | Missing Bid Items? | 1) Page 25 shows a "Silt Fence Drainage Outlet, Rock Bags" detail. There is no bid item for this outlet or for Rock Bags. Is this incidental to the "Silt Fence" bid item? Will the "Culvert Pipe Checks" bid item be utilized and run over quantity? Or, will "Rock Bags" be added? 2) Page 30 shows a barrier of sand bags. The t-barrier shows the ballast of sand bags. Is the wall of sand bags incidental to the work, incidental to the t-barrier, or should a "Sand Bags" bid item be added? | 1) The item Rock Bags will be added to the proposal to match the construction detail â€œSILT FENCE DRAINAGE OUTLET, ROCK BAGS. Heavy Silt Fence does have the rock bags or sandbags as incidental to the item. The culvert pipe checks are being utilized and were calculated based on the information shown in the erosion control plans. The quantity should be accurate. 2) The sand bags are incidental to the turbidity barrier per the standard specifications. | Jill Fehrman | 3 | 2020-10-27 10:22 | 2020-11-01 19:57
20201110 | 20201110019 | 19 | Removing Concrete Pavement / Earthwork Summary table | Trying to verify removing concrete pavement quantities bid item 204.0100 6,380 SY. Do these quantities include the existing rubbelized reinforced concrete pavement shown on the typical existing sections? Please clarify. Earthwork summary table (plan sht. 169)- Salvaged/Unuseable Pavement Material. Do these quantities include just the existing asphalt or does these include the existing rubbelized concrete? Please clarify. | The removing concrete pavement quantity includes removing the pavement to the bottom of proposed pavement depth. The pavement depth for USH 12 with asphalt pavement is 14â€. The pavement depth for USH 12 with concrete pavement is 15.5â€. Depending on the proposed profile, there could be some portions that will include removal of the existing rubbelized concrete pavement that would be paid for under common excavation & the removing pavement bid items. The salvaged/unusable pavement material is for information only and is paid for with the common excavation bid item. This quantity includes any materials that would not be useable for fill to get an accurate borrow quantity. | Jill Fehrman | 4 | 2020-10-28 12:32 | 2020-11-02 10:39
20201110 | 20201110019 | 19 | Traffic control on Pell Lake road/B-64-23/24 | What specific traffic control will be required or used for the Pell Lake road structures B-64-23/24 as it pertains to Pell Lake road? | Nighttime closures on Pell Lake Drive are anticipated to remove the deck for B-64-23 & B-64-24. All other construction activities can be completed while maintaining traffic on Pell Lake Drive. | Jill Fehrman | 5 | 2020-10-29 11:09 | 2020-11-01 19:45
20201110 | 20201110019 | 19 | 643.0500 Flexible Tubular Markers | Hello, in Stage 1 of this project there are 880 Flexible Tubular Markers installed, however on Stage 2 the quantity is almost doubled to 1,750 Flexible Tubular Markers. It appears that they are installed over the same length and same spacing as Stage 1; is the quantity for Stage 2 too high or will there be 1,750 posts installed? Thanks | The quantity for Stage 2 is high and will be similar to the Stage 1 quantity. | Jill Fehrman | 6 | 2020-10-29 13:55 | 2020-11-01 19:49
20201110 | 20201110019 | 19 | IR Reports | Can you post the IR reports for bridges B-64-19, 26, and 27? | The IR Reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110019/ Deanna, please create a link in the SE Region Preliminary Plans Page for proposal #19. | Mike Coleman | 7 | 2020-11-04 12:23 | 2020-11-04 12:28
20201110 | 20201110019 | 19 | Interim Completion Durations | The interim completions listed for USH 12 and Pell Lake Dr interchange describe to reopen after structure overlay, parapet repair, etc. (page 6 of 53 in the special provisions) These structures are not overlays but deck replacements. Is the provided 50 calendar days for an overlay or deck replacement work? This is an aggressive duration for a deck replacement. The 3 overlay structures allow for 28 calendar day closures each. Considering the amount of deck prep quantity anticipated is this an appropriate duration for the scope of work on these structures? Can the DOT provide their preliminary schedule for this job? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110019/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 8 | 2020-11-05 11:58 | 2020-11-05 14:33
20201110 | 20201110021 | 21 | Traffic Control channelizing devices | Hello, what is the intent of the following traffic control channelizing devices: 643.0300 Traffic Control Drums (9,150 days) 643.0500 Traffic Control Flexible Marker Posts (1,820 each) 643.1070 Traffic Control 42-Inch Cones (18,310 days) On most prior projects similar to this one, Drums have been used for short durations at beam guard sites; but the 42" cones are not usually included in this type of project, especially with that high of a quantity. Flexible Marker Posts are usually installed for longer term applications, and with this project controlled by Flagging Operations, the temporary traffic controls will be moved daily and I don't see a place for these to be installed. Thanks | The moving lane closure scenario impacted quantities for several traffic control items with some being eliminated. There is also a reduction of traffic drums for the beam guard improvements. This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2020-10-21 09:28 | 2020-10-29 06:35
20201110 | 20201110021 | 21 | Temp Epoxy on Centerline Rumbles | Page 28 of 29 of the proposal (#18) states that there should be temporary Epoxy on the edgelines, as well as the centerline prior to the installation of the rumble strips. Misc quantities only show quantities for the edgelines. Will there be an addendum to add quantities of temporary epoxy for the centerline? | This will be addressed in an upcoming addendum. | Mike Coleman | 2 | 2020-10-26 10:22 | 2020-10-29 06:35
20201110 | 20201110021 | 21 | Pavement Markings | In looking at the addendum that came out on 11.02.2020, it appears there is a temporary paint quantity for the edge lines on the surface that will, in essence, provide for the layout of the shoulder rumble strips which makes perfect sense. I do not see any temporary paint for the milled surface (allowed for up to 72 hours per the note on page 3 of 29). In looking at the temporary epoxy for the surface, it makes perfect sense as that item will be put down daily after paving. I am wondering if you might add a same day bid item back into the project insure the presence of a center line daily after the installation of the sinusoidal centerline rumble strips from station 706+30-860+00 * 906+00-992+70? Will an addendum be issued to cover these items? Thank you. | Quantity is accounted for with temp epoxy â€“ 6,920 LF for 4â€™/50â€™ skips for the length of the project. Temporary epoxy item now includes application of long line markings on the same day the pavement is placed or milled, per 649.3(5) of the 2021 Std Spec. The Marking Line Epoxy 4-Inch bid item is then included to re-mark the CL markings where CL rumble strips have been installed. There is 92,700 LF of epoxy to cover this application. No addendum to be issued. | Mike Coleman | 3 | 2020-11-03 08:56 | 2020-11-03 11:54
20201110 | 20201110021 | 21 | Line 0014 Base Aggregate 1 1/4inch | The miscellaneous quantities show the 72ton for the 1 1/4inch base being for PE's and CE's. As there is no excavation in these area shouldn't this quantity be accounted for in line 0012 Base Aggregate Dense 3/4 inch. | An addendum is being issued to correct this. | Mike Coleman | 5 | 2020-11-03 15:18 | 2020-11-05 14:08
20201110 | 20201110021 | 21 | Preparation for foundation for asphaltic shoulders | Sheet 8 shows 2 foot widening in rural section throughout the project. Would a preparation of foundation for asphaltic shoulder item be proper for the grading prep prior to the paving work? | An addendum will be issued to clarify. | Mike Coleman | 6 | 2020-11-03 15:23 | 2020-11-05 14:09
20201110 | 20201110022 | 22 | Culvert Pipe Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | The CPRC Class III bid items will be changed to Culvert Pipe Class III-A bid items in an upcoming addendum. Class III-B pipes will not be utilized as our max fill height is less than 11ft. This will allow the contractor the flexibility in choice of pipe materials. 522.0118 Culvert Pipe Reinforced Concrete Class III 18-Inch will become 520.3318 Culvert Pipe Class III-A 18-Inch 522.0124 Culvert Pipe Reinforced Concrete Class III 24-Inch will become 520.3324 Culvert Pipe Class III-A 24-Inch 522.0136 Culvert Pipe Reinforced Concrete Class III 36-Inch will become 520.3336 Culvert Pipe Class III-A 36-Inch There was a typographical error on the bid items in the previous answer. | Mike Coleman | 1 | 2020-10-12 14:17 | 2020-10-20 06:31
20201110 | 20201110022 | 22 | Clearing and Grubbing | Why is station clearing/grubbing shown as left and right in the same station range for one alignment? Why are Xâ€™s shown on the plans for tree removal, but no clearing/grubbing for those locations are shown in the miscellaneous quantities. | Errors regarding clearing/grubbing locations and quantities have been confirmed on the plan and miscellaneous quantity sheets. An addendum will be issued to correct these errors. | Mike Coleman | 2 | 2020-10-16 06:26 | 2020-10-16 06:27
20201110 | 20201110022 | 22 | Tied Longitudinal Joint | The typical section for STH 67 concrete construction shows a tied longitudinal joint at the 12-foot mark on a 15-foot wide slab, leaving only a 3-foot wide portion of the concrete slab to the outside of the joint. Is that correct? Also, why are the joints not shown on the paving detail? | The longitudinal jointing shown on the typical sections is shown correctly as intended. For concrete pavement less than 10 inches thick, the maximum allowed width of slab without a tied joint is 12 feet. The joint was placed at the 12-foot mark to meet this design requirement and to best define the edge of lane. The locations of the joints are adequately shown on the typical sections and do not need to be shown on the paving details. | Jill Fehrman | 3 | 2020-10-23 07:18 | 2020-10-23 07:19
20201110 | 20201110022 | 22 | Design Schedule | Can the department's design schedule be made available? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110022/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 4 | 2020-10-26 11:21 | 2020-10-26 13:18
20201110 | 20201110022 | 22 | Temp Epoxy - Layout Rumbles | Page 45 of 55 of the proposal (#28) states that temp epoxy should be used to layout the centerline and edgeline rumble strips. The misc quantities only have enough temp epoxy for the centerline layout. The temp paint looks to be used for the edgeline layout, but wouldn't be warrantied if the permanent markings(epoxy) are installed on top of paint. Therefore, the temp paint being used for layout of the edgeline rumbles should be changed to Temp Epoxy. Will there be an addendum issued to fix this issue? | The edgeline rumble strips are Type 1 on this project and only Type 2 edgeline rumble strips require Temporary Marking Line Epoxy per the special provision. An Addendum will be issued to remove the references to Type 2 rumble strips from that provision and to add a note to the miscellaneous quantities to define Type 1 edgeline rumble strips. | Mike Coleman | 5 | 2020-10-26 11:30 | 2020-10-27 14:21
20201110 | 20201110022 | 22 | MQ & Earthwork | Are the Misc Quantity tables and earthwork data sheets available in Excel? | The files requested can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110022/ These files are for information only and bids should be based on the info shown in the advertised materials. The contractor is required to meet the specification in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2020-10-26 15:50 | 2020-10-29 06:28
20201110 | 20201110022 | 22 | Article 38 of Special Provisions | For Article 38 of the special provisions, why is the required standard for flexural stress and flexural modulus of elasticity set so high? Can/should the required standard be reduced? | The department agrees that the required standard noted in Article 38 for flexural stress and flexural modulus of elasticity is set higher than whatâ€™s necessary for this work and can be reduced. An addendum will be issued to reduce the requirement for flexural stress and flexural modulus of elasticity to match the minimum standards per ASTM F1216. The addendum will also add clarification to the method of measurement for this item. | Mike Coleman | 7 | 2020-10-26 16:38 | 2020-10-26 16:39
20201110 | 20201110022 | 22 | HMA Pavement Types | The general notes on sheet 2 call out the 4" and 4.5" HMA pavement sections as having a lower lift of 3 LT. The plans and miscellaneous quantities appear to have it all figured as 4 LT. Should this note show both lifts as 4 LT? | The entire thickness of the 4 ï¿½-INCH HMA should be HMA PAVEMENT TYPE 4 LT 58-28 S. Therefore, both layers should be TYPE 4 LT. A correction will be made to the General Notes on plan sheet 2 to address this issue as part of an upcoming addendum. The 4-INCH HMA PAVEMENT as used on mainline within Elkhart Lake area consists of two layers - the lower layer HMA TYPE 3 and the upper layer HMA TYPE 4 as shown in the General Notes. However, within the concrete section at the south end of the project, the right-side shoulders are HMA PAVEMENT 4-INCH and those could be paved in one single layer since it is a shoulder application and are all HMA TYPE 4 LT. As part of an upcoming addendum, additional text will be added to the General Notes on plan sheet 2 for HMA PAVEMENT 4-INCH SHOULDER with an UPPER LAYER THICKNESS 4-INCHES OF HMA PAVEMENT TYPE 4 LT 58-28 S. | Mike Coleman | 8 | 2020-11-02 13:53 | 2020-11-03 16:04
20201110 | 20201110022 | 22 | CLEANING STORM SEWER PIPES / 24 LOCATIONS AND LOCATIONS DIRECTED BY ENGINEER | Do we have information on what is being asked at each location? Are we cleaning just a catch basin, or are we cleaning a lead, or are we cleaning a storm sewer pipe. If we are cleaning storm pipe, then what size and length. The cost differential in these scenarios are huge. | The payment section under article 32 explains that payment covers the cleaning out of â€œâ€¦drainage pipes and connected structuresâ€¦â€. The measurement section explains that each unit of work is â€œmeasured structure to structureâ€. So, the intent is that each unit of work includes the pipe run from structure to structure, including the structures. To help bidders quantify the work for each unit, information regarding the pipe diameter and approximate length will be added to the miscellaneous quantity table for this item as part of an upcoming addendum. | Mike Coleman | 9 | 2020-11-02 16:22 | 2020-11-05 06:01
20201110 | 20201110022 | 22 | Reclaimed Asphalt | SPV states Reclaimed asphaltic pavement will not be allowed as a base aggregate substitute in widening areas along the project. Can RAP be used in other areas on the project if it meets 305 spec? Is there a specific reason for this SPV? | The reason for the provision under the prosecution and progress article that prohibits the use of reclaimed asphaltic pavement (RAP) as a base aggregate substitute in widening areas is to ensure proper lateral drainage of the base layer and subgrade surface regardless of the adjacent pavement type. This provision applies to the outer area of the roadway cross section that is being widened or reconstructed down to the subgrade according to the typical sections and cross sections. RAP may be used in other areas on the project if it meets the requirements of section 305 of the standard spec. | Mike Coleman | 11 | 2020-11-02 20:41 | 2020-11-03 09:54
20201110 | 20201110022 | 22 | PST B-59-108 | With the 15 WD restriction on this bridge, is the Department okay with applying PST after the 15 WD's? With the wet cure and specification about placing PST, there does not seem to be enough time to apply PST within the window specified under the full closure. | The intent is re-open structure B-59-108 to traffic immediately after the 15 working day window has expired to complete the structure work. Per standard spec 502.3.13.2, application and proper drying of the protective surface treatment is required before opening to traffic. The department has reviewed the anticipated schedule for bridge work and feels 15 working days is adequate time to complete all the items associated with this structure, including the protective surface treatment according to the required time frames defined in the standard specs. | Mike Coleman | 12 | 2020-11-03 10:55 | 2020-11-04 05:43
20201110 | 20201110022 | 22 | Cofferdam Utility Conflicts | Can the department verify any underground utilities in the vicinity of the B-59-115 location that may conflict with the cofferdam? | At the time of field survey conducted during the design phase of this project, there were no underground utilities within the vicinity of C-59-115. The Department is aware of a utility permit issued for a fiber optic underground facility (Net-Lec) to be located on the west side of STH 67 in the vicinity of the box culvert. The utility company was informed of the future box culvert work and instructed to install their facilities low enough. Per standard specifications, the contractor is still responsible to coordinate with utility companies regarding existing facilities prior to the start of construction. | Mike Coleman | 13 | 2020-11-03 10:57 | 2020-11-04 05:41
20201110 | 20201110022 | 22 | Protection Angle Removal Excavation | Looking at deck detail A-A, it shows a 1" deep horizontal sawcut 6" down form top of deck. Removal is included in Type 2 quantities. Approach pavement removal is required to complete sawcut. There are no additional quantities for pavement removal or additional HMA for this area. This would not be excavation common. Would the department entertain the elimination of sawcut to solve this issue? | The existing typical section for this portion of STH 67 shows the existing asphaltic pavement depth to be approximately 8â€. In order for the contractor to make the horizontal sawcut shown in the bridge plans, we anticipate that the contractor will have to excavate deeper than the bottom of the existing 8â€ asphaltic pavement, which would classify the removal of both the asphaltic pavement and underlying base material as excavation. Since the general notes on the structure plan state that any excavation necessary to complete the overlay is to be considered incidental to the bid item â€œconcrete masonry overlay decks,â€ no pavement removal was quantified for this work. Furthermore, the department will not entertain the elimination of the horizontal sawcut, as it is considered necessary to properly remove the protection angles and adjacent concrete per the structure plan. However, in order to accommodate the excavation of asphaltic pavement and underlying base material at the approaches to both ends of the deck, plan notes and a quantity for sawing asphalt will be added to the plan as part of an upcoming addendum. The addendum will also add a note to the plan explaining that the removed asphaltic pavement will be replaced with HMA bid items at types and thicknesses directed by the engineer. | Mike Coleman | 14 | 2020-11-03 11:00 | 2020-11-04 05:43
20201110 | 20201110022 | 22 | Ryder Cup Special Event | Will working days be charged during the Ryder Cup hauling restriction from September 20, 2021 to September 27, 2021? | Working days will not be charged during the Ryder Cup special event period described in Article 5. | Mike Coleman | 15 | 2020-11-03 16:34 | 2020-11-04 08:00
20201110 | 20201110022 | 22 | Pipe Installation | 3 of the cross drains (Sta 152+92, 527+31, and 528+75) are 13' or more deep. Because it doesn't appear that the schedule will allow for the installation of these culverts when the roadway is closed, can the department add a bid item for lane shifts as has been done on other projects? | Articles 3 and 4 of the proposal require cross drain culvert pipe installations to be completed during the 15-working days allowed for detour #1 and associated closure. The department has reviewed the schedule and feels this is an appropriate duration to complete this work. The department will not be adding any lane shift items to this 2-way 2-lane highway project. | Mike Coleman | 16 | 2020-11-04 09:45 | 2020-11-04 14:31
20201110 | 20201110022 | 22 | Concrete Removal | In the areas where the concrete pavement needs to be removed it does not seem to be in the Excavation Quantities. I see the note in the cross sections but the existing grades in the cross sections seem higher than the new pavement. Which would mean there is excavation below the pavement. Should the pavement be in the excavation quantities if the cross sections are shown correctly? Please clarify. There is a quantity for pavement in the earthwork chart but doesn't seem to correlate with the SY of asphalt removal. Please clarify. | Removing Concrete Pavement is paid wherever it is being removed along the project (south end). Excavation Common is paid only for specified station ranges at the south end as indicated by labels on the cross section sheets. The earthwork data sheets (page 382 â€“ 408) are by Division (ie Stage). Division 2 is mainly NB STH 67 while Division 4 is mainly SB STH 67. When you add the cut from Division 2 to the cut from Division 4, you will find that it is large enough to account for the existing concrete pavement. The Note 1 on the EW Data Sheets is incorrect and will be changed in Addendum No 2 to remove the word NOT so that it reads â€œCut does include salvaged/unusable pavement material. Salvaged/unusable pavement material is calculated on the summary sheet.â€ The earthwork summary (miscellaneous quantities table) correctly states that salvaged/unusable pavement material is included in cut. Please keep in mind that the volume for the salvaged/unusable pavement material in the earthwork summary only includes the volumes for the station ranges that have earthwork. For Division 2, the earthwork summary lists From/To Station as 23+44 to 54+00 but not every station within that range has earthwork, only the stations indicated on the cross sections and the earthwork data sheets have earthwork and salvaged/unusable pavement material volumes (and the values would only be for the work area that falls within Stage 2). The existing DTM surface is mainly based on flown data with supplemental field survey as needed. There may be slight variations to the existing surface shown on the cross section sheets that can be attributed to the nature of flown surfaces. Proposed paving grades were established utilizing all the information at hand including field survey shots of the existing curb and gutter and centerlines, asbuilts, proposed pavement cross slopes which vary slightly from existing in some locations, and DTM surface. When a specific cross section station is labeled â€˜No Grading Requiredâ€™ that is the intention. The existing concrete pavement should be removed, the existing aggregate should be trimmed, shaped, and smoothed as necessary under the bid item Prepare Foundation for Concrete Pavement for the proposed concrete pavement to be placed. | Mike Coleman | 17 | 2020-11-04 14:25 | 2020-11-05 10:20
20201110 | 20201110024 | 24 | Design Schedule | Can the Design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110024/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-10-19 09:58 | 2020-10-20 07:11
20201110 | 20201110024 | 24 | Curb Ramps | What is the plan for the curb ramps that don't have construction details? Are they being rebuilt similarly to the ones that do have details? | The curb ramps without construction details are not being reconstructed. The existing ramps at these locations are to have a rectangular or radial area cut out and detectable warning field plates installed. The locations and radii of radial detectable warning fields are indicated on the plan sheets. | Mike Coleman | 2 | 2020-10-26 12:45 | 2020-10-26 12:46
20201110 | 20201110024 | 24 | Asphalt Patching at Curb | What item will the asphalt at curb removal areas get paid under? Can you provide a detail for depth and material please? | An addendum will be issued to clarify. | Mike Coleman | 3 | 2020-10-28 15:20 | 2020-11-02 09:00
20201110 | 20201110025 | 25 | Payment for Excavation Common under Sidewalk, Driveways and Curb & Gutter | There is a bid item for Excavation Common for EBS Areas, but nothing shown for the excavation under sidewalks, driveways and curb & gutter where Base Aggregate Dense 1 1/4-Inch is being placed. How is the Excavation Common being paid for under the removed and replaced items of sidewalk, driveway and curb & gutter ?? | The area under the sidewalks, driveways, and curb and gutter where Base Aggregate Dense 1.25â€ is being placed will be paid as Excavation Common. The total volume for these areas in the plan is 150 CY. | Mike Coleman | 1 | 2020-10-22 13:54 | 2020-10-26 14:28
20201110 | 20201110025 | 25 | Reconstructing Manholes | Is The Manhole At Station 114+11 A Sanitary Manhole, Is It In The Sidewalk & Does It Need To Be Set To a Revised Elevation. Thank You. | The manhole at station 114+11 is a sanitary manhole. It is currently in the sidewalk but will be outside of the sidewalk (in the terrace) following the reconstruction of the adjacent curb ramp. The rim elevation of this manhole will need to be lowered to match the adjacent sidewalk. | Jill Fehrman | 2 | 2020-11-02 11:23 | 2020-11-02 16:07
20201110 | 20201110025 | 25 | Manholes 4-Ft Diameter | The Plan Shows Only 1 Pipe To This Manhole. It looks Like There Could Be More And There Is A Box Culvert In The Same Area. Should We Assume The 1 Pipe To Reconnect. Thank You. | It should be assumed that there are 2 pipes to reconnect; one to the north and another to the south. The contractor will be responsible for verifying existing pipe connections, sizes, and elevations prior to construction. | Jill Fehrman | 3 | 2020-11-02 11:26 | 2020-11-02 16:07
20201110 | 20201110026 | 26 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110026/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-10-26 11:06 | 2020-10-26 12:52
20201110 | 20201110026 | 26 | Salvaged Base Aggregate Dense 3/4-Inch | The typical section shows Salvaged 4" Base Aggregate Dense for Shoulders. There doesn't seem to be a bid item that covers the scope of salvaging and replacing the shoulder gravel after paving. How does the department intend to pay for this scope of work? | Proposed response: Payment for using excavated base to shape remaining aggregate shoulders is covered under the item of 211.0400 â€“ Prepare Foundation for Asphaltic Shoulders, see 211.3.5.1(2). | Jill Fehrman | 2 | 2020-10-28 10:12 | 2020-11-01 19:44
20201110 | 20201110027 | 27 | Culvert Pipe | The project has an SPV item for 100' of 62"x102" Arch pipe and two endwalls. Arch pipe is not a standard or available. However, 68"x106" Elliptical pipe and the endwalls are available. Please advise if an addendum will be issued to allow this larger sized elliptical pipe instead of the arch pipe. Thanks. | An addendum is being issued to adjust the size. | Mike Coleman | 1 | 2020-10-08 08:35 | 2020-10-27 10:38
20201110 | 20201110027 | 27 | Culvert Pipe Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB (non-metal) culverts shall be used at every opportunity possible, up to 20,000 Design ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) CPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for culvert pipe Class IIIA and/or IIIB in lieu of the sole specified CPRC Class III? | The proposal will be changed by addendum to allow non-metal pipes. This issue will be addressed by an upcoming addendum. | Mike Coleman | 2 | 2020-10-12 13:55 | 2020-10-20 06:43
20201110 | 20201110027 | 27 | Design Schedule | Could you make the schedule developed during design available? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110027/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2020-10-21 12:35 | 2020-10-29 14:55
20201110 | 20201110027 | 27 | Boring Information near Station 405+00 | Could the boring information be provided near Station 405+00? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110027/ | Mike Coleman | 4 | 2020-10-21 12:36 | 2020-10-22 09:50
20201110 | 20201110028 | 28 | Storm Pipe Materials | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III and/or IV? | We have conferred with design staff and the City of Waupaca and will issue an addenda to replace all of the existing RCP Class III bid items with the following items: 608.3615 Storm Sewer Pipe Class III-B 15-Inch LF 608.3618 Storm Sewer Pipe Class III-B 18-Inch LF 608.3624 Storm Sewer Pipe Class III-B 24-Inch LF 608.3630 Storm Sewer Pipe Class III-B 30-Inch LF 608.3636 Storm Sewer Pipe Class III-B 36-Inch LF | Mike Coleman | 1 | 2020-10-12 14:13 | 2020-10-15 05:54
20201110 | 20201110028 | 28 | Silva Cell System Alternates | Regarding bid item â€œSoil Cell Systemâ€ It appears the specification is a cut and pasted version of the GreenBlue Rootspace propriety specification and as such indicates Rootspace as the only acceptable product. Iâ€™m requesting that Deeproot Silva Cell be added as an approved equal. If this is not possible please provide an explanation as to why. | Yes, Deeproot Silva Cell would be considered an approved equal, and we will revise the specification to clarify this as part of an upcoming addendum. | Mike Coleman | 2 | 2020-10-14 14:26 | 2020-10-19 08:03
20201110 | 20201110028 | 28 | Temporary Asphalt | On the traffic control plans in stage 1 for the 10 day closure there a note for placing temporary asphalt. There is no quantity or thickness in the plans. Should an item be added for the Temporary Asphalt? | Temporary asphalt will be added via an upcoming addendum. | Mike Coleman | 3 | 2020-10-15 09:07 | 2020-10-16 06:33
20201110 | 20201110028 | 28 | 7" conc pavement | Will the 7" concrete Pavement be a doweled Pavement with transverse contraction baskets | Yes, it will be. We will also be adding SDD 13C13 Urban Doweled Concrete Pavement to the plans, via an upcoming addenda. | Mike Coleman | 4 | 2020-10-16 09:28 | 2020-10-19 11:25
20201110 | 20201110028 | 28 | Soils Report | With some of the storm sewer 22 ft deep and the water main being at a minimum cover depth of 8ft is there a soils report available for this project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110028/ | Mike Coleman | 5 | 2020-10-21 08:16 | 2020-10-21 11:02
20201110 | 20201110028 | 28 | Maintain water service | The special provisions does not really say anything a service outage when the final connection is done for the water service. Is the contractor required to maintain water service 100% of the time? | No, water service is not expected to be connected 100% of the time. Short term service disruptions are expected during connection to the new service line and 48 hours notice required per the water SPV special provisions. | Mike Coleman | 7 | 2020-10-21 08:25 | 2020-10-21 11:05
20201110 | 20201110028 | 28 | Salvaged Trolley Rail | The special provisions says what to do with the rail that is salvaged but does not address what the contractor is supposed to do with any railroad ties if they are encountered while removing and salvaging these rails. How will the contractor be compensated for disposing of railroad ties which will most likely need to be disposed of at a landfill? | The ties will become the property of the contractor, and disposal if needed, should be included in the bid amount for this item. | Mike Coleman | 8 | 2020-10-21 10:22 | 2020-10-26 07:25
20201110 | 20201110028 | 28 | Sanitary Sewer Main Air Test | The presence of many laterals along the proposed sanitary main line makes air testing of the proposed main impractical. Can the air test requirement for the sanitary main be removed? | Air testing on mains with active laterals will not be required. The language is standard language and the test shall be performed if an entire run (manhole to manhole) is installed with no active laterals connected to it during main installation. | Jill Fehrman | 9 | 2020-11-05 15:01 | 2020-11-06 08:31
20201110 | 20201110028 | 28 | Water Main Removal/abandonment | Does all replaced watermain get removed? Can watermain get plugged and left in place when it is not in conflict with other new construction? If in-place abandonment is acceptable would the pipe have to be filled with sand or slurry? | No, the existing watermain does not all have to be removed, only as needed to facilitate other construction and excavation activities. Yes, the existing watermain that does remain in place can be abandoned by plugging the ends and capping. No slurry or sand fill would be required. | Jill Fehrman | 10 | 2020-11-05 15:14 | 2020-11-06 12:12
20201110 | 20201110028 | 28 | Sanitary and Water Trench Backfill | Will native soil be suitable for backfill of the sanitary and water main trenches? | It is anticipated that native soil will be acceptable for backfill material, however soil types, layer thickness, and moisture content will not be known until excavation has been completed. The soils report is available for contractor review prior to make their own determination. | Jill Fehrman | 11 | 2020-11-05 15:15 | 2020-11-06 08:32
20201110 | 20201110028 | 28 | Railing SPV.0090.01 | Is there a detail available for the proposed railing? | Yes, there is a detail for the railing on page 18 of the plan. Shop drawings are to be provided per the special provisions for Railing, Item SPV.0090.01 and following Standard Specifications 513 and 654.3. | Jill Fehrman | 12 | 2020-11-05 15:47 | 2020-11-06 08:33
20201110 | 20201110028 | 28 | Railing SPV.0090.01 - Response | Respectfully, plan sheet 18 is not a detail of railing. It just states "Railing 42-Inch". Special Provision SPV.0090.01 only tells me it's a steel railing. Standard Specification 513 only tells me it's galvanized and might be painted. Is the railing painted? Is the fabricator responsible to design and engineer the railing (uncommon for a WisDOT project)? Is it just a 3-pipe railing? Is it a guardrail with pickets? When I scale the drawing, it looks like the run of the ramp is 8'-3" inches which results in a rise greater than 6-inches; thus requiring a handrail on both sides per ADA. A 42-inch railing doesn't meet ADA either. | Yes, the railing and all components are to be painted black and is 2-inch tubular 3-pipe railing with horizontal members equally spaced | Mike Coleman | 13 | 2020-11-06 09:04 | 2020-11-09 06:38
20201110 | 20201110029 | 29 | Design Schedule | Could the DOT submit the schedule developed during design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20201110029/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2020-10-21 12:33 | 2020-10-22 09:35
20201110 | 20201110030 | 30 | Traffic Signals & Mounting Hardware | Can you please confirm if traffic signals, push buttons and mounting hardware are to be yellow or black? Also if the pedestrian signal face should have the tunnel visor or z-crate visor? | â€¢ Traffic signal faces, pedestrian push buttons, and signal mounting hardware are to be yellow. â€¢ Pedestrian signal faces are to have a z-crate visor. | Mike Coleman | 1 | 2020-10-26 12:51 | 2020-10-26 16:31
20201110 | 20201110031 | 31 | B-17-226 Proposal 31 plate detail | The girder detail page notes a beveled anchor plate with the details on the superstructure sheet; however, there are no plate details on either superstructure sheet. Please confirm the existence of a beveled anchor plate, and if so, provide details. | The plate is a mistake in the plans. It should show a semi-expansion girder end detail. An addenda will be issued to correct this detail. | Mike Coleman | 1 | 2020-10-20 14:28 | 2020-10-21 08:52
20201110 | 20201110032 | 32 | Lane Repair Item | The special item Lane Repair in the proposal, page 33 under C Construction states â€œthe engineer shall determine the location and depth of the extra milling.â€ In the plan it shows a detail on sheet 19 with the lane repair area being 12â€™ wide and 2â€ deep. If the engineer changes the thickness this changes the amount of milling and HMA needed for the patch and could require a change in price since this item is paid by the LF. If we use the detail on page 19 in the plan, we know what we need to do. If changes are expected please clarify what the maximum/minimum values could be for pricing or consider changing the unit to allow for variations. | The intent of this item is to have a depth of 2â€, with the ability of the engineer to increase that depth if needed and that lane areas with additional depth beyond 2â€, in 2â€ depth increments, would be paid for as additional LF of the Lane Repair item. | Mike Coleman | 1 | 2020-11-02 15:24 | 2020-11-05 08:06
20201110 | 20201110032 | 32 | Temporary Pavement Markings | Good afternoon. Can you please elaborate on the temporary pavement markings. It would appear that temporary paint will be needed on the milled surface as well as the lower layer but the quantities included do not seem to account for the applications needed. In addition, it appears there are center line rumble strips throughout the project and, while you have a same day epoxy item to stripe the surface after each days paving, there does not appear to be enough quantity included to re-stripe the center line after the rumbles are installed. Will more clarification and/or an addendum be issued to address this matter? Thank you. | Additional quantities of temporary marking will be included for the interim milled/lower surface as well as for the final top pavement surface for centerline marking prior to rumble installation. The Same Day marking will be changed to standard Epoxy to be marked after the rumbles have been installed. These changes will be included in the upcoming addenda. | Mike Coleman | 2 | 2020-11-02 15:41 | 2020-11-05 08:07
20201110 | 20201110032 | 32 | Culvert Patch HMA Type | On sheet 2 of the plan in the lower right corner it shows the pavement layers and types. For the culvert patches it shows placing 3 lifts of 5MT58-34V. Due to the staging and work restrictions in the proposal the culvert patches most likely need to be completed prior to starting milling. They will likely be paved up to surface and then milled and overlayed per the plan with the 5MT. It appears all the 5MT falls under the PWL specification. PWL will not work for the culvert patches. To do QMP testing on the small amount needed for the culvert patches is not the best either. We suggest using the asphaltic surface item for the culvert patches. The type of HMA and Asphalt Cement could be specified if needed. The Lane Repair item requires a 4MT58-28S so it would be best to stay consistent with that if required. | The pavement type used for the lowest layer in the culvert replacement areas will be changed to Asphaltic Surface, and this change will be included in the upcoming addenda along with a detail. | Mike Coleman | 3 | 2020-11-02 16:13 | 2020-11-05 08:08
20201110 | 20201110032 | 32 | Retaining Wall | Is Rockwood Retaining Walls Classic Colonial 8-Inch an acceptable alternative for the Modular Block MSE Wall? | As long as the block type is on the WisDOT approved products list and meets the requirements of the retaining wall plans it is anticipated to be acceptable. | Mike Coleman | 4 | 2020-11-03 12:59 | 2020-11-05 09:57
20201110 | 20201110032 | 32 | Retaining Wall | The proposed retaining wall will require temporary shoring as shown in the plan in order to maintain access along State St. and will also provide a way to perform the required excavation for the proposed wall and soil reinforcement near the existing home on the west end of the proposed wall. This area is currently congested with multiple overhead utility crossings and also has existing water and sewer running directly underneath the existing wall in several locations. It appears that most of the utilities in this are are shown as "No conflicts or relocations are anticipated." Can anything be done to address the utility concerns in this area? | The existing sewer and water laterals are required to remain in place to maintain those facilities to the adjacent properties. Through coordination with Xcel Energy the overhead utility was not anticipated to be relocated for the construction activities. Coordination with Xcel Energy may be required for the overhead utility if due to the contractor means and methods, it is determined that the overhead utility impedes the construction operations. | Mike Coleman | 5 | 2020-11-03 13:33 | 2020-11-05 14:05
20201110 | 20201110032 | 32 | 511.1200 Temp Shoring R-47-22 | Traditional temporary shoring methods will not be feasible in this location due to the proximity of the existing house as well as existing utilities. What method of temporary shoring was used by the designer during the constructability review? | The shoring method is typically determined by the contractorâ€™s mean and methods and a specific shoring type was not determined by the designer. Due to the site conditions and constraints unconventional shoring methods may be required. | Mike Coleman | 6 | 2020-11-03 14:48 | 2020-11-05 14:05
20201110 | 20201110032 | 32 | Common Ex | The plan shows common excavation quantities at the several of the culvert replacements. The cross sections seem to show most of that quantity comes from directly above the pipe. Will the department actually pay for that excavation as common ex or will it end up being incidental to the pipe installation? | The excavation for the culvert replacement will be incidental to the culvert pipe. The excavation quantity will be reviewed and if needed updated in an upcoming addendum. | Mike Coleman | 7 | 2020-11-05 05:35 | 2020-11-05 09:00
20201110 | 20201110032 | 32 | R-47-0022 Railing Detail | Are there railing details available for structure R-47-0022? | The pipe railing used for the retaining wall should follow the standard specifications for the item and the details shown in the retaining wall plans. | Jill Fehrman | 8 | 2020-11-05 15:40 | 2020-11-06 12:11
20201110 | 20201110032 | 32 | Temporary markings on surface | Good morning and thank you for addressing our previous question. Typically the temporary markings on the surface prior to the rumbles is a temporary epoxy item rather than a temporary paint item to allow for proper adhesion of the final epoxy markings. Typically the zones are also placed in advance of the rumbles as well. Can/will an addendum be issued to address this matter? Thank you. |  |  | 10 | 2020-11-07 07:33
20201110 | 20201110017 | 17 | Difference Between Base Patching and Pavement Replacements on STH 38. | Normally Base Patching is performed and paid in areas that will be overlaid with asphalt as provided for in WisDOT Standard Specification 390. The plan calls for both Base Patches and Concrete Replacements between STA 129+00 and 227+00 which if overlaid are normally considered Base Patches. Can WisDOT explain why it is using the Concrete Replacement Item in this area? Will Base Patches over 15 feet be paid as Concrete Replacements or is there some other reasoning? Please clarify. | Yes, for this project, base patches that are greater than 15 feet in length will be paid for as Concrete Replacement item. | Mike Coleman | 13 | 2020-11-08 13:17 | 2020-11-09 10:53
20201110 | 20201110028 | 28 | Decorative Paver and Soil Cell System Compaction Frequency and Testing Expectations | Looking at the plans and specials for the #28 job and there was compaction that was called out for the sub grade and base course for the Decorative Pavers and soil density testing on the Soil Cell System. For bidding purposes, I am not sure what you are looking for as far as a frequency of this testing, for example, per lift, per soil cell system, per paver area placed?? There are quite a few areas that require this and didn't know if it was missed or if the intention is to test every area placed. | For the decorative pavers, the dense graded base and subgrade would be compacted and tested per WI DOT standard specifications 305 (Dense-Graded Base) and 350 (Subbase). Compaction testing could be completed in conjunction with required testing for the dense graded base and subbase beneath the colored custom concrete and sidewalk. For the soil cells, assuming that the criteria in the Furnishing and Planting Plant Materials special provision is met (including testing required in standard DOT specifications for planting soil (632.2.3.1 and 632.2.3.4, separate soil density testing after installation of soil in the soil cell system is not needed according to the manufacturers. Once the soil cell system is in place it is essentially impossible to compact the soil because of the support provided by the plastic soil cells. To reiterate, soil in the system should ONLY be â€œfoot compactedâ€, no mechanical compaction equipment should be used on the soil in the tree pits. | Mike Coleman | 14 | 2020-11-09 09:15 | 2020-11-09 11:45
20201110 | 20201110028 | 28 | Compaction testing for sanitart sewer, water main and all laterals | reading thru all the special provisions it is confusing who is paying for compaction testing if required. In some places it looks to be by the contractor, some places it says it is incidental to the work, than the specification turns around than tells us that costs for retests will be deducted from the payments to the contractor, again what is the contractor responsible for and who is paying for it????? | Density/compaction testing in water main and sanitary sewer excavations is paid for by the contractor (whether it is incidental or out of a payment deduction). One density test (a satisfactory test) will be required, and as long as existing material, moisture content, and backfill methods remain relatively consistent throughout the installation process, only one test will be required on all installations. Should the existing material change substantially or the contractorâ€™s mean and methods change, another test may be required by the engineer. | Jill Fehrman | 15 | 2020-11-09 13:43 | 2020-11-09 15:52