## qandasearchletting_results
Date: | 2021-02-08
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210209 | 20210209001 | 1 | DBE Goal | Is there a DBE goal on this project? | There is no federal funding on this project, therefore, there are no DBE goals. | Mike Coleman | 1 | 2021-01-13 13:21 | 2021-01-14 07:47
20210209 | 20210209004 | 4 | Plans and Specs | Can the earthwork data sheets be made available? |  |  | 1 | 2021-01-18 11:38
20210209 | 20210209004 | 4 | Geotech Repor | Is a geotechnical report available for this project and can it be made available? | The Geotech report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209004/ | Mike Coleman | 2 | 2021-01-27 12:42 | 2021-01-28 13:53
20210209 | 20210209004 | 4 | Inlets 2.1 and 2.2 | Are Inlets 2.1 and 2.2 shown on sheet 60 new? We do not see them in the schedule of items or the misc. qty's. | They are listed in the Misc Qty on page 49 under Culvert Summary as they are part of that network. | Mike Coleman | 3 | 2021-02-02 09:02 | 2021-02-03 05:35
20210209 | 20210209005 | 5 | CTH K - Vernon Co. | We bid this job last May. The the unit prices were published, so I assume it was awarded. Why was it not constructed in 2020? | The low bidder rescinded their bid after it was awarded. Subsequently, the project was rejected and is being re-let at this time. | Mike Coleman | 1 | 2021-01-14 10:44 | 2021-01-15 07:42
20210209 | 20210209006 | 6 | Permanent Pavement Marking Item | Good morning. Being that you are looking to have the final markings placed on the same day as the final pass of asphalt on the surface, shouldn't the 4" epoxy item be changed to be a 4" same day epoxy item so the department's requirements of placing the 4" item the same day as the final pass match the proper bid item? Thank you. | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-01-21 09:09 | 2021-01-26 08:03
20210209 | 20210209008 | 8 | Replace Hydrant | On the plans it states the City will provide the hydrants and contractor to just install. In the Specials of the specs it states contractor will furnish and install the hydrants. Which statement should I go with? | The city will furnish the hydrants and the contractor will install the hydrants per the plan. The specials are incorrect. An addendum was issued to correct this. | Mike Coleman | 1 | 2021-01-19 13:31 | 2021-01-25 06:41
20210209 | 20210209008 | 8 | Bid item #0186 | Good morning. Bid item #0186, marking crosswalk epoxy transverse line - 12 inch is referenced as grooved in both in the proposal and on the plan sheets. Will this bid item be corrected to show this as well? Thank you. | An addendum will be issued to clarify this. | Mike Coleman | 2 | 2021-01-21 10:17 | 2021-01-25 11:33
20210209 | 20210209008 | 8 | Lighting Base Reinforcement | Do the lighting bases require reinforcement? The notes on page 8 of the plan reference steel reinforcement. | No, the lighting bases do not require reinforcement. Notes (7) and (8) on page 8 of the plans are meant for lighting bases that are 7â€™ deep. Notes (7) and (8) do not apply. | Mike Coleman | 3 | 2021-02-08 11:28 | 2021-02-08 11:29
20210209 | 20210209009 | 9 | Soil Borings | Are there soil borings available for the project? | The soil borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209009/ | Mike Coleman | 1 | 2021-01-21 08:02 | 2021-01-25 11:20
20210209 | 20210209009 | 9 | Water | Will the bid item Water be added to the contract? | The bid item water will be added via addendum. | Mike Coleman | 2 | 2021-01-22 13:42 | 2021-01-25 11:58
20210209 | 20210209012 | 12 | Detail for item 78 Cover Plates Temporary | On page 32 of the plan set under step 1 for installation of cover plates temporary. There is not an item for backfill using asphalt surface patching. Will an item be added for this work? | The backfill item using will be Asphaltic Surface Temporary item instead of the asphalt surface patching. Yes, We will update the construction details to reflect this change and misc qty table to include this item. | Mike Coleman | 1 | 2021-01-21 10:56 | 2021-01-26 08:07
20210209 | 20210209012 | 12 | SPV.0060.01 Precast Sound Barrier Panel Support Repair | Concerning the Precast Sound Barrier Panel Support Repair: In the notes below the Total Estimated Quantities tables it states to â€œRepair both sides of sound panel when repairs are made.â€ In regards to payment quantity on this item: when removing 1 bayâ€™s worth of panels, and repairing 2 of the support brackets at each bay, will this quantity be paid as 1 EA based on each bay, or 2 EA based on each support repair? | Payment will be for each individual support bracket that requires repair. If a panel needs repair of support brackets at both ends, then this would be considered as a quantity of 2 EACH. | Mike Coleman | 2 | 2021-01-26 11:46 | 2021-01-27 14:45
20210209 | 20210209012 | 12 | manhole adjust | please clarify the structure adjusting items. there are a lot of things listed as incidental to the adjustment item on sheet 32 and there is not enough quantity to cover the work. | Agree, we will revise the quantity for this item. An addendum will soon be submitted with the updated quantity to Adjusting Manhole Covers item. | Mike Coleman | 3 | 2021-01-27 11:55 | 2021-01-28 14:05
20210209 | 20210209012 | 12 | Addendum 3 Change | What are the pertinent sections of standard specification 532.3.2 in relation to Precast Sound Barrier? | This will be revised via addendum. | Mike Coleman | 4 | 2021-02-01 14:39 | 2021-02-03 05:41
20210209 | 20210209012 | 12 | Panel Support Replacement | What is the criteria in which the Engineer will use to evaluate in the field if the barrier panel support will be repaired or replaced? If the panel support is replaced, would the replacement be constructed per proposed repair or constructed per original design? | The field engineer in consultation with the DOT bridge maintenance engineer will review and determine repair locations based on conditions observed at the time of construction. Panel supports will be repaired per the details shown on the plan. | Mike Coleman | 5 | 2021-02-01 14:42 | 2021-02-02 09:46
20210209 | 20210209012 | 12 | Removing Old Structure Items | Can some clarification be shed on what "Old Structure"(s) are intended to be removed? The plan locations are unclear. | Removing Old Structure item is included to cover removals needed for the sound barrier panel support repairs along the entire length of a given sound barrier. | Mike Coleman | 6 | 2021-02-01 14:42 | 2021-02-02 09:47
20210209 | 20210209012 | 12 | Lane Closures | Are daytime lane 2 lane closures allowed during off-peak hours? | One lane of traffic is to be maintained during daytime off-peak hours. Lane 2 closures during daytime off-peak hours for base patching/concrete pavement replacements work on lane 2 are NOT allowed. However, lane 2 closures during daytime off-peak hours are allowed for various work outside of lane 2, i.e. shoulder work, slope work, noise wall work, electrical work, etc., but the traffic must be staged appropriately. | Mike Coleman | 7 | 2021-02-01 15:11 | 2021-02-03 05:43
20210209 | 20210209012 | 12 | Structure Overcoating Cleaning and Priming - Define Area to be Painted? | Please confirm exactly what surfaces are to be painted in the surface areas shown in the specifications. In addition to the new panel support brackets is painting required only on the traffic side flange and edges, both flanges and edges (access from private residences outside ROW) or the entire surface of the W8 structural support post (flanges and webs...which would require all noise wall panels to be removed)? | In order to repair the support brackets, it is anticipated that the entire group of panels above the bracket will need to be removed. After removal of the panels, the intent is that all exposed faces of the support posts and brackets are to be repainted at a given repair location. | Mike Coleman | 8 | 2021-02-03 18:03 | 2021-02-04 09:32
20210209 | 20210209012 | 12 | Design Schedule | Can the design schedule be provided? |  |  | 9 | 2021-02-04 07:57
20210209 | 20210209012 | 12 | Removal of lower lift asphalt at match points. | Once the lower layer asphalt is placed at all match points an asphalt wedge would be needed for opening to traffic. Would there be an item added for this removal for placement of surface course? | The Removing Pavement Butt Joints item 204.0105 will be paid for at all match point on the full depth milling per the detail, and after placement of any binder ramps to match existing pavement, before placing surface course. | Mike Coleman | 11 | 2021-02-04 08:01 | 2021-02-08 06:02
20210209 | 20210209012 | 12 | SHES Base Patching | Can a detailed break down of the location of the SHES Base Patches be provided or can we take it the SHES Base Patches will be evenly distributed between lanes 1 and 2? |  |  | 12 | 2021-02-06 11:51
20210209 | 20210209013 | 13 | Excavation | Can some sort of breakdown for the excavation and breaker run be provided? There are no Miscellaneous Quantity sheets, cross sections, etc. It also seems like there is far more bid quantity than needed to undercut all the concrete repair areas. Is there a lot of Excavation in the shoulders? The bid quantity for Excavation seems quite high. | All locations and extents of the undercuts/EBS will be determined in the field by the Engineer. Shoulders were estimated such that 5% of the total areas to be replaced would need undercutting/EBS/Breaker Run, again as determined by the Engineer. Undercutting/EBS/Breaker Run for concrete pavement repairs/replacements was accounted for at every location in the plans and the engineer in the field will determine if it is needed, as stated in the Construction Details. MQs for Excavation Common and Breaker Run are provided in the same table as the associated work operation. No cross sections will be provided for this project, therefore there are no earthwork data sheets. | Mike Coleman | 2 | 2021-01-12 08:58 | 2021-01-25 06:37
20210209 | 20210209013 | 13 | Removing Asphalt. | Will an item be added for Removing Asphalt? | No, Removing Asphalt will not be added as it is included in Common Excavation. | Mike Coleman | 3 | 2021-01-12 15:14 | 2021-01-25 06:38
20210209 | 20210209013 | 13 | Disposal of diamond ground materials | The plans show where diamond ground materials canâ€™t be disposed of. Will the contractor then be allowed to dispose of materials in other places, and if so, how much? | The project documents indicate side discharging diamond-ground concrete materials will be allowed in a manner as shown in the project documents and as directed by the Engineer. The Contractor shall perform their own calculations regarding amount of materials that can be disposed of on-site however a very rough approximation might be in the 60-70% range. | Mike Coleman | 4 | 2021-01-25 12:54 | 2021-01-25 12:55
20210209 | 20210209013 | 13 | Lane Closures | Do lane closures stay up or do they come down during peak hours. Plan doesn't all out for opening up but specs show peak and non-peak hours. | The â€˜off peakâ€™ hours are only shown for when traffic control switches are allowed to take place. Lane closure will remain in place and be continuous per stage. | Mike Coleman | 5 | 2021-01-27 13:49 | 2021-02-01 09:44
20210209 | 20210209013 | 13 | 22. STATE FURNISHED SIGNAL CABINET | The traffic signal cabinet controller is listed as Econolite in the plans, but specs in proposal under #22 state to contact TAPCO and normally also lists to contact TCC @ 651-439-1737 or mallwood@tcc1.com to schedule cabinet acceptance testing, but that is missing. Should this be added? | Follow the specifications of Proposal 13. | Mike Coleman | 6 | 2021-01-29 14:33 | 2021-02-04 05:47
20210209 | 20210209013 | 13 | Pavement Markings | Good morning. In looking at the pavement marking plans and bid item, the plans show grooved wet reflective contrast epoxy lane lines (4" skips & 8" turn lanes) which is typical for a project like this. However, the miscellaneous quantities and bid items for these markings are grooved wet reflective epoxy (4" & 8") rather than contrast. Will an addendum be issued to address this? In addition, the plan shows cold weather epoxy for the edge lines but there is not a permanent item for the edge lines. Typically, there would be a permanent item such as grooved in wet reflective epoxy on a project such as this with a cold weather item just in case it is needed. What are the department's intentions with this item and will a permanent item be added for the edge lines? Will an addendum be issued to address this? Thank you. | These concerns will be addressed in a forthcoming Addendum. | Mike Coleman | 7 | 2021-01-30 08:52 | 2021-02-04 05:44
20210209 | 20210209013 | 13 | Pavement Markings | Good morning. In looking at the pavement marking plans and bid item, the plans show grooved wet reflective contrast epoxy lane lines (4" skips & 8" turn lanes) which is typical for a project like this. However, the miscellaneous quantities and bid items for these markings are grooved wet reflective epoxy (4" & 8") rather than contrast. Will an addendum be issued to address this? In addition, the plan shows cold weather epoxy for the edge lines but there is not a permanent item for the edge lines. Typically, there would be a permanent item such as grooved in wet reflective epoxy on a project such as this with a cold weather item just in case it is needed. What are the department's intentions with this item and will a permanent item be added for the edge lines? Will an addendum be issued to address this? Thank you. | These concerns will be addressed in a forthcoming Addendum. | Mike Coleman | 8 | 2021-01-30 08:53 | 2021-02-04 05:44
20210209 | 20210209013 | 13 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209013/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 9 | 2021-02-04 07:32 | 2021-02-05 07:20
20210209 | 20210209013 | 13 | Should an item for water be added. | Should we bid the project expecting no water will be needed? |  |  | 10 | 2021-02-07 11:26
20210209 | 20210209014 | 14 | Completion time | On the front of the proposal it shows Nov 1 2022 as completion date, is this accurate. | There is an interim completion date for the roadwork items in the Prosecution & Progress section of the Special Provisions of Nov 1 2021. The Nov 1 2022 date is accurate and represents the contract work completion which includes landscaping, planting & surveillance items only to be performed from Nov 1 2021 to Nov 1 2022. | Mike Coleman | 1 | 2021-01-19 07:36 | 2021-01-20 10:10
20210209 | 20210209014 | 14 | Municipal Monument Sign and Informational Sign Post | On page 26 of the plan, the upper left corner has a detail for information related to one or both of these bid items, item numbers 464 and 488. Page 186 shows the location of the left detailed sign at station 377+90 in the median, but it doesn't state what is being done with it. I can't find either bid item in the MQ's. The right detail on page 26 seems like it could be wrong or misleading. Can you please clarify what sign and posts are associated with line 464 for the "Remove, Stockpile, and Reinstall Municipal Monument Sign" and also clarify if line 488 "Informational Sign Post" is part of this same installation or something else entirely? | Line item 464 is Item SPV.0060.22 REMOVE, STOCKPILE AND REINSTALL MUNICIPAL MONUMENT SIGN. A detail of what the existing sign looks like is on the upper left corner of pg. 26. That detail also includes the new breakaway post mounting needed for the re-installation of that sign. The existing sign location is shown on pg. 186 of the state signing plan at approx. Sta. 377+90. The proposed (re-installation) location is shown on pg. 160 (Village Streetscaping plan set) at approx. Sta. 377+60. The MQ for this item is on pg. 415 (in the local streetscaping section). In hindsight, we should have added a note on pg. 186 at the â€œWelcome toâ€ sign to go to pg. 160 for reinstallation location. WisDOT calls the municipal signs â€œWelcome Toâ€ signs as a generic label for these type of municipal name signs even though this one didnâ€™t actually have the words â€œwelcome toâ€ on it (which may have caused some confusion). The â€˜right detailsâ€™ on pg. 26 is for the Masonry Wall (top) and Pillar (bottom) which are not signs and their proposed locations are shown on the streetscaping plan set and MQs on pg. 415-416. I donâ€™t believe you meant Line 488 as it is the item of â€˜Utility Line Openingâ€™ and instead meant Line 486 which is SPV.0060.33 INFORMATIONAL SIGN POST and is an entirely different sign than above. A detail of the sign is on pg. 22 (included with bioswale details). On Pg. 23 in the â€˜notesâ€™ section states that the proposed location â€œdetermined by engineerâ€ in the general vicinity of the bioswale. The MQ is on pg. 412 (in the bioswale items section). | Mike Coleman | 2 | 2021-01-20 10:43 | 2021-01-26 08:08
20210209 | 20210209014 | 14 | Manhole Adjustments | The way Manhole Adjustments is written (Sheet12) you will have multiple contractors working on the same item which we have found to be a MAJOR complication on our current project #2030-13-70 Hwy 100, which is written the same way. We would like to see it changed to just "Manhole Adjustments" which would be performed by a Sewer Contractor only which is how Call Order 12 STH 794 is written, (Sheet 42). | We disagree that every â€œsewer contractorâ€ is able to perform all of these items on every WisDOT project as it requires different equipment (example full depth concrete pavement saws) and access to different materials (example temp asph surface). Weâ€™ve administered numerous contracts where the sewer contractor may do all the work, and where other subcontractors contribute to the manhole work by doing the sawing, pavement removal and installing temp asph surface etc. That is one reason the items are separate pay items and not all incidental to the manhole adjustment item. We understand that there are instances that both the sewer subcontractor and pavement subcontractor can both do the work and suggest the work be coordinated with the prime contractor. | Mike Coleman | 3 | 2021-01-25 09:55 | 2021-01-26 08:11
20210209 | 20210209014 | 14 | STH 100 & 51ST ST | Should new signal mounting hardware be quoted for this intersection, and if so, what proposal line number should it be included in? | Signal mounting hardware is included in the unit cost for SPV.0105.15 REMOVE, TRNSPRT, PAINT AND REINSTALL TRAF SIG AND LIGHT EQUIP STH 100 & 51ST. It is stated in Article 99 of the Special Provisions and the Proposal Line Number for this item is 0576. | Mike Coleman | 4 | 2021-01-28 15:22 | 2021-01-29 10:21
20210209 | 20210209014 | 14 | Field office | Is the field office needed to be maintained till the Nov 1 2022 completion date ? | Field Office will be needed through December 2021. It is not needed in 2022 during the plant maintenance and care cycles period. | Mike Coleman | 5 | 2021-02-02 08:30 | 2021-02-03 05:36
20210209 | 20210209014 | 14 | Construction staking | For all the new electrical lighting, is there not a need for construction staking I do not see it any where. I received a call from a staking contractor wondering how this is covered so he can price it accordingly | Include the cost of construction staking in the item cost. | Mike Coleman | 6 | 2021-02-05 12:45 | 2021-02-08 10:47
20210209 | 20210209015 | 15 | Stage Removal Line on Bridge | Traffic control details shown on Plan sheet 22 indicate a 17'6" clear roadway width and 2' allowance for concrete barrier for a total required width of 19'6". Reviewing existing bridge plans, 19'6" from the existing curb line ends up 3" past the CL of girder line #5. This is in conflict with the detail on sheet 94 (2 of 27 structure plan) which shows constructing the stage 1 deck to a point 1'0" short of girder line #5. Please review staging limits and indicate where the cut line should be for stage 1 removal. Also indicate if proposed barrier wall will need to be anchored to the deck in any stage and if so add the standard bid item for this work 603.8505. | The width of the clear lane will be adjusted to 15.5â€™ in Stage 1 in order to avoid the conflict. An addendum will be issued. According to SDD 14 B 7-15e, (Free Standing Barrier Requirements) we meet the 2â€™ or more clearance space requirements and anchoring the barrier is not needed. | Mike Coleman | 1 | 2021-02-02 15:40 | 2021-02-03 09:26
20210209 | 20210209015 | 15 | Temporary Pedestrian Walkway Accommodations along Lincoln Creek Parkway | Plan sheets 24 & 29 (stages 1A & 2A) show the temporary pedestrian walkway along Lincoln Creek Pkwy lined with concrete barrier. However, this quantity is not accounted for on sheet 39 of the miscellaneous quantities. Instead, a quantity of approximately 650 LF of temporary pedestrian barricades is shown for each of these stages. What is the Department's desire for temporary pedestrian walkway protection on Lincoln Creek Pkwy? Please provide clarification on the staging detail sheets and associated miscellaneous quantities. |  |  | 2 | 2021-02-03 15:50
20210209 | 20210209015 | 15 | Follow up to question #1 | Plan details show a 2'7" lap splice for the transverse deck steel. Revising the clear roadway width in stage 1 still does not allow room to fit these bars. Should bar couplers be used instead of traditional bar laps? |  |  | 3 | 2021-02-03 20:24
20210209 | 20210209018 | 18 | Project Schedule | Will the Department please provide the preliminary project schedule used for design? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209018/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-01-31 17:23 | 2021-02-01 08:43
20210209 | 20210209018 | 18 | Traffic Control for Passing Lane | Since flagging operations will be required to control traffic for the milling & paving operations, it would be safest to restrict areas where 3 lanes are present, down to 2 lanes, so that the traffic can be safely controlled by flagging operations. In the areas where a 3rd lane exists, will the contractor be allowed to fully close a single lane using the Traffic Control Drums and Barricades provided in the contract? If so, will single lane closures be allowed to remain overnight in the direction of travel that has both a travel lane and passing lane? The passing lane in the SB direction extends from Sta 718+00 to 832+97, or approx. 2 miles; a full closure of this 3rd lane would exceed the 1.5 miles allowed per Article 4 of the Special Provisions. | An addendum will be issued to address this. | Mike Coleman | 2 | 2021-01-31 17:33 | 2021-02-02 05:36
20210209 | 20210209019 | 19 | Removal B-26-0006 | Is there a plan available on the construction of B-26-0006 to evaluate for the Demolition of the Structure? | The as-built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209019/ | Mike Coleman | 1 | 2021-01-26 09:03 | 2021-01-27 05:52
20210209 | 20210209019 | 19 | Roundabout - Mix type Selection | In the WisDOT Facilities Development Manual, Chapter 14, Section 10 - 35.3.3 HMA Intersection, states that HMA intersections (including roundabouts and J-Turns) should be designed to avoid rutting and/or shoving due to the stresses applied by vehicles at high traffic intersections with stop conditions and a high percentage of turning movements. HMA intersections with these conditions, should be constructed with a HMA mixture that is increased by one traffic level or more from the mainline to ensure good pavement performance. In addition to the above statement we feel Michigan Loads should be considered in the conditions for the roundabout. Can the 4MT for the roundabout be changed to a 4HT? | The mix design was discussed during preparation of the pavement design report. It was determined that the Type MV mix with a Type V asphaltic binder is the correct HMA mix for the application and traffic volume. The Type HT mix is not needed for the roundabout. | Mike Coleman | 2 | 2021-01-27 16:05 | 2021-01-28 14:05
20210209 | 20210209019 | 19 | Existing B-26-0006 | What is the current load rating of the existing B-26-0006 structure? | The latest bridge inspection shows the design and inventory load ratings as HS20 and the operating load rating as HS33. The bridge inspection report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209019/ | Mike Coleman | 3 | 2021-01-27 17:52 | 2021-01-28 13:58
20210209 | 20210209019 | 19 | Soil Borings | Are there soil borings available for the project? | The soils report and borings can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209019/ | Mike Coleman | 4 | 2021-02-04 08:30 | 2021-02-04 11:12
20210209 | 20210209021 | 21 | work at B-39-69 | What is the traffic control plan for the work at structure B-39-69? Will Traffic be permitted to run on the milled surface after the removal of the existing polymer overlay? | Traffic for the bridge work is intended to be managed with flaggers, closing one side of the roadway at a time for milling, and then for paving. Traffic will be allowed to travel on the milled surface after removal of the polymer overlay. The intent is to place the asphalt overlay as soon as possible after milling, to minimize maintenance or cleaning of the milled area caused by traffic between milling and paving. | Mike Coleman | 1 | 2021-01-18 07:06 | 2021-01-25 06:39
20210209 | 20210209021 | 21 | Soil Borings | Are there soil borings available for the project? | Attached are borings that cover STH 82 in Adams county from the Marquette/Adams county line to STH 13. They are stationed by log mile beginning at the county line and going westerly. These are from 20 years ago, so they do not reflect the current â€œwhite toppingâ€ pavement structure. They can be found at that following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209021/ | Mike Coleman | 2 | 2021-01-22 10:09 | 2021-01-29 07:37
20210209 | 20210209021 | 21 | Construction Staking | Is the slope staking quantity correct? | The slope staking quantity should be correct. The slope staking item is only intended for areas where ditching is required, as any staking for all other areas where the subgrade is just being extended out to match the existing slope should be covered by the subgrade staking item. | Mike Coleman | 3 | 2021-02-04 17:00 | 2021-02-05 10:01
20210209 | 20210209021 | 21 | Landmark Reference Monuments | Is the quantity for Landmark Reference Monuments missing? | Since the landmark reference monuments are typically well away from the roadway and the work associated with this project is all within or very close to the roadbed, it is not anticipated that any landmark reference monuments will be disturbed. Therefore, it was determined the Landmark Reference Monuments item was not needed in the contract. | Mike Coleman | 4 | 2021-02-04 17:02 | 2021-02-05 10:03
20210209 | 20210209022 | 22 | Flagging on an active detour route | For the ADT count on this stretch of roadway, has the Department taken into account that this project will be on the active detour route for the previous proposal in this letting, #21? Will the increase in traffic force the contractor to regularly suspend flagging operations on this project due to it being a part of the detour? | Yes, the department is aware of and has considered the additional traffic through this project due to the detoured traffic from the STH 82 project, Proposal #21 (20210209021) in this letting. Flagging operations are not anticipated to be regularly suspended due to the additional traffic from the STH 82 detour. Higher volumes may be experienced during the peak hours of peak tourist travel periods. The department will require vehicles be held in queue no longer than 15 minutes during the flagging operations. Coordination with the STH 82 project traffic control and work operations will be required. | Mike Coleman | 1 | 2021-01-20 11:15 | 2021-01-29 10:23
20210209 | 20210209022 | 22 | Temporary Markings | Good afternoon. In looking at plan sheets 19 & 20, there appears to be conflicting information in that it is showing temporary paint center line with temporary tape edge lines on sheet 19 and temporary tape center and edge lines on sheet 20. Being these items are being placed on the finished asphalt surface, it would make sense that it would be temporary tape rather than temporary paint so as to not damage the finished surface when these items are removed. The other issue is there is no bid item (that I can see) that takes into account the temporary tape item other than an 18" removable tape item. Will WisDOT address this issue with an addendum so it is clear what is desired? Thank you. | The temporary markings on sheets 19 and 20 are shown incorrectly. An Addendum will be issued to correct the temporary markings and add the missing Temporary Marking Line Removable Tape 4-Inch bid item. | Mike Coleman | 2 | 2021-01-25 14:59 | 2021-02-01 06:11
20210209 | 20210209022 | 22 | Working Days | Due to having to stop and restart work types for each stage, the associated mobilizations, and Temp Paint and Traffic Control setups/switches for each stage, it will be very difficult to complete this project in 25 work days. Could this project have more working days added or can the staging be changed to allow for a more productive schedule? | The department will allow the curb and gutter, sidewalk, beam guard upgrades and extension, shouldering and restoration work to be completed outside the main traffic control stages provided the proper traffic control per the appropriate standard detail drawings is utilized. All other standard and special provisions still apply including standard spec 104.6.1.2.3 Drop-off and Hazard Protection. The contract completion time will not be changed. | Mike Coleman | 3 | 2021-01-26 15:13 | 2021-02-01 06:12
20210209 | 20210209023 | 23 | Pipe Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-01-14 10:05 | 2021-01-20 05:29
20210209 | 20210209023 | 23 | Asphaltic Surface Questions | 1. For the culvert replacements the Asphaltic surface is required to be a 5 MT according to Sheet 13 of 6310-00-60. In the special provisions this material is required to be a MT only. Which is correct and can a 3 MT or 4 MT be allowed? 2. For the concrete curb replacements the required asphalt mix is under the 5 MT H item in all the plans. Could this be changed to an Asphaltic Surface bid item requiring an MT mixture as this will not be tested and the contractor could use a 3 MT or 4 MT? | 1. 5 MT is required per the plan. 2. 5 MT is required per the plan. | Mike Coleman | 2 | 2021-01-25 11:02 | 2021-01-28 14:14
20210209 | 20210209023 | 23 | Slope Grading | For the slope grading should an item for slope staking be added? | All staking in the guardrail areas are included under Barrier System Grading Shaping Finishing. Addenda will be issued to add slope staking for culvert replacement at STA 813+45 | Mike Coleman | 3 | 2021-01-25 11:04 | 2021-01-28 14:12
20210209 | 20210209023 | 23 | Culvert Liners | Is the liner size listed in the plans the minimum inside diameter required for the liner? With the Mannings value for RCP for the host pipe, most of the locations will not be able to achieve the 95% capacity as required by the SPV. | Liner size is not needed on the plans. Manning value of 0.015 for concrete pipe can be used. The Q(full) has been recalculated using this parameter. Addendum will be issued with the revised Q(full) and the liner size removed. | Mike Coleman | 4 | 2021-02-02 09:36 | 2021-02-03 05:42
20210209 | 20210209023 | 23 | Curb Ramps | Project Number 6170-00-61. Plan Sheet #15 Traffic Control. Note 2 states that temporary curb ramps are to be used. Should there be bid items added for the temporary ramps? | The bid items 644.1410 Temporary Pedestrian Surface Asphalt and 644.1601 Temporary Pedestrian Curb Ramp are already included in project ID 6170-00-61 for that purpose. | Mike Coleman | 5 | 2021-02-02 11:13 | 2021-02-03 09:44
20210209 | 20210209023 | 23 | Pipe Liners | 1. When addendum 2 was created it eliminated the pipe liner sizes. However the bid items are still based on the deleted pipe sizes. So if a contractor determines that a 27" pipe liner would meet requirements then they would be bidding a 24" liner item with a 27" liner for a 30" existing RCP. Should the bid items be changed to eliminate confusion? 2. To meet the 95% flow requirements with the allowable Mannings values provided by the approved products most liners will have to be 3" I.D. less than the existing RCP. The O.D. of the liner would be 1" or less than the RCP I.D. With this if there is any deflection in the pipe over the years there is a chance that the liner will not fit. Also when the liner is properly placed there is insufficient room for grout tubes for a proper procedure to be done. | 1. Addendum #3 will be issued revising the size of the liner to reference the existing culvert size. Actual liner size will be determined by the contractor according to the special provisions. 2. Products to appropriately line concrete pipes of these sizes are available on the WisDOT approved products list. The Item Cleaning Culvert Pipes for Liner Verification includes inspecting the pipes as soon as possible after contract execution, and coordinating with the engineer on culvert condition. Deflection in the pipes should be discussed with the engineer. The specification indicates that an approved grouting plan is required. | Mike Coleman | 6 | 2021-02-04 09:41 | 2021-02-04 15:20
20210209 | 20210209023 | 23 | Cofferdam | Project has an item "Cofferdam Special) for the pipe at STA 813+46. Is there any flow, Q2 available for this location? During the site visit it didn't seem like there is any water flowing through the pipe currently. | The cofferdam specification was added to the project at the request of WDNR. Water levels through this area fluctuate seasonally. | Mike Coleman | 7 | 2021-02-04 13:30 | 2021-02-05 10:06
20210209 | 20210209023 | 23 | Culvert STA 575+28 | As plan shows right now placing culvert at STA 575+28 under traffic half at the time under traffic and having two lanes open at the end of the day does not seem constructible due to great depth and big volumes for pipe excavation/backfill. Can road be closed and detoured during pipe installation or items of temporary signals and concrete barrier added for having one lane open for overnight hours? | The culvert work and staging was discussed at length with the Region. No changes will be made at this time. | Mike Coleman | 8 | 2021-02-05 08:01 | 2021-02-05 10:08
20210209 | 20210209023 | 23 | Culvert Liners #2 | There are concerns with the 089 and 092 pipes. You will not be able to achieve 95% capacity on 089 with a 24" ID liner and a 27" may not fit and would not be able to be grouted. You won't be able to achieve 95% capacity on 092 with an 18" ID liner and a 21" may not fit and would not be able to be grouted. However, I would guess that if these pipes are in need of lining, the 0.015 Manning's number is not the existing condition of the pipe. | There are products available on the departmentâ€™s approved products list that are intended to meet the requirements of the project for the lining concrete pipes of this size and slope. | Mike Coleman | 9 | 2021-02-05 15:13 | 2021-02-08 09:04
20210209 | 20210209024 | 24 | Guardrail Bid Items | Line 194 is 60 LF of temporary guardrail. Line 196 is 60 LF of salvaged rail. I can't find any mention of these items in the plan or the Miscellaneous Quantities. Can you point me in the right direction? | The items questioned are part of the structure plans for C-49-24. The Steel Plate Beam Guard Temporary and Salvage Rail items can be found in the Total Estimated Quantities for the structure items on plan Sheet 286, and the installation and plan details are shown on Sheet 296 and Sheet 299. | Mike Coleman | 1 | 2021-01-20 14:30 | 2021-01-25 11:22
20210209 | 20210209024 | 24 | Sluice Gate Structure | It appears as though the Sluice Gate Structure is detailed for Cast In Place. Will the Department allow this structure to be Precast? Thanks. | No, this Sluice Gate Structure needs to be Cast In Place as shown. This structure will be under constant head, and prone to seepage at any joint that is not water-tight. Long-term seepage through such joints can lead to loss of material, and in turn embankment settlement and other larger issues. | Mike Coleman | 2 | 2021-01-21 14:03 | 2021-01-25 11:24
20210209 | 20210209024 | 24 | Private Line Slide Gate | Section SPV.0105.08 indicates a 12-inch slide gate is to be provided for the private supply line, however no location or details can be found in the plan set. Please clarify the location and provide a detail of the area. | The item SPV 0105.08 Private Supply Slide Gate (12-inch) will be deleted and removed from the project via an upcoming Addendum. | Mike Coleman | 3 | 2021-01-27 07:47 | 2021-01-27 14:47
20210209 | 20210209024 | 24 | C-49-24 Estimated Quantities | Can estimated concrete and steel reinforcement quantities be provided for the Primary Spillway Structure, Sluice Gate Structure, and the Culvert Downstream End Section? | The quantity breakdown as requested are not available. | Mike Coleman | 4 | 2021-01-27 07:51 | 2021-02-01 08:46
20210209 | 20210209024 | 24 | Stoplogs | SPV.0105.03.B.2 implies that the stop logs and frames shall be of stainless construction, however section C.2 and implies that the stoplogs are wood. Please verify which governs. If section B.2 governs, please provide details of the bottom sill connection and the stoplog lifter. | The special provisions and structure plans will be revised and included in an upcoming addendum. | Mike Coleman | 5 | 2021-01-27 11:08 | 2021-01-28 06:23
20210209 | 20210209024 | 24 | Pipe Grates | What size are the pipe grates? | The Pipe Grate sizes can be found in the Storm Sewer tables of the miscellaneous quantity plan sheets 119-120, and are sized as follows: AEW 1- 24-INCH, AEW 4- 30-INCH and AEW 6- 42-INCH. | Mike Coleman | 6 | 2021-01-28 11:18 | 2021-01-29 07:40
20210209 | 20210209024 | 24 | Grit Structures | Can the grit structures be made in precast sections. | YES, all previous project grit structures were pre-fabricated. | Mike Coleman | 7 | 2021-01-28 11:36 | 2021-01-29 07:41
20210209 | 20210209024 | 24 | Approved Fabricators? | Please verify if approved fabricators, fabricated bridge components are required for the following items: - Primary spillway access stairs - Primary spillway operator walkway bridge - Primary spillway stoplog slots - Sluice gate structure fixed ladder - Galvanized steel trash guard | The department will not require that the contractor use an approved fabricator from the APL for fabricated bridge components for these items. | Mike Coleman | 8 | 2021-01-29 08:45 | 2021-02-01 09:53
20210209 | 20210209024 | 24 | Utility Contradiction | Section 6: Utilities reference 3 different structures (C-9-42, C-49-2, C-49-02). Please verify that these references are meant to be structure C-49-24? Additionally, Section 3 states that the box culvert must be completed within 21 calendar days. Section 6 states that AT&T will required 25 working days to complete the shoring of the fiber duct bank. Please verify if these durations are correct? | Yes, all references are for structure C-49-24. The time frames as specified are correct. It is anticipated that early and proper coordination with AT&T will allow utility work to occur before and during the road closure, with backfill operations potentially continuing after the closure is complete and traffic is restored, depending on contractor operations. | Mike Coleman | 9 | 2021-01-29 10:46 | 2021-02-03 05:37
20210209 | 20210209024 | 24 | C-49-24 Dimensions | It appears there is an issue the pdf formatting on the dimensions for some of the sheets in the C-49-24 structure plans. Sheets 290, 291 and 293 have issues with display of dimensions. Can these plan sheets be re issued with the proper dimensions provided? | An addendum has been issued to clear up the dimensions. | Mike Coleman | 10 | 2021-01-29 13:24 | 2021-02-01 09:55
20210209 | 20210209024 | 24 | Cad Files | Can you provide cad files for the project. | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209024/ | Mike Coleman | 11 | 2021-01-29 15:57 | 2021-02-01 10:29
20210209 | 20210209024 | 24 | Concrete Curb and Gutter Integral 30-inch Type A | The detail on sheet 11 for Concrete Curb and Gutter Integral 30-inch Type A shows four feet of pavement in the integral placement. The notes clearly say that the 4 feet of pavement is being paid for as Concrete Pavement 9-inch. Is it your intention that the 4-feet of pavement contain dowel bars? This should be clarified. It is a significant amount of dowel bars and small baskets that would need to be fabricated. WCPA would recommend that this four feet not be doweled, but the plan is not clear. Please provide your answer. | Yes, the 4-foot section of concrete pavement should include dowel bars and be constructed per the detail and the Section 13 SDD details for Concrete Pavement 9-inch as shown in the plans. | Mike Coleman | 12 | 2021-02-02 14:41 | 2021-02-03 13:46
20210209 | 20210209024 | 24 | Concrete Mix | Is class C fly ash acceptable for use at the spillway structure, sluice gate structure, and the downstream culvert end? | Yes, Class C fly ash is acceptable for use at the spillway structure, sluice gate structure, and downstream culvert end in accordance with Section 504 of the standard specs | Mike Coleman | 13 | 2021-02-04 06:50 | 2021-02-05 07:22
20210209 | 20210209024 | 24 | Mud Slab Mix Design | Would Class C Fly Ash be acceptable in lieu of Class F? Multiple vendors in the area are unable to provide the specified Class F Fly Ash. Additionally, would a fresh unit weight of ~130#/CF be acceptable? | Yes, if Class F fly ash is not available, and the contractor can provide sufficient evidence of the unavailability, Class C fly ash and 130 pcf weight would be acceptable. A contract modification would be completed to modify the SPV article and permit the use of the product substitutions. | Mike Coleman | 14 | 2021-02-04 13:35 | 2021-02-05 10:12
20210209 | 20210209024 | 24 | Link for Soil Borings | Could WisDOT provide a link for the soil borings for the project and pond area? | The Geotechnical Information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209024/ Variances between boring log information and field conditions may exist due to natural currents, sedimentation and time since borings were completed. | Mike Coleman | 15 | 2021-02-07 14:51 | 2021-02-08 10:41
20210209 | 20210209024 | 24 | 404 Permit | Can you post a copy of the 404 permit? | The 404 Permit Information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209024/ | Mike Coleman | 16 | 2021-02-08 11:20 | 2021-02-08 11:22
20210209 | 20210209025 | 25 | Curb Ramps | Plan Sheet # 18 Has Radial Detectable Warning Fields. Should there be a bid item for the Radials? | Yes, an addenda will be issued for the radial detectable warning field. | Mike Coleman | 1 | 2021-02-01 11:12 | 2021-02-02 09:49
20210209 | 20210209025 | 25 | 72"x113" he pipe | Can the 90" elliptical pipe be upsized to 96" elliptical along with the two endwalls. | The Departmentâ€™s preference is to keep the bid items as specified in the plans. | Mike Coleman | 2 | 2021-02-03 17:26 | 2021-02-04 09:40
20210209 | 20210209027 | 27 | Pavement Markings | Good afternoon. Could you please elaborate on where all of the standard 4" epoxy quantities are to be placed? It appears the quantity may be double what is needed for the project based on the quantity of the same day epoxy center line that is to be placed as the 4" quantity, if it is just center line, is usually close to that quantity. I realize there are quantities included for a small section of edge line as well as some parking boxes, but would appreciate some additional information as time allows. Thank you. | The pavement marking quantity is not correct. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-01-26 12:08 | 2021-01-26 14:10
20210209 | 20210209027 | 27 | Sheet 37 HMA PWL Mixture Acceptance Table | The 4MT quantity for PWL acceptance incentive air voids does not add up to the bid quantity of the 4MT. Or does the PWL acceptance incentive air voids not apply to the full quantity? | The PWL table is incorrect and will be added to an upcoming addendum. | Mike Coleman | 2 | 2021-01-27 16:17 | 2021-01-28 14:00
20210209 | 20210209027 | 27 | Soil Borings | Are there soil borings available for the project? | The soil boring information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209027/ | Mike Coleman | 3 | 2021-02-04 08:29 | 2021-02-04 16:08
20210209 | 20210209027 | 27 | Geotechnical Information | Please post any soil boring information available for this project? | The soil boring information can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209027/ | Mike Coleman | 4 | 2021-02-04 10:18 | 2021-02-04 16:10
20210209 | 20210209027 | 27 | Item SPV.0090.34 HDD HDPE Water Service 1-inch | Is it acceptable to perform a hole mole boring installation for the HDD HDPE Water Service 1 inch item? | The specifications call for horizontal directional drilling (HDD). Hole Mole (or â€œImpact Molingâ€) is an acceptable substitution method. However, the Contractor should review the geotechnical report (link provided below) to ensure that they believe that the method will be compatible with the soils found within the project area and at the depth specified. In addition, the Contractor should be aware that minimum depth requirements will be enforced strictly, so vertical deviation outside of tolerances will be grounds for rejecting the work. The file can be located in the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210209027/ | Mike Coleman | 5 | 2021-02-04 10:50 | 2021-02-05 07:33
20210209 | 20210209027 | 27 | Pavement Markings | Good morning. Is it still the department's intent to issue an addendum to correct the pavement marking quantities? Thank you. |  |  | 6 | 2021-02-06 07:47
20210209 | 20210209028 | 28 | Modular Block Wall | Can you verify the accuracy of the modular block wall quantity? Plan quantity is showing 1620 SF but it appears the wall is only 47' in length? | The estimated quantity in the proposal for this item is not correct and an addenda will be submitted to correct it. | Mike Coleman | 1 | 2021-01-20 13:31 | 2021-01-25 11:35
20210209 | 20210209028 | 28 | Prepare Foundation Sequence | Under Prep of Foundation in the notes on the detail the loose material and patching occurs after the milling. We would suggest leaving it up to the contractor on whether or not to crack patch before or after milling. If we are able to crack patch before milling it gives traffic more time to help compact the HMA material into the cracks and when the milling occurs it leaves a better surface which results in less reflection through the new pavement lifts. | The proposal will not be changed however the contractor may follow section 104.10 of the Standard Specifications. | Mike Coleman | 2 | 2021-01-25 20:29 | 2021-01-26 12:34
20210209 | 20210209028 | 28 | MTV | In the Proposal Table of Contents it shows Material Transfer Vehicle as item 22, however the specification is not included and there is not a pay item. We are assuming it was decided an MTV is not required but thought we should check. | The Material Transfer Vehicle requirement is not included in this contract. The Special Provisions Table of Contents will be revised by addenda. | Mike Coleman | 4 | 2021-01-25 21:11 | 2021-01-26 12:32
20210209 | 20210209028 | 28 | Adjusting Manhole Covers | Based on experience including projects in Rice Lake and Superior we suggest considering raising the manhole covers after the upper layer of HMA is completed. After completing the upper layer, sawcut and remove the pavement over the manhole, raise the manhole cover to the final grade and pour concrete around the manhole cover flush with the asphalt pavement. The area could also be patched in with HMA. However, when overlaying an existing concrete pavement by pouring concrete around the structure the condition of the ride, pavement and structure are better over a longer period of time because there is less differential settlement and movement during freeze/thaw cycles. (same material below the overlay â€“ Concrete) | The proposal will not be changed however the contractor may follow section 104.10 of the Standard Specifications. | Mike Coleman | 5 | 2021-01-25 21:23 | 2021-01-26 12:34
20210209 | 20210209030 | 30 | Removing Asphaltic Surface | Should there be additional quantity for removing asphaltic surface on the southern portion of the project? (7650-01-74) | In portions of the roadway in 7650-01-74 that have only asphalt pavement, Excavation Common is quantified to the bottom of the 4â€ maximum depth of the Base Aggregate Dense 1 ï¿½-Inch layer shown on the typical sections, therefore the volume of asphalt pavement proposed for removal is included in the cubic yard measurement for Excavation Common. Additional quantity for removing asphaltic surface should not be added as it planned to be paid as Excavation Common. A general note included in the plan details this further. | Mike Coleman | 1 | 2021-02-02 19:24 | 2021-02-04 09:34
20210209 | 20210209030 | 30 | Structure B-47-230 | Can this structure be two precast single cells laid side by side instead of a twin cell precast structure. | The plans do state the contractor may furnish a precast concrete box culvert in lieu of the cast in place box culvert and the precast concrete box shall conform to the precast details in the chapter 36 standards of the current bridge manual. Standard 36.05 (https://wisconsindot.gov/dtsdManuals/strct/manuals/bridge/std3605.pdf) shows a multi-cell option in which two single cell boxes are used in parallel. The notes in this standard state that for this case the clear spacing between the barrels shall be 6â€ and filled from the top of bedding to top of top slab with Grade â€œBâ€ concrete. As long as these and other requirements in chapter 36 of the bridge manual and standards are followed, using two single cell precast boxes placed next to each other would be acceptable. The change to the center wall thickness compared to the cast-in-place option will change the inlet and outlet wing/apron details so that would need to be addressed and the contractor submit shop drawings of all changes as indicated in the plan note. One other thing to note is that with the depth of fill above this culvert, using precast sections may require special analysis because the ASTM C1577 design tables only cover up to 20 feet of fill. | Mike Coleman | 2 | 2021-02-04 10:21 | 2021-02-04 12:16
20210209 | 20210209030 | 30 | Topsoil | Please clarify the intent of the topsoil bid item. The finished typical sections show adding topsoil on the roadway slopes for the entire length of the project, but the erosion control plans do not clearly identify the areas of topsoil and mulch. | This is addressed in the Typical Sections. On the 7650-00-74/01-75/02-73 plan there is a note on the Typical Finished Section sheets that states: â€œAll disturbed areas will be restored with Topsoil, Seed No. 30, Fertilizer Type B and Mulch. Replace mulch with erosion mat Class I Type A as identified in the plan. Seed and fertilizer to be placed from slope intercept up to finished shoulder point.â€ To clarify, topsoil and mulch or erosion mat to be placed from slope intercept up to subgrade point. On the 7650-01-74 plan set, there is a dimension with a callout on each typical finished section stating â€œPlace Topsoil, Seeding Mixture No. 30, Fertilizer Type B, and Mulch or E-mat (Typ.). The erosion control plans include a hatch pattern for areas that erosion mat is being called for. | Mike Coleman | 3 | 2021-02-04 14:35 | 2021-02-05 07:25
20210209 | 20210209030 | 30 | Salvaged and Unusable | Please clarify the earthwork summary for project id 7650-01-74. The earthwork summary table has 3,141cy of salvaged unusable pavement, while the computer earthwork data tables show 21,127cy of salvaged unusable pavement. | The earthwork data table toward the end of the plan is correct, and incorrect data was used to populate the earthwork miscellaneous quantity table. Revising the earthwork miscellaneous quantity table results in no actual bid item quantity change associated with the correction, but the quantity of unusable pavement material increases and the waste volume decreases accordingly. | Mike Coleman | 4 | 2021-02-04 14:42 | 2021-02-05 07:25
20210209 | 20210209031 | 31 | Contract time seems too short, temp shoring and crack & damage survey seem like they should be added | Hi, this proposal is a 40 working day contract. That seems extremely brief given the scope of work. Removing an existing pier, pre-boring piling, in conjunction with cure time on approach slabs, curb and gutter, sidewalks, etc. make this a longer project than is currently allotted. The storm sewer work alone will delay pouring approach slabs as well. We would appreciate significant contract time to be added (60 working days seems far more appropriate) to make this more affordable and workable. Additionally, the excavation for structure on the SE quadrant seems to be very close to the Dell's Mill, which is a historic structure. Respectfully speaking, we feel temp shoring and a crack and damage survey should be added to the scope of work. | An addendum is being prepared that includes increasing the working days and adds temporary shoring, seismograph, and crack & damage survey items. | Mike Coleman | 1 | 2021-01-14 14:42 | 2021-01-20 10:07
20210209 | 20210209031 | 31 | Pile foundations clarification | The plans indicate driving to bearing but the pre-bore spec indicates firmly seating the piles before backfilling with cement grout. Please clarify. | Pile resistance to be confirmed by driving after seating the prebored piling. | Mike Coleman | 2 | 2021-02-02 11:22 | 2021-02-03 09:22
20210209 | 20210209031 | 31 | Follow up to question #2 - Prebore Piling Clarification | Since the piling are to be driven to bearing per plan. Will casing of the prebored hole & backfilling with cement grout be also required? Per Specifications 550.3.9.3 (2) & (3) |  |  | 3 | 2021-02-03 15:45
20210209 | 20210209033 | 33 | Temporary Bypass pavement marking | The standard detail for Temporary Bypass Roadway shows temporary pavement markings, but there aren't any quantities included for this. Since this is a dead-end road are the temporary pavement markings not installed? Thanks | Temporary bypass pavement markings are not required for this base aggregate temporary bypass. | Mike Coleman | 1 | 2021-01-21 10:54 | 2021-01-25 11:23
20210209 | 20210209035 | 35 | Prosecution - Progress | The proposal says we have to pave all milled surfaces by end of construction on Friday. This is quite cumbersome from a construction standpoint. We will have to send our mill sub away likely on Thursday and come back the following Monday to continue milling. This will add more cost to the project. Can we just mill the entire project and then perform the asphaltic base milling/patching and then pave the lower lift? The project is detoured. | We think there is merit to revising the requirement currently in the special provisions. The designer will be preparing an addendum and will submit as soon as possible. | Mike Coleman | 1 | 2021-01-27 15:51 | 2021-01-29 07:42