## qandasearchletting_results
Date: | 2021-07-12
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210713 | 20210713001 | 1 | Field Office Fixed | Can this item be changed to a monthly unit of measure instead of a lump sum? The statement "The field office shall remain available for department until the engineer approves its closure. These field facilities are for the sole use of the department and upon contract completion remain the contractorâ€™s property." leaves it open for interpretation that it could be left open indefinitely. There are many jobs that are open for several years and this could lock us into keeping it for the entire time. If it cannot be changed to a monthly unit of measure, could a date be given for the closure of the office? | The item will be changed to the Month unit of measurement in an upcoming addendum. | Mike Coleman | 1 | 2021-06-17 10:45 | 2021-06-21 13:50
20210713 | 20210713001 | 1 | Design Schedule Request | Can you please provide the design schedule? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210713001/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-06-21 11:05 | 2021-06-21 13:55
20210713 | 20210713001 | 1 | QMP Subgrade | QMP subgrade doesn't make sense on this project. All grading occurs at night (no drying time) and lanes have to be open to traffic the next morning with a safe slope, so if the dirt is bad it needs to be dug out and backfilled with Rock that night, no other option. 45,000 CY of Common and only 2,000 cy of fill, the entire project is all waste dirt. QMP Subgrade should be removed from this project. | QMP Subgrade will not be removed from this project. | Mike Coleman | 3 | 2021-06-24 20:08 | 2021-06-29 06:48
20210713 | 20210713001 | 1 | Geotechnical Reports | Can you provide the geotechnical reports for this project? | The geotechnical reports can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210713001/ | Mike Coleman | 4 | 2021-06-25 10:35 | 2021-06-25 10:39
20210713 | 20210713001 | 1 | Crushed Aggregate Base Course | Does all existing project asphalt pavement have to be screened to be resused on the project or can it simply be milled and reused. We understand it has to be crushed and screened but we see other contractors milling and reusing existing milled asphalt as base and request clarification as a result. | Yes, it all needs to be screened. | Mike Coleman | 5 | 2021-06-26 19:07 | 2021-06-29 06:49
20210713 | 20210713001 | 1 | Sawing Concrete | Should the Sawing Concrete item really be Sawing Asphalt? Does WisDOT want the concrete sawed or only the asphalt along the existing concrete as is typical? The Typical Detail says,"PLACE SAW CUT AT EGDE OF EXISTING CONCRETE TRAVEL LANE". Please clarify precisely what the intent is. | The intent is to pay Sawing Concrete at the interface which gives the department flexibility at deteriorated joints. | Mike Coleman | 6 | 2021-07-05 16:17 | 2021-07-06 13:28
20210713 | 20210713001 | 1 | Aggregate Items | The miscellaneous quantities table for the Aggregate Items has a row for an undistributed quantity but this does not appear to be included in the Project Total. Please review. | Agree. This issue will be corrected in Addendum #2. | Mike Coleman | 7 | 2021-07-07 07:13 | 2021-07-08 10:46
20210713 | 20210713001 | 1 | Typical Sections | The typical sections and the cross sections depict the construction of the base aggregates directly below the edge of the asphalt pavement. Please confirm that the Department acknowledges that this is incorrect and the aggregates will be constructed a minimum of 2' wider than the proposed edge of asphalt pavement. In addition, the select crushed is typically daylighted out to the 3:1 slopes to allow for drainage within the base aggregate layers along with the placement of an aggregate shoulder along the edge of pavement to construct the 3:1 slope. Please confirm this construction method. | The intent is to construct the roadway per the typical sections and cross sections to minimize disturbance for a temporary condition. Relief trenches will be constructed per the construction detail and locations shown on sheet 12. | Mike Coleman | 8 | 2021-07-07 07:20 | 2021-07-08 10:47
20210713 | 20210713001 | 1 | Cold Patch | Is the 1000 ton quantity of cold patch correct? If so, are there plans showing where all of this material will be used? | The Cold Patch quantity will be adjusted to 100 tons in Addendum #2. The item is intended to be used for pavement repair as directed by the engineer. | Mike Coleman | 9 | 2021-07-07 11:47 | 2021-07-08 10:47
20210713 | 20210713001 | 1 | Typical Sections | The typical sections and the cross sections depict the construction of the base aggregates directly below the edge of the asphalt pavement. Please confirm that in order to provide a stable foundation for the temporary pavement, the aggregates must be constructed a minimum of 2' wider than the proposed edge of asphalt pavement. |  |  | 10 | 2021-07-08 15:40
20210713 | 20210713001 | 1 | QMP Subgrade | How will densities and drying be obtained on the subgrade when the work will be completed at night in September and October? Please note that the proposed excavation is performed along existing pavement in which the existing underdrain will be removed, which will then result in water seeping out from the existing aggregate onto the proposed subgrade. How will the existing water be controlled? | QMP Subgrade is required on the project per the Special Provisions, and work will be coordinated with the engineer. QMP Subgrade will ensure that a fully certified grading technician will be on site to help aid decisions that will need to take place during night closures. | Mike Coleman | 11 | 2021-07-08 15:48 | 2021-07-12 13:37
20210713 | 20210713001 | 1 | Please expand on the response to Question 6 | Can Question 6 please be further clarified? In particular "give Department flexibility at deteriorated joints." Does this mean the entire longitudinal joint where the sawing concrete is planned is going to include sawing off the edge of concrete to assure all deterioration is removed? There is a substantial cost difference between sawing the asphalt at the interface and full depth sawing the concrete? | The intent is to saw the joint at the interface. Work at deteriorated joints will be coordinated with the engineer. This sawing is quantified as Sawing Concrete. Per standard spec 690.3.3 (1), â€œsaw full-depth unless the plans indicate otherwise or the engineer directs or allows otherwiseâ€. | Mike Coleman | 12 | 2021-07-10 11:13 | 2021-07-12 13:47
20210713 | 20210713001 | 1 | What are the rules for where equipment can and cannot be parked? | Can the precise rules of where contractors can and cannot park equipment please be provided? | Equipment storage is detailed in Article #3 (Prosecution and Progress), Article #5 (Traffic), Article #19 (Notice to Contractor â€“ Project Storage and Staging Areas), and Article #24 (Material and Equipment Staging). In addition, the northeast quadrant and southwest quadrant of the Brown Deer Road interchange are listed in the plans and special provisions as locations where the storage of equipment and materials will be allowed after written permission to use the sites is provided by the department. | Mike Coleman | 13 | 2021-07-11 09:09 | 2021-07-12 13:51
20210713 | 20210713001 | 1 | Work in Stages 1 and 2. | Is there a reason that some of the excavation and aggregate work can't be performed in Stage 1 that is shown in Stage 2 if it is convenient for Contractor to do so? | Stage 2 excavation and aggregate work can be performed in Stage 1 if the work does not impede the opening of travel lanes and conforms to the Nightly Freeway Shoulder Restoration requirements as specified in the contract and as approved by the engineer. | Mike Coleman | 16 | 2021-07-11 13:23 | 2021-07-12 13:53
20210713 | 20210713001 | 1 | Night time work on Port Washington Road. | The specifications require work to be performed between 9:00pm and 5:30am at night when lane closures are allowed. There are two large hotels on the project. The Special Provisions also require compliance with all local noise ordinances. Fox Point's noise ordinance does not allow contruction between 7:00pm and 7:00am. Fox Point has informed us they have no intention of providing a waiver for their night time noise ordinance. Please elaborate on how WisDOT expects the contractor to construct the work on Port Washington Road when it requires the work to be performed at night and meet all local noise ordinances when the local noise ordinance does now allow night time construction work. |  |  | 17 | 2021-07-12 07:19
20210713 | 20210713002 | 2 | Cold Weather Paving | With a November 5 completion date, will the cold weather paving item be added to the project? | An addendum will be issued to add the bid item Cold Weather Paving. | Mike Coleman | 1 | 2021-07-01 08:55 | 2021-07-06 06:02
20210713 | 20210713003 | 3 | CTH Q Closure Clarification | The contract states that CTH Q is closed to through traffic during construction operations. Can work be done on 4304-05-71 (B-36-0242) and 4304-06-71 (B-36-0241) concurrently? Can both bridges be removed/closed at the same time? | Only one bridge can be closed to traffic at a time. The south bridge for project 4304-05-71 must be constructed first. This will be clarified in an upcoming addendum. | Jill Fehrman | 1 | 2021-06-16 14:49 | 2021-06-17 16:05
20210713 | 20210713004 | 4 | Cold Weather Paving | With a November 5th completion date, will cold weather paving be added to the contract? | Proposal 04 is a working day contract and has cold weather paving in the soi | Mike Coleman | 1 | 2021-07-01 10:22 | 2021-07-06 10:23
20210713 | 20210713006 | 6 | Temporary Pavement Markings | Item 649.0150 has White, Yellow, and Black Temporary Removeable Tape all included in one item. Can the 1,100' of Black non-reflective tape be separated out to its own item: 649.0506 Temporary Pavement Marking Removable Mask-Out Tape 6-Inch? Thanks | Proposal 20210713006 will keep all the temporary removal tape items under bid item 649.0150 and no addendum will be issued for the requested change to separate out the black non-reflective tape. | Mike Coleman | 1 | 2021-06-22 15:02 | 2021-06-30 07:02
20210713 | 20210713006 | 6 | Damage inspection report | It states in the General Notes section that a damage inspection report for B-27-0053 was prepared and is available upon request. Could this report be provided by the department? | The Damage Inspection Report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210713006/ A Non-Destructive Testing Report has been added to the same location. | Mike Coleman | 2 | 2021-06-30 09:23 | 2021-06-30 13:50
20210713 | 20210713006 | 6 | New Diaphragm Quantity | Sheet 48 of the plans includes new diaphragms for D11 and D12 only, but sheet 51 has note that says new diaphragms D10, D11, and D12. Please clarify how many new diaphragms will be required. | Sheet 48 of the plans is correct. There are 2 new diaphragms required for the project. The new diaphragms are located at D11 and D12. | Mike Coleman | 3 | 2021-07-07 10:04 | 2021-07-08 06:48
20210713 | 20210713006 | 6 | Remove & Replace Connection Plate Quantities | Sheet 45 of the plans shows 9 locations where the connection plate will have to be removed and replaced. Sheet 48 of the plans only shows 8 of these locations (difference is D13 - Bay 3). Please clarify how many locations the existing connection plates will need to be removed and replaced. | Sheet 48 of the plans is correct. There are 8 locations where the connection plate will have to be removed and replaced. The existing connection plate (and diaphragm) at girder 3, bay three, D13 will remain. No cracking was noted at this connection plate per the Fickett report. | Mike Coleman | 4 | 2021-07-07 10:07 | 2021-07-08 06:50
20210713 | 20210713006 | 6 | Welded Splice for new Girder | Would the Department allow a full penetration welded splice in the new girder section to allow for earlier delivery? Mill rolling for this girder section are out in Middle of October and would mean girder delivery in early November. |  |  | 5 | 2021-07-12 08:59
20210713 | 20210713007 | 7 | Schedule | Could you please provide the DOTâ€™s construction schedule for this job? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210713007/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-06-21 10:28 | 2021-06-22 07:54
20210713 | 20210713007 | 7 | Structure Adjustments | Just to confirm what needs to be done - Sanitary Manholes - Excavate, remove existing rings and replace with HDPE rings, install Chimney Seal and set to milled surface elevation, adjust with cast iron riser to finish elevation? Storm Manholes - Excavate to remove casting, install temp cover plate, reset casting after binder lift to finish elevation? Gate Valves - Excavate as necessary to turn valve box down to milled elevation. Adjust to surface elevation with cast iron riser? | For the sanitary manholes on the 8949-00-71 project (Village of Hammond), excavate to remove casting, install temp cover plate, reset casting after binder lift to finish elevation (paid for as 611.8110 Adjusting Manhole Covers/611.8120.S Cover Plates Temporary). For the sanitary manholes on the 8949-00-74 project (Village of Baldwin), excavate, remove existing rings and replace with HDPE rings, install Chimney Seal and set to milled surface elevation, adjust with cast iron riser to finish elevation (paid for as SPV.0060.004 Resetting and Adjusting Manhole Casting). The descriptions of work for the Storm Manholes and Gate Valves are accurate. | Mike Coleman | 2 | 2021-06-23 07:57 | 2021-06-24 10:14
20210713 | 20210713007 | 7 | Existing Box Culvert Backfill | It appears the new box is being built outside of the foot print of the existing box culvert. Upon removal of the existing box, does that volume get filled with Structure Backfill? There doesn't appear to be quantity for that. | The existing box culvert can be filled with material that is suitable for roadway fill. The fill material required outside of the new structure envelope is accounted for in the third earthwork data table on sheet 254 at Station 699+50 and 699+89. | Mike Coleman | 3 | 2021-06-23 15:56 | 2021-06-24 12:34
20210713 | 20210713007 | 7 | Traffic Contol - Lane Closure Restrictions | Under Traffic it states that maximum work zone lane closures shall be limited to one mile in length and delays due to flagging may not exceed 5 minutes in any direction. This is unreasonable for rural mainline paving operations. Add the requirement to mill and fill and it gets more unattainable. Add attempting to do lane repair in between milling and paving operations in the same closure and it gets worse. Please consider revising these requirements. | The requirements in the Traffic section and Lane Repair special provision have been altered to extend the delay time and allowable time between milling and lane repair completion. Revisions are shown in Addendum 1 for this proposal. The modification of time requirement to place the lower HMA layer after milling in the Prosecution and Progress section will be addressed in an additional addendum and will match the Lane Repair requirement. | Jill Fehrman | 4 | 2021-07-01 17:37 | 2021-07-02 10:33
20210713 | 20210713007 | 7 | Traffic Control - Work Hours | Under Traffic it states that Flagging operations will only be allowed between 1 hour after sunrise and 1 hour before sunset. We typically have good visibility 1/2 hr before sunrise and 1/2 hr after sunset. This will reduce our available time to work each day by at least 2 hours. This work will be occurring in the fall when we have reduced daylight hours available to work. Please consider removing this provision and allowing work per standard safe practices. | The restrictions on flagging hours will be removed in an upcoming addendum. The contractor is still required to meet all OSHA requirements/guidelines based on the working hours when flagging is being utilized. | Mike Coleman | 5 | 2021-07-01 17:39 | 2021-07-07 09:28
20210713 | 20210713007 | 7 | Schedule - Completion Dates | Please consider extending the interim completion date for paving of October 14th and final completion date of October 29th. Working late in the fall is not preferred, however the project is bidding July 13th. Earliest award is likely July 20th if it does not go under further review. It has been taking 4+ weeks to get contracts signed and processed putting the earliest start date mid to late August. Later in the season there are more weather days and less daylight hours available. | The Department will not be changing the interim or final completion dates for this contract. The HMA Cold Weather Paving item will be added with an upcoming addendum to address paving that will happen prior to the interim deadline but may occur under cold weather conditions that are specified in standard spec 450. | Mike Coleman | 6 | 2021-07-01 17:40 | 2021-07-07 06:53
20210713 | 20210713007 | 7 | Lane Repair | Under prosecution and progress, paving operations, the contractor is required to place the lower layer of pavement on the same day as milling (mill & fill). This project has 5,000 LF of undistributed lane repair. This will require a mill and paving crew on standby to mill and pave these areas in behind the mainline milling operation and before the mainline paving operation. This will increase costs. This will also result in paving over hot patches completed in front of the mainline paving operation which may not be desirable and could add variability to the PWL density test results. The department may want to consider milling and paving these patches full depth prior to starting the mainline mill & fill operation or consider allowing traffic to drive on the milled surface for a period of time to allow the contractor to complete the lane repair prior to paving the lower layer. | The requirements in the Lane Repair special provision have been altered to extend the allowable time between milling and lane repair completion. Revisions are shown in Addendum 1 for this proposal. The modification of time requirement to place the lower HMA layer after milling in the Prosecution and Progress section will be addressed in an additional addendum and will match the Lane Repair requirement. | Jill Fehrman | 7 | 2021-07-01 17:50 | 2021-07-02 10:35
20210713 | 20210713007 | 7 | Paving Pass Detail | Sheet 21 of the plans shows milling 2 feet past centerline on the first pass on the upper left Plan View. On the lower left Cross Section view it shows 2 inches. Milling the additional 2â€ as allowed under the HMA Pavement Longitudinal Joint Density spec (C 11) is a good plan. It is a good idea to mill the second pass at centerline, taking the 1-2â€ of material out that does not get compacted as well next to vertical joint. Please confirm we are not expected to mill 2 feet past centerline. | The contractor is not expected to mill 2â€™ beyond the centerline. This was an error in the original detail. This detail has been revised in Addendum 1 to also allow for milling to the centerline and remove the 2â€™ reference. Milling 2â€ beyond the centerline is still allowed as stated in the HMA Longitudinal Joint Density spec. | Jill Fehrman | 8 | 2021-07-01 17:57 | 2021-07-02 10:36
20210713 | 20210713007 | 7 | Baldwin 8949-00-74 - Mill & Pave Same Day | In the Village of Baldwin (8949-00-74) consider removing the requirement to mill and pave same day. It would be better for traffic and paving operations to mill the entire surface prior to paving. It also appears the intent was to complete the utility adjustments after milling and before paving? If the manholes were lowered and set to the milled surface elevation prior to milling they will be 2â€ deep and many of them are in the wheel path of the NB lane. | The modification of time requirement to place the lower HMA layer (or in the case of the 8949-00-74 project, the only layer) after milling in the Prosecution and Progress section will be addressed in an upcoming addendum and will match the Lane Repair requirement change in addendum 1 | Jill Fehrman | 9 | 2021-07-01 18:00 | 2021-07-02 11:06
20210713 | 20210713007 | 7 | Cold Weather Paving | The department may want to consider adding the HMA Cold Weather Paving item to the project due to the time of year this will be constructed. | An addendum will be issued to add Cold Weather Paving. | Mike Coleman | 10 | 2021-07-01 18:06 | 2021-07-06 06:03
20210713 | 20210713007 | 7 | Construction Staking | 1. It appears there is a greater storm sewer staking quantity than actual storm sewer items. Can you provide clarification on this? 2. Will construction staking be needed for the electrical work on the project? | The storm sewer staking quantity is shown incorrectly in the miscellaneous quantity table. This will be addressed in an upcoming addendum which will also add staking for electrical installations. | Mike Coleman | 11 | 2021-07-06 20:13 | 2021-07-07 13:36