## qandasearchletting_results
Date: | 2021-08-09
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210810 | 20210810001 | 1 | Patching concrete pavement | Is the existing 9 inch pavement doweled or plain pavement. | We believe based on as-builts the existing pavement is doweled concrete pavement. An addendum will be issued to add a note that it is doweled concrete pavement. | Mike Coleman | 1 | 2021-07-13 10:12 | 2021-07-14 11:17
20210810 | 20210810001 | 1 | Can work please be done this year? | Given the extreme lack of work in the industry, can the schedule allow work to be performed this year. We are exiting a pandemic and any work that can be done this year would be very helpful. | The last sentence of paragraph two of the Prosecution and Progress article, states the following: â€œThe start notice will not be given prior to April 1, 2022.â€ | Mike Coleman | 2 | 2021-07-13 19:05 | 2021-07-14 10:48
20210810 | 20210810001 | 1 | Flow @ Culverts Requiring Lining | Is any information available regarding water levels at the culverts requiring lining? Is any information available regarding the current internal condition of these culverts? Will lining spec ASTM F2019 be allowed for UV CURE to ensure zero downstream water discharge from lining operations? Is a bypass plan/dewatering plan available for draw down and disposal opertions? | 1. No other information is available. The bidder may do a site visit to obtain the existing condition and water levels currently at these pipes. 2. Allowable materials and construction methods are as specified in the plans, special provisions and on the departments approved products list. 3. As Specified in Article 14 under C.1, C.2, and the Payment section of the special provisions that all pumping, draining, and cleaning required to install liner is considered incidental to the items in that article. | Mike Coleman | 3 | 2021-07-20 22:05 | 2021-07-21 13:52
20210810 | 20210810001 | 1 | Pavement Markings | Good morning, In looking at plan sheet 11, it is referencing temporary epoxy to be placed on STH 49 and on plan sheet 12 it is referencing epoxy to be placed the same day STH 49 is paved prior to the rumbles. Will the department issue an addendum to add the temporary epoxy item as well as a same day epoxy item to cover the same day application? In addition, it does not appear there is enough temporary paint (934') for STH 49 based on the notes on plan sheets 11 and 12. Will this also be addressed in an addendum? Thank you. | Yes, an addendum will be added to add the temporary epoxy item as well as increase the temporary paint item. | Mike Coleman | 4 | 2021-07-22 07:57 | 2021-07-23 06:13
20210810 | 20210810001 | 1 | Can the design schedule please be provided? | Can the design schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810001/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 5 | 2021-07-25 07:39 | 2021-07-26 08:02
20210810 | 20210810001 | 1 | 644.1601 TEMPORARY CURB RAMP | Plans don't specify if the curb ramps shall be parallel or perpendicular. | Exact type and location will be determined by the engineer in the field based on the contractorâ€™s method of operations. If required, perpendicular ramps would likely be used on Shaler Drive and parallel ramps would likely be needed on Gateway Drive. | Mike Coleman | 6 | 2021-07-27 07:39 | 2021-07-27 12:44
20210810 | 20210810001 | 1 | Pavement Markings | Good morning and thank you for your response to the previous question, i appreciate it. Will you also be addressing the same day epoxy item in the forthcoming addendum? Enjoy your day. | Yes, temporary epoxy item is specified and noted on revised construction detail that it will be placed same day as paving operation and prior to centerline rumble strip installation. | Mike Coleman | 7 | 2021-07-27 08:35 | 2021-07-27 12:05
20210810 | 20210810001 | 1 | Butt Joint Item | Will a milling asphaltic surface butt joint item be added? | No, the milling depth and proposed HMA depth are the same, therefore the butt joint item is not needed. The saw cut item will be required as indicated. Sheets indicating the butt joint item is required will be amended and included in addendum. | Mike Coleman | 8 | 2021-07-27 13:52 | 2021-07-28 11:37
20210810 | 20210810001 | 1 | HMA Detail | The plan details show a HMA pavement 5 HT lower and 4 HT upper as well as 5 MT lower and 4 MT upper. Is this detail correct? |  |  | 9 | 2021-08-05 09:58
20210810 | 20210810001 | 1 | Milling detail | Per the construction detail on sheet 11, would the department allow the cross section to be milled full width instead of one lane at a time? | No, the contractor will be required to maintain traffic at all times and avoid placing vehicles on the milled surfaces to protect the existing subgrade. | Jill Fehrman | 10 | 2021-08-05 10:00 | 2021-08-06 13:45
20210810 | 20210810001 | 1 | Crossover | Sheet 66 details the crossovers to be built with 2 lifts of 4 HT. Would the department consider adding 'Asphaltic Surface Temporary' and placing in one lift of 3 MT as allowed per 460.3.2 note 3 (for use on crossovers and shoulders)? | The crossovers will remain in place for future projects, 4 HT will be required. | Jill Fehrman | 11 | 2021-08-05 10:02 | 2021-08-06 13:36
20210810 | 20210810001 | 1 | Base Patching | The design schedule shows 2,900 SY of base patching. There are 6,600 in the plan. Is the plan accurate? | The plans are correct with 6600 SY of base patching. | Jill Fehrman | 12 | 2021-08-05 13:43 | 2021-08-06 13:37
20210810 | 20210810001 | 1 | Is the existing 9" concrete reinforced? | Is there steel mesh in the existing 9" concrete pavement? | See addendum #01. | Mike Coleman | 13 | 2021-08-09 11:42 | 2021-08-09 13:27
20210810 | 20210810002 | 2 | Pavement Markings | Good morning, on page 3 of 7 of the proposal, it states "provide same day markings on the centerline..." which is typical of this type of project. Will there be an addendum to add a "same day" pavement marking item? Thank you. | An addendum will be issued to clarify. | Mike Coleman | 1 | 2021-07-22 08:39 | 2021-07-26 06:30
20210810 | 20210810003 | 3 | Pier piling clarification. | Page 42 of 62 (sheet 2 of 15 bridge plans) General note states "Piles placed in pre-bored holes into rock do not require driving". Page 50/62 Pier 1 Note center of page states - Pier to be supported on HP 10 x 42 steel piling (with pile points) "driven" to a req'd driving resistance of 180 tons per pile. The same note appears on Page 51/62 for Pier 2. If placed in pre-bored holes do they need to be driven and if not will they need pile points? | We reviewed the question with the geotechnical engineer and it is not anticipated that the pier piling will need to be driven in order to confirm the pile capacity is achieved. Pile points will only be needed at the abutments. An addendum will be issued to clarify. | Mike Coleman | 1 | 2021-07-14 15:56 | 2021-07-22 07:08
20210810 | 20210810005 | 5 | Schedule | Knowing the issues with getting traffic poles, 4+ weeks for shop drawings and 24+ weeks for the poles once approved. Would this schedule be allow to move to next year? Second will there be any consideration on the work done this year? Third will LD's apply to delays on the traffic items? | 1. As noted in the plans and specials, the City pre-ordered the monotube signal poles and arms, cabinet, and other traffic signal equipment. The preliminary delivery dates provided by the traffic signal equipment suppliers at the time of the Cityâ€™s order were August or earlier. The project is intended to be completed in Fall 2021. 2. Not sure what this means. 3. As previously noted, the City will be furnishing most of the traffic signal equipment. The schedule assumes if the traffic signal equipment is available, project construction can be completed by the contract completion date. | Mike Coleman | 1 | 2021-07-11 09:56 | 2021-07-14 14:18
20210810 | 20210810005 | 5 | Pavement Markings | Good morning, in looking at page 14 of 18, the standard specification for cold weather marking,646.5.5, was removed and 646.5.1 was modified so it is resembles 646.5.5. Wouldn't it be better to just use the cold weather marking bid item instead of modifying the standard specification to resemble it so as to avoid any issues during the completion of the contract work? Will an addendum be issued to change the standard epoxy items to cold weather as that is actually what it appears the department is looking for? Thank you. | This will be clarified in an upcoming addendum. | Mike Coleman | 2 | 2021-07-22 11:23 | 2021-07-29 12:51
20210810 | 20210810005 | 5 | Signal Heads | Line 0124 for 3S signal lists quantity of 7, but the traffic signal plan sheet only shows 6. It appears signal head number 12 is the issue. Should signal head 12 be a 3 section RYG, or a 5 section RYG YA GA as shown on the plan sheet? | Plan sheet 25 is correct, showing signal head #12 as a 5-section R-Y-G-<Y-<G. Miscellaneous Quantities sheet (#45) should show a Qty of (6) 3-section heads and (4) 5-section heads. An addendum will be issued to correct this. | Mike Coleman | 3 | 2021-07-22 13:09 | 2021-07-26 07:57
20210810 | 20210810010 | 10 | HMA Bid Item | Bid items, Plan Quantities, and cross sections all show using 3 LT mix for both lower HMA and surface HMA. The surface should be 4 LT mix. | Yes, the upper layer should be 4 LT 58-28 S. This will be corrected in an upcoming addendum. | Mike Coleman | 1 | 2021-07-12 15:49 | 2021-07-14 14:15
20210810 | 20210810010 | 10 | Item 0158 - 460.2000 Incentive Density HMA Pavement | Should the unit price for Item 0158 - 460.2000 Incentive Density HMA Pavement be $1.00? It is currently blank on the addendum and in AASHTOware. |  |  | 2 | 2021-08-04 16:25
20210810 | 20210810010 | 10 | Cut/Fill Earthwork Charts SPV.0195.01 | Please verify if the qty of SPV.0195.01 (10,601 ton) is included in the 16,901 Cy of Cut shown in 205.0100. Thanks. | No, the item for salvaging the asphaltic pavement includes removing the asphalt pavement, hauling it, and stockpiling it. The earthwork tables show the cut without the salvaged asphaltic pavement. | Mike Coleman | 3 | 2021-08-09 07:57 | 2021-08-09 13:10
20210810 | 20210810010 | 10 | Geotechnical Information | Please provide any geotechnical information available for the project area. | On sheet 2 of the plans, there is a table that shows the soil boring information. | Mike Coleman | 4 | 2021-08-09 10:06 | 2021-08-09 13:13
20210810 | 20210810011 | 11 | Design Files | Can the Department provide the meta-data, any geotechnical reports, and design schedule for this project? | The requested files can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810011/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-07-07 08:22 | 2021-07-19 10:33
20210810 | 20210810011 | 11 | Traffic Control- Storm Sewer Crossings | Per the special provisions (page 4 of 26) there are multiple full closures allowed for storm crossings. Question 1: For USH 51 NB it states there are 2 nights (total) for 4 runs of pipe. Is the intent to allow 2 night time closures for each run of pipe or 2 nights to perform all 4 runs (ie multiple crews)? Question 2: For STH 138 it states there is 1 night closure allowed for 2 runs of pipe. Is the intent to allow 1 night time closure for each run of pipe or 1 night to perform both runs (ie multiple crews)? Question 3: During the installation of the run from 110 to 105, USH 51 is allowed to be closed. Per the plans the pipe runs down Silverado Dr and will need to be closed for installation as well. Will Silverado Dr be closed as well during the 2 day installation of 110 to 105?â€ | Response to Question 1: In accordance with the Special Provisions, only two total night time closures are allowed to install all four pipe runs (not two night time closures for each pipe run). Response to Question 2: In accordance with the Special Provisions, only one total night time closure is allowed to install both pipe runs (not one night time closure for each pipe run). Response to Question 3: In accordance with the Special Provisions, Silverado is allowed to be closed to all traffic for up to 14 consecutive calendar days during Stage 1. The design intent is that the installation of pipe run 110 to 105 will be timed as such that the allowable two total night closure of US 51 NB will occur concurrent with the allowable 14 consecutive calendar day closure of Silverado. | Mike Coleman | 2 | 2021-07-19 15:36 | 2021-07-26 06:25
20210810 | 20210810011 | 11 | Earthwork files | Would the Dept please provide the earthwork tables in excel format (.xls). | The earthwork tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810011/ | Mike Coleman | 3 | 2021-07-22 13:20 | 2021-07-26 06:23
20210810 | 20210810011 | 11 | Select Crushed Alt | Would the Dept accept any alternate material for the select crushed, like 3" BAD or another that's not from a quarry? | This was discussed with the region pavement engineer. The department prefers to use Select Crushed Material per the plan. | Mike Coleman | 4 | 2021-08-03 19:42 | 2021-08-04 08:16
20210810 | 20210810012 | 12 | Catch Basins | Are the Catch Basins Type A or Type B casting openings? | Catch basin Castings should be Type B. Note E specifies the opening size on the miscellaneous quantities sheet. | Mike Coleman | 1 | 2021-07-27 11:44 | 2021-07-27 12:02
20210810 | 20210810014 | 14 | Additional Permit information | Can the department provide links or .ftp site for the additional permits listed. 404 permit, WDNR right to work, construction of navigable waters marker permit | The waterway marker permit and DNR final concurrence with erosion control permit can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810014/ The County has requested the WDNR right to work permit, as we donâ€™t have an actual permit yet, just correspondence from DNR at this time. | Mike Coleman | 1 | 2021-07-20 10:23 | 2021-07-26 08:10
20210810 | 20210810014 | 14 | Traffic Restrictions | Hello- With a completion date of 5/18/22 and a work schedule of 198 days per the Misc. Qty table for Traffic Control, this puts the start date of the project around 11/1/2021. Article 5 of the Special Provisions states that County H must be open to traffic at three separate times after this estimated start date (Thanksgiving 2021, Christmas 2021, New Years 2021/22). Is the contractor expected to remove the road closure and detour and open County H to traffic for these restricted dates? Thanks | For the three restrictive dates, the intent is that the detour would still remain up and the bridge would remain closed, but construction work at the bridge, trucking, and hauling operations are not permitted on those three dates. | Mike Coleman | 2 | 2021-07-20 15:32 | 2021-07-22 07:04
20210810 | 20210810014 | 14 | SPV.0165.01 Wall Modular Block Gravity Landscape | We have a few concerns with this bid item: 1. The pay item states 90 SF, but the wall is over 4-feet tall and 90-feet long. Please clarify the quantity or limits of this bid item. 2. The greatest dimension in the drawings between leveling pad and top of wall is 4.47-feet. Design criteria will dictate that either a gridded wall (not gravity) or a big block wall is needed. Will a big block wall be allowed on this project? This will likely lead to a larger excavation, possibly encroaching on ROW. A gridded wall will likely impact that ROW line even more. Please advise. | 1. The correct quantity should be 360 SF. It was originally shown in the MQ table as a LF item. An addendum will be issued to correct this. 2. A wet cast big block wall will be allowed, per the specifications. If a big block wall is used, the base of the wall should be at a similar location as if a dry cast modular block were used, so the excavation depth should be similar. | Mike Coleman | 3 | 2021-07-26 09:23 | 2021-07-30 07:20
20210810 | 20210810014 | 14 | Structure Removal Criteria Conflict | The Special provisions note a Debris Capture System is to be used for structure removal; however, the ability to reach the center pier for removal requires a causeway which would contradict the rationale to utilize a debris capture system. Has the Department considered the access required to remove the center pier while specify a debris capture system? | Removing Old Structures Over Waterway With Debris Capture System is a DNR requirement on the project. The contractor is responsible for submitting a structure removal plan as part of the erosion control implementation plan. Given the sensitive nature of the river, it is unlikely that a causeway built in the river will be an acceptable method for structure removal. | Mike Coleman | 4 | 2021-07-27 09:23 | 2021-07-30 07:22
20210810 | 20210810014 | 14 | Polymer Overlay Timeframes | will the Department waive the 28 day curing requirements of the bridge deck prior to placing the polymer overlay in order to meet the contract completion date of May 18th, 2022? | The standard specification requirements regarding the 28-day curing time needs to be followed. | Mike Coleman | 5 | 2021-07-27 09:29 | 2021-07-29 14:18
20210810 | 20210810014 | 14 | Culverts | There are bid items for Culvert pipes CL IV which allows steel to used per the thickness in the contract. I have been thru the plan 3 times and can find what the required steel thickness is. The specials are also silent on the subject. | Corrugated steel pipe culvert would need to be minimum 16 gauge steel for the culverts shown on the drawings. | Mike Coleman | 6 | 2021-08-02 13:59 | 2021-08-05 08:10
20210810 | 20210810014 | 14 | Culvert Endwall CUT OFF WALLS | The detail on plan sheet 8 does not match the detail on plan sheet 13. 4' deep vs 2' deep and 12" wider on both sides of endwall vs 1.5' wider Which detail do we follow? | Use the detail on sheet 13 for the cutoff wall. Disregard notes/dimensions related to the cutoff wall on sheet 8. | Mike Coleman | 7 | 2021-08-02 15:30 | 2021-08-05 08:12
20210810 | 20210810014 | 14 | Construction Staking | Will there be any wall staking or storm sewer staking required? |  |  | 8 | 2021-08-04 15:41
20210810 | 20210810014 | 14 | Oak Drive Traffic Control | Is Oak Drive to be under a full closure during construction near project limits? Can the design schedule be shared? | Oak Drive is not shown to be under a full closure during construction near project limits. The Contract Time of for Completion chart will be posted at the following link: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810014/ | Jill Fehrman | 9 | 2021-08-06 10:06 | 2021-08-06 14:09
20210810 | 20210810016 | 16 | Signal Mounting Hardware | For signal line items it appears there is only proposal line number 0272 for 1S 12-Inch signals, and 0274 for signal mounting hardware. It does not appear that any of the signals in the intersection listed (IH39 & CTH B) need mounting hardware as they are already existing. What items need to be provided in the proposal line number 0274 for signal mounting hardware then? Is it mounting hardware for the flashing beacons? | Yes, the intent for line number 0274 658.5069 Signal Mounting Hardware 1LS is to install line number 0272 658.0171 Traffic Signal Face 1S 12-Inch 10Each per the beacon installation details shown in the plan or per manufacturers recommendations. No other signal head work is specified with this contract. | Mike Coleman | 1 | 2021-07-27 09:47 | 2021-07-29 07:47
20210810 | 20210810016 | 16 | Culvert Liner | The proposal calls for a 24" liner. When we go to plan sheet 97 the plan says the existing culvert is a 24" CPRC. So one would think the liner would be a 21" or possibly a 18" ( not sure if they even make 21" liner pipe. The plan further calls for 24" RCP Endwalls to be installed on the ends of the liner pipe. Are the notes on the plan wrong? Are we trying to pipe burst this? What is really the intent here? | The bid item title, Culvert Pipe Liners, 24-inch, specifies the existing culvert pipe size that is required be lined. The contractor is required to provide a liner that results in the pipe having a capacity within +/- 5% of the original flow capacity of the pipe. In addition the pipe is to be installed horizontally to provide even annular space between the host pipe and sides of the liner, with the flowline as close to the host pipe invert as possible. The contractor is expected to determine the appropriate size liner to ensure these terms of the provision are met. Install endwalls either prior to, or upon completion of the pipe liner installation. Perform the liner installation in a manner to ensure that endwalls can be installed as required. | Mike Coleman | 2 | 2021-08-02 15:19 | 2021-08-03 10:46
20210810 | 20210810016 | 16 | Can the Design Schedule be provided? | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810016/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2021-08-02 19:55 | 2021-08-03 10:58
20210810 | 20210810017 | 17 | Traffic after prep | Will traffic be allowed on areas where polymer overlay has been removed before new Polymer Overlay is applied? | No, the project was planned so all work would be completed in a stage. We did not include temporary markings to stage this separately and there are also US 51 work zone work time restrictions so design team planned to have work completed to new polymer surface in each stage. â€¢ Set up work zone â€¢ Removal of existing polymer â€¢ Shot blasting and surface prep â€¢ Polymer overlay first layer â€¢ Polymer overlay second layer â€¢ Pavement marking â€“ we did provide some flexibility in final marking timing. | Mike Coleman | 1 | 2021-07-29 10:47 | 2021-08-02 10:25
20210810 | 20210810017 | 17 | Railroad Insurance | This contract's Special Provision Proposal book includes a section pertaining to Railroad Insurance and Coordination - Wisconsin Central Ltd (CN). None of the work associated with this contract occurs within close proximity to the Railroad ROW. Is Railroad Protective Insurance required for this contract? | Railroad Insurance is required. There are two locations where traffic control will be in Railroad right of way. We confirmed that with the region Railroad Coordinator. | Mike Coleman | 2 | 2021-08-02 12:07 | 2021-08-04 06:13
20210810 | 20210810018 | 18 | Prosecution & Progress - construction in 2024? | Section 3 of the specials states that work is to be within the 2024 construction season. Is this a typo and it is supposed to completed in the 2022 season? | It should have 2022. An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-07-21 08:12 | 2021-07-21 13:47
20210810 | 20210810018 | 18 | Temp Portage Path | There are no details in the plan set. Who chooses the route? Must the route be surveyed to install the pedestrian barricades? Is there a surface to walk on? There are no accommodations of the construction/removal of the path under other bid items. | The proposed temporary portage layout is shown on page 22 of the plan. The route depicted provides 10â€™ +/- past the farthest slope intercept from stages 1, 2 & 3. The portage is not needed for stage 4 so it doesnâ€™t consider the final section. It does not need to be surveyed, just place it outside the slope stakes. The special provisions state â€œThe route on which the portage is located shall be clear of debris, shrubs, and trees.â€ The special provision for clearing and grubbing states that the limits are, â€œ5 feet outside the temporary portage path.â€ There is no additional improvement to the surface that needs to be installed or removed. The NC Region discussed using mulch to surface the path but decided against it. | Mike Coleman | 2 | 2021-07-29 11:41 | 2021-08-02 13:37
20210810 | 20210810018 | 18 | Contract Time v. State Date v. In-Stream Restrictions | There seems to be a conflict on contract time in conjunction with other project restrictions. The contract allows instream work May 2-14 and July 11- September 29. By contract, the notice to proceed will be issued by May 1. This forces Stage 2 instream structure work into the May 2-14 window and Stage 3 instream work into the July 11- September 29 window. Problem is, without a suspension, by July 11 (51) days have been charged and leave only (29) days to complete Stages 3 and 4. Stage 3 includes substantially more work than Stage 2. It is not feasible to complete Stages 3 & 4 in nearly half the time of Stages 1 and 2. The May 1 start notice precludes conducting all instream work in the July 11- September 29 window. Was there an oversight on these interconnected restrictions, or is the culvert removal not considered instream work? | We believe that the project can be completed according to the Contract Time for Completion chart. The chart can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810018/ This schedule is based on probable working days and has stage 2 ending approximately July 10th with roughly half the working days remaining. If there are fewer delays for bad weather and stage 2 is complete prior to July 11th, the Region will suspend working days until the instream restriction has ended. Culvert removal is considered instream work and the upstream half must be removed in the May 2-14 window. | Mike Coleman | 3 | 2021-08-03 13:34 | 2021-08-04 09:18
20210810 | 20210810019 | 19 | Traffic Control - Weekend Lane Closures | Per Article 4 - Traffic, the special provisions state that weekend lane closures will not be allowed. Due to the scope of work, contractor requests that work under flagging operations be allowed on Saturdays. The scope of work is linear in nature and consists of the following steps: removing shoulder, pulverizing, widening, fine grading, and paving, all within 72 hours per the prosecution and progress. | Article 4. Traffic of the special provisions state: Weekend lane closures will not be allowed unless approved by engineer in writing. | Mike Coleman | 1 | 2021-08-03 11:15 | 2021-08-05 08:51
20210810 | 20210810020 | 20 | Diversion Channel for 84" Culvert | Can existing pipes be used as a diversion pipes while new culvert is being installed? Can WisDOT provide Q2 flow data for E Br. Eau Claire River? | The existing culvert pipes may be utilized as part of the diversion channel. Q2 flow for the E. Br. Eau Claire River is 112 cfs. | Mike Coleman | 1 | 2021-07-27 12:08 | 2021-07-27 14:02
20210810 | 20210810021 | 21 | Staging | Would it be acceptable to switch stage 1 work with stage 2 in order for the paving operation to begin at the centerline of the road. Said efforts will be made in an attempt to provide the best possible ride. | Stage 2 may be completed prior to Stage 1. | Mike Coleman | 1 | 2021-08-03 19:43 | 2021-08-04 10:14
20210810 | 20210810024 | 24 | Schedule | Contractor is requesting a copy of the DOT's preliminary schedule. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210810024/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-07-26 11:48 | 2021-07-27 12:10
20210810 | 20210810024 | 24 | 48 hour milling | Do to the road being closed to through traffic and detoured, and that the culvert patches are allowed to stay exposed for 72 hours, could the exposed milled surface remain open to traffic for a period of 72 hours? | The existing pavement depth requires the exposed milled surface to be covered within 48-hours. | Mike Coleman | 2 | 2021-07-28 13:12 | 2021-07-29 10:01
20210810 | 20210810024 | 24 | 21 day detour | The special provisions state that milling, paving, culvert pipe replacements , and beam guard will happen while the road is closed to traffic under a 21-calendar day detour. Based discussions with multiple excavation sub- contractors, the contractor feels the DOTâ€™s preliminary schedule is in error, and the 21 days does not allow enough time to complete the work indicated. Could the detour time be extended, or could the milling and paving be completed after the detour is removed? | The 21 day detour is to allow the contractor to complete any operations that would require the road to be closed to thru traffic. Any operations that take place outside the 21 day detour would need to be completed utilizing flagging operations. | Mike Coleman | 3 | 2021-08-03 16:48 | 2021-08-04 10:39
20210810 | 20210810025 | 25 | Pavement Markings | Good morning, could you please check the quantity of 41,450 LFT of temporary epoxy and confirm that is the correct amount? Typically this item would closely resemble the quantity, in this case 31,100 LFT, of permanent markings placed. In addition, on page 2 of 6, it states that the milled surface cannot be left exposed for longer than 72 hours. What is the plan for temporary markings on the milled surface? Will an addendum or clarification be issued to address these questions? Thank you. | The quantities for the temporary pavement marking epoxy are correct. They include both marking on milled surface and in lieu of Same Day Pavement marking bid item, as part of the calculations, the following assumption was made: That the milling operation would start prior to the paving operations and be between half of a working day and a full working day ahead of the paver (25% to 50% of the projectâ€™s length), and that at the end of the working day the milled surface between the paver and mill would need temporary pavement markings. This overlap caused the temporary pavement marking epoxy quantity to be computed at double the total centerline length. | Mike Coleman | 1 | 2021-07-26 11:05 | 2021-07-28 10:02
20210810 | 20210810025 | 25 | Paving around beamguard posts | The proposed typical section on Sheet 11 of the plan for STA 266+00 - STA 270+92 calls for paving around the beamguard posts. Will an emulsified asphalt or low strength grout be required around the posts? A mow strip of some sort? Can additional details be provided? |  |  | 2 | 2021-08-02 16:25
20210810 | 20210810025 | 25 | Utility Conflict at Guardrail Location | Section 3 and Section 9 of the Special Provisions state that the existing fiber optic will interfere with guardrail installation. It also states to reference the SDD for MGS Guardrail and to coordinate with the engineer and Solarus. In referencing the SDD's, I'm assuming you are referencing sheet 14B42-06C, which states that the contractor can add an additional 4-inches to the blockout for utilites. 4-inches won't clear a utility conflict. The 2nd detail states that only 1 or 2 posts can be placed with a total of 36-inch blockout. I don't see how this resolves the fiber optic conflict. Can you explain what SDD you are referring to that helps this conflict? In regards to coordinating with the engineer and Solarus, is it possible that through coordination Solarus will move the fiber optic cable or warranty that the line is deep enough and not in conflict? I don't understand how this language in the Special Provisions changes or eliminates the conflict. What coordination is possible? |  |  | 3 | 2021-08-04 13:57
20210810 | 20210810026 | 26 | Overlay on B-19-5 | Would the Department consider an alternative overlay mix in lieu of the Grade "E" currently specified? | After consulting with BOS, the Department will not consider an alternative overlay mix. | Mike Coleman | 2 | 2021-07-26 10:55 | 2021-07-29 06:19