## qandasearchletting_results
Date: | 2021-09-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20210914 | 20210914002 | 2 | Cabinet Specs | Current specs call for the Econolite Cobalt Controller & the Siemens size P cabinet. Can the Econolite P size cabinet be accepted/approved as well? | Bid as specified. | Mike Coleman | 1 | 2021-08-19 15:44 | 2021-08-23 08:42
20210914 | 20210914002 | 2 | Can the Design Schedule be provided? | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914002/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-09-02 08:01 | 2021-09-02 13:22
20210914 | 20210914003 | 3 | 1706-01-80 Quantities | It appears that the quantities for the 80 project are missing from the plan. Please confirm. | The 1706-01-80 quantities are located on sheets 50 - 52. | Mike Coleman | 1 | 2021-08-24 10:04 | 2021-08-24 11:53
20210914 | 20210914004 | 4 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers and culverts shall be used at every opportunity possible when proposed permanent long-term installations are: - 12-36 inches in diameter - non interstate or divided US Highways - Storm sewer in all ADT Ranges - Culvert installations at ADT of 20k or less Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | This project is a local program project and the local unit of government has elected to use the pipe material specified. | Mike Coleman | 1 | 2021-09-07 17:13 | 2021-09-08 13:29
20210914 | 20210914006 | 6 | Temporary and Same Day Pavement Markings | Good morning. On page 3 of 16 in the proposal, it references placing temporary/same day markings on both the lower and upper layer of pavement. I do not see any temporary or same day pavement markings included in the plan or proposal. Will an addendum or clarification be issued to address this? Thank you. | This will be addressed in an upcoming addendum. | Mike Coleman | 1 | 2021-08-24 07:47 | 2021-09-01 08:13
20210914 | 20210914006 | 6 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914006/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-09-02 08:02 | 2021-09-07 11:22
20210914 | 20210914006 | 6 | Are the Concrete Repairs Contininuously Reinforced or Doweled. | There is a Standard Detail Drawing showing the standard for repairing existing concrete pavement with continuously reinfored pavement with continuous reinforcement. Please explain how the concrete repairs are to be repaired and wether the standard plate with dowels will be used or the standard plate with continuous reinforcement will be used. It appears dowels will be used but please clarify. | Existing pavement is 9â€ non-reinforced concrete pavement. This will be addressed via addendum. The SDD 13 c 9-15 should be used. | Mike Coleman | 3 | 2021-09-06 10:51 | 2021-09-10 07:46
20210914 | 20210914006 | 6 | Existing Continuous Reinforcement in the existing CRCP. | Can the pattern of the Continuous Reinforcment in the CRCP be provided? Please also confirm that dowels will be drilled between the reinforcement and not through the reinforcement. Rock drills used to drill the holes for the dowel bars do not drill through steel. | Existing pavement is 9â€ non-reinforced concrete pavement. This will be addressed via addendum. The SDD 13 c 9-15 should be used. | Mike Coleman | 4 | 2021-09-06 11:02 | 2021-09-10 07:47
20210914 | 20210914006 | 6 | Asphalt layers | Under Milling and HMA Resurfacing on Page 3 of the Special Provisions, it states "any pavement that is milled is required to have the lower layer placed prior to opening traffic". Shouldn't the 2" asphalt should be in one lift? | Existing asphalt depth is 3â€. This is being addressed via addendum. The intent of this language is to not have a drop-off left in place at the edge of concrete pavement. | Mike Coleman | 5 | 2021-09-07 08:29 | 2021-09-10 07:49
20210914 | 20210914006 | 6 | Continuous Diamond Grinding concrete slurry | For the Continuous Diamond Grinding concrete, can the slurry be placed on-site, such as the median, or on the aggregate shoulders? | Conform to the requirements of 107.18. The department will allow placement of slurry along shoulders that are located a minimum of 200 ft from any delineated, known, or potential wetland. | Mike Coleman | 6 | 2021-09-07 10:49 | 2021-09-08 13:35
20210914 | 20210914006 | 6 | Asphalt layer thickness | The plans show a 3" mill and 3" pave. Page 2 of the special Provisions references 2" of asphalt pavement. Which is correct? | 3â€ is correct. This was addressed in Addendum #1. | Mike Coleman | 7 | 2021-09-09 21:09 | 2021-09-10 08:34
20210914 | 20210914007 | 7 | Existing Reinforcing Steel. | Can information be provided of the spacing, size, etc. of the continuous steel in the existing pavement. | The as-built plans can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914007/ The as-built plan has the information requested. Specifically, the bottom of sheet 8 (sheet 2.7 of the plan) includes detailed information on the size and spacing of the continuously reinforced steel in the existing concrete pavement. | Mike Coleman | 1 | 2021-08-12 06:44 | 2021-08-16 07:52
20210914 | 20210914007 | 7 | Bearing Repair B-64-39 | We are looking for some clarity on the Bearing Repair bid item #542 for B-64-39. In the special provisions it states to remove the bearings, clean, paint, and reinstall them. On plan sheet 178 for this structure, under the anchor bolt notes it is stating to replace the anchor bolts at 5 bearings. Is the intent to remove/clean/paint/reinstall all 5 bearings at these locations or just to replace the raised anchor bolts called out in the plan? | Per SPV.0060.06, Bearing Repair, the bearings noted for bearing repair on plan sheet 178 shall be removed, cleaned, painted, and reinstalled with new anchor bolts. | Mike Coleman | 2 | 2021-08-18 13:29 | 2021-08-27 07:45
20210914 | 20210914007 | 7 | Drilling Shafts 24-inch | Please clarify if a bid item for drilling shafts 531.2024, which would accompany the plan bid items 531.1100 and 531.1140, should be included with a quantity for this project. | No, item 531.2024 is not needed nor required for Type I signs on steel posts. The 531.2024 item is used for footings for overhead sign structures, not ground mounted Type I signs on steel posts. | Mike Coleman | 3 | 2021-08-27 13:55 | 2021-09-01 08:08
20210914 | 20210914007 | 7 | Bearing repair/anchor bolt follow up question | As a follow up to question #2 concerning the bearing repair work. For the new anchor bolts on this item, can new offset holes be drilled in the masonry plates to accommodate the new bolts? The existing bolts could then be burned off flush, and new holes also drilled into the abutment/pier for the new anchor bolts. This has been done in the past on similar bearing repairs. | Yes, it would be acceptable for the new anchor bolts to be offset from the existing. An acceptable offset will need to be coordinated with the Bureau of Structures. | Mike Coleman | 4 | 2021-08-30 15:40 | 2021-09-07 11:49
20210914 | 20210914007 | 7 | Drilling Shafts Follow-Up | First, I apologize for using this forum. I'm not sure what the alternative is. In regards to the previous answer, in the old spec, 636 Concrete Sign Supports, excavating and backfilling were covered through the concrete masonry bid item in 636.5(2) for payment. Under the new spec, 531, it doesn't read this way. Under 531.5(2), the concrete masonry is for placing the concrete and anchor rod assemblies. Only under 531.5(4) is the excavating and backfilling covered, which is the drilling shafts bid item. For the sake of bid item consistency, as we've seen with all projects since the new specifications started, I ask you to review this issue. | Bid item 531.2024, Drilling Shaft 24-Inch, will be added to the project with an addendum. | Mike Coleman | 5 | 2021-09-01 10:00 | 2021-09-10 07:50
20210914 | 20210914007 | 7 | Dowel Bars and Continuous Steel Reinforcement. | Can WisDOT confirm that drilling for Dowel Bars cannot mechanically be done through existing rebar including the Existing Continuous Steel Reinforcement. longitudinal and transverse bars and the drilling must occur next to the Existing Continuous Steel Reinforcement and not through it? Rock Drills will not drill through steel. | Yes, it is expected dowel bar placement will be adjusted to miss the existing longitudinal steel. | Mike Coleman | 6 | 2021-09-02 06:09 | 2021-09-07 11:32
20210914 | 20210914007 | 7 | Can the cross over work start this fall? | Can the cross over work start this fall? | There is nothing in the contract documents preventing work from starting this fall. Contractors should be aware of other projects in the area under construction in 2021 that have traffic control which may conflict with this USH 12 project. Traffic control for this USH 12 project would not be allowed if it conflicts with other projects that are trying to complete work in calendar year 2021. Cold weather HMA that is not directed (but permitted) by the Department will be the responsibility of the contractor and the Department would not pay for the additives. In addition, be aware of dates and requirements in the WisDOT Standard Specifications. | Mike Coleman | 7 | 2021-09-02 06:11 | 2021-09-07 06:38
20210914 | 20210914007 | 7 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914007/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 8 | 2021-09-02 16:48 | 2021-09-07 11:29
20210914 | 20210914007 | 7 | Clarification on Base Patching before or after milling. | It looks like in stages 2 and 3 the Base Patching occurs after milling. Can it be clarified if the SHES Base Patching and Base Patching in Stage 5 and in particular 5C is done through the asphalt or can the base patching be done after milling on the ramps and other locations? Same with the Base Patching on the remaining stages. Also, will the SHES Base Patching be done through the asphalt or after milling? | The following paragraph will be added to the Prosecution & Progress article via an addendum. â€˜Traffic is not permitted on any milled surface. In locations where lane and ramp closures are permitted for more than overnight, all base patching shall be completed after the existing asphalt has been milled/removed. In locations where lane and ramp closures are only permitted overnight, all base patching shall be completed prior to the existing asphalt being milled/removed.â€™ | Mike Coleman | 9 | 2021-09-04 06:33 | 2021-09-08 08:32
20210914 | 20210914007 | 7 | Asbestos Reports | Can the asbestos reports for the structures be provided? | The asbestos report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914007/ | Mike Coleman | 10 | 2021-09-07 07:03 | 2021-09-07 07:10
20210914 | 20210914007 | 7 | Staging | Can the Staging timing be adjusted forward given it does not adversely impact traffic control on other projects or this project? | The contractor can begin work in calendar year 2022 as early as the weather will allow. As for completing work in the final months of 2021, there is a current USH 12 project, from the state line to STH 50, that is scheduled to run through the remainder of the 2021 construction. That project may include traffic control that extends into or through the STH 50 interchange, which could impact any work in the area of the existing south crossover in 2021. There is also a current project on IH 43 that may include traffic control within the IH 43/USH 12 interchange for the remainder of the 2021 construction season. Any work proposed for the 2021 construction season for the STH 50 to STH 67 USH 12 project would need to take into account the current construction projects and be approved by the DOTâ€™s construction engineer. | Mike Coleman | 11 | 2021-09-10 13:42 | 2021-09-13 11:02
20210914 | 20210914007 | 7 | Utilization of cloverleafs | Can contractors plan on utilizing the existing cloverleafs both within the project limits and those within close proximity (~five miles of the project) as temporary staging, site for crushing materials, concrete plants or hot mix asphalt plants for the duration of this project? Obviously, wetland designation would preclude the use of some cloverleafs. |  |  | 12 | 2021-09-11 10:11
20210914 | 20210914008 | 8 | Lines 362 & 370 | Are these lines supposed to be 10 Awg IMSA Cable? I am unware of IMSA Cable coming in 10 Awg. |  |  | 1 | 2021-09-09 12:45
20210914 | 20210914009 | 9 | Drilling Shafts for Ground-Mounted Type I's | It appears that bid item 531.2024 is missing for the footings of the ground-mounted type I's. Please confirm. | Item 531.2024 is not needed for ground mounted type I signs. The drilling shaft item is only needed for the overhead sign structures which is shown on the overhead sign structure pay items for each overhead sign structure It was confirmed this with BTO (Ryan Mayer, state signing engineer) | Mike Coleman | 1 | 2021-08-27 14:03 | 2021-08-31 10:09
20210914 | 20210914009 | 9 | Drilling Shafts Follow-Up | First, I apologize for using this forum. I'm not sure what the alternative is. In regards to the previous answer, in the old spec, 636 Concrete Sign Supports, excavating and backfilling were covered through the concrete masonry bid item in 636.5(2) for payment. Under the new spec, 531, it doesn't read this way. Under 531.5(2), the concrete masonry is for placing the concrete and anchor rod assemblies. Only under 531.5(4) is the excavating and backfilling covered, which is the drilling shafts bid item. For the sake of bid item consistency, as we've seen with all projects since the new specifications started, I ask you to review this issue. |  |  | 2 | 2021-09-01 09:59
20210914 | 20210914009 | 9 | Painting | Bridge B-40-280: Drawing sheets 153 and 154 say to paint girder ends. However, drawing sheets 456 and 457 say to paint the entire structure. Which is correct? Bridge B-40-281: Drawing sheets 171 and 172 say to paint girder ends. However, drawing sheets 458 and 459 say to paint the entire structure. Which is correct? | The girder ends on structures B-40-280 and B-40-281 are to be painted as part of the redeck work. The abutments are being converted from expansion abutments to semi-expansion abutments, and the girder ends will require concrete encasement. Cleaning and repainting the steel girder ends prior to concrete placement is required as part of this work. Full repainting for the remaining steel girder areas will be performed later in the project schedule within the 1360-15-70 ID to better fit with the traffic control proposed on the mainline resurfacing project. | Mike Coleman | 3 | 2021-09-02 14:16 | 2021-09-07 11:24
20210914 | 20210914009 | 9 | 614.0800 Crash Cushion Permanent | Hello, there is limited information in the plan regarding the Permanent Crash Cushion. Can you provide the test level, back width, and hazard being protected? Also, regarding the location of the cushion, is this the permanent cushion called out on page 227 of the plans? The miscellaneous quantities only give a station mark range of 172.5 - 180.0 as a reference. Thanks | â€¢ Location: STA 184+27, 59â€™ LT â€¢ Back Width: 2â€™ â€¢ Object Marking Pattern: OM-3C (W5-58M) â€¢ Crash Test Level: TL-3 â€¢ Traffic Direction: Unidirectional â€¢ Traffic: L and R â€¢ Crash Cushion Shields: Permanent Concrete Barrier between ramp and mainline STH 145 | Mike Coleman | 4 | 2021-09-08 12:18 | 2021-09-09 07:12
20210914 | 20210914009 | 9 | Concrete Base Patching | Is the concrete base patching to be performed before or after milling operations? | The contractor may perform the work as they see fit; standard spec 104.6.1.2.3 needs to be followed for the center lane. | Mike Coleman | 5 | 2021-09-10 14:59 | 2021-09-13 11:14
20210914 | 20210914009 | 9 | Echelon Paving | Proposal #9 on Page 5 or 99 reads as follows: Echelon Paving STH 145 Paving of both NB and SB STH 145 shall be done in echelon for the following locations: â€¢ Existing outside lane, outside shoulder and any adjacent ramp deceleration/acceleration lanes to the ramp gore point, during Stage 1. â€¢ Two inside lanes during nighttime closures. Is it safe to assume the only "non-echelon" paving on this project would include the ramps, portions of the gores and the inside shoulder? Basically, longitudinal cold joints would exist between the inside shoulder and lane one, along with a cold joint between lanes two and three. is this state correct? |  |  | 6 | 2021-09-11 09:58
20210914 | 20210914009 | 9 | Clear Zone | What is distance of the Clear Zone on this project? |  |  | 7 | 2021-09-11 20:58
20210914 | 20210914012 | 12 | Even Cross Section Profile Withng 72 HRS? | â€œFor paved surface open to through traffic, provide an even cross-sectional profile of the roadway within 72 hours of paving adjacent lane.â€ Will this be required if the contractor utilizes a notched wedge to eliminate the vertical longitudinal joint per the standard specification. | Yes, an even cross section will be required within 72 hours even if the contractor utilizes a notched wedge. | Jill Fehrman | 1 | 2021-09-10 08:35 | 2021-09-10 16:36
20210914 | 20210914013 | 13 | Tack Coat | There is no pay item for tack coat. Will tack coat be required and a pay item added for this? | Tack coat will be required and the item 455.0605 Tack Coat will be added to the proposal. An addendum will be issued. | Mike Coleman | 1 | 2021-08-27 12:06 | 2021-09-01 08:02
20210914 | 20210914013 | 13 | Concrete Masonry Bridges - Quantity? | Please confirm the Bid quantity for "Concrete Masonry Bridges" | The quantity for Concrete Masonry Bridges was re-checked and found to be incorrect. An addendum will be issued to revise the quantity for Concrete Masonry Bridges. | Mike Coleman | 2 | 2021-09-03 11:00 | 2021-09-08 08:25
20210914 | 20210914013 | 13 | IH 39 Shoulder Milling and Paving | The project schedule calls for all work to be completed in 2021 with the exception of the Bridge painting which will be done in 2023. Will the shoulders on IH 39 need to be milled and paved in 2022 or will this be required to be done in the spring of 2023? |  |  | 3 | 2021-09-09 13:16
20210914 | 20210914015 | 15 | preliminary schedule | The contractor is requesting a copy of the DOT's preliminary schedule. | The design schedule can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914015/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-08-23 08:41 | 2021-08-24 07:41
20210914 | 20210914015 | 15 | Temporary Paint/miscellaneous quantities | Good afternoon, Can you please clarify the quantities for the temporary paint on project 1590-18-61? There appears to be enough to do 2 passes rather than just on the milled surface. In addition, the miscellaneous quantities do not include the temporary epoxy item for project 1590-18-60. Thank you. | The miscellaneous quantity table on sheet 26 for pavement marking was cut off and did not show Temporary Marking Line Epoxy 4-Inch. The quantity for Temporary Marking Line Paint 4-Inch includes quantity for centerline marking on the milled surface and to the tapered centerline joint in the HMA Pavement, pass #1, if required. An addendum was issued to replace the sheet. | Mike Coleman | 2 | 2021-08-31 14:43 | 2021-09-07 06:37
20210914 | 20210914015 | 15 | Culvert Patching and bridge approaches | The asphalt patching for the culvert replacements and asphalt needed for the traffic switch for structure B-21-1 needs to be installed prior to constructing a test strip. Can this asphalt quantity be moved from the 4MT item to an asphaltic surface item? | The asphalt patching for the culvert replacements and the asphalt for B-21-1 will be changed to asphaltic surface via addendum. The upper layer of asphaltic surface is to be removed by mainline milling and replaced with mainline HMA pavement. | Mike Coleman | 3 | 2021-09-02 15:41 | 2021-09-08 08:52
20210914 | 20210914015 | 15 | Culvert Patching and bridge approaches | The asphalt patching for the culvert replacements and asphalt needed for the traffic switch for structure B-21-1 needs to be installed prior to constructing a test strip. Can this asphalt quantity be moved from the 4MT item to an asphaltic surface item? | The asphalt patching for the culvert replacements and the asphalt for B-21-1 will be changed to asphaltic surface via addendum. The upper layer of asphaltic surface is to be removed by mainline milling and replaced with mainline HMA pavement. | Mike Coleman | 4 | 2021-09-02 15:41 | 2021-09-08 08:51
20210914 | 20210914015 | 15 | Structure B-21-10 | Per plan, B-21-10 has 506 ton of HMA and is currently listed as 4MT PWL material. Can this be changed to an asphaltic surface item? This bridge is a standalone project about 20 miles from the main project and the scope of work is tie-ins and widenings at the bridge. | The asphalt material for B-21-10 will be changed to asphaltic surface via addendum. | Mike Coleman | 5 | 2021-09-02 15:43 | 2021-09-08 08:33
20210914 | 20210914016 | 16 | B-50-21 & B-50-22 Flambeau River Bridges | Can the Tapers be extended to encompass the limits of the asphaltic milling & butt joint work in order to complete the asphalt milling work concurrently with the bridge deck milling in each stage? If so, is the department willing to cover the extra traffic control items to facilitate this change? | Due to the location of private entrances near the work zones and anticipated traffic delay which is directly based on the distance between stop bars, the contractor should bid the traffic control layout as shown. The plan notes specifically indicate the need for the contractor to adjust the traffic control drums during the approach work. | Mike Coleman | 1 | 2021-09-03 11:14 | 2021-09-07 11:30
20210914 | 20210914017 | 17 | HMA Paving | 1. The Rumble Strips being removed and replaced with HMA paving appear to all be the same dimensions. Why are the HMA plan quantities not the same tonnage for each rumble strip? 2. The HMA paving on hwy 13 sta 22+42 to 27+18 and on hwy 21 sta 496+22 to 500+59 have 4% variable width paved shoulders. The width of these shoulders varies from 2' to up to 17' with a lot of change in width through out. This will be hard to pave. Can the HMA shoulders be changed to all 2% in these areas to make them more practical to construct? This will be cheaper to construct and it will cut down on the cold joints. |  |  | 1 | 2021-09-08 09:35
20210914 | 20210914018 | 18 | Water lateral install | Per the Special Provisions it states that only one water or storm lateral may be worked on at a time during the 10 working day detour. We do not believe this is a realistic time frame given this restriction. We understand the intention is to maintain access for the businesses and property owners as much as possible. Would the Department be willing to change this restriction to one lateral at a time per block? This would allow multiple crews to work on laterals to ensure completion while allowing simple access from side streets to the residents. Secondly, could you clarify the statement on two lanes being open to traffic in the closed work zone? Are we going to be able to dig the trench completely across the road for the hookup, or are we to maintain traffic doing this half at a time? Doing this half at a time can be done, but will generally result in a longer shut down for the property owner to get them switched over as we won't have access to the corp. | Yes, multiple crews can be working within the road closure if access is maintained and coordinated with property owners and businesses. Also, on page 6 of the special provisions, the Stage 2B Construction traffic description states the following, â€œâ€¦Contractor can coordinate with residents and businesses to work on more than one lateral at a time if approval from the property owners is received.â€ Two lanes through the work zone are required at the end of each working day to maintain access to residents and businesses. The intent was to construct the entire lateral at one time. The special provision states to â€˜Backfill water line trenches at the end of each day.â€™ | Jill Fehrman | 1 | 2021-09-09 17:25 | 2021-09-10 16:42
20210914 | 20210914020 | 20 | Cleaning Culvert Pipes | Should box culverts be included in this item when they are paid by each and there is a substantial difference in cleaning an 8x8 or 10x10 box and a 24" diameter culvert pipe? | Yes, box culverts should be included in the Cleaning Culvert Pipes item. | Mike Coleman | 1 | 2021-08-24 15:40 | 2021-08-27 07:38
20210914 | 20210914020 | 20 | LNPZ | Good morning, should there be a locating no passing zone bid item on this project? Other similar projects typically have one. Thank you. | A â€˜Locating No Passing Zoneâ€™ bid item should NOT be included on this project. It clearly states on page 31 of the plans that the passing and no passing zones should be replaced at their existing locations. | Mike Coleman | 2 | 2021-08-30 07:02 | 2021-08-31 10:51
20210914 | 20210914020 | 20 | Joint Ties | Are joint ties required when making a connection with a concrete collar? We have been required to install them as well in the past. | The answer to the question is no, ties are not required at the culvert pipe joints that are receiving concrete collars. | Mike Coleman | 3 | 2021-09-02 08:15 | 2021-09-07 06:33
20210914 | 20210914020 | 20 | Box Culvert Repair | Do the steel plates need to be galvanized? This has been CO'ed in on past projects. Can mechanical anchors or Tapcon anchors be used for plate installation? This has been allowed on past projects. | Steel plates should be galvanized along with the anchors. An addendum covering this change has been prepared and submitted a few minutes ago. Mechanical anchors will be allowed in the overhead joint repair only. Adhesive anchors are required for the vertical walls as the plans show. Mechanical anchors should not be used on the vertical walls. | Mike Coleman | 4 | 2021-09-02 15:16 | 2021-09-10 07:51
20210914 | 20210914021 | 21 | Lower Layer HMA | Would the lower layer of HMA be able to be considered a leveling layer similar to Proposal 20 in this same letting? If not would the lower layer be considered to be constructed directly on crushed aggregate or recylcled base and the minimum desity be reduced by 2.0%? | After further review with the designer and regional staff we have come to the conclusion that this minimum density should be reduced to 91%. | Mike Coleman | 1 | 2021-08-30 17:45 | 2021-09-01 08:05
20210914 | 20210914021 | 21 | CIR Turn Lanes | The plan shows completing CIR for the Bypass lanes, however does not show this for the turn lanes. Would the departement want the turn lanes to have CIR completed on them as well or only the bypass lanes? | CIR is not needed for the turn lanes on this project. Bypass lanes were included as they will see more traffic than the turn lanes. | Mike Coleman | 2 | 2021-08-30 17:46 | 2021-09-01 08:07
20210914 | 20210914021 | 21 | Safety Edge | In the plan the typical section shows Safety Edge Req'd(Typ). Normally when there is a 5' paved shoulder this is not required. Confirming this is required. | The Safety Edge item shall remain on this project. | Mike Coleman | 3 | 2021-08-30 17:53 | 2021-09-01 08:06
20210914 | 20210914022 | 22 | LNPZ | Should this project have a bid item for locating no passing zones added? Thank you. | This project should not have a bid item for relocating the no passing zones. This has been coordinated with the regional pavement marking engineers. | Mike Coleman | 1 | 2021-08-30 08:25 | 2021-08-31 10:56
20210914 | 20210914022 | 22 | 2021 Construction | Under Prosecution and Progess it states to provide the time frame for construction of the project within the 2021 construction season. Should this be 2022? | Yes, this should say the 2022 construction season. This will be revised via addendum. | Mike Coleman | 2 | 2021-08-30 18:11 | 2021-08-31 10:58
20210914 | 20210914022 | 22 | HMA Type | The project calls for a 4MT58-34V. On Hwy 8 HT mixes have been specified in the past. Confirming this is the correct mix type. | The DOT has reviewed the HMA mix type, and we are going to continue to use the mix type as specified in the advertised bid documents. | Mike Coleman | 3 | 2021-08-30 18:29 | 2021-09-01 13:05
20210914 | 20210914022 | 22 | Traffic Restrictions | Under Traffic, USH 8 Milling; restrictions of 48 hours to cover the milled surface and 10 calendar days to cover the leveling layer are included. Assuming this was added due to concerns with the road holding up under traffic. Note any additional time that would be acceptable would be helpful in reducing costs. | The 48 hour restriction for covering up the milled surface will not be extended due to the risk of breaking through the remaining thin asphalt layer. The 10 day restriction for paving the upper layer has been reviewed and will be lengthened in Addenda #1. | Mike Coleman | 4 | 2021-08-30 18:36 | 2021-09-01 13:06
20210914 | 20210914024 | 24 | Schedule | Can the DOT share the design schedule for this project ? | The design schedules can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914024/ The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-08-17 12:57 | 2021-08-19 06:57
20210914 | 20210914024 | 24 | Areas on ROW to waste Dirt | Will DOT allow waste Common Excavation to place on ROW in all 4 Quadrants of the STH 57 & STH 100 old interchange where the ramps were or anywhere the DOT knowns of? There is a lot of unused ROW that berms can be placed to provide noise shields and save money for the tax payers. If allowable can the DOT provide slope requirements, height requirements, any areas these berms will not be allowed and any other information that is known? | The department will not allow additional berms or fills outside of what the design provides. The excess R/W may be sold at a later date. | Mike Coleman | 2 | 2021-08-17 13:08 | 2021-08-18 10:30
20210914 | 20210914024 | 24 | Pre-Bid Contact with Native American Tribe | Please provide the contact information of the Native American tribe that contractors need to reach-out to before the bid. | The advertisement originally showed proposal 24 requiring pre-bid contact with the Native American Tribe. It was quickly realized the wrong proposal was listed. The advertisement was revised on August 13 to address this. There is no pre-bid contact for this proposal. | Mike Coleman | 3 | 2021-08-20 11:43 | 2021-08-23 09:09
20210914 | 20210914024 | 24 | sanitary sewer inside drop | Is the proposed inside drop for the new force main connection to MH 826.061? If yes to what invert do we build the bottom of the drop to? | Sanitary sewer inside drop work will be removed from the plans via addendum. | Mike Coleman | 6 | 2021-08-23 08:54 | 2021-08-24 08:50
20210914 | 20210914024 | 24 | Removing inside drop | Is the removing inside drop for the abandonment of the force main ? | Removing inside drop work will be removed from the plans via addendum. | Mike Coleman | 7 | 2021-08-23 08:55 | 2021-08-24 08:49
20210914 | 20210914024 | 24 | Granular backfill grade 1 | In the storm sewer notes it tells us that this material is to be used to backfill storm sewer trenches in the traveled way including shoulders. Is this material going to be used and paid for any storm removal trenches in the same manor? The breakdown in the miscellaneous quantities does not really help to clarify. | The backfill for the proposed storm sewer trenches is incidental to construction of the proposed storm sewer per Standard Specification Section 608. The Backfill Granular Grade 1 (Item #209.1500) shown in the Miscellaneous Quantities is for backfilling the storm sewer removal trenches that are within the proposed roadway/shoulder areas. | Mike Coleman | 8 | 2021-08-23 09:14 | 2021-08-24 08:47
20210914 | 20210914024 | 24 | grade 1 granular backfill | Does this quantity include the bedding and cover material around the pipe? | The backfill for the proposed storm sewer trenches is incidental to construction of the proposed storm sewer per Standard Specification Section 608. The Backfill Granular Grade 1 (Item #209.1500) shown in the Miscellaneous Quantities is for backfilling the storm sewer removal trenches that are within the proposed roadway/shoulder areas. | Mike Coleman | 11 | 2021-08-23 09:47 | 2021-08-24 08:48
20210914 | 20210914024 | 24 | Storm Sewer Notes | Per the recently answered questions, what are the storm sewer notes on plan sheet 167 STORM SEWER- CONSTRUCTION DETAILS telling us. I am referring to the 7 th and 8th bullet points "For structures and pipes outside the traveled way inclusive of shoulders, native backfill may be used and shall conform to section 207 embankment specifications" "For structures and pipes within the traveled way inclusive of shoulders, backfill shall conform to section 209 and be paid for as backfill granular Grade 1" | The notes will be revised with a future addendum to: For structures and pipes outside the traveled way inclusive of shoulders, native backfill may be used and shall conform to section 207 embankment specifications. Backfill conforming to section 207 is incidental to proposed storm sewer pipe and storm sewer pipe removal. For structures and pipes within the traveled way inclusive of shoulders, backfill shall conform to section 209. Backfill for storm sewer pipe removal will be paid for as Backfill Granular Grade 1. Backfill for proposed storm sewer pipe is incidental per Section 608. | Mike Coleman | 12 | 2021-08-24 09:48 | 2021-08-27 07:48
20210914 | 20210914024 | 24 | sanitary sewer work | Will full road closures be allowed for this work? There is little detail or instruction as to how traffic would be handled during the performance of this sewer work and the associated bypass pumping. What are the restrictions? | Full closures are allowed for pipe crossing work per the Traffic Special Provision Article within the Definitions/Full Closure Hours section. Work may also be completed under staged construction at Donges Bay Road per the staging plans or under flagging operations on STH 57 as described within the Special Provisions. | Mike Coleman | 13 | 2021-08-24 09:53 | 2021-08-27 07:50
20210914 | 20210914024 | 24 | Electronic Files | Can the Department please provide the storm sewer and earthwork tables in Excel format? | The requested quantity tables can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914024/ | Mike Coleman | 14 | 2021-08-24 10:33 | 2021-08-27 07:58
20210914 | 20210914024 | 24 | Base Patching Asphalt | The Base Patching Asphaltic detail shows the removal of only 2" of existing asphalt but requires asphaltic material per 390.2. The mix required under 390.2 is a 1" or 25mm design. The minimum lift thickness for this design is 3". Please clarify. | The construction detail will be revised to indicate 3â€ removal instead of 2â€ in a future addendum. | Mike Coleman | 15 | 2021-08-26 07:43 | 2021-08-31 07:52
20210914 | 20210914024 | 24 | Common BId items for different project numbers | One example is the Removing Storm sewer 12" there is a line number 42 for a quantity of 837 ft and line number 44 is for a quantity of 3525 ft They show up in misc. quantities as 837 ft for project 2565-07-70 and the 3525 ft shows up for 2270-04-70. Are they going to be paid that way using line number 42 for 12" removed on 2565-07-70 and line 44 for 12" removed on 2270-07-70? There is a similar situation for the Removing 24" Storm Sewer. | Line numbers 0042 and 0044 quantities should be combined into one line item. Line numbers 0050 and 0052 quantities should also be combined into one line item. These will be revised in a future addendum. | Mike Coleman | 16 | 2021-08-26 08:47 | 2021-08-27 08:51
20210914 | 20210914024 | 24 | Granular backfill | Ok since the backfill for the new storm installation is considered incidental and grade 2 granular is acceptable for the storm sewer trenches, why are we using grade 1 for the removal trenches? Wouldn't it make more sense for these materials to be the same? | Backfill Granular Grade 1 (Item #209.1500) is what was selected and planned for to backfill the storm sewer removal trenches. | Mike Coleman | 17 | 2021-08-27 07:57 | 2021-08-31 07:54
20210914 | 20210914024 | 24 | Soil Boring | Can the soil borings be provided for this project? | The requested soils report can be found at the following location: ftp://ftp.dot.wi.gov/dtsd/hcci/projectdocuments/20210914024/ | Mike Coleman | 18 | 2021-09-03 13:00 | 2021-09-08 08:31
20210914 | 20210914024 | 24 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) SSPRC Class III min/max cover heights are identical to SSP Class IIIB and less than 11 feet for Class IIIA within the current FDM guidance. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class III? | An addendum is being issued to correct this. | Mike Coleman | 19 | 2021-09-07 17:14 | 2021-09-09 07:13
20210914 | 20210914024 | 24 | 24. Material Stockpile and Equipment Storage. | The Article 24. Material Stockpile and Equipment Storage doesn't make any sense. The existing project configuration is an overhead interchange which is currently 25-30 feet higher than proposed grades. 5' high equipment doesn't exist, pickup trucks are higher than that, so no parking of Foreman/Engineer trucks on the grade during work, only cars allowed? Obtain written permission and necessary permits from the property owner and local governments/agencies, what permits are required to work on DOT ROW, how do get these permits/permission and why would any adjacent land owner give you permission? This article is unrealistic and can't be achieved. Please remove this entire Article. | Special provision article has been revised with an emergency addendum. | Mike Coleman | 20 | 2021-09-09 15:49 | 2021-09-13 11:08