## qandasearchletting_results
Date: | 2021-12-13
Letting | Proposal | Call Order | Subject | Question | Answer | Answered By | Number | Asked | Answered
20211214 | 20211214001 | 1 | Dynamic Late Merge System / Queue Warning System | Good morning, just looking to confirm the following items will be paid as shown on page 47 of the plans, as there have been various methods of measurement and payment depending on the WisDOT region the project is located in: 643.1100.S Dynamic Late Merge System will be paid by the complete system (3 PCMS and 1 FBS = 1 paid day per direction) 643.1200.S Portable Automated Real-Time Traffic Queue Warning System will be paid by each individual PCMS in the system per day - NOT by the complete system per day Thanks | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-11-22 10:39 | 2021-11-30 12:44
20211214 | 20211214001 | 1 | Polymer overlay | The Polymer overlay requires a 28 day cure time, would the work for that be performed using drums after all bridges are complete, and what would the time restrictions be? | The work can be completed with drums during off peak time that would allow for single lane closure, which would not require the Queue Warning System to be set up. | Fred Schunke | 2 | 2021-12-09 14:36 | 2021-12-13 11:41
20211214 | 20211214002 | 2 | Meta Data | Can the Department provide meta data/contractor staking packet for this project? | The metadata packet can be found at the following location: https://wisdot.box.com/s/wcyxy5t3geelovrnoq3oa1pnnhmy1akf Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. For each month going forward, available Contractor Data Packages will be on the letting pages at the time of advertisement. | Mike Coleman | 1 | 2021-11-16 13:31 | 2021-11-17 12:13
20211214 | 20211214003 | 3 | 3 inch base | there is 623 tons of dense base agg 3 inch bid on this project. Nobody in that area let alone any area makes 3 inch base anymore or rarely, also it doesn't make any sense for an agg producer to manufacture such a small amount that would only be used on this project. Why isn't the bid item select crushed or breaker run as it is on the majority of projects |  |  | 1 | 2021-12-08 17:06
20211214 | 20211214004 | 4 | 3 inch dense base agg bid item | There is a bid item of 1020 tons of 3 inch dense base agg on this project. No one produces in the area or any other area in the state because it isn't used on any other projects but wisdot projects, so it isn't cost effective to produce such a small quantity. If a agg producer does make this product, we would have to buy it from them as well as the other base agg products and the trucking cost could be prohibative. Why isn't this bid item select crushed or breaker run as is bid on a majority of wisdot projects? |  |  | 1 | 2021-12-08 17:18
20211214 | 20211214005 | 5 | Bird deterrent system | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethelene. There are no domestic manufacturers of either currently located in the US. While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 1 | 2021-12-09 10:17
20211214 | 20211214006 | 6 | Location of the break in slope for milling and paving operations | In the existing & typical sections on sheets 4 and 5 where does the 2% slope break to a 4% slope? Is the intention to break the slope 12â€™ off centerline or 15â€™ off centerline? | For the Proposed Typical Section for Bypass Lane (STA 1155+37 â€“ STA 1156+75) shown on page 4, the intention of the designer that the pavement cross slope breaks at 25â€™ left of centerline. For all other proposed typical sections, the intention of the designer that the pavement cross slope breaks at 12â€™ offset from centerline. | Mike Coleman | 1 | 2021-11-19 16:44 | 2021-11-22 09:11
20211214 | 20211214008 | 8 | DOT Schedule | Can you post the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/qji16r1ul53hpvzy78zpvjolm0z0pwv2 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-11-18 09:12 | 2021-11-18 12:05
20211214 | 20211214008 | 8 | CIR Base Layer | Under Prosecution and Progress, it states that paving of the lower layer of HMA Pavement must be within 72 hours of the CIR operation. Under the CIR Asphalt Base Layer Item 327.1000.S, C.7.1 Curing, it states that paving of the lower layer HMA Pavement will not be allowed until the moisture content of the CIR layer is not more than 2.50% or if the change in moisture content is less than 0.30 percentage points for three consecutive calendar days. Which special provision is the contractor supposed to follow? Thank you. | That requirement will be removed from the prosecution and progress via an addendum. | Mike Coleman | 2 | 2021-12-06 15:41 | 2021-12-07 13:16
20211214 | 20211214008 | 8 | Elbow Degrees and length | Looking for the length breakdown including the elbow degree and length and tee lengths for Stations: 834+78 1062+62 I only see the overall length listed. Also a thickness requirement for the type3 in Corrugated metal on this project. | The length of the pipe under the road to the elbow for station 834+78 is 87â€™ and from the elbow down to the Tee is 14â€™. The length of the pipe under the road to the elbow for station 1062+62 is 62â€™ and from the elbow down to the Tee is 10â€™. The thicknesses for all the pipes are shown in the mq table, page 69. The two pipes (station 834+78 and 1062+62) that have bid items of culvert pipe corrugated steel have the thickness shown in the table for steel. The notes on the cross sections refer to culvert pipe class III but those are incorrect. The notes on the plans and the mq table are correct. | Fred Schunke | 3 | 2021-12-07 13:34 | 2021-12-08 15:28
20211214 | 20211214008 | 8 | Elbow Degrees | What is the degree for the elbows? | The bends are 45 degrees. | Fred Schunke | 4 | 2021-12-09 13:14 | 2021-12-09 14:11
20211214 | 20211214009 | 9 | Transportation Project Plat update | There was an updated to the TPP for parcels 23 and 24 TLE's. Please post the updated documents. | The updated TPP documents can be at the following location: https://wisdot.box.com/s/19hj52xsc6yt519mtbcxb0c4x4mzjtko or can be accessed HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2021-11-18 06:46 | 2021-11-18 06:54
20211214 | 20211214009 | 9 | MSE Wall - Sta 10+00 | The SPV's call for a minimum block depth of 8" while the details in the plans call for a minimum 24" depth. Which is required? If the 24" depth is required and big block walls must be used, will this wall require any staining? | The minimum block depth of 8â€ stated in the SPV is correct for this wall. The plan detail should have shown 8â€ instead of 2â€™-0â€ MIN., 2â€™-4â€ MAX. The 8â€ is in the specials and they control. An addendum is not necessary. | Fred Schunke | 2 | 2021-12-07 16:22 | 2021-12-09 13:56
20211214 | 20211214009 | 9 | Proejct Letting # 009 - Precast Modular Block Wall Face Texture Approval | We are looking to quote our Bronco Retaining Wall System, which is a WI Dot approved system, however we see the listings of approved face textures in the spec section on Page 38. I am writing to make sure the Bronco Face Texture is approved as well. Can you review this face that is similar to the specified choices? Here is a web link: https://www.versa-lok.com/products/big-block/bronco-18h/ Thank you. | The Department will consider the face texture of the Bronco product as an approved equal based on the supplied information. The structural design of the wall will still need to be submitted for review. | Fred Schunke | 3 | 2021-12-07 16:33 | 2021-12-10 13:19
20211214 | 20211214009 | 9 | Concrete Base Railing - Adhesive Anchors | The detail in the plans calls for stainless steel anchor rods embedded 7" for the adhesive anchor option. The SPV's for the base railing calls for galvanized anchors. Which is required? | Please use the 7â€ adhesive anchor option shown on the plans. The anchor rod section in the SPV is being eliminated in an addenda. | Fred Schunke | 4 | 2021-12-08 11:33 | 2021-12-09 14:07
20211214 | 20211214009 | 9 | Wall A Pay Limits | Pay limits have typically been from the design grade at the top of the wall to the design grade 1'6" below the bottom of the wall. The bid quantity for Wall A does not seem to include the 1'6" bury square footage. The pay limits shown on sheet 37 shows from top of wall to bottom of wall. |  |  | 5 | 2021-12-13 09:22
20211214 | 20211214010 | 10 | Distressed Milling | Where is the mix tonnage for the distressed milling? Should there be an asphalt item corresponding to the 10,800 SY of distressed milling? | Updated items and quantities will be provided via an upcoming Addendum. | Mike Coleman | 1 | 2021-11-17 10:37 | 2021-11-22 12:49
20211214 | 20211214010 | 10 | Notched Wedge | Will a notched wedge satisfy the 1/2-inch max drop off between lanes for the surface lift of pavement? | With approval from the Engineer, Contractor shall follow the SDD HMA longitudinal Joints in plans and spec 450.3.2.8. | Mike Coleman | 2 | 2021-11-17 10:55 | 2021-11-22 12:51
20211214 | 20211214011 | 11 | MGS Short Radius | Please review the details for the short radius beamguard corner. It appears that a quantity of MGS 3 is missing from the plans. On SDD 14B53-01A, notes 4 and 6 both state a minimum amount of MGS 3 quantity on either end of the short radius. There should be a minimum of 53 LF of MGS 3 in the bid items. | An addendum will be issued to clarify. | Mike Coleman | 1 | 2021-12-06 09:46 | 2021-12-06 16:12
20211214 | 20211214012 | 12 | Turbidity Barrier | There is a t-barrier bid item in the specials. However, the Estimate of Quantities doesn't list any. The erosion control plan sheets don't show any. The MQ's don't list any. There are no Q2 elevations or streambed elevations. Please provide more information regarding this bid item. | 20211214012plan, Page 7, Construction Detail: Channel Realignment â€“ Profile Grade Line has stations and elevations 20211214012plan, Page 8, Construction Detail: Calls out turbidity barrier locations 20211214012plan, Page 10, Estimate of Quantities: Line 0078, Item 628.6005 Turbidity Barriers, 180 SY 20211214012plan, Page 13, Miscellaneous Quantities: top right corner, calls out turbidity barrier for the west and east abutments 20211214012plan, Page 19, Plan & Profile: Channel Realignment â€“ Plan & Profile of channel realignment 20211214012plan, Page 69, Structures General Plan: Design Data, Q2 Elevation is 708.19 FT | Mike Coleman | 1 | 2021-11-18 11:36 | 2021-11-18 13:58
20211214 | 20211214012 | 12 | MGS Short Radius | Please review the details for the short radius beamguard corner. It appears that a quantity of MGS 3 is missing from the plans. On SDD 14B53-01A, notes 4 and 6 both state a minimum amount of MGS 3 quantity on either end of the short radius. There should be a minimum of 53 LF of MGS 3 in the bid items. | An addendum will be issued to clarify. | Mike Coleman | 2 | 2021-12-06 09:54 | 2021-12-06 16:15
20211214 | 20211214013 | 13 | Bird deterrent system | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethelene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 1 | 2021-12-09 10:24
20211214 | 20211214014 | 14 | Guardrail Operations | In the MQ's for the Grade/Shapes, there are hundreds of yards of fill and topsoil placement that must be done between cable barrier removal and MGS installation. Will the Department consider allowing 72 hours between removal and installation for the guardrail operations? | the 48 hour timeframe is going to remain. | Mike Coleman | 1 | 2021-11-18 14:55 | 2021-11-29 08:07
20211214 | 20211214014 | 14 | HMA lift paving sequence. | In the special provisions it reads "Pave the upper layer within 48 hours of paving the lower layer". Is the intent of this spec to pave the upper lift within 48 hours of completing the lower layer in its entirety or pave the upper lift within 48 hours of each individual lower lift operation? | The intent of the spec is to begin paving the upper lift within 48 hours of completing the lower layer in its entirety. | Fred Schunke | 2 | 2021-12-07 14:05 | 2021-12-09 11:57
20211214 | 20211214014 | 14 | HMA Lift paving sequence | In the special provisions it reads "pave the upper layer within 48 hours of paving the lower layer" is the intent of this spec to pave the upper lift within 48 hours of completing the lower layer in its entirety or to pave the upper lift within 48 hours of each individual lower lift operation. | The intent of the spec is to begin paving the upper lift within 48 hours of completing the lower layer in its entirety. | Fred Schunke | 3 | 2021-12-08 11:37 | 2021-12-09 11:57
20211214 | 20211214017 | 17 | Contract Time | Could someone take a look at the working days for this contract? As a slab span slab with parapets it does not seem to have concrete curing built into the schedule which is required before parapets can begin. With parapets, a project such as this would be 38-40 days. Even with 2 full crews working, 25 days does not look possible. | The contract completion time will be revised from 25 working days to 40 working days via addendum. | Mike Coleman | 1 | 2021-12-01 10:24 | 2021-12-02 08:46
20211214 | 20211214018 | 18 | Pavement marking | Item 0088 on the schedule of Items is 646.77405 Marking Crosswalk PAINT Transverse Line 6". On plan Pages 10 on (5990-01-28) & 8 on (5990-01-30) Item #3 on those pages says EPOXY. Is it Paint or Epoxy ? Thank You | An addendum will be issued to correct this. | Mike Coleman | 1 | 2021-11-23 10:50 | 2021-11-30 12:37
20211214 | 20211214019 | 19 | Storm Sewer Material | Per updated FDM Chapter 13 (updated Feb 18 2020) the use of Class IIIA and Class IIIB storm sewers shall be used at every opportunity possible, regardless of ADT, when installations are: - 12-36 inches in diameter - located on non-interstate or divided US Highways (except for use in temporary use or maintenance crossovers in the median) - Maximum cover heights are 15 feet or less for Class IIIB and 11 feet or less for Class IIIA storm sewer pipe. - Minimum cover heights are greater than or equal to 2 feet. Based on this design guidance, will the contractors be permitted to bid with proper competitive bid items for SSP Class IIIA and/or IIIB in lieu of the sole specified SSPRC Class IV? | The majority of storm sewer does not meet the criteria for the storm sewer to be SSP Class IIIA, SSP Class IIIB or SSPRC Class III. Only one SSPRC Class IV 24-inch 79-feet in length (between structures 10.1 and 10.2) meets the criteria. Per FDM 17.3.1 â€œDesigners are not expected, for example, to change materials back and forth between manholes as fill heights change, or call out a few individual short runs of Class III-A or B pipe on a site where it otherwise doesnâ€™t fit the conditionsâ€. Considering this guidance the specified storm sewer materials shall be bid. | Mike Coleman | 1 | 2021-12-01 13:33 | 2021-12-06 16:20
20211214 | 20211214019 | 19 | Undistributed EBS Excavation | Please remove the undistributed EBS quantity listed in the plan (4361 CY) and in turn the select crushed backfill (8117 TON). These are arbitrary numbers with nothing called out in the plan for EBS and given the proposed base and pavement structure there is no need for it. | Following the recommendations of the Southwest Regionâ€™s Soils Engineer and Pavement Design Engineer as documented in the Pavement Design Report dated 02/28/2019 an undistributed quantity of EBS was included in the project. The design team is not proposing any modifications to the EBS or select crushed quantities. | Mike Coleman | 2 | 2021-12-06 08:55 | 2021-12-06 16:25
20211214 | 20211214020 | 20 | B-11-176 Preboring Quantity and location | Sheet 1 of the plans for B-11-176 calls out preboring at the North Abutment. The total estimated quantities on sheet 2 put the 100 LF of preboring at the south abutment. Can it please be confirmed that the north abutment is the only abutment that requires preboring? | The north abutment is the only abutment that requires preboring. | Mike Coleman | 1 | 2021-11-24 06:57 | 2021-11-24 13:10
20211214 | 20211214021 | 21 | Temp Pedestrian Surface | Three different temp pedestrian surfaces are called for in this bid; each item has the same quantity. Is the intention to utilize all three temp pedestrian surfaces during the project, or is it the contractor's choice to utilize which surface the contractor prefers? Please clarify what the intention is for the use of these different surfaces. | We usually include all three bid items as we want to offer some flexibility to the contractors to use what they feel is most appropriate for the scenario and the duration with which the surface may be needed. In some cases it might be a short term utility lateral may require a metal plate or plywood vs a longer term surface might warrant asphalt. The intent is to not dictate means and methods but rather allow the contractor the option that best fits their work and methods. | Mike Coleman | 1 | 2021-11-16 13:32 | 2021-11-18 09:49
20211214 | 20211214021 | 21 | Geotechnical Data | Please provide any soil boring information available for this project area. | The geotechnical report can be found at the following location: https://wisdot.box.com/s/2xxy8jnk3o64ddva8ochlbe8u1mis0qr or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2021-11-19 09:48 | 2021-11-22 09:15
20211214 | 20211214021 | 21 | Integral Curb Requirement | WCPA Contractor member review of the plans has revealed that the requirement for integral curb on this project will be in direct conflict with the utility poles. There will not be enough clearance for the slipform paver to clear the utility poles. There appears to be only 1.5 feet of clearance between the back of curb and the utility pole. Most paving companies would be looking at 3 feet to clear the tracks and stringlines. Please advise us on how you would like this paved. Or, please advise us on whether you will be moving the utility poles to accommodate paving operations. Simple solution would be to place the curb separately. But it is our understanding that the city wants integral curb and gutter. | The design team had made changes to the plans and will be replacing the integral curb with standard curb and gutter. This change is reflected in the documents submitted in the addenda. | Fred Schunke | 3 | 2021-12-07 09:32 | 2021-12-10 13:15
20211214 | 20211214023 | 23 | Design Schedule | Can you please post the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/rvqi7o5ragtfotcgegv7jpe7naweias8 or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-11-19 10:52 | 2021-11-22 09:07
20211214 | 20211214023 | 23 | Schedule VS Specials | The schedule shows guardrail removal on working days 6-16. It then shows installations on days 24-45. The Specials state, in summary, no more than 7 days between removal and installation. I understand that the schedule isn't for bidding purposes, but I question the completion date when the bid items are placed in a more accurate location on the schedule. If the removals start immediately prior to the paving, and the guardrail installation starts immediately following the start of paving, there aren't enough days left in the schedule for 11 days of removal and 22 days of installation. Furthermore, the flagging operations between guardrail removal, paving, and guardrail installation will conflict to the point that guardrail operations won't be able to happen every day of the 33 days needed. Please review this and either help me understand where I have this wrong or re-evaluate the completion date after allowing for the Specials language regarding removal and installation of guardrail. | The schedule was based on the number of days to do the work, not necessarily addressing when the work would need to be completed within the project timeframe. The intent is for the contractor remove and replace the guardrail per article 4, paragraph 4 of the special provisions for maximum amount of time the guardrail can be down. | Mike Coleman | 2 | 2021-11-23 08:34 | 2021-11-30 07:17
20211214 | 20211214023 | 23 | Terminal Grading | Are there any estimated quantities for common excavation or borrow for the terminal pads? | An addendum will be issued to show the estimated quantities. | Mike Coleman | 3 | 2021-12-06 12:43 | 2021-12-07 13:28
20211214 | 20211214023 | 23 | Curb and Gutter - Prep and Schedule | At station 740 to 745, the asphalt curb needs to be removed and concrete curb is being installed. 1.) Will this area need to be sawcut and the existing HMA removed to get the new curb installed? Will that be paid by the applicable items? Also, with the existing HMA being 6" thick, Base Ag will probably need to be placed to get to bottom of curb elevation. 2.) Schedule - For this area, as well as the curb at station 597, the guardrail will need to be removed. These areas will then have to be prepped and the curb poured. Will the guardrail need to be reinstalled within 7 days for these areas? That may be difficult with cure time on the curb. | The segment from station 740 to station 745 is proposed as a mill and relay. No sawcut will be required. The new HMA pavement will only be 4â€ thick, so some recycled base will have to be trimmed to install the curb & gutter at this location. The department will not count days necessary for concrete curing against the guardrail installation time requirement. Traffic Control Drums will be required for delineation. | Mike Coleman | 4 | 2021-12-06 13:36 | 2021-12-07 13:29
20211214 | 20211214024 | 24 | Electronic Data | Can the department please provide the excel files for the storm sewer pipe and structures in the miscellaneous quantities, as well as the earthwork summary and the earthwork data tables? | The requested files can be found at the following location: https://wisdot.box.com/s/cc133hy2hfq7mkr98nalh06fzne6hia1 or can be accessed on the HCCI November bid letting page under Supplemental Information. | Mike Coleman | 1 | 2021-11-12 13:22 | 2021-11-16 11:04
20211214 | 20211214024 | 24 | job 24 | Will the 8" pavement use joint spacing per sht 36 or per sht 967. Is the 4'-0" Concrete pad incidental to the Barrier or the !0'-1/2" main line pavement,as drawn on sheet 14. | Question #1: Ramps will be 8â€ concrete pavement. See page 971 of the plan for ramp jointing details. Question #2: The concrete pad is not incidental. It will be paid for separately using the respective concrete pavement bid item. Details of the concrete barrier pad and the Concrete Barrier Type S42 and Type S56 Special are shown on page 38 of the plan. | Mike Coleman | 2 | 2021-11-15 08:42 | 2021-11-17 12:08
20211214 | 20211214024 | 24 | Geotechnical & Meta Data | Can the Department provide the meta data files and geotechnical report(s) for this project? | The metadata packet can be found at the following location: https://wisdot.box.com/s/wcyxy5t3geelovrnoq3oa1pnnhmy1akf Starting with the November 9, 2021 letting, the HCCI bid letting page has additional information. After the addenda section is a section titled Supplemental Information. There is a link to the Contractor Data Packets. If you click on the link, it will direct you to two folders. One in Contractor Data Packages and the other is Questions and Answers. Click on the Contractor Data Packages and it will bring you to the proposals that have the information. Click on the proposal number and download the .zip file. The Geotechnical Reports are available at the following location: https://wisdot.box.com/s/cc133hy2hfq7mkr98nalh06fzne6hia1 or can be access on the HCCI site for the December bid letting page under Supplemental Information. | Jill Fehrman | 3 | 2021-11-16 09:38 | 2021-11-19 17:08
20211214 | 20211214024 | 24 | Proposed Construction Schedule | Please provide the engineers proposed construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/cc133hy2hfq7mkr98nalh06fzne6hia1 or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Jill Fehrman | 4 | 2021-11-18 11:06 | 2021-11-19 16:55
20211214 | 20211214024 | 24 | R-45-44, can not find drawings | Special 4008. Wall Concrete Panel Mechanically Stabilized Earth R-45-44 I was not able to find the drawings for R-45-44 | Plans for B-45-44 were inserted into the advertised plan set, rather than the plans for R-45-44. The R-45-44 plans will be added via a forthcoming addendum. | Mike Coleman | 5 | 2021-11-18 13:15 | 2021-11-22 10:02
20211214 | 20211214024 | 24 | INLET TYPE TEE SPECIALS | BID ITEM SPV.0060.0106 INLET TYPE TEE SPECIAL QUANTITY OF 2 EACH. IS THERE ANY DETAILS OR INFORMATION ON SIZES, DEPTHS AND COVERS REQUIRED FOR THIS BID ITEM? ARE THEY TO BE BUILT ON NEW OR EXISTING PIPES? ALSO PLAN SHEETS 307 AND 310 HAVE NOTES STATING SEE BEEEHIVE SECTION DETAIL. IS THERE A DETAIL AVAILABLE FOR THIS? | A construction detail for INLET TYPE TEE SPECIAL is included via a forthcoming addendum and will include information for size, depth, and cover type. The structures are to be built on proposed pipes. | Mike Coleman | 6 | 2021-11-18 17:18 | 2021-11-22 12:46
20211214 | 20211214024 | 24 | Additional CAD Files | 1. Can a CAD file showing the linework from the removal plans (split into stages) be added to the ftp site? 2. Can a CAD file showing the stage work areas (match lines) as shown on the traffic control staging plans be added to the ftp site? | The additional CAD Files can be found at the following location: https://wisdot.box.com/s/cc133hy2hfq7mkr98nalh06fzne6hia1 or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 7 | 2021-11-19 11:17 | 2021-11-22 09:59
20211214 | 20211214024 | 24 | Article QMP Base Aggregate Dense 1 1/4-Inch Compaction, Item 371.2000.S. | This Article doesn't seem necessary on a concrete pavement project. | The QMP Base Aggregate Dense 1 ï¿½-Inch Compaction item is used in areas of asphalt pavement travel lanes constructed on an improved subgrade. Addendum No. 01 is being issued to revise the Miscellaneous Quantity table of the plan to indicate this item will be used on N Port Washington Road (CTH W) and W County Line Road. | Mike Coleman | 8 | 2021-11-22 14:30 | 2021-11-23 13:00
20211214 | 20211214024 | 24 | Polymer Overlay | Could not find a closure that would allow polymer overlay on 43NB except on stage 5. But the Specials on page 11 suggest it's on stage 4B. Could you clarify please? | The thin polymer overlay (TPO) is for the Port Washington Rd bridges over I-43. In stage 4, utilize single lane closures to complete the application of the TPO. | Mike Coleman | 9 | 2021-11-23 14:26 | 2021-11-24 13:13
20211214 | 20211214024 | 24 | Removing Old Structure B-45-18 | Don't see a bid item for Removing B-45-18. Assumption is that item #22 - Removing Structure, 56DB+59 is the item to use for this work scope. Please confirm. | Existing structure B-45-18 is to be removed as part of the B-45-106 items per the note on sheet 1382 and shown as bid item â€œ203.0220 REMOVING STRUCTURE B-45-18â€ on sheet 1301. It is correct that Item â€œ0022 203.0220 Removing Structure (structure) 2003. 56DB+59â€ on the proposal schedule of items is intended for the B-45-18 removal. | Mike Coleman | 10 | 2021-12-01 14:58 | 2021-12-06 08:38
20211214 | 20211214024 | 24 | Removing Temp. Shoring Left-in-Place | Can any details be provided on this? A shoring design should have been submitted to project staff for the project that installed it. | The temporary shoring was not installed on the previous project as originally planned, so there is nothing to remove as part of this project. This bid item will be eliminated in a forthcoming addendum. | Mike Coleman | 11 | 2021-12-01 15:18 | 2021-12-06 08:34
20211214 | 20211214024 | 24 | B-45-102 Excavation for Structures | No item for excavation for structure for B-45-102. Is this item required for any excavation for pier construction or will this be constructed on roadway fill? | B-45-102 plan sheet 4 (sheet 1,226) details the removal, excavation, and backfill limits. No separate excavation is anticipated for the pier construction. The excavation around the pier is covered in the Removing Structure limits/bid item. Any fill needed below or around the proposed pier footings is considered part of the roadway work. | Mike Coleman | 12 | 2021-12-01 15:24 | 2021-12-06 08:39
20211214 | 20211214024 | 24 | Full Freeway Closures for Bridge Demo/ Girder Erection | Can Department consider adding to the allowed 6 Full Freeway Closures? 14-16 full closures will be needed to adequately perform the work. | Additional full freeway closures will be included in a forthcoming addendum. | Mike Coleman | 13 | 2021-12-02 13:23 | 2021-12-06 16:48
20211214 | 20211214024 | 24 | Concrete Masonry Retaining Walls Quantity Check | Plan quantity is 895 cy. R-45-28 has 648 cy and R-45-29 has 217 cy for a total of 865 cy. Where is the additional 30 cy? | Wall R-45-44 includes a quantity of 30 cy of concrete masonry retaining walls. Plan sheets were included in addendum #1. | Mike Coleman | 14 | 2021-12-03 12:02 | 2021-12-06 16:52
20211214 | 20211214024 | 24 | HPC Dowels - Joint Details | Sheets 36 and 37 of the plans show various spacing details for the HPC Dowels in the concrete pavement. Is there a reason this is included in this project and was not in the previous project on the corridor? The odd spacing makes ordering and storing materials challenging for the minor cost savings. Will these details continue in other projects in the corridor or will each project be different? | Plan sheets 36 and 37 (Construction Details for HPC Pavement Joints) will be deleted with a forthcoming addendum. The layout and spacing of the dowel bars will follow the relevant standard detail drawings. | Fred Schunke | 15 | 2021-12-03 15:27 | 2021-12-09 13:24
20211214 | 20211214024 | 24 | Anchoring Concrete Barrier Temporary Precast Item | It appears most of the temporary precast barrier wall needs to be anchored in Stage 1 (1' to shoulder drop off) and Stage 2 (shoring within 1' and all other areas the pavement will be sawed within 4' to allow for new construction causing a drop off within probably 1-2' of wall and the paver will be within 4' of the barrier wall during construction) and stage 3 for similar reasons. Please add an anchoring item, like there was one on the last IH-43 project bid last month. | The anchoring concrete barrier temporary precast bid item will be added via a forthcoming addendum. Traffic control typical sections for stage 3 will be revised to provide a 4-ft buffer to the work zone. | Fred Schunke | 16 | 2021-12-03 15:57 | 2021-12-08 15:25
20211214 | 20211214024 | 24 | MSE Wall Winter Backfill | It appears based on the special provisions and the schedule provided in the supplemental information that MSE Walls R-40-653 & R-40-654 will need to be constructed in late winter/early spring. Will WisDOT make winter MSE backfill an option for these walls, if so please provide a specification for the material. Will any additional payment be made to facilitate winter construction of these walls? | The specifications included in the contract for R-40-653 and R-40-654 do not include any seasonal or temperature limitations, so the walls can be constructed at any time as long as the quality control requirements are met. Because of that, MSE winter backfill has not been included in the contract. Additional payment will not be made to facilitate winter construction of the walls, if the contractor decides to build them then. Each wall is its own individual bid item, so contractors have the opportunity to account for various factors in their bid prices. | Fred Schunke | 17 | 2021-12-07 10:46 | 2021-12-10 13:13
20211214 | 20211214024 | 24 | Stage 2 Traffic | Per the special provisions on page 19 schedule of operations in Stage 2. "Ingress and Egress into the staging zone along I43, Shall be completed during freeway closures." Is this intended to complete all work at night or to only haul materials in and out of the work zone? There is barrier wall up along the work zone, and on sheet 474 of the Traffic Control Details allowing Work Zone Egress, and Ingress. Why does the work have to to be completed during Freeway Closure Hours? | Ingress and egress to the work zone is allowed at locations approved by the engineer as detailed on sheet 474 and described in Section J of the Prosecution and Progress Article of the Special Provisions. If egress from within the work zone directly to the freeway is required at other locations, it is limited per the Traffic article. It is not intended to complete all work at night. | Fred Schunke | 18 | 2021-12-09 10:09 | 2021-12-13 11:40
20211214 | 20211214024 | 24 | Anti-Seep Collar | I am not finding a drawing for the anti seep collar Line 0810 Need at least the diameter and type of pipe it will go on and the outer measurements. | Refer to â€œPORT WASHINGTON RD POND SECTION B-Bâ€ detail on sheet 341. Pipe 424-S1 to 424A-S1 is a Class III-A 24-Inch reinforced concrete pipe. For the outer measurements, refer to Article 133 Section C. Extend the collar dimensions a minimum of 1 foot vertically above the pipe and 2-1/4 feet in all other directions around the outside of the pipe or beyond the limits of the trench backfill, whichever is greater, measured perpendicular to the pipe. | Fred Schunke | 19 | 2021-12-09 11:48 | 2021-12-10 12:47
20211214 | 20211214024 | 24 | Asphalt Pavement | Details on sheet 14 & 17 show median asphalt of 7.5" thick x 4' wide. Miscellaneous quantities do not reference this asphalt. Will asphalt be used in these areas or will it be concrete pavement? |  |  | 20 | 2021-12-10 09:44
20211214 | 20211214024 | 24 | Maintain & Salvage Temp Barrier, Maintain Temp Barrier Left in Place | These quantities are shown in stage 2 traffic control and the temp barrier is not shown in stage 1 traffic control. Per special provisions, payment includes maintenance and removal (for Salvaged item). How is the installation paid? |  |  | 21 | 2021-12-12 11:01
20211214 | 20211214027 | 27 | Can the soils report be provided? |  | The Soils Report can be found at the following location: https://wisdot.box.com/s/7f8lgmdoz0cv0zpjh0lnd5nrwa8op6mk or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 1 | 2021-11-26 17:24 | 2021-11-29 12:53
20211214 | 20211214027 | 27 | Design Schedule | Can the Design Schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/7f8lgmdoz0cv0zpjh0lnd5nrwa8op6mk or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-12-05 06:06 | 2021-12-06 09:42
20211214 | 20211214028 | 28 | BR Trees | The bid form and plans call for bareroot trees, but the project completion date is in November and bareroot plants are only available in the spring. Is the intention for these to be planted in spring 2023? | This question will be addressed by addendum. | Mike Coleman | 1 | 2021-11-19 14:23 | 2021-11-22 13:46
20211214 | 20211214028 | 28 | Project Construction Schedule | Could the department provide the designer's construction schedule. | The design schedule can be found at the following location: https://wisdot.box.com/s/jv1wzd5208lmqkjklqx8jxo2ouepo3pj or can be accessed on the HCCI December bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 2 | 2021-11-22 10:02 | 2021-11-22 13:44
20211214 | 20211214028 | 28 | IH 43 Inside Shoulder Slope | The typical section shows the inside shoulder slope at 4%. Would the department allow this to be milled and paved at a 2% to match the lane? | The DOT will not allow for the milling and paving of the inside shoulders to 2%. The inside shoulders cannot change profile from plans to accommodate for the existing cable guard in place. | Mike Coleman | 3 | 2021-11-22 13:52 | 2021-11-30 12:46
20211214 | 20211214028 | 28 | Fencing Questions | 1. For the planting of living snow fence how is the weed barrier fabric paid for? 2. Existing wire woven fence has vegetation/old wooden snow fence attached, how is this to be paid for? 3. How is clearing and grubbing to be handled for the installation of new wire woven fence? | 1. Weed barrier Fabric cost is part of item for trees/shrubs. 2. Vegetation/old wooden snow fence is considered incidental to the bid item Removing Fence. 3. Clearing and grubbing for new wire woven fence is incidental to the item of Fence Woven Wire. | Mike Coleman | 4 | 2021-12-01 07:09 | 2021-12-01 07:11
20211214 | 20211214028 | 28 | Woven Wire Fence | As of Right now woven wire fence suppliers are stating that wire availability is currently 6-8 months out for delivery, if wire cannot be received in a timely manner, will the dept. allow for extra time on the project due to interruptions in material availability? | At this time, the department is not considering the material supply issue as an excusable delay and will not be granting a time extension. Also, the department will not provide a price adjustment for escalated materials costs. Only extraordinary delays in material deliveries attributed to the reasons in 108.10.2.1(3)2 are excusable, but they are extremely rare. | Mike Coleman | 5 | 2021-12-03 06:57 | 2021-12-06 16:54
20211214 | 20211214028 | 28 | 643.1205.S Basic Queue Warning System | If there are multiple lane closures on a single direction of travel, will a Queue Warning System be required for each lane closure? Or will a single Queue Warning System per direction be sufficient? Currently each project ID has 115 days per direction allocated for the QWS; if only one system per direction will be needed this overall quantity of 460 days is significantly overstated. Thanks | There may be times when multiple lane closures in the NB and SB directions of travel. A single QWS will not be sufficient in these cases. We feel that the quantity for Basic QWS is not overstated for the amount of work to be accomplished and lane closures needed to do work. | Mike Coleman | 6 | 2021-12-06 09:39 | 2021-12-06 16:55
20211214 | 20211214028 | 28 | BR Trees | The plan calls for 2 fertilizer units per tree. Spec is minimum of 1 ounce per packet. Would the DOT accept 1- 2ounce fertilizer unit in place of the 2- 1 ounce units for these trees? | The fertilizer will not be required for BR plantings, an addendum will be coming to remove fertilizer requirement. | Fred Schunke | 7 | 2021-12-08 11:55 | 2021-12-09 13:20
20211214 | 20211214028 | 28 | Shoulder Pavement | In the past we have always paved ramps in echelon with two pavers to eliminate cold joints. Would the department consider allowing the shoulders on the ramps to be paved with the 4 HT mix and allow them to be paved at 2%? At a minimum could the 4â€™ shoulder be changed? | The department would consider paving in echelon and the use of 4HT mix for 4â€™ shoulder(at no additional cost to department paid as LT mix), but will not change the typical section to pave shoulder at 2%. 8 ft shoulder would remain as LT mix. | Fred Schunke | 8 | 2021-12-08 15:00 | 2021-12-08 15:03
20211214 | 20211214028 | 28 | Ramp Paving Mix | With STH 147 having to be open by June 2nd the ramps could potentially be partially paved before mainline PWL paving starts, would the department consider changing these ramps to 4 LT to match the pavement on STH 147 or change the 4 HT to QMP testing? | The department would consider changing 4HT to QMP testing for the STH 147 ramps only, due to timing of work. | Fred Schunke | 9 | 2021-12-08 15:02 | 2021-12-08 15:03
20211214 | 20211214028 | 28 | Landscape Planting Surveillance and Care Cycles | Plan notes on sheet 20 call for a max of 13 care cycles per growing season and the living snow fence quantities on sheet 97 call for a total of 26 cycles, but the bid form quantity is 52 cycles. Please clarify which is correct. | The care cycles for this project are on both 1227-12-71 and 1227-12-72 IDs please see page 466 for the additional 26 cycles. The bid form is correct. | Fred Schunke | 10 | 2021-12-09 12:56 | 2021-12-09 14:09
20211214 | 20211214028 | 28 | Pea Gravel at Shrubs | Note 8 in the initial planting process on sheet 20 calls for pea gravel at 2 inch depth at each shrub, but the gravel ring detail on the same sheet calls for 4.75" depth. Please clarify which is correct. | The gravel ring detail on the sheet is incorrect, the pea gravel mulch is needed at a 2 inch depth. | Fred Schunke | 11 | 2021-12-09 13:01 | 2021-12-10 13:01
20211214 | 20211214028 | 28 | Shrub Requirements | In the plant data chart, does the column "type" refer to the number of required stems per shrub? | The â€œTypeâ€ in plant data chart is in reference to mature size and that it is a shrub, not number of stems. | Fred Schunke | 12 | 2021-12-09 17:05 | 2021-12-13 11:31
20211214 | 20211214028 | 28 | Shrub fabric width | Shrub planting details show 1'6" of fabric beyond the outer row of plants. Please confirm this 1'6" is in addition to the 1' that gets buried. | The weed fabric will extend 1â€™-6â€ pass the outside row of plants and then there will be an additional 1â€™ that is buried as shown in details. | Jill Fehrman | 13 | 2021-12-09 17:07 | 2021-12-13 07:43
20211214 | 20211214028 | 28 | Shrub spacing | Shrub planting details call for 4' on center spacing, but appear to show 4' between each row of shrubs with shrubs in a triangular arrangement. If 4' on center spacing with a triangular arrangement is desired, the rows will be closer than 4' apart. Please clarify if the plants should be 4' on center or if the rows should be 4' apart. | The rows should be 4 foot apart. | Fred Schunke | 14 | 2021-12-09 17:09 | 2021-12-13 11:30
20211214 | 20211214028 | 28 | Living Snow Fence | Can different varieties of shrubs be used for living snow fence besides what is named in the plant table? | Grey Dogwood, American Cranberry Bush, Wet areas- Sandbar willow and common buttonbush can be substituted for varieties in plant table. Chosen materials mush be at least 20% of total plant count. | Fred Schunke | 15 | 2021-12-10 13:03 | 2021-12-10 13:04
20211214 | 20211214030 | 30 | Design Schedule | Could the department provide the construction schedule developed in design? | The design schedule can be found at the following location: https://wisdot.box.com/s/ye5mezlbsfx6y7j2lq1p5f6qgs341qme or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 1 | 2021-11-18 09:41 | 2021-11-18 12:12
20211214 | 20211214030 | 30 | Detour length | Will STH 32/57 remain under a detour as detailed on page 49 (approximately 44 working days) throughout the project? Will any flagging be necessary during the beamguard work? | All Beam guard work can be done with lane closures in the divided highway section of project. The detour on page 49 will only be for the work at the roundabout, it will not be for the entire contract working days. | Mike Coleman | 2 | 2021-11-18 10:43 | 2021-11-30 12:40
20211214 | 20211214030 | 30 | Temporary Paint | Can you please clarify where the temporary paint is to be used? Plan sheet 72 shows 2 single lines (both labeled edge lines) on the lower and upper layer with no accommodation for center lines. Thank you. | The centerline will not need temporary marking, the centerline will have barrels the whole time due to one lane being closed at all times until permanent marking are in place. | Mike Coleman | 3 | 2021-11-23 13:11 | 2021-11-30 12:40
20211214 | 20211214030 | 30 | Interim Completion Connectors at the South Junction | The current specials have 2 working days for the milling and paving of the connectors. There appears to be no mentioning of shouldering the connectors in this time frame as well as the amount of milling and paving in those areas will require more time. If the scope requires milling , paving and shouldering the areas, the Contractor is requesting 6 working days. | Days will be addressed by forthcoming addenda. | Mike Coleman | 4 | 2021-12-02 13:22 | 2021-12-06 16:37
20211214 | 20211214030 | 30 | PWL Tonnage Table | Could the department provide an acceptance table for the mixture and density requirements for the HMA? | New PWL table will be added via addenda. | Mike Coleman | 5 | 2021-12-02 13:22 | 2021-12-06 16:43
20211214 | 20211214030 | 30 | Wedging on Supers | Could the department provide an item for Asphaltic Surface for the wedging required on the supers? | Item will be added via addenda | Mike Coleman | 6 | 2021-12-02 13:23 | 2021-12-06 16:45
20211214 | 20211214030 | 30 | Construction staking | Should an item be added for construction slope staking for areas required at the beam guards? | Item will be added via addenda | Mike Coleman | 7 | 2021-12-02 13:24 | 2021-12-06 16:45
20211214 | 20211214031 | 31 | Bridge Approach | I feel the approach slab quanity should be 380 sy not 578 sy is the quanity correct at 578sy? | There is a discrepancy between the plans and miscellaneous quantity tables. What is shown on the plan detail sheets is correct, the following quantities will be updated in an upcoming addendum: 415.0080 Concrete Pavement 8-Inch: 9,559 SY 415.0410 Concrete Pavement Approach Slab: 407 SY | Mike Coleman | 1 | 2021-11-16 09:27 | 2021-11-17 09:59
20211214 | 20211214031 | 31 | Sewer Lining | Are there better maps with manhole numbers to show the sewers to be lined? Also, are there videos of the sewers to be lined that we can review? | 1. The detail sheets as well as miscellaneous quantities should identify the sewers to be lined. 2. The videos can be found at the following location: https://wisdot.box.com/s/s444yn2i1drhfu9r5uz9txgf6wm6c7lj or can be accessed on the HCCI December bid letting page under Supplemental Information. | Mike Coleman | 2 | 2021-11-18 15:01 | 2021-11-29 12:45
20211214 | 20211214031 | 31 | Design schedule | Would the Department be willing to share the design schedule for this project? | The design schedule can be found at the following location: https://wisdot.box.com/s/s444yn2i1drhfu9r5uz9txgf6wm6c7lj or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 3 | 2021-12-02 11:14 | 2021-12-02 14:55
20211214 | 20211214031 | 31 | Taylor Drive Crossing | Is the water main pipe still going to measured and paid for per LF under bid item SPV.0090 Special 10 12" above adn beyond the cost for bid item SPV SPV .0060 Special 25 South Taylor Drive Crossing? | The bid item South Taylor Drive Crossing does not include cost for the water main pipe. The pipe will be paid for under the 12â€ PVC Watermain. | Mike Coleman | 4 | 2021-12-06 10:06 | 2021-12-06 15:42
20211214 | 20211214031 | 31 | Box Culvert Crossing | Is the 12" water main SPV .0090 Special 10 still going to be paid per lf above and beyond the cost for bid item SPV .0060 Box Culvert Crossing? | The bid item Box Culvert Crossing does not include cost for the water main pipe. The pipe will be paid for under the 12â€ PVC Watermain. | Mike Coleman | 5 | 2021-12-06 10:08 | 2021-12-06 15:47
20211214 | 20211214031 | 31 | Water Service at Box Culvert Water Main Crossing | If the contractor selects the directional drilling option for this crossing, what is the acceptable means of connecting the proposed water service to the HDPE pipe? | Service taps for HDPE water main shall be by HDPE electrofusion welded corporation saddle. Outlet size shall be one inch or 2 inch CTS with brass CC threads conforming to AWWA C800 and a butt welded outlet. Welding shall be conducted by an operating technician certified in the use of electrofusion processors. | Mike Coleman | 6 | 2021-12-06 10:58 | 2021-12-07 13:12
20211214 | 20211214031 | 31 | reconstructing sanitary manhole | The special provision uses the term remove and replacement of the manhole cone. Does this mean reinstalling the existing cone or are we to remove, dispose of and then furnish and install a new cone? | Remove, dispose and then furnish a new one. | Mike Coleman | 7 | 2021-12-06 14:51 | 2021-12-07 09:02
20211214 | 20211214031 | 31 | Soils Report | Rumor has it that when Taylor Drive was built that there are concrete pavement panels buried on the south side of Indiana Ave to fill in a swamp that existed at that time. This buried concrete may exist in the area of the proposed water main crossing. If this buried concrete does exist will dealing with it be considered extra work? |  |  | 8 | 2021-12-07 07:18
20211214 | 20211214031 | 31 | Structure Excavation/Backfill for Parapet Footing | There is not an item for Structure Excavation nor for Backfill for the Parapet Footing. Will these items be added to the contract? I do not see where it is incidental to any item. | Excavation required for the parapet footing construction and backfill for all volume which is not occupied by the roadway pavement structure or the parapet footing shall be considered incidental to â€œConcrete Masonry Bridgesâ€. The backfill for the parapet footing shall be Backfill Structure Type A. | Fred Schunke | 9 | 2021-12-07 10:05 | 2021-12-13 10:42
20211214 | 20211214031 | 31 | Expansion Joint Gland | The expansion joint appears to be 1" tighter then the asbuilt temperature table indicates. The minimum installation opening for the 4 glands at 24 degrees was already at or tighter then the minimums. Would the Department consider using emseal if the openings restrict gland replacement? | Per correspondence with WisDOT Bureau of Structures, it is their opinion that the intended gland replacement can be installed with proper tools from the joint manufacturer. Bid the project as shown in the contract documents. | Fred Schunke | 10 | 2021-12-07 10:21 | 2021-12-10 12:55
20211214 | 20211214031 | 31 | Adhesive Anchor Embedment Depth | What is the embedment depth for the adhesive anchors for the parapet wall? | The embedment depth for the adhesive anchors from the 42SS parapet into the concrete deck is 7 1/4â€ per â€œSection D-Dâ€ on Sheet 7 of the bridge drawings. | Fred Schunke | 11 | 2021-12-07 10:22 | 2021-12-08 14:32
20211214 | 20211214033 | 33 | Bridge Work During Fishing Restrictions | The specials say that NTP can be issued on March 1, does that mean bridge work can be done during fish restrictions time out period? | No, in-stream disturbance cannot happen until June 15. A conditional NTP will have to be done to place Bird deterrent system on bridge before nesting season, because this is now a bid item in contract- no working days will be charged for this work. | Fred Schunke | 1 | 2021-12-10 13:07 | 2021-12-10 13:07
20211214 | 20211214034 | 34 | Dowel Bar Repairs | The construction detail shows the repairs to be placed over the top of the existing expansion material. Should new replacement expansion be added to the construction detail? | See note 2 on plan sheet 141 (SDD Concrete Pavement Partial Depth Repair). | Mike Coleman | 1 | 2021-11-10 06:40 | 2021-11-16 11:34
20211214 | 20211214034 | 34 | Butt Joints- Sheet 12 Detail | Please clarify the expected butt joint operation, the depiction on this plan detail does not match the required depths and operations on the project. Where does the full depth milling start in relationship to the terminus point? To which locations on the project does this detail apply? Anticipated needs based on typical sections: 1. Mill 4.22â€ at centerline to 3.5â€ on shoulder 2. Place Binder lift 2.5â€ to 1.75â€ 3. Place temporary wedge to fill back up to existing surface elevation? 4. Mill out surface butt joint 1.75â€ 5. Place surface lift of HMA into butt joint | An addendum will be issued to clarify. | Mike Coleman | 2 | 2021-11-22 10:54 | 2021-11-29 08:50
20211214 | 20211214034 | 34 | Butt Joint Detail Sheet 15 | Since the existing and finished elevations need to match, what is the actual milling depth(s) required? 4.5â€ of New HMA will be placed, which means that the end of the butt joint 4.5â€ of existing material needs to be removed. How is this being paid? Is the top 2.125â€ of removal paid is milling? Is the existing PCC approach panel being milled? If so, should a Removing Pavement Butt Joints items be added? Please clarify the intent. | An addendum will be issued to clarify. | Mike Coleman | 3 | 2021-11-22 10:55 | 2021-11-29 08:50
20211214 | 20211214034 | 34 | Construction Staging | Is there a reason that the Temp. Crossovers need to be completed in Stage 1? Could they be installed in stage 2 after the mainline pavement is completed in that area. | The temporary cross overs can be constructed at any time prior to the traffic switchover in Stage 3, provided the contractor complies with the maximum lane closure length of 5 miles and a minimum distance between lane closures in the same direction of 2 miles. Construction documents included the construction of the temporary cross overs in Stage 1 to reduce the amount of work effort in either Stage 2 or the beginning of Stage 3 when traffic on IH 39 is typically heavier. | Mike Coleman | 4 | 2021-12-01 11:02 | 2021-12-03 08:59
20211214 | 20211214034 | 34 | PWL HMA Density | The typical finished section is showing placing 2.5" at centerline and 1.75" on the edge line for the lower lift pavement. The lower lift is included in PWL density. The inconsistent lift thickness does not allow for uniform compaction required by the PWL spec. Would DOT consider changing the lower lift HMA to QMP density? The lower lift quantity can remain in PWL volumetric testing? | An addendum has been prepared to clarify the intent and address concerns. The Addendum also addresses a few other minor clarifications that were needed. | Fred Schunke | 5 | 2021-12-03 10:52 | 2021-12-08 15:32
20211214 | 20211214034 | 34 | Design Schedule | Can the design schedule be provided? | The design schedule can be found at the following location: https://wisdot.box.com/s/2s45xmv8y9bx14gd0nhxp6s79n9kheff or can be accessed on the HCCI November bid letting page under Supplemental Information. The schedule provided is draft and not for bidding purposes. The contractor is required to develop their own schedule and bid to meet the specifications in the plans, special provisions and any addendum that is developed. | Mike Coleman | 6 | 2021-12-05 06:10 | 2021-12-06 16:07
20211214 | 20211214034 | 34 | Stage 3 Restrictions | Are there any restrictions as to when Stage 3 can be done? | After review of the traffic volumes by dates and times and backup ques that will be developed in the bidirectional section during the travel on I-39 it has been determined that Stage 3 must be restricted to after Labor Day 2022. | Fred Schunke | 7 | 2021-12-09 13:30 | 2021-12-09 13:32
20211214 | 20211214034 | 34 | Driving on Binder | Are there any restrictions as to how many days traffic can drive on the binder layer of HMA prior to the surface paving being placed? | After consultation with WisDOT paving engineers it has been determined that traffic will be allowed to drive for a maximum of 3-weeks on the binder layer of HMA. | Fred Schunke | 8 | 2021-12-09 13:30 | 2021-12-09 13:32
20211214 | 20211214034 | 34 | Centerline Over-mill | At the centerline over-mill into the adjacent lane can the can the 3-foot area be milled at the slope of the adjacent lane? For example, when the passing lane is milled at the lane cross slope the 3-foot area of the driving lane would be milled at the passing lane cross slope. | As long as the project is milled down to the existing concrete surface the means and method that the contractor chooses to use to accomplish this is up to the contractor. | Fred Schunke | 9 | 2021-12-09 13:31 | 2021-12-09 13:32
20211214 | 20211214034 | 34 | Can any parts of Stage 2 be started before Stage 1 is complete? |  | Portions of work scheduled to be completed during Stage 2 can be constructed at any time prior to Stage 2 (i.e. during Stage 1), provided the contractor complies with the maximum lane closure length of 5 miles and a minimum distance between lane closures in the same direction of 2 miles. | Fred Schunke | 10 | 2021-12-09 13:36 | 2021-12-10 12:43
20211214 | 20211214035 | 35 | Bird Deterrent System | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethylene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 1 | 2021-12-09 10:26
20211214 | 20211214036 | 36 | Item 550.0500 Pile Points | Estimate of Quantities States Qty 14. Each Abutment contains 9 pipe piles in the plan. Please confirm Final Quantity as Notes do not explain. | An addendum will be issued to correct. | Mike Coleman | 1 | 2021-12-03 09:37 | 2021-12-07 13:21
20211214 | 20211214036 | 36 | Bird deterrent system | Under item #3 "Prosecution and Progress" of the Special Provisions, there is a reference to a bird deterrent system bid item, which is not currently listed in the plan. Will this be added by addendum? If it is added by addendum, The specs for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethylene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? We have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow a polyethelene net with knots? |  |  | 2 | 2021-12-09 10:56
20211214 | 20211214037 | 37 | Construction Staking Resurfacing Reference | It appears the item Construction Staking Resurfacing Reference needs to be added to the contract. | An addendum will be issued. | Fred Schunke | 1 | 2021-12-07 14:36 | 2021-12-09 11:16
20211214 | 20211214038 | 38 | Bird deterrent system | This project does not have a bird deterrent system included in the bid items. Will this be added by addendum or a post let revision, or is the Department not concerned about swallows on this structure? | No migratory bird activity has been observed on the existing structure therefore no bird deterrent system is required for this project. | Fred Schunke | 1 | 2021-12-09 10:32 | 2021-12-10 12:42
20211214 | 20211214040 | 40 | Field Office | It appears the field office item needs to be added? | An addendum will be issued to add a field office. | Mike Coleman | 1 | 2021-11-24 10:41 | 2021-11-29 08:57
20211214 | 20211214040 | 40 | Cornwall Ave & Riverplace | Plan sheet 45 shows removal items and sawcutting at Cornwall Ave & Riverplace, however sheets 76 & 77 specify no work at these intersections? | There will be no removals at these intersections. | Mike Coleman | 2 | 2021-11-24 11:00 | 2021-11-29 08:13
20211214 | 20211214040 | 40 | Undistributed Quantities | Note that there are undistributed quantities in the plan. If a DBE contractor preforms the work and ends up underrunning the quantity and/or not meeting the committed dollar amount this is undesirable for the DBE program. Sawing asphalt and concrete are specific items where this has occurred on many projects recently. | We will remove the undistributed quantity of sawcut via addendum. | Mike Coleman | 3 | 2021-11-24 11:15 | 2021-11-30 07:22
20211214 | 20211214040 | 40 | Contract Time | Completing the project in 40 working days does not appear to be enough time at this point and does not line up with time allowed for other similar projects. We suggest reviewing the time requirement. | We reviewed the timeframe, and while possible with the current proposed schedule, more time may be permitted. A revised 60 working days will be submitted as an addendum. | Mike Coleman | 4 | 2021-11-24 11:29 | 2021-11-30 07:23
20211214 | 20211214040 | 40 | HMA Mix Type | The department may want to consider using a 4MT instead of a 5MT for the 1.75" lower pavement layer to help with costs. |  |  | 5 | 2021-12-08 14:33
20211214 | 20211214041 | 41 | Bird deterrent system | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethylene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 1 | 2021-12-09 10:27
20211214 | 20211214042 | 42 | #42 Existing Deck Rebar | I was wondering if the existing rebar in the bridge deck is black rebar or epoxy coated? I could not find the as-built plans online. Thanks. | This bridge was constructed in 1975 without plans. WisDOT BOS did not add criteria for epoxy coated rebars on structures until 1981. A bit of history: Epoxy coated rebar was first used on a bridge in PA in 1973. Since this is a local Town Rd with AADT < 1000 it wouldnâ€™t have been required to use epoxy coated bars until 2015. 1981 â€¢ Criteria was added for the use of epoxy coated rebars on structures 1983 â€¢ The use of epoxy coated bar steel was expanded to off-system bridges within the corporate limits of Villages and Cities 1985 â€¢ Provided requirements for expanding the use of epoxy coated reinforcement to the top layer of all new or replaced bridge decks 1987 â€¢ Required the use of epoxy coated bar steel for both top and bottom layer stab steel on all new or re-decked bridges carrying an ADT greater than 5000 1988 â€¢ Required additional use of epoxy coated bar steel on piers detailed with expansion joints and on median piers at grade separations where the ADT under the bridge is greater than 3500 1991 â€¢ Epoxy coated bar steel required for all top and bottom steel on all State Highway bridges and on all local bridges having ADTâ€™s greater than 1000 1995 â€¢ Epoxy rebars are preferred by WisDOT 2005 â€¢ Epoxy rebars are preferred by WisDOT 2009 â€¢ Epoxy coated reinforcement bars are preferred by WisDOT. 2015 January â€¢ Epoxy coated reinforcing steel and deck sealers preferred by WisDOT â€¢ All deck reinforcement bars shall be epoxy-coated and the top reinforcing bars shall have a minimum of 2 ï¿½ inches of cover | Mike Coleman | 1 | 2021-12-02 08:16 | 2021-12-03 05:45
20211214 | 20211214043 | 43 | Bird deterrent system | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethylene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 1 | 2021-12-09 10:28
20211214 | 20211214044 | 44 | HMA Type | On Sheet 2 of the plans under the General Notes it states that a #3(19mm) mix is to be used for the lower layers and a #4(12.5mm) mix is to be used for the upper layers. Due to the small quantity and type of project would the department allow a #4 (12.5mm) mix to be used for all layers? | Yes, this would be allowed. An addenda is pending. | Fred Schunke | 1 | 2021-12-06 08:15 | 2021-12-08 14:32
20211214 | 20211214044 | 44 | Bird deterrent system | The special provisions for the bird deterrent system call for (as one of the options) a "1/2â€ x 1/2â€ or 3/4" x 3/4â€ knotless, flame resistant, U.V. stabilized polyethylene netting with minimum 40-pound breaking strength per strand, or engineer proved equal." In conversations with 3 different suppliers/manufacturers, the knotless bird netting is made from Polypropylene, not polyethylene. There are no domestic manufacturers of either currently located in the US. Will certifications for the materials be required? While the specifications outline several deterrent methods, we have found the bird netting to be both more cost effective and easier to work with. Will the Department permit a Polypropylene bird net that meets the other stated requirements, or allow for a polyethylene netting with knots? Further, can the contractor substitute 3/4"x2"x8' treated plywood strips in lieu of the 1"x2" treated lumber? Please advise. |  |  | 2 | 2021-12-09 10:29